## Sheet1
Lot No | Entered By | Date Entered | Region | Main Area | Sub Area | Activity | Work Lot Type | Responsible Engineer | Description | Date Opened | Actual Works Completion | Est. Works Completion | Closed By | Date Closed | Initial Date Closed | Status | Related AMS | ITPs | Checklists | Permits | Punch List | Defects | Related Work Lots | Child Work Lots | Design Package No | Design Package Title | Design Package Type | Approved Mix Codes | Chainage Start (km) | Chainage End (km) | Submitted By | Date Submitted | Compliance Tags | NCR No | NCR Status | Pour No | Related Hold & Witness Point Items | Last Compliance Status | Last Compliance Comments | Last Compliance Comments Date | IV Last Status | IV Last Comments | IV Last Comments Date | Document Editors | Stakeholders | Attachments | Work Lot URL | Date Extracted | Subcontractors | Subcontract Packages | Cost Code(PCR) | Cost Code | CR Date Raised | CR Raised By | CR Status
WLD/N2NS/01672 | Ben Foster | 2021-08-19 07:34 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 22nc August to 28th August 2021 TOTAL QTY - TBC Tonnes | 2021-08-19 |  | 2021-08-28 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 |  |  |  |  | WLD/N2NS/00259 | [5 empty] | 0 | 0 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/141056 |  | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551
WLD/N2NS/01671 | Arjan Sidhu | 2021-08-19 07:09 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Capping | Earthworks | Arjan Sidhu | JCQ Runnymede Capping Supply - 4000T Stockpile 22 | 2021-08-19 |  | 2021-08-21 10:00 |  |  |  | Pending | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 625.55 | 667 | Arjan Sidhu | 2021-08-19 07:11 | [5 empty] | Submitted for closure |  | 2021-08-19 07:11 |  |  |  | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  | N-21-193-18.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/141052
WLD/N2NS/01670 | Arjan Sidhu | 2021-08-19 06:58 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Capping | Earthworks | Arjan Sidhu | JCQ Runnymede Capping Supply - 4000T Stockpile 21 | 2021-08-19 |  | 2021-08-21 10:00 |  |  |  | Pending | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 625.55 | 667 | Arjan Sidhu | 2021-08-19 07:08 | [5 empty] | Submitted for closure |  | 2021-08-19 07:08 |  |  |  | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  | N-21-193-17.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/141049
WLD/N2NS/01669 | James Martin | 2021-08-19 02:22 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - Mainline and Siding - CH697.330 to CH697.910 | 2021-08-19 |  | 2021-08-20 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 697.33 | 607.91 | [6 empty] | HWP/N2NS/00459 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/141030 |  |  |  | 7632-3C41220
WLD/N2NS/01668 | Richard Doering | 2021-08-18 21:46 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Excavation (Cut) | Earthworks | Richard Doering | Cut inc Ground Prep | 2021-08-19 |  | 2021-08-16 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 657.74 | 657.88 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140981 |  |  |  | 7632-2C41220
WLD/N2NS/01667 | Richard Doering | 2021-08-18 07:50 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 1 | 2021-08-18 |  | 2021-08-15 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 658 | 658 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140965 |  |  |  | 7632-2C41552
WLD/N2NS/01666 | Richard Doering | 2021-08-18 07:48 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 2 | 2021-08-18 |  | 2021-08-20 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 658 | 658 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140964 |  |  |  | 7632-2C41552
WLD/N2NS/01665 | Richard Doering | 2021-08-18 07:42 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 2 | 2021-08-18 |  | 2021-08-19 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 658 | 658 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140963 |  |  |  | 7632-2C41552
WLD/N2NS/01664 | James Martin | 2021-08-18 07:16 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type C3 Insitu stabilisation - 250mm - CH693.900 to CH694.000 | 2021-08-18 |  | 2021-08-19 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00015 | [9 empty] | 693.9 | 694 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140962 |  |  |  | 7632-3C41552
WLD/N2NS/01663 | Aziz Kamaoui | 2021-08-18 07:02 | Stage 2 - Penneys Road to Moree | Trackwork | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Trackwork - Bottom Ballast | Track | Aziz Kamaoui | LX555 - Installation of Bottom Ballast CH636.330 to CH636.350 |  |  | 2021-08-18 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00007 | CHK/N2NS/00033 | [9 empty] | 636.33 | 636.35 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140961
WLD/N2NS/01662 | James Martin | 2021-08-18 07:02 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - Stage 3 - CH691.040 to CH691.760 - Layer 2 - 400mm | 2021-08-18 |  | 2021-08-19 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 691.04 | 691.76 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140960 |  |  |  | 7632-3C41552
WLD/N2NS/01661 | Aziz Kamaoui | 2021-08-18 06:58 | Stage 2 - Penneys Road to Moree | Trackwork | Level Crossing - 635.600, LX554, Gurley Creek Road (Type 4, rubber, sealed), RX-5 | Trackwork - Bottom Ballast | Track | Aziz Kamaoui | LX554 - Bottom Ballast Installation CH635.680 to CH635.710 |  |  | 2021-08-18 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00007 | CHK/N2NS/00033 | [9 empty] | 635.68 | 635.71 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140959
WLD/N2NS/01660 | James Martin | 2021-08-18 06:55 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - Stage 3 - CH689.000 to CH689.750 - Layer 2 - 400mm | 2021-08-18 |  | 2021-08-19 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 689 | 689.75 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140956 |  |  |  | 7632-3C41552
WLD/N2NS/01659 | Aziz Kamaoui | 2021-08-18 06:54 | Stage 2 - Penneys Road to Moree | Trackwork | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Trackwork - Bottom Ballast | Track | Aziz Kamaoui | LX3066 - Installation of Bottom Ballast CH634.510 to CH634.540 |  |  | 2021-08-18 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00007 | CHK/N2NS/00033 | [9 empty] | 634.51 | 634.54 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140955
WLD/N2NS/01658 | Aziz Kamaoui | 2021-08-18 06:48 | Stage 2 - Penneys Road to Moree | Trackwork | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Trackwork - Bottom Ballast | Track | Aziz Kamaoui | LX553 - Bottom Ballast - CH631.155 to CH631.180 |  |  | 2021-08-19 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00007 | CHK/N2NS/00033 | [9 empty] | 631.16 | 631.18 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140950
WLD/N2NS/01657 | Laura Buckland | 2021-08-18 05:52 | Stage 3 - Camurra North to North Star | Earthworks | Bridge - 740.665 Yallaroi Creek (9m ¦ 6 spans ¦ offline) | Bridgeworks - Other | Earthworks | Laura Buckland | Ash inspection at southern and northern abutment | 2021-08-18 |  | 2021-09-11 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 740.6 | 740.7 | [6 empty] | HWP/N2NS/00456 | [6 empty] | Chris Chant, Dan Kandamby, Danika Green, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140942
WLD/N2NS/01656 | Keegan Baker | 2021-08-18 01:05 | Stage 2 - Penneys Road to Moree | Culverts | 647.155, 40/3000x2400, remove and rebuild | Drainage - Other | Other | Frank Paraha | Backfill of Culvert 647.155 |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00037 | [9 empty] | 647.16 | 647.16 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140907
WLD/N2NS/01655 | Keegan Baker | 2021-08-18 01:03 | Stage 2 - Penneys Road to Moree | Culverts | 652.530, 2/1800x600, remove and rebuild | Drainage - Other | Other | Frank Paraha | Backfill of Culvert 652.530 |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00037 | [9 empty] | 652.53 | 652.53 | [6 empty] | HWP/N2NS/00452 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140906
WLD/N2NS/01654 | Richard Doering | 2021-08-17 07:35 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 | 2021-08-17 |  | 2021-08-18 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 658 | 658 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140884 |  |  |  | 7632-2C41552
WLD/N2NS/01653 | Kallen Doong | 2021-08-17 06:57 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - Stage 3 - CH688.600 to CH689.000 - Layer 2 - 400mm | 2021-08-18 |  | 2021-08-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 688.6 | 689 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140883 |  |  |  | 7632-3C41552
WLD/N2NS/01652 | Keegan Baker | 2021-08-17 03:13 | Stage 2 - Penneys Road to Moree | Culverts | 640.650, 15/1800x1200, new build | Drainage - Other | Other | Keegan Baker | Backfill of Culvert 640.650 |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00037 | [9 empty] | 640.65 | 640.65 | [6 empty] | HWP/N2NS/00445 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140854
WLD/N2NS/01651 | Keegan Baker | 2021-08-17 03:12 | Stage 2 - Penneys Road to Moree | Culverts | 640.380, 20/1800x900, new build | Drainage - Other | Other | Keegan Baker | Backfill of Culvert 640.380 |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00037 | [9 empty] | 640.38 | 640.38 | [6 empty] | HWP/N2NS/00444 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140852
WLD/N2NS/01650 | Keegan Baker | 2021-08-17 03:05 | Stage 2 - Penneys Road to Moree | Culverts | 640.650, 15/1800x1200, new build | Culverts - Other | Other | Keegan Baker | 640.650 - Precast Culvert Installation |  |  | 2021-10-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00041 | [9 empty] | 640.65 | 640.65 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140848
WLD/N2NS/01649 | Keegan Baker | 2021-08-17 03:03 | Stage 2 - Penneys Road to Moree | Culverts | 640.380, 20/1800x900, new build | Culverts - Other | Other | Keegan Baker | 640.380 - Precast Culvert Installation |  |  | 2021-09-09 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00041 | [9 empty] | 640.38 | 640.38 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140847
WLD/N2NS/01648 | Frank Paraha | 2021-08-16 23:08 | Stage 2 - Penneys Road to Moree | Culverts | 656,240 New | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Frank Paraha | 656.240 - Cast In Situ Apron Slab | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 656.24 | 656.24 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140828 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72200
WLD/N2NS/01647 | Frank Paraha | 2021-08-16 23:07 | Stage 2 - Penneys Road to Moree | Culverts | 652.530, 2/1800x600, remove and rebuild | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Frank Paraha | 652.530 - Cast In Situ Apron Slab | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 652.53 | 652.53 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140827 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72200
WLD/N2NS/01646 | Frank Paraha | 2021-08-16 22:59 | Stage 2 - Penneys Road to Moree | Culverts | 652.715, 1/1800x600, remove and rebuild | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Frank Paraha | 652.715 - Cast In Situ Apron Slab | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 652.72 | 652.72 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140826 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72200
WLD/N2NS/01645 | Frank Paraha | 2021-08-16 22:58 | Stage 2 - Penneys Road to Moree | Culverts | 650.690, 2/2400x900, remove and rebuild | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Frank Paraha | 650.690 - Cast In Situ Apron Slab | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 650.69 | 650.69 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140825 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72200
WLD/N2NS/01644 | Frank Paraha | 2021-08-16 22:56 | Stage 2 - Penneys Road to Moree | Culverts | 650.330, 1/2400x900, remove and rebuild | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Frank Paraha | 650.330 - Cast In Situ Apron Slab | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 650.33 | 650.33 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140824 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72200
WLD/N2NS/01643 | Frank Paraha | 2021-08-16 22:55 | Stage 2 - Penneys Road to Moree | Culverts | 649.185, 2/1800x600, remove and rebuild | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Frank Paraha | 649.185 - Cast In Situ Apron Slab | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 649.19 | 649.19 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140823 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72200
WLD/N2NS/01642 | Frank Paraha | 2021-08-16 22:54 | Stage 2 - Penneys Road to Moree | Culverts | 648.635, 6/2400x900, remove and rebuild | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Frank Paraha | 648.635 - Cast In Situ Apron Slab | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 648.64 | 648.64 | [6 empty] | HWP/N2NS/00457 | [6 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140822 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72200
WLD/N2NS/01641 | Frank Paraha | 2021-08-16 22:53 | Stage 2 - Penneys Road to Moree | Culverts | 648.395, 10/3000x2400, remove and rebuild | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Frank Paraha | 648.395 - Cast In Situ Apron Slab | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 648.4 | 648.4 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140821 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72200
WLD/N2NS/01640 | Frank Paraha | 2021-08-16 22:52 | Stage 2 - Penneys Road to Moree | Culverts | 648.240, 6/2400x900, remove and rebuild | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Frank Paraha | 648.240 - Cast In Situ Apron Slab | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 648.24 | 648.24 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140820 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72200
WLD/N2NS/01639 | Frank Paraha | 2021-08-16 22:49 | Stage 2 - Penneys Road to Moree | Culverts | 655.980, 5/3000x1200, remove and rebuild (RRA) | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Frank Paraha | 655.980 - Cast In Situ Cut-Off Walls | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 655.98 | 655.98 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140819 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72200
WLD/N2NS/01638 | Frank Paraha | 2021-08-16 22:48 | Stage 2 - Penneys Road to Moree | Culverts | 655.270, 6/3000x1200, remove and rebuild (RRA) | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Frank Paraha | 655.270 - Cast In Situ Cut-Off Walls | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 655.27 | 655.27 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140818 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72200
WLD/N2NS/01637 | Frank Paraha | 2021-08-16 22:48 | Stage 2 - Penneys Road to Moree | Culverts | 654.525, 1/1800x900, remove and rebuild | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Frank Paraha | 654.525 - Cast In Situ Cut-Off Walls | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 654.53 | 654.53 | [6 empty] | HWP/N2NS/00442, HWP/N2NS/00443 | [6 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140817 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72200
WLD/N2NS/01636 | Frank Paraha | 2021-08-16 22:47 | Stage 2 - Penneys Road to Moree | Culverts | 653.700, 1/2400x900, remove and rebuild | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Frank Paraha | 653.700 - Cast In Situ Cut-Off Walls | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 653.7 | 653.7 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140816 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72200
WLD/N2NS/01635 | Frank Paraha | 2021-08-16 22:45 | Stage 2 - Penneys Road to Moree | Culverts | 653.620, 6/2400x900, remove and rebuild | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Frank Paraha | 653.620 - Cast In Situ Cut-Off Walls | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 653.62 | 653.62 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140815 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72200
WLD/N2NS/01634 | Frank Paraha | 2021-08-16 22:39 | Stage 2 - Penneys Road to Moree | Culverts | 650,040 NEW | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Frank Paraha | 650.040 - Cast In Situ Cut-Off Walls | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 650.04 | 650.04 | [6 empty] | HWP/N2NS/00458 | [6 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140814 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72200
WLD/N2NS/01633 | Frank Paraha | 2021-08-16 22:38 | Stage 2 - Penneys Road to Moree | Culverts | 649,700 NEW | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Frank Paraha | 649.700 - Cast In Situ Cut-Off Walls | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 649.7 | 649.7 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140813 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72200
WLD/N2NS/01632 | James Martin | 2021-08-16 07:38 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - Stage 3 - CH695.760 to CH696.700 - Layer 1 - 400mm | 2021-08-16 |  | 2021-08-17 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 695.76 | 696.7 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140775 |  |  |  | 7632-3C41552
WLD/N2NS/01631 | James Martin | 2021-08-16 07:26 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - Stage 3 - CH686.760 to CH687.440 - Layer 2 - 400mm | 2021-08-16 |  | 2021-08-17 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 686.76 | 687.44 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140774 |  |  |  | 7632-3C41552
WLD/N2NS/01630 | Arjan Sidhu | 2021-08-16 03:58 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Arjan Sidhu | Capping placement CH 627.525 to 627.76 | 2021-08-16 |  | 2021-08-18 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 627.53 | 627.76 | [6 empty] | HWP/N2NS/00441 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140754 |  |  |  | 7632-1C47051
WLD/N2NS/01629 | Richard Doering | 2021-08-16 00:41 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 2 - Eastern Turnout Pad only - CH657.500 to 657.630 | 2021-08-16 |  | 2021-08-17 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 657.5 | 657.63 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140730 |  |  |  | 7632-2C41552
WLD/N2NS/01628 | Frank Paraha | 2021-08-15 11:22 | Stage 2 - Penneys Road to Moree | Culverts | 647.670, 10/3000x1500, remove and rebuild | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Frank Paraha | 647.670 - Cast In Situ Cut-Off Walls | 2021-08-15 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 647.67 | 647.67 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140719 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72200
WLD/N2NS/01627 | Frank Paraha | 2021-08-15 11:15 | Stage 2 - Penneys Road to Moree | Culverts | 647.315, 10/3000x1200, remove and rebuild | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Frank Paraha | 647.315 - Cast In Situ Apron Slab | 2021-08-15 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 647.32 | 647.32 | [6 empty] | HWP/N2NS/00425, HWP/N2NS/00426, HWP/N2NS/00427 | [6 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140718 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72200
WLD/N2NS/01626 | Arjan Sidhu | 2021-08-15 08:01 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Arjan Sidhu | Capping placement CH625.831 to CH625.9 Tie in to Existing Track | 2021-08-15 |  | 2021-08-12 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 625.83 | 625.9 | [6 empty] | HWP/N2NS/00437, HWP/N2NS/00455 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140717 |  |  |  | 7632-2C47051
WLD/N2NS/01625 | Richard Doering | 2021-08-15 07:27 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - spare | 2021-08-15 |  | 2021-08-16 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 658 | 658 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140715 |  |  |  | 7632-2C41552
WLD/N2NS/01624 | Arjan Sidhu | 2021-08-15 02:21 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Trackwork - Bottom Ballast | Track | Jake Mossman | Mackellar Excavations Gunnedah Quarry, Ballast Stockpile 1 first 300T | 2021-08-15 |  | 2021-05-12 10:00 | Benjamin Philip | 2021-08-15 | 2021-08-15 04:01 | Closed | AMS/N2NS/00007 | ITP/N2NS/00007 | CHK/N2NS/00033 | [9 empty] | 625.55 | 666 | Arjan Sidhu | 2021-08-15 02:23 | [5 empty] | Lot closed |  | 2021-08-15 04:01 |  |  |  | Arjan Sidhu, Jake Mossman, Miaya Tighe |  | Wet Attrition - May '21.pdf, Ballast test report - May '21.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140714 |  |  |  | 7632-GR82101 |  | 2021-08-15 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/01623 | Arjan Sidhu | 2021-08-15 01:44 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Capping | Earthworks | Arjan Sidhu | JCQ Runnymede Capping Supply - 4000T Stockpile 20 | 2021-08-15 |  | 2021-08-18 10:00 | Benjamin Philip | 2021-08-15 | 2021-08-15 04:07 | Closed | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 625.55 | 667 | Arjan Sidhu | 2021-08-15 01:46 | [5 empty] | Lot closed |  | 2021-08-15 04:07 |  |  |  | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  | N-21-193-16.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140713 | [5 empty] | 2021-08-15 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/01622 | Keegan Baker | 2021-08-15 01:08 | Stage 2 - Penneys Road to Moree | Culverts | Other (Specify Location in Lot) | Drainage - Other | Earthworks | Keegan Baker | Backfill of Existing Culvert 627.490 |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00037 | [9 empty] | 627.49 | 627.49 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140712
WLD/N2NS/01621 | Richard Doering | 2021-08-14 07:41 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - spare | 2021-08-14 |  | 2021-08-15 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 658 | 658 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140711 |  |  |  | 7632-2C41552
WLD/N2NS/01620 | Arjan Sidhu | 2021-08-14 06:55 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Capping | Earthworks | Arjan Sidhu | JCQ Runnymede Capping Supply - 4000T Stockpile 19 | 2021-08-14 |  | 2021-08-18 10:00 | Benjamin Philip | 2021-08-15 | 2021-08-15 04:10 | Closed | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 625.55 | 667 | Arjan Sidhu | 2021-08-14 06:58 | [5 empty] | Lot closed |  | 2021-08-15 04:10 |  |  |  | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  | N-21-193-15.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140710 | [5 empty] | 2021-08-15 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/01619 | Kallen Doong | 2021-08-14 00:06 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Trackwork - Bottom Ballast | Track | Arjan Sidhu | Installation of Bottom Ballast - CH631.180 to CH632.800 |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00007 | CHK/N2NS/00033 | [9 empty] | 631.18 | 632.8 | [6 empty] | HWP/N2NS/00424 | [6 empty] | Arjan Sidhu, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140708
WLD/N2NS/01618 | Kallen Doong | 2021-08-14 00:04 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Trackwork - Bottom Ballast | Track | Arjan Sidhu | Installation of Bottom Ballast - CH628.600 to CH631.135 |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00007 | CHK/N2NS/00033 | [9 empty] | 628.6 | 631.14 | [6 empty] | HWP/N2NS/00423 | [6 empty] | Arjan Sidhu, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140707
WLD/N2NS/01617 | Kallen Doong | 2021-08-14 00:02 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Trackwork - Bottom Ballast | Track | Arjan Sidhu | Installation of Bottom Ballast - CH627.950 to CH628.600 |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00007 | CHK/N2NS/00033 | [9 empty] | 627.95 | 628.6 | [6 empty] | HWP/N2NS/00423, HWP/N2NS/00424 | [6 empty] | Arjan Sidhu, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140706
WLD/N2NS/01616 | Jarryd Davis | 2021-08-13 03:37 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Callum Todd | Construction of skeleton track including placement of sleepers and threading of rail between CH656.000 to CH658.00 on the mainline (Stage 2Aii) |  |  | 2021-09-30 10:00 |  |  |  | Planned | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 656 | 658 | [13 empty] | Harris Ahmad, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140691
WLD/N2NS/01615 | Jarryd Davis | 2021-08-13 03:36 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Callum Todd | Construction of skeleton track including placement of sleepers and threading of rail between CH654.000 to CH656.00 on the mainline (Stage 2Aii) |  |  | 2021-09-30 10:00 |  |  |  | Planned | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 654 | 656 | [13 empty] | Harris Ahmad, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140690
WLD/N2NS/01614 | Jarryd Davis | 2021-08-13 03:35 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Callum Todd | Construction of skeleton track including placement of sleepers and threading of rail between CH650.000 to CH652.00 on the mainline (Stage 2Aii) |  |  | 2021-09-30 10:00 |  |  |  | Planned | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 650 | 652 | [13 empty] | Harris Ahmad, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140689
WLD/N2NS/01613 | Benjamin Philip | 2021-08-13 03:35 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Delivery of Precast Large & Small Concrete Box Culvert and Wing Walls - Week Ending 22 August 2021 |  |  | 2021-08-22 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058, ITP/N2NS/00059, ITP/N2NS/00060 | [9 empty] | MIX/N2NS/00001 | 0 | 0 | [13 empty] | Ganan Ganeshanantham, Johannes Mason |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140688 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/01612 | Jarryd Davis | 2021-08-13 03:34 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Callum Todd | Construction of skeleton track including placement of sleepers and threading of rail between CH648.000 to CH650.00 on the mainline (Stage 2Aii) |  |  | 2021-09-30 10:00 |  |  |  | Planned | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 648 | 650 | [13 empty] | Harris Ahmad, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140687
WLD/N2NS/01611 | Benjamin Philip | 2021-08-13 03:32 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Delivery of Precast Large & Small Concrete Box Culvert and Wing Walls - Week Ending 15 August 2021 | 2021-08-14 |  | 2021-08-15 10:00 | Benjamin Philip | 2021-08-14 | 2021-08-14 05:33 | Closed | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058, ITP/N2NS/00059, ITP/N2NS/00060 | [9 empty] | MIX/N2NS/00001 | 0 | 0 | Benjamin Philip | 2021-08-14 05:33 | [5 empty] | Lot closed |  | 2021-08-14 05:33 |  |  |  | Ganan Ganeshanantham, Johannes Mason |  | 20210815 CoCs.pdf, 15 August 2021 Precast Units Delivered Register.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140686 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006 |  |  | 2021-08-14 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/01610 | Jarryd Davis | 2021-08-13 03:32 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Callum Todd | Construction of skeleton track including placement of sleepers and threading of rail between CH646.000 to CH648.00 on the mainline (Stage 2Aii) |  |  | 2021-09-30 10:00 |  |  |  | Planned | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 646 | 648 | [13 empty] | Harris Ahmad, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140685
WLD/N2NS/01609 | Jarryd Davis | 2021-08-13 03:31 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Callum Todd | Construction of skeleton track including placement of sleepers and threading of rail between CH640.000 to CH642.00 on the mainline (Stage 2Ai) |  |  | 2021-09-30 10:00 |  |  |  | Planned | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 640 | 642 | [13 empty] | Harris Ahmad, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140684
WLD/N2NS/01608 | Benjamin Philip | 2021-08-13 03:30 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Delivery of Precast Large & Small Concrete Box Culvert and Wing Walls - Week Ending 08 August 2021 | 2021-08-14 |  | 2021-08-08 10:00 | Benjamin Philip | 2021-08-14 | 2021-08-14 05:30 | Closed | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058, ITP/N2NS/00059, ITP/N2NS/00060 | [9 empty] | MIX/N2NS/00001 | 0 | 0 | Benjamin Philip | 2021-08-14 05:30 | [5 empty] | Lot closed |  | 2021-08-14 05:30 |  |  |  | Ganan Ganeshanantham, Johannes Mason |  | 20210808 CoCs.pdf, 08 August 2021 Precast Units Delivered Register.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140683 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006 |  |  | 2021-08-14 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/01607 | Jarryd Davis | 2021-08-13 03:30 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Callum Todd | Construction of skeleton track including placement of sleepers and threading of rail between CH638.000 to CH640.00 on the mainline (Stage 2Ai) |  |  | 2021-09-30 10:00 |  |  |  | Planned | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 638 | 640 | [13 empty] | Harris Ahmad, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140682
WLD/N2NS/01606 | Jarryd Davis | 2021-08-13 03:29 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Callum Todd | Construction of skeleton track including placement of sleepers and threading of rail between CH636.000 to CH638.00 on the mainline (Stage 2Ai) | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 636 | 638 | [13 empty] | Harris Ahmad, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140681
WLD/N2NS/01605 | Benjamin Philip | 2021-08-13 03:27 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Delivery of Precast Large & Small Concrete Box Culvert and Wing Walls - Week Ending 01 August 2021 | 2021-08-14 |  | 2021-08-01 10:00 | Benjamin Philip | 2021-08-14 | 2021-08-14 05:28 | Closed | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058, ITP/N2NS/00059, ITP/N2NS/00060 | [9 empty] | MIX/N2NS/00001 | 0 | 0 | Benjamin Philip | 2021-08-14 05:28 | [5 empty] | Lot closed |  | 2021-08-14 05:28 |  |  |  | Ganan Ganeshanantham, Johannes Mason |  | 20210801 CoCs.pdf, 01 August 2021 Precast Units Delivered Register.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140680 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006 |  |  | 2021-08-14 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/01604 | Jarryd Davis | 2021-08-13 03:26 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Callum Todd | Construction of skeleton track including placement of sleepers and threading of rail between CH634.000 to CH636.00 on the mainline (Stage 2Ai) | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 634 | 636 | [13 empty] | Harris Ahmad, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140679
WLD/N2NS/01603 | Jarryd Davis | 2021-08-13 03:25 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Callum Todd | Construction of skeleton track including placement of sleepers and threading of rail between CH632.000 to CH634.00 on the mainline (Stage 2Ai) | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 632 | 634 | [13 empty] | Harris Ahmad, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140678
WLD/N2NS/01602 | Benjamin Philip | 2021-08-13 03:25 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Delivery of Precast Large & Small Concrete Box Culvert and Wing Walls - Week Ending 25 July 2021 | 2021-08-14 |  | 2021-07-25 10:00 | Benjamin Philip | 2021-08-14 | 2021-08-14 05:25 | Closed | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058, ITP/N2NS/00059, ITP/N2NS/00060 | [9 empty] | MIX/N2NS/00001 | 0 | 0 | Benjamin Philip | 2021-08-14 05:25 | [5 empty] | Lot closed |  | 2021-08-14 05:25 |  |  |  | Ganan Ganeshanantham, Johannes Mason |  | 20210725 CoCs.pdf, 25 July 2021 Precast Units Delivered Register.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140677 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006 |  |  | 2021-08-14 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/01601 | Jarryd Davis | 2021-08-13 03:25 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Callum Todd | Construction of skeleton track including placement of sleepers and threading of rail between CH630.000 to CH632.00 on the mainline (Stage 2Ai) | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 630 | 632 | [13 empty] | Harris Ahmad, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140676
WLD/N2NS/01600 | Jarryd Davis | 2021-08-13 03:23 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Callum Todd | Construction of skeleton track including placement of sleepers and threading of rail between CH628.000 to CH630.00 on the mainline (Stage 2Ai) | 2021-08-13 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 628 | 630 | [13 empty] | Harris Ahmad, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140675
WLD/N2NS/01599 | Benjamin Philip | 2021-08-13 03:23 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Delivery of Precast Large & Small Concrete Box Culvert and Wing Walls - Week Ending 18 July 2021 | 2021-08-14 |  | 2021-07-18 10:00 | Benjamin Philip | 2021-08-14 | 2021-08-14 05:23 | Closed | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058, ITP/N2NS/00059, ITP/N2NS/00060 | [9 empty] | MIX/N2NS/00001 | 0 | 0 | Benjamin Philip | 2021-08-14 05:23 | [5 empty] | Lot closed |  | 2021-08-14 05:23 |  |  |  | Ganan Ganeshanantham, Johannes Mason |  | 18 July 2021 Precast Units Delivered Register.pdf, 20210718 CoCs.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140674 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006 |  |  | 2021-08-14 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/01598 | Jarryd Davis | 2021-08-13 03:20 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Callum Todd | Construction of skeleton track including placement of sleepers and threading of rail between CH626.000 to CH628.00 on the mainline (Stage 2Ai) | 2021-08-17 |  | 2021-09-30 10:00 |  |  |  | Open | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 626 | 628 | [13 empty] | Harris Ahmad, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140673
WLD/N2NS/01597 | Benjamin Philip | 2021-08-13 03:19 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Delivery of Precast Large & Small Concrete Box Culvert and Wing Walls - Week Ending 11 July 2021 | 2021-08-14 |  | 2021-07-11 10:00 | Benjamin Philip | 2021-08-14 | 2021-08-14 05:20 | Closed | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058, ITP/N2NS/00059, ITP/N2NS/00060 | [9 empty] | MIX/N2NS/00001 | 0 | 0 | Benjamin Philip | 2021-08-14 05:20 | [5 empty] | Lot closed |  | 2021-08-14 05:20 |  |  |  | Ganan Ganeshanantham, Johannes Mason |  | 20210711 CoCs.pdf, 11 July Precast Units Delivered Register.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140672 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006 |  |  | 2021-08-14 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/01596 | Jarryd Davis | 2021-08-13 03:18 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Callum Todd | Construction of skeleton track including placement of sleepers and threading of rail between CH625.831 to CH626.00 on the mainline (Stage 2Ai) |  |  | 2021-09-30 10:00 |  |  |  | Planned | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 625.83 | 626 | [13 empty] | Harris Ahmad, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140671
WLD/N2NS/01595 | Benjamin Philip | 2021-08-13 03:16 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Delivery of Precast Large & Small Concrete Box Culvert and Wing Walls - Week Ending 4 July 2021 | 2021-08-14 |  | 2021-07-04 10:00 | Benjamin Philip | 2021-08-14 | 2021-08-14 05:17 | Closed | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058, ITP/N2NS/00059, ITP/N2NS/00060 | [9 empty] | MIX/N2NS/00001 | 0 | 0 | Benjamin Philip | 2021-08-14 05:17 | [5 empty] | Lot closed |  | 2021-08-14 05:17 |  |  |  | Ganan Ganeshanantham, Johannes Mason |  | 04 July 2021 Precast Units Delivered Register.pdf, 20210704 CoCs.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140670 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006 |  |  | 2021-08-14 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/01594 | Richard Doering | 2021-08-12 07:48 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - spare | 2021-08-12 |  | 2021-08-13 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 658 | 658 | [15 empty] | N-21-179-842.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140645 |  |  |  | 7632-2C41552
WLD/N2NS/01593 | Richard Doering | 2021-08-12 07:47 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - spare | 2021-08-12 |  | 2021-08-13 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 658 | 658 | [15 empty] | N-21-179-843.pdf, N-21-179-858.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140644 |  |  |  | 7632-2C41552
WLD/N2NS/01592 | Samuel Withers | 2021-08-12 04:11 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH695.000 to CH695.760 - Layer 1 - 400mm | 2021-08-16 |  | 2021-08-24 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 695 | 695.76 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140638 |  |  |  | 7632-3C41552
WLD/N2NS/01591 | Jake Mossman | 2021-08-12 00:47 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Bottom Ballast | Track | Jake Mossman | Mackellar Excavations - Ballast Stockpile 1 |  |  | 2021-08-16 10:00 |  |  |  | Planned | [12 empty] | 625.55 | 658 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140617
WLD/N2NS/01590 | Frank Paraha | 2021-08-11 13:23 | Stage 2 - Penneys Road to Moree | Culverts | 640.650, 15/1800x1200, new build | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Keegan Baker | 640.650 - Cast In Situ Cut-off Walls | 2021-08-11 |  | 2021-09-07 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 640.38 | 640.38 | [6 empty] | HWP/N2NS/00418 | [6 empty] | Frank Paraha, Keegan Baker, Maddie Dahlstrom, Nabin Koirala |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140590 |  |  |  | 7632-2S72200
WLD/N2NS/01589 | Richard Doering | 2021-08-11 08:13 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - spare | 2021-08-11 |  | 2021-08-12 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 658 | 658 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140589 |  |  |  | 7632-2C41552
WLD/N2NS/01588 | Richard Doering | 2021-08-11 08:12 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - spare | 2021-08-11 |  | 2021-08-12 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 658 | 658 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140588 |  |  |  | 7632-2C41552
WLD/N2NS/01587 | Ryan Shenton | 2021-08-11 07:41 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH693.700 to CH695.000 - Layer 1 - 400mm | 2021-08-11 |  | 2021-08-24 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 693.7 | 695 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 01066 Panda results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140586 |  |  |  | 7632-3C41552
WLD/N2NS/01586 | Ben Foster | 2021-08-11 05:26 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 14th August to 21st August 2021 TOTAL QTY - TBC Tonnes | 2021-08-11 |  | 2021-08-21 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 |  |  |  |  | WLD/N2NS/00259 | [5 empty] | 0 | 0 | [15 empty] | 1136768.pdf, 1028456 & 1028457.pdf, 8641.pdf, 1136819.pdf, 1136815.pdf, 1028458.pdf, 1028454 & 1028455.pdf, 1028440 & 1028441.pdf, 1028443 & 1028444.pdf, 1136844.pdf, 1136843.pdf, 1028464 & 1028466.pdf, 1136845.pdf, 1136842.pdf, 1028473 & 1028474.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140561 |  | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551
WLD/N2NS/01585 | Samuel Withers | 2021-08-11 03:18 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Cut Inc Ground Preparation - CH696.640 - 696.750 |  |  | 2021-08-21 10:00 |  |  |  | Planned | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 696.64 | 696.75 | [6 empty] | HWP/N2NS/00417 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140553 |  |  |  | 7632-3C41220
WLD/N2NS/01584 | Samuel Withers | 2021-08-11 02:39 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Cut Inc Ground Preparation - CH700,960 to 701,740 |  |  | 2021-08-21 10:00 |  |  |  | Planned | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 700.96 | 701.74 | [6 empty] | HWP/N2NS/00416 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140547 |  |  |  | 7632-3C41220
WLD/N2NS/01583 | Samuel Withers | 2021-08-11 02:38 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Cut Inc Ground Preparation - CH700,760 to 700,920 |  |  | 2021-08-21 10:00 |  |  |  | Planned | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 700.76 | 700.92 | [6 empty] | HWP/N2NS/00416 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140546 |  |  |  | 7632-3C41220
WLD/N2NS/01582 | Ryan Shenton | 2021-08-10 08:30 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type C3 - Stage 3 - CH696.460 to CH696.520 - Insitu 250mm | 2021-08-10 |  | 2021-08-24 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 696.46 | 696.52 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140516 |  |  |  | 7632-3C41552
WLD/N2NS/01581 | Ryan Shenton | 2021-08-10 08:09 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - Stage 3 - CH685.890 to CH686.760 - Layer 2 - 400mm | 2021-08-10 |  | 2021-08-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 685.89 | 686.76 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140515 |  |  |  | 7632-3C41552
WLD/N2NS/01580 | Ryan Shenton | 2021-08-10 08:02 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH692.610 to CH693.600 - Layer 1 - 400mm | 2021-08-10 |  | 2021-08-24 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 692.61 | 693.6 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140514 |  |  |  | 7632-3C41552
WLD/N2NS/01579 | Ryan Shenton | 2021-08-10 07:38 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH690.300 to CH690.490 - Layer 1 - 400mm | 2021-08-10 |  | 2021-08-24 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 690.3 | 690.49 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140508 |  |  |  | 7632-3C41552
WLD/N2NS/01578 | Frank Paraha | 2021-08-10 07:23 | Stage 2 - Penneys Road to Moree | Culverts | 640.380, 20/1800x900, new build | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Keegan Baker | 640.380 - Cast In Situ Cut-off Walls | 2021-08-10 |  | 2021-09-07 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 640.38 | 640.38 | [6 empty] | HWP/N2NS/00428 | [9 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140502 |  |  |  | 7632-2S72200
WLD/N2NS/01577 | Richard Doering | 2021-08-10 07:17 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 1 (Siding) CH655.575 to CH655.800 | 2021-08-10 |  | 2021-08-11 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 655.58 | 655.8 | [15 empty] | N-21-179-829.pdf, Test Request 01053 Panda Results.pdf, N-21-179-859.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140501 |  |  |  | 7632-2C41552
WLD/N2NS/01576 | Patrick Coria | 2021-08-10 03:18 | Stage 2 - Penneys Road to Moree | Culverts | 653.150, 1/600x600, remove and rebuild | Drainage - Other | Other | Frank Paraha | Cast- In Situ Apron Slab | 2021-08-10 |  | 2021-09-24 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00038 | [9 empty] | 653.15 | 653.15 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140467
WLD/N2NS/01575 | Miaya Tighe | 2021-08-09 22:34 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Capping | Earthworks | Jake Mossman | JCQ Runnymede Capping Supply - 4000T Stockpile 18 | 2021-08-10 |  | 2021-08-27 10:00 | Benjamin Philip | 2021-08-11 | 2021-08-10 22:13 | Closed | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 625.55 | 667 | Miaya Tighe | 2021-08-10 21:56 | [5 empty] | Lot closed |  | 2021-08-10 22:13 |  |  |  | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  | N-21-193-14.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140385 | [5 empty] | 2021-08-16 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/01574 | Ryan Shenton | 2021-08-09 08:26 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH691.040 to CH691.700 - Layer 1 - 400mm |  |  | 2021-08-17 10:00 |  |  |  | Planned | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 689.14 | 689.84 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140378 |  |  |  | 7632-3C41552
WLD/N2NS/01573 | Richard Doering | 2021-08-09 08:17 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 2 CH655.430 to 655.575 | 2021-08-09 |  | 2021-08-10 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 655.43 | 655.58 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140377 |  |  |  | 7632-2C41552
WLD/N2NS/01572 | Ryan Shenton | 2021-08-09 08:17 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH689.080 to CH690.300 - Layer 1 - 400mm | 2021-08-09 |  | 2021-08-17 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 689.08 | 690.3 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 01045 Panda Results.pdf, Test Request 01050 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140376 |  |  |  | 7632-3C41552
WLD/N2NS/01571 | Ryan Shenton | 2021-08-09 07:52 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Cut Inc Ground Preparation - CH695.500 - CH696.640 | 2021-08-09 |  | 2021-08-21 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 695.5 | 696.64 | [6 empty] | HWP/N2NS/00407 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140375 |  |  |  | 7632-3C41220
WLD/N2NS/01570 | Jarryd Davis | 2021-08-09 06:47 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Harris Ahmad | Construction of skeleton track including placement of sleepers, threading of rail, welding and clipping up at Tycannah level crossing (LX 1829). |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 649.41 | 649.44 | [13 empty] | Callum Todd, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140373
WLD/N2NS/01569 | Jarryd Davis | 2021-08-09 06:43 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Harris Ahmad | Construction of skeleton track including placement of sleepers, threading of rail, welding and clipping up at Tycannah East level crossing (LX 3067). |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 648.1 | 648.13 | [13 empty] | Callum Todd, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140372
WLD/N2NS/01568 | Jarryd Davis | 2021-08-09 06:27 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Harris Ahmad | Construction of skeleton track including placement of sleepers, threading of rail, welding and clipping up at Pad 2 access level crossing (LX 556). |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 641.09 | 641.14 | [13 empty] | Callum Todd, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140368
WLD/N2NS/01567 | Jarryd Davis | 2021-08-09 05:58 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Harris Ahmad | Construction of skeleton track including placement of sleepers, threading of rail, welding and clipping up at Gurley Silos level crossing (LX 555). |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 636.32 | 636.35 | [13 empty] | Callum Todd, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140366
WLD/N2NS/01566 | Jarryd Davis | 2021-08-09 05:43 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Harris Ahmad | Construction of skeleton track including placement of sleepers, threading of rail, welding and clipping up at Gurley Creek Rd level crossing (LX 554). |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 635.69 | 635.72 | [13 empty] | Callum Todd, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140365
WLD/N2NS/01565 | Callum Todd | 2021-08-08 23:13 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Harris Ahmad | Construction of skeleton track including placement of sleepers, threading of rail, welding and clipping up at Kanimbla level crossing (LX 553). |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 631.15 | 631.18 | [13 empty] | Callum Todd, Jarryd Davis, Jazz Robinson, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140326
WLD/N2NS/01564 | Ryan Shenton | 2021-08-08 07:36 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH691.040 to CH691.820 - Layer 1 - 400mm | 2021-08-08 |  | 2021-08-17 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 691.04 | 691.82 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140320 |  |  |  | 7632-3C41552
WLD/N2NS/01563 | Ryan Shenton | 2021-08-08 07:29 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH688.540 to CH689.080 - Layer 1 - 400mm | 2021-08-08 |  | 2021-08-17 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 688.54 | 689.08 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test request 01041 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140319 |  |  |  | 7632-3C41552
WLD/N2NS/01562 | Ryan Shenton | 2021-08-08 07:13 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Clearing & Grubbing | Earthworks | Ryan Shenton | Clearing and Grubbing - Stage 3 - CH690.000 to 700.000 | 2021-08-08 |  | 2021-08-29 10:00 |  |  |  | Open | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00001 | [10 empty] | 690 | 700 | [6 empty] | HWP/N2NS/00399 | [6 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140318
WLD/N2NS/01561 | Ryan Shenton | 2021-08-07 05:27 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Topsoil Removal | Earthworks | Ryan Shenton | Topsoil Removal - Stage 3 - CH695.000 to CH705.000 | 2021-08-07 |  | 2021-08-28 10:00 |  |  |  | Open | AMS/N2NS/00001 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 695 | 705 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140310 |  |  |  | 7632-3C41190
WLD/N2NS/01560 | Ryan Shenton | 2021-08-07 05:24 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Topsoil Removal | Earthworks | Ryan Shenton | Topsoil Removal - Stage 3 - CH688.560 to CH695.000 | 2021-08-07 |  | 2021-08-28 10:00 |  |  |  | Open | AMS/N2NS/00001 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 688.56 | 695 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140309 |  |  |  | 7632-3C41190
WLD/N2NS/01559 | Ryan Shenton | 2021-08-07 05:19 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Topsoil Removal | Earthworks | Ryan Shenton | Topsoil Removal - Stage 3 - CH680.000 to CH687.500 | 2021-08-07 |  | 2021-08-28 10:00 |  |  |  | Open | AMS/N2NS/00001 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 680 | 687.5 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140308 |  |  |  | 7632-3C41190
WLD/N2NS/01558 | Ryan Shenton | 2021-08-07 05:09 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Cut Inc Ground Preparation - CH694.580 - CH695.500 | 2021-08-07 |  | 2021-08-21 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 694.58 | 695.5 | [6 empty] | HWP/N2NS/00388 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140307 |  |  |  | 7632-3C41220
WLD/N2NS/01557 | Ryan Shenton | 2021-08-06 07:19 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH681.925 to CH682.750 - Layer 2 - 400mm | 2021-08-06 |  | 2021-08-17 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 681.93 | 682.75 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 01025 Panda Result.pdf, N-21-179-828.pdf, Test Request 01039 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140304 |  |  |  | 7632-3C41552
WLD/N2NS/01556 | Richard Doering | 2021-08-06 07:10 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - spare | 2021-08-06 |  | 2021-08-09 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 658 | 658 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140303 |  |  |  | 7632-2C41552
WLD/N2NS/01555 | Richard Doering | 2021-08-06 07:09 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 Layer 1 (Siding) CH655.310 to 655.430 | 2021-08-06 |  | 2021-08-09 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 655.31 | 655.43 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140302 |  |  |  | 7632-2C41552
WLD/N2NS/01554 | Richard Doering | 2021-08-06 07:08 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - spare | 2021-08-06 |  | 2021-08-08 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 658 | 658 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140301 |  |  |  | 7632-2C41552
WLD/N2NS/01553 | Richard Doering | 2021-08-06 07:06 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - spare | 2021-08-06 |  | 2021-08-07 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 658 | 658 | [15 empty] | N-21-179-824.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140300 |  |  |  | 7632-2C41552
WLD/N2NS/01552 | Benjamin Philip | 2021-08-06 04:33 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Manufacture of Precast Rail Large & Small Concrete Box Culvert and Wing Walls - August 2021 | 2021-08-06 |  | 2021-08-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058 | [9 empty] | MIX/N2NS/00001 | 0 | 0 |  |  |  | PNC/N2NS/00132, PNC/N2NS/00134, PNC/N2NS/00136, PNC/N2NS/00137, PNC/N2NS/00138, PNC/N2NS/00139, PNC/N2NS/00142, PNC/N2NS/00143 | Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Pending Disposition Approval, Pending Disposition Approval, Pending Disposition Approval, Pending Disposition Approval | [8 empty] | Ganan Ganeshanantham, Johannes Mason |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140283 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/01551 | Ben Foster | 2021-08-05 21:05 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 8th August to 14th August 2021 TOTAL QTY - 1191.05 Tonnes | 2021-08-06 |  | 2021-08-14 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 |  |  |  |  | WLD/N2NS/00259 | [5 empty] | 0 | 0 | [15 empty] | 1028390 & 1028391.pdf, 1136542.pdf, 1136563.pdf, 1028376.pdf, 1136571.pdf, 1070269.pdf, 1028403 & 1028404.pdf, 1028407 & 1028408.pdf, 1028401 &1028402.pdf, 1028405 & 1028406.pdf, 1028417 & 1028418.pdf, 1028409.pdf, 1028415 1028416.pdf, 1136630.pdf, 1136564.pdf, 1028413 1028414.pdf, 1028431 & 1028432.pdf, 1028429 & 1028430.pdf, 1028423 & 1028424.pdf, 1028419 & 1028420.pdf, 1028426 & 1028427.pdf, 1028435.pdf, 1028425.pdf, 1136662.pdf, 1136681.pdf, 1028436 & 1028437.pdf, 1028445 & 1028446.pdf, 1136720.pdf, 5447.pdf, 1136543.pdf, 1136731.pdf, 2CH-202108-0011-00077332-F.pdf, 2AT-202108-0085-00077334-F.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140247 |  | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551
WLD/N2NS/01550 | Nabin Koirala | 2021-08-05 07:57 | Stage 2 - Penneys Road to Moree | Culverts | 647.925, 4/2400x1200, remove and rebuild | Culverts - Other | Other | Nabin Koirala | Excavation and Foundation preparation for Drainage Structures - Wing Walls |  |  | 2022-01-13 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 648.64 | 648.64 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Maddie Dahlstrom |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140246
WLD/N2NS/01549 | Nabin Koirala | 2021-08-05 07:56 | Stage 2 - Penneys Road to Moree | Culverts | 648.635, 6/2400x900, remove and rebuild | Culverts - Other | Other | Nabin Koirala | Excavation and Foundation preparation for Drainage Structures - Wing Walls |  |  | 2022-01-13 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 648.64 | 648.64 | [6 empty] | HWP/N2NS/00369, HWP/N2NS/00370, HWP/N2NS/00396 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Maddie Dahlstrom |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140245
WLD/N2NS/01548 | Richard Doering | 2021-08-05 07:50 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - spare | 2021-08-05 |  | 2021-08-06 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 658 | 658 | [15 empty] | TR 1016 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140244 |  |  |  | 7632-2C41552
WLD/N2NS/01547 | James Martin | 2021-08-05 07:36 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH693.700 - CH694.580 | 2021-08-05 |  | 2021-08-06 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 693.7 | 694.58 | [6 empty] | HWP/N2NS/00367 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140243 |  |  |  | 7632-3C41220
WLD/N2NS/01546 | Richard Doering | 2021-08-05 05:39 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - spare | 2021-08-05 |  | 2021-08-05 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 658 | 658 | [15 empty] | N-21-179-826.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140235 |  |  |  | 7632-2C41552
WLD/N2NS/01545 | Richard Doering | 2021-08-05 05:36 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 1 CH646.540 to CH647.080 | 2021-08-05 |  | 2021-08-05 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 646.54 | 647.08 | [15 empty] | TR 1014 Panda Results.pdf, Test Request 01024 Panda Results.pdf, N-21-179-812.pdf, E3 Stabilised Layer 1 WLD-N2NS-01545.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140234 |  |  |  | 7632-2C41552
WLD/N2NS/01544 | Harris Ahmad | 2021-08-04 22:13 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Harris Ahmad | Construction of skeleton track including placement of sleepers, threading of rail, welding and clipping up at waterloo level crossing (LX 1828). |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 627913 | 627941 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140203
WLD/N2NS/01543 | Arjan Sidhu | 2021-08-04 08:42 | Stage 2 - Penneys Road to Moree | Signalling | Other (Specify Location in Lot) | Signalling - URX / ULX | Other | Arjan Sidhu | Under Line Crossing (ULX) at CH 628 912. Route ID: WAT 17 + MCR |  |  | 2021-08-07 10:00 |  |  |  | Planned | AMS/N2NS/00012 | [11 empty] | 630.78 | 630.78 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140193 |  |  |  | 7632-GR81103
WLD/N2NS/01542 | Arjan Sidhu | 2021-08-04 08:41 | Stage 2 - Penneys Road to Moree | Signalling | Other (Specify Location in Lot) | Signalling - URX / ULX | Other | Arjan Sidhu | Under Line Crossing (ULX) at CH 628 912. Route ID: WAT 11 |  |  | 2021-08-07 10:00 |  |  |  | Planned | AMS/N2NS/00012 | [11 empty] | 6289.12 | 629.12 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140192 |  |  |  | 7632-GR81103
WLD/N2NS/01541 | Arjan Sidhu | 2021-08-04 08:38 | Stage 2 - Penneys Road to Moree | Signalling | Other (Specify Location in Lot) | Signalling - URX / ULX | Other | Arjan Sidhu | Under Line Crossing (ULX) at CH 628 742. Route ID: WAT 10B |  |  | 2021-08-07 10:00 |  |  |  | Planned | AMS/N2NS/00012 | [11 empty] | 628.74 | 628.74 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140191 |  |  |  | 7632-GR81103
WLD/N2NS/01540 | Richard Doering | 2021-08-04 08:04 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 2 - Mainline CH655.620 to CH656.220 | 2021-08-04 |  | 2021-08-05 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 655.62 | 656.22 | [15 empty] | Test Request 01008 Panda Results.pdf, Test Request 01023 Panda Results.pdf, N-21-179-830.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140190 |  |  |  | 7632-2C41552
WLD/N2NS/01539 | James Martin | 2021-08-04 07:28 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - Stage 2 - CH627.485 to CH627.585 - Layer 2 - 400mm | 2021-08-04 |  | 2021-08-05 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 627.49 | 627.59 | [6 empty] | HWP/N2NS/00390 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 01007 Panda Results.pdf, TR 1006 Panda Results.pdf, N-21-179-821.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140189 |  |  |  | 7632-2C41552
WLD/N2NS/01538 | Nabin Koirala | 2021-08-04 00:52 | Stage 2 - Penneys Road to Moree | Culverts | 650,040 NEW | Drainage - Other | Other | Frank Paraha | Excavation and Foundation Preparation for Wing Walls |  |  | 2021-08-06 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 650.04 | 650.04 | [6 empty] | HWP/N2NS/00374, HWP/N2NS/00397, HWP/N2NS/00398, HWP/N2NS/00402 | [6 empty] | Emma Conroy, Frank Paraha, Maddie Dahlstrom |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140165
WLD/N2NS/01537 | Nabin Koirala | 2021-08-04 | Stage 2 - Penneys Road to Moree | Culverts | 647.155, 40/3000x2400, remove and rebuild | Drainage - Other | Other | Frank Paraha | Cast- In Situ Apron Slab |  |  | 2022-01-18 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00038 | [9 empty] | 647.16 | 647.16 | [6 empty] | HWP/N2NS/00355, HWP/N2NS/00412 | [6 empty] | Emma Conroy, Frank Paraha, Maddie Dahlstrom |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140160
WLD/N2NS/01536 | Nabin Koirala | 2021-08-03 23:58 | Stage 2 - Penneys Road to Moree | Culverts | 647.925, 4/2400x1200, remove and rebuild | Culverts - Other | Other | Frank Paraha | Excavation and foundation preparation for Drainage Structures - WIng Walls |  |  | 2021-11-19 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 647.93 | 647.93 | [6 empty] | HWP/N2NS/00352, HWP/N2NS/00353, HWP/N2NS/00356, HWP/N2NS/00371, HWP/N2NS/00372, HWP/N2NS/00373, HWP/N2NS/00400, HWP/N2NS/00401 | [6 empty] | Emma Conroy, Maddie Dahlstrom |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140159
WLD/N2NS/01535 | Harris Ahmad | 2021-08-03 10:02 | Stage 2 - Penneys Road to Moree | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Railway Trackwork | Track | Harris Ahmad | Construction of skeleton track including placement of sleepers, threading of rail, welding and clipping up between CH625.831 to CH627.175 on the mainline (Stage 2A II) | 2021-08-03 |  | 2021-08-31 10:00 |  |  |  | Open | AMS/N2NS/00009 | ITP/N2NS/00013 | [10 empty] | 625.83 | 627.18 |  |  |  | PNC/N2NS/00130 | Open | [11 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140147
WLD/N2NS/01534 | Richard Doering | 2021-08-03 07:24 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 Layer 2 CH657.280 to CH657.740 | 2021-08-03 |  | 2021-08-04 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 657.28 | 657.74 | [15 empty] | N-21-179-808.pdf, Test Request 01022 Panda Results.pdf, Test Request 0995 Panda Results.pdf, N-21-179-860.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140144 |  |  |  | 7632-2C41552
WLD/N2NS/01533 | Richard Doering | 2021-08-03 07:22 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 2 - Mainline | 2021-08-03 |  | 2021-08-03 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 656.26 | 656.32 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140143 |  |  |  | 7632-2C41552
WLD/N2NS/01532 | Emma Conroy | 2021-08-02 22:42 | Stage 2 - Penneys Road to Moree | Culverts | 650.690, 2/2400x900, remove and rebuild | Drainage - Other | Other | Frank Paraha | excavation and foundation preparation for wingwalls |  |  | 2022-05-20 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 650.69 | 650.69 | [13 empty] | Frank Paraha, Maddie Dahlstrom, Nabin Koirala |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140103
WLD/N2NS/01531 | Emma Conroy | 2021-08-02 22:41 | Stage 2 - Penneys Road to Moree | Culverts | 650.330, 1/2400x900, remove and rebuild | Drainage - Other | Other | Frank Paraha | excavation and foundation preparation for wingwalls |  |  | 2022-05-20 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 650.33 | 650.33 | [13 empty] | Frank Paraha, Maddie Dahlstrom, Nabin Koirala |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140102
WLD/N2NS/01530 | Emma Conroy | 2021-08-02 22:39 | Stage 2 - Penneys Road to Moree | Culverts | 648.240, 6/2400x900, remove and rebuild | Drainage - Other | Other | Frank Paraha | excavation and foundation preparation for wingwalls |  |  | 2022-05-20 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 648.24 | 648.24 | [13 empty] | Frank Paraha, Maddie Dahlstrom, Nabin Koirala |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140101
WLD/N2NS/01529 | Emma Conroy | 2021-08-02 22:37 | Stage 2 - Penneys Road to Moree | Culverts | 647.670, 10/3000x1500, remove and rebuild | Drainage - Other | Other | Frank Paraha | excavation and foundation preparation for wingwalls |  |  | 2022-05-20 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 647.67 | 647.67 | [13 empty] | Frank Paraha, Maddie Dahlstrom, Nabin Koirala |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140100
WLD/N2NS/01528 | Emma Conroy | 2021-08-02 22:36 | Stage 2 - Penneys Road to Moree | Culverts | 647.315, 10/3000x1200, remove and rebuild | Drainage - Other | Other | Frank Paraha | excavation and foundation preparation for wingwalls |  |  | 2022-05-20 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 647.32 | 647.32 | [13 empty] | Frank Paraha, Maddie Dahlstrom, Nabin Koirala |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140099
WLD/N2NS/01527 | Emma Conroy | 2021-08-02 22:35 | Stage 2 - Penneys Road to Moree | Culverts | 647.155, 40/3000x2400, remove and rebuild | Drainage - Other | Other | Frank Paraha | excavation and foundation preparation for wingwalls |  |  | 2022-05-20 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 647.16 | 647.16 | [13 empty] | Frank Paraha, Maddie Dahlstrom, Nabin Koirala |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140098
WLD/N2NS/01526 | Emma Conroy | 2021-08-02 22:31 | Stage 2 - Penneys Road to Moree | Culverts | 647.155, 40/3000x2400, remove and rebuild | Culverts - Other | Earthworks | Frank Paraha | 647.155 - Excavation & Foundation Preparation - Wingwalls |  |  | 2021-07-26 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 |  |  |  | WLD/N2NS/00572, WLD/N2NS/01062, WLD/N2NS/01449 | [5 empty] | 647 | 652.72 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Maddie Dahlstrom, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140097 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2C41460
WLD/N2NS/01525 | Richard Doering | 2021-08-02 08:14 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Richard Doering | Cut inc Ground Prep | 2021-08-02 |  | 2021-08-02 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 647.2 | 647.46 | [15 empty] | N-21-179-792.pdf, N-21-179-811.pdf, N-21-179-823.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140092 |  |  |  | 7632-2C41220
WLD/N2NS/01524 | Richard Doering | 2021-08-02 08:02 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 Layer 2 CH657.030 to CH657.280 | 2021-08-02 |  | 2021-08-03 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 657.03 | 657.28 | [15 empty] | Test Request 0991 Panda Results.pdf, N-21-179-827.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140090 |  |  |  | 7632-2C41552
WLD/N2NS/01523 | Aziz Kamaoui | 2021-08-02 07:52 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Trackwork - Bottom Ballast | Track | Aziz Kamaoui | LX1828 - CH627.920 - CH627.950 - Installation of Bottom Ballast | 2021-08-02 |  | 2021-08-06 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00007 | CHK/N2NS/00033 | [9 empty] | 627.92 | 627.95 | [6 empty] | HWP/N2NS/00351 | [9 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140087
WLD/N2NS/01522 | James Martin | 2021-08-02 07:24 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - Stage 3 - CH68X.XXX to CH68X.XXX - Layer 2 - 400mm | 2021-08-02 |  | 2021-08-17 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 1 | 2 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | N-21-179-825.pdf, Test Request 01026 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140086 |  |  |  | 7632-3C41552
WLD/N2NS/01521 | James Martin | 2021-08-02 07:11 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - Stage 2 - CH627.485 to CH627.585 - Layer 1 - 400mm | 2021-08-02 |  | 2021-08-14 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 627.49 | 627.59 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR 988 Panda Results.pdf, Test Request 0943 Panda Results.pdf, N-21-179-783.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140085 |  |  |  | 7632-2C41552
WLD/N2NS/01520 | Miaya Tighe | 2021-08-02 03:24 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Jake Mossman | capping placement CH 640.665 - 641.150 Mainline |  |  | 2021-08-09 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 640.67 | 641.15 | [13 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140053
WLD/N2NS/01519 | Miaya Tighe | 2021-08-02 03:17 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Jake Mossman | capping placement CH 640.405 - 640.635 Mainline |  |  | 2021-08-22 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 640.41 | 604.64 | [13 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140052
WLD/N2NS/01518 | Miaya Tighe | 2021-08-02 01:55 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Jake Mossman | capping placement CH 640.085 - 640.355 Mainline |  |  | 2021-08-21 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 640.09 | 640.36 | [13 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140050
WLD/N2NS/01517 | Miaya Tighe | 2021-08-02 01:47 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Jake Mossman | capping placement CH 639.830 - 640.075 Mainline |  |  | 2021-08-10 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 639.83 | 640.08 | [13 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140049
WLD/N2NS/01516 | Miaya Tighe | 2021-08-02 01:29 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Jake Mossman | capping placement CH 639.170 - 639.650 Mainline |  |  | 2021-08-10 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 639.17 | 639.65 | [6 empty] | HWP/N2NS/00421, HWP/N2NS/00422 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140048
WLD/N2NS/01515 | Miaya Tighe | 2021-08-02 01:21 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Jake Mossman | capping placement CH 638.925 - 639.150 Mainline |  |  | 2021-08-09 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 638.93 | 639.15 | [6 empty] | HWP/N2NS/00421 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140047
WLD/N2NS/01514 | Miaya Tighe | 2021-08-02 01:12 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Jake Mossman | capping placement CH 638.530 - 638.900 Mainline |  |  | 2021-08-07 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 638.53 | 638.9 | [6 empty] | HWP/N2NS/00421 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140046
WLD/N2NS/01513 | Miaya Tighe | 2021-08-02 01:03 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Jake Mossman | Capping placement CH 638.140 - 638.500 Mainline |  |  | 2021-08-07 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 638.14 | 638.5 | [6 empty] | HWP/N2NS/00421 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140044
WLD/N2NS/01512 | Miaya Tighe | 2021-08-02 00:52 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Jake Mossman | Capping placement CH637.290 - 638.140 Mainline |  |  | 2021-08-06 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 637.29 | 638.14 | [6 empty] | HWP/N2NS/00420 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140043
WLD/N2NS/01511 | Miaya Tighe | 2021-08-02 00:45 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Jake Mossman | Capping Placement CH 637.170 - 637.29 Mainline |  |  | 2021-08-04 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 637.17 | 637.29 | [6 empty] | HWP/N2NS/00420 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140042
WLD/N2NS/01510 | Miaya Tighe | 2021-08-02 00:36 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Jake Mossman | Capping placement CH636.720 - 637.170 Mainline |  |  | 2021-08-04 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 |  |  |  | WLD/N2NS/01379 | [5 empty] | 636.72 | 637.17 | [6 empty] | HWP/N2NS/00419 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140041
WLD/N2NS/01509 | Miaya Tighe | 2021-08-02 00:08 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Jake Mossman | Capping Placement CH 633.450 - 633.700 Main alignment |  |  | 2021-08-14 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 633.45 | 633.7 | [6 empty] | HWP/N2NS/00455 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140039
WLD/N2NS/01508 | Keegan Baker | 2021-08-01 22:32 | Stage 2 - Penneys Road to Moree | Culverts | 627.280, 50/3000x2400, remove and rebuild | Drainage - Other | Other | Keegan Baker | Backfill of Culvert 627.280 |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00037 | [9 empty] | 627.28 | 627.28 | [6 empty] | HWP/N2NS/00384 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140036
WLD/N2NS/01507 | Keegan Baker | 2021-08-01 22:31 | Stage 2 - Penneys Road to Moree | Culverts | 633.780, 35/3000x2400, remove and rebuild | Drainage - Other | Other | Keegan Baker | Backfill of Culvert 633.780 |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00037 | [9 empty] | 633.78 | 633.78 | [6 empty] | HWP/N2NS/00409 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140035
WLD/N2NS/01506 | Keegan Baker | 2021-08-01 22:17 | Stage 2 - Penneys Road to Moree | Culverts | 639.740, 60/2400x900, remove and rebuild | Drainage - Other | Other | Keegan Baker | Backfill of Culvert 639.740 |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00037 | [9 empty] | 639.74 | 639.74 | [6 empty] | HWP/N2NS/00381 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140034
WLD/N2NS/01505 | Keegan Baker | 2021-08-01 22:16 | Stage 2 - Penneys Road to Moree | Culverts | 640,080, 5/2400x900, new build | Drainage - Other | Other | Keegan Baker | Backfill of Culvert 640.080 |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00037 | [9 empty] | 647.16 | 647.16 | [6 empty] | HWP/N2NS/00380 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140033
WLD/N2NS/01504 | James Martin | 2021-08-01 07:48 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - Stage 2 - CH633.840 to CH634.400 - Layer 2 - 400mm | 2021-08-07 |  | 2021-08-16 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 633.84 | 634.56 | [6 empty] | HWP/N2NS/00390 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 01036 Panda Results.pdf, 41DE89AD-60C7-46B5-9A8B-F469B625BA23.JPG, 65F29003-035F-4DB5-98D5-B8B452E61F1E.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140031 |  |  |  | 7632-2C41552
WLD/N2NS/01503 | James Martin | 2021-08-01 07:34 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - Stage 3 - CH682.750 to CH683.400 - Layer 2 - 400mm | 2021-08-15 |  | 2021-08-16 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 682.75 | 683.4 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140030 |  |  |  | 7632-3C41552
WLD/N2NS/01502 | Keegan Baker | 2021-08-01 07:21 | Stage 2 - Penneys Road to Moree | Culverts | 638.525, 13/2400x900, remove and rebuild | Culverts - Other | Concrete | Keegan Baker | 638.525 - Cast-In-situ Cut-off Walls |  |  | 2021-09-30 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [9 empty] | 638.53 | 638.53 | [6 empty] | HWP/N2NS/00347, HWP/N2NS/00413 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140029
WLD/N2NS/01501 | Arjan Sidhu | 2021-08-01 06:52 | Stage 2 - Penneys Road to Moree | Signalling | Other (Specify Location in Lot) | Signalling - URX / ULX | Other | Arjan Sidhu | Under Line Crossing (ULX) at CH 628 55 |  |  | 2021-08-07 10:00 |  |  |  | Planned | AMS/N2NS/00012 | [11 empty] | 628.55 | 628.55 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140028 |  |  |  | 7632-GR81103
WLD/N2NS/01500 | James Martin | 2021-08-01 06:46 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH692.800 - CH693.700 | 2021-08-01 |  | 2021-08-02 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 692.8 | 693.7 | [6 empty] | HWP/N2NS/00346 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140027 |  |  |  | 7632-3C41220
WLD/N2NS/01499 | Keegan Baker | 2021-08-01 03:32 | Stage 2 - Penneys Road to Moree | Culverts | Other (Specify Location in Lot) | Culverts - Other | Concrete | Keegan Baker | Existing Culvert 627.490 - Headwall Extension |  |  | 2021-09-30 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00038 | [9 empty] | 627.49 | 627.49 | [6 empty] | HWP/N2NS/00345, HWP/N2NS/00368, HWP/N2NS/00386 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140026
WLD/N2NS/01498 | Keegan Baker | 2021-07-31 07:26 | Stage 2 - Penneys Road to Moree | Culverts | 636.705, 4/600x600, remove and rebuild (RRA) | Culverts - Other | Earthworks | Keegan Baker | Culvert Backfill Proof Rolls |  |  | 2021-08-31 10:00 |  |  |  | Planned | [12 empty] | 627.2 | 637 | [6 empty] | HWP/N2NS/00338, HWP/N2NS/00339 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140025
WLD/N2NS/01497 | Richard Doering | 2021-07-31 06:27 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 Layer 2 (Siding) CH655.800 to CH655.960 | 2021-07-31 |  | 2021-08-02 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 655.8 | 655.96 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140024 |  |  |  | 7632-2C41552
WLD/N2NS/01496 | Richard Doering | 2021-07-31 05:38 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 Layer 3 of 3 CH653.985 to CH654.520 | 2021-07-31 |  | 2021-08-02 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 653.99 | 654.52 | [15 empty] | TR 1009 Panda Results.pdf, Test Request 0946 Panda Results.pdf, N-21-179-791.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140023 |  |  |  | 7632-2C41552
WLD/N2NS/01495 | Richard Doering | 2021-07-31 05:33 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 Layer 3 of 3 CH653.180 to 653.985 | 2021-07-31 |  | 2021-08-01 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 653.18 | 653.99 | [15 empty] | Test Request 0945 Panda Results.pdf, N-21-179-790.pdf, Test Request 0996 Panda Results.pdf, N-21-179-837.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140022 |  |  |  | 7632-2C41552
WLD/N2NS/01494 | Richard Doering | 2021-07-31 05:26 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 1 - Tycannah Siding CH656.000 to CH656.230 | 2021-07-31 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 656 | 656.23 | [15 empty] | Test Request 0944 Panda Results.pdf, N-21-179-786.pdf, TR 992 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140021 |  |  |  | 7632-2C41552
WLD/N2NS/01493 | Keegan Baker | 2021-07-30 08:02 | Stage 2 - Penneys Road to Moree | Culverts | 633.780, 35/3000x2400, remove and rebuild | Culverts - Other | Concrete | Keegan Baker | 633.780 - Cast-In-situ Apron Slab |  |  | 2021-09-30 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [9 empty] | 633.78 | 633.78 | [6 empty] | HWP/N2NS/00337 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140006
WLD/N2NS/01492 | Keegan Baker | 2021-07-30 07:01 | Stage 2 - Penneys Road to Moree | Culverts | 639.740, 60/2400x900, remove and rebuild | Culverts - Other | Concrete | Keegan Baker | 639.740 - Cast-In-situ Cut-off Walls |  |  | 2021-09-30 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [9 empty] | 639.74 | 639.74 | [6 empty] | HWP/N2NS/00335 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140004
WLD/N2NS/01491 | Kallen Doong | 2021-07-30 06:53 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH683.400 to CH684.100 - Layer 2 - 400mm | 2021-08-12 |  | 2021-08-11 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 683.4 | 684.1 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0930 Panda Results.pdf, N-21-186-142.pdf, Test Request 0986 Panda Result.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/140003 |  |  |  | 7632-3C41552
WLD/N2NS/01490 | Ben Foster | 2021-07-30 04:01 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH690.830 - CH691.800 | 2021-07-30 |  | 2021-08-15 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 690.83 | 691.8 | [6 empty] | HWP/N2NS/00334 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139998 |  |  |  | 7632-3C41220
WLD/N2NS/01489 | Ben Foster | 2021-07-30 00:18 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 1st August to 7th August 2021 TOTAL QTY - 798.01 Tonnes | 2021-07-30 |  | 2021-08-07 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 |  |  |  |  | WLD/N2NS/00259 | [5 empty] | 0 | 0 | [15 empty] | 1028349.pdf, 1028352 & 1028353.pdf, 1028358 & 1028359.pdf, 1028356 & 1028357.pdf, 1028363 & 1028364.pdf, 1136398.pdf, 1136424.pdf, 1028365 & 1028366.pdf, 1136468.pdf, 1028351.pdf, 1136440.pdf, 1136507.pdf, 1028373 & 1028374.pdf, 1028377 & 1028378.pdf, 1028375.pdf, 1070246.pdf, 1028383 1028384.pdf, 1136527.pdf, 1136541.pdf, 1136492.pdf, 1028385 & 1028386.pdf, 2CH-202108-0007-00077253-F.pdf, 2AT-202108-0005-00077304-F.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139991 |  | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551
WLD/N2NS/01488 | Keegan Baker | 2021-07-29 08:04 | Stage 2 - Penneys Road to Moree | Culverts | 638.525, 13/2400x900, remove and rebuild | Drainage - Other | Other | Keegan Baker | Backfill of Culvert 638.525 |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00037 | [9 empty] | 638.53 | 638.53 | [6 empty] | HWP/N2NS/00383 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139984
WLD/N2NS/01487 | Richard Doering | 2021-07-29 07:09 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 2 CH650.090 to CH650.320 | 2021-07-29 |  | 2021-07-30 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 650.09 | 650.32 | [15 empty] | Test Request 0919 Panda Results.pdf, N-21-179-787.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139974 |  |  |  | 7632-2C41552
WLD/N2NS/01486 | Brendan Meagher | 2021-07-29 05:29 | Stage 2 - Penneys Road to Moree | Culverts | 638.920, 14/1800x600, new build | Culverts - Rock Protection | Other | Keegan Baker | 638.920 - Rock Apron / Scour Protection | 2021-07-29 |  | 2021-07-16 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00009 | [9 empty] | 638.92 | 638.92 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139967
WLD/N2NS/01485 | Brendan Meagher | 2021-07-29 05:20 | Stage 2 - Penneys Road to Moree | Culverts | 639.160, 14/1800x600, new build | Culverts - Rock Protection | Other | Keegan Baker | 639.160 - Rock Apron / Scour Protection | 2021-07-29 |  | 2021-07-16 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00009 | [9 empty] | 639.16 | 639.16 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139966
WLD/N2NS/01484 | Brendan Meagher | 2021-07-29 04:56 | Stage 2 - Penneys Road to Moree | Culverts | 627.760, 10/2400x1200, new build | Culverts - Rock Protection | Other | Keegan Baker | 627.760 - Rock Apron / Scour Protection | 2021-07-29 |  | 2021-07-16 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00009 | [9 empty] | 627.76 | 627.76 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139965
WLD/N2NS/01483 | Ryan Shenton | 2021-07-29 02:55 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH639.830 to CH640.070 - Layer 2 - 400mm | 2021-08-03 |  | 2021-08-08 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 639.83 | 640.07 | [6 empty] | HWP/N2NS/00336 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0935 Panda Results.pdf, Test Request 0917 Panda Results.pdf, N-21-179-731.pdf, N-21-179-757.pdf, E3 Stabilised Layer 2 WLD-N2NS-01483.pdf, N-21-179-836.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139945 |  |  |  | 7632-3C41552
WLD/N2NS/01482 | Ryan Shenton | 2021-07-29 02:46 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH684.100 to CH684.830 - Layer 2 - 400mm | 2021-07-29 |  | 2021-08-08 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 684.1 | 684.83 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0916 Panda Results.pdf, N-21-186-145.pdf, Test Request 0929 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139944 |  |  |  | 7632-3C41552
WLD/N2NS/01481 | Miaya Tighe | 2021-07-29 00:18 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Arjan Sidhu | Capping placement CH 632.60 - 633.450 Mainline | 2021-07-29 |  | 2021-08-12 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 632.6 | 633.45 | [6 empty] | HWP/N2NS/00331, HWP/N2NS/00344 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139934 |  |  |  | 7632-2C47051
WLD/N2NS/01480 | Miaya Tighe | 2021-07-29 00:06 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Arjan Sidhu | Capping placement CH 631.595 - 632.600 Mainline | 2021-07-29 |  | 2021-08-12 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 631.6 | 632.6 | [6 empty] | HWP/N2NS/00331 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139933 |  |  |  | 7632-2C47051
WLD/N2NS/01479 | Miaya Tighe | 2021-07-28 23:40 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Arjan Sidhu | Capping placement CH630.930 - 631.125 Mainline | 2021-07-29 |  | 2021-08-12 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 630.93 | 631.13 | [6 empty] | HWP/N2NS/00344 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139930 |  |  |  | 7632-2C47051
WLD/N2NS/01478 | Miaya Tighe | 2021-07-28 23:08 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Arjan Sidhu | Capping placement CH 626.640 - 627.140 Mainline | 2021-07-29 |  | 2021-08-12 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 626.64 | 627.14 |  |  |  | PNC/N2NS/00145 | Draft |  | HWP/N2NS/00455 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139929 |  |  |  | 7632-1C47051
WLD/N2NS/01477 | Miaya Tighe | 2021-07-28 21:57 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Arjan Sidhu | Capping Placement CH 635.430 - 635.74 Mainline | 2021-07-29 |  | 2021-08-12 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 635.43 | 635.74 | [6 empty] | HWP/N2NS/00332, HWP/N2NS/00377 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139928 |  |  |  | 7632-1C47051
WLD/N2NS/01476 | Miaya Tighe | 2021-07-28 21:42 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Arjan Sidhu | Capping Placement CH 635.13 - 635.39 Mainline | 2021-07-29 |  | 2021-08-12 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 635.13 | 635.39 | [6 empty] | HWP/N2NS/00332 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139927 |  |  |  | 7632-1C47051
WLD/N2NS/01475 | Arjan Sidhu | 2021-07-28 08:19 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Arjan Sidhu | Capping Placement 25m either side of Waterloo Road Level Crossing (CH627.9 - 627.95) | 2021-07-28 |  | 2021-08-11 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 627.9 | 627.95 | [13 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139925 |  |  |  | 7632-1C47051
WLD/N2NS/01474 | Ryan Shenton | 2021-07-28 07:59 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH684.800 to CH685.470 - Layer 2 - 400mm | 2021-07-28 |  | 2021-08-08 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 684.8 | 685.47 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0914 Panda Results.pdf, Test Request 0893 Panda Results.pdf, N-21-186-143.pdf, N-21-186-149.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139924 |  |  |  | 7632-3C41552
WLD/N2NS/01473 | Ryan Shenton | 2021-07-28 07:26 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Cut Inc Ground Preparation - CH690.830 - CH691.800 | 2021-07-28 |  | 2021-08-15 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 690.83 | 691.8 | [6 empty] | HWP/N2NS/00334 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139919 |  |  |  | 7632-3C41220
WLD/N2NS/01472 | Miaya Tighe | 2021-07-28 06:31 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Arjan Sidhu | Capping Placement CH 634.45 - 635.130 Mainline | 2021-07-28 |  | 2021-08-11 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 634.45 | 635.13 | [6 empty] | HWP/N2NS/00325 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139911 |  |  |  | 7632-1C47051
WLD/N2NS/01471 | George Yousef | 2021-07-27 23:31 | Stage 2 - Penneys Road to Moree | Culverts | 650,040 NEW | Culverts - Installation of Box Culverts | Concrete | Frank Paraha | 650.040 - Cast In Situ Base Slab | 2021-07-28 |  | 2021-08-06 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00038 |  |  |  | WLD/N2NS/00090, WLD/N2NS/00574 |  |  |  |  | MIX/N2NS/00007 | 650.04 | 650.04 | [13 empty] | Emma Conroy, Keegan Baker, Maddie Dahlstrom, Nabin Koirala |  | 650.040 - Concrete Pour Record.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139896 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/01470 | Ryan Shenton | 2021-07-27 08:40 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Cut Inc Ground Preparation - CH690.040 - CH690.800 | 2021-07-27 |  | 2021-08-15 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 690.04 | 690.8 | [6 empty] | HWP/N2NS/00324, HWP/N2NS/00334 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139888 |  |  |  | 7632-3C41220
WLD/N2NS/01469 | Ryan Shenton | 2021-07-27 08:10 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH630.400 to CH630.800 RMAR & Widenings- Layer 1 - 400mm | 2021-07-27 |  | 2021-08-08 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 630.4 | 630.8 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0915 Panda Results.pdf, Test Request 0886 Panda Results.pdf, N-21-179-749.pdf, N-21-179-754.pdf, N-21-179-838.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139887 |  |  |  | 7632-3C41552
WLD/N2NS/01468 | Richard Doering | 2021-07-27 07:54 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 Layer 2 CH648.120 to 648.380 | 2021-07-27 |  | 2021-07-28 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 648.12 | 648.32 | [15 empty] | Test Request 0918 Panda Results.pdf, Test Request 0948 Panda Results.pdf, N-21-179-788.pdf, 19CB52BB-63D1-4347-A709-29B33936FAC7.JPG, F381085E-179D-4786-92DE-EBF0EA068707.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139886 |  |  |  | 7632-2C41552
WLD/N2NS/01467 | Richard Doering | 2021-07-27 07:47 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 2 CH649.150 to 649.500 | 2021-07-27 |  | 2021-07-28 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 649.15 | 649.5 | [15 empty] | Test Request 0881 Panda Results.pdf, N-21-179-834.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139885 |  |  |  | 7632-2C41552
WLD/N2NS/01466 | Ryan Shenton | 2021-07-27 07:37 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH634.400 to CH634.564- Layer 2 - 400mm | 2021-07-27 |  | 2021-08-15 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 634.4 | 634.56 | [6 empty] | HWP/N2NS/00429 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | 19CB52BB-63D1-4347-A709-29B33936FAC7.JPG, F381085E-179D-4786-92DE-EBF0EA068707.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139884 |  |  |  | 7632-3C41552
WLD/N2NS/01465 | Ryan Shenton | 2021-07-27 07:20 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH685.470 to CH685.890 - Layer 2 - 400mm | 2021-07-27 |  | 2021-08-08 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 685.47 | 685.89 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0879 Panda Results.pdf, N-21-186-144.pdf, Test Request 0892 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139883 |  |  |  | 7632-3C41552
WLD/N2NS/01464 | Ryan Shenton | 2021-07-27 05:27 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Stage 3 - Layer 1 Type E3 Treatment 400mm - CH687.870 to CH688.540 | 2021-07-27 |  | 2021-08-17 10:00 |  |  |  | Open | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00001 |  |  |  |  | WLD/N2NS/00397 | [5 empty] | 687.87 | 688.54 | [13 empty] | Richard Doering |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139833 |  |  |  | 7632-GC48000
WLD/N2NS/01463 | Aziz Kamaoui | 2021-07-27 04:20 | Stage 2 - Penneys Road to Moree | Drainage | Other (Specify Location in Lot) | Drainage - Reinforced Concrete Pipes | Roadworks | Aziz Kamaoui | CCTV Lot for LC RCP Pipes in Stage 2 |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00038 | [9 empty] | 627.8 | 643.57 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139808
WLD/N2NS/01462 | Keegan Baker | 2021-07-27 02:12 | Stage 2 - Penneys Road to Moree | Culverts | 638.140, 5/2400x1200, remove and rebuild | Culverts - Other | Other | Keegan Baker | 639.160 - Backfill of Culverts |  |  | 2021-09-30 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00037 | [9 empty] | 639.16 | 639.16 | [6 empty] | HWP/N2NS/00343 | [6 empty] | Brendan Meagher, Emma Conroy, Keegan Baker, Maddie Dahlstrom, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139801
WLD/N2NS/01461 | Miaya Tighe | 2021-07-26 23:57 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Earthworks - Filling | Earthworks | Arjan Sidhu | Matpol Structural Fill 40,000T Stockpile SF6S | 2021-07-27 |  | 2021-08-30 10:00 | Benjamin Philip | 2021-07-27 | 2021-07-27 00:07 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 | [9 empty] | 625.55 | 667 | Miaya Tighe | 2021-07-26 23:58 | [5 empty] | Lot closed |  | 2021-07-27 00:07 |  |  |  | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  | N-21-253-2.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139798 | 2021-07-29 18:40 |  |  |  |  | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/01460 | Ryan Shenton | 2021-07-26 08:01 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH630.010 to CH630.400 RMAR & Widenings- Layer 1 - 400mm | 2021-07-26 |  | 2021-08-08 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 630.01 | 630.4 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | N-21-179-706.pdf, Test Request 0869 Panda Results.pdf, N-21-179-781.pdf, TR 885 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139782 |  |  |  | 7632-3C41552
WLD/N2NS/01459 | Ryan Shenton | 2021-07-26 07:07 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH686.490 to CH687.500 - Layer 1 - 400mm | 2021-07-26 |  | 2021-08-08 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 686.49 | 687.5 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR 866 Panda Results.pdf, N-21-186-135.pdf, N-21-179-835.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139767 |  |  |  | 7632-3C41552
WLD/N2NS/01458 | Miaya Tighe | 2021-07-26 04:55 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Earthworks - Filling | Earthworks | Arjan Sidhu | Matpol Structural Fill 20,000T Stockpile SF6A | 2021-07-26 |  | 2021-08-30 10:00 | Benjamin Philip | 2021-07-27 | 2021-07-26 22:18 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 | [9 empty] | 625.55 | 667 | Miaya Tighe | 2021-07-26 04:58 | [5 empty] | Lot closed |  | 2021-07-26 22:18 |  |  |  | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  | N-21-253-1.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139722 | 2021-07-29 18:40 |  |  |  |  | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/01457 | Ryan Shenton | 2021-07-25 08:13 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Cut Inc Ground Preparation - CH688.540 - CH690.040 | 2021-07-25 |  | 2021-08-15 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 688.54 | 690.04 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_4645.JPG, IMG_4636.JPG, IMG_4641.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139619 |  |  |  | 7632-3C41220
WLD/N2NS/01456 | Ryan Shenton | 2021-07-25 08:07 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH685.900 to CH686.350 - Layer 1 - 400mm | 2021-07-25 |  | 2021-08-08 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 685.9 | 686.35 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR 864 Panda results.pdf, Test Request 0872 Panda Results.pdf, N-21-186-122.pdf, N-21-186-140.pdf, N-21-186-148.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139618 |  |  |  | 7632-3C41552
WLD/N2NS/01455 | Ryan Shenton | 2021-07-25 07:57 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH628.475 to CH629.060 RMAR & Widenings- Layer 1 - 400mm | 2021-07-25 |  | 2021-08-08 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 628.48 | 629.06 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0934 Retests Panda Results.pdf, Test Request 0870 Panda Results.pdf, N-21-179-682.pdf, N-21-179-778.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139617 |  |  |  | 7632-3C41552
WLD/N2NS/01454 | Frank Paraha | 2021-07-24 12:06 | Stage 2 - Penneys Road to Moree | Culverts | 648.240, 6/2400x900, remove and rebuild | Culverts - Other | Earthworks | Frank Paraha | 648.240 - Excavation & Foundation Preparation - Wingwalls | 2021-07-24 |  | 2021-07-24 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 648.24 | 648.24 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Maddie Dahlstrom, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139615 |  |  |  | 7632-2C41460
WLD/N2NS/01453 | Brendan Meagher | 2021-07-24 03:48 | Stage 2 - Penneys Road to Moree | Culverts | 638.920, 14/1800x600, new build | Culverts - Other | Other | Nabin Koirala | 638.920 - Backfill of Culverts | 2021-07-24 |  | 2021-08-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00037 | [9 empty] | 638.92 | 638.92 | [6 empty] | HWP/N2NS/00342 | [6 empty] | Brendan Meagher, Emma Conroy, Keegan Baker, Maddie Dahlstrom, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139613
WLD/N2NS/01452 | Brendan Meagher | 2021-07-24 03:46 | Stage 2 - Penneys Road to Moree | Culverts | 638.140, 5/2400x1200, remove and rebuild | Culverts - Other | Other | Nabin Koirala | 638.140 - Backfill of Culverts | 2021-07-24 |  | 2021-08-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00037 | [9 empty] | 638.14 | 638.14 | [6 empty] | HWP/N2NS/00341 | [6 empty] | Brendan Meagher, Emma Conroy, Keegan Baker, Maddie Dahlstrom, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139612
WLD/N2NS/01451 | Brendan Meagher | 2021-07-24 02:18 | Stage 2 - Penneys Road to Moree | Culverts | 656,240 New | Culverts - Other | Earthworks | Frank Paraha | 656.240 - Backfill | 2021-07-24 |  | 2021-07-20 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 | [9 empty] | 656.24 | 656.24 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139611 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2C41460
WLD/N2NS/01450 | Brendan Meagher | 2021-07-24 02:17 | Stage 2 - Penneys Road to Moree | Culverts | 653.150, 1/600x600, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | 653.150 - Installation of Pre-Cast Units | 2021-07-24 |  | 2021-07-20 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 |  |  |  | WLD/N2NS/00571, WLD/N2NS/00708, WLD/N2NS/01390 | [5 empty] | 653.15 | 653.15 |  |  |  | PNC/N2NS/00111 | Disposition Approved | [8 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | WLDN2NS01450LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139610 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/01449 | Brendan Meagher | 2021-07-24 02:17 | Stage 2 - Penneys Road to Moree | Culverts | 652.715, 1/1800x600, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | 652.715 - Installation of Pre-Cast Units | 2021-07-24 |  | 2021-07-20 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 |  |  |  | WLD/N2NS/00572, WLD/N2NS/01062, WLD/N2NS/01388 | [5 empty] | 652.72 | 652.72 | [6 empty] | HWP/N2NS/00453 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | WLDN2NS01449LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139609 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/01448 | Brendan Meagher | 2021-07-24 02:16 | Stage 2 - Penneys Road to Moree | Culverts | 652.530, 2/1800x600, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | 652.530 - Installation of Pre-Cast Units | 2021-07-24 |  | 2021-07-20 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 |  |  |  | WLD/N2NS/00573, WLD/N2NS/01334, WLD/N2NS/01387 | [5 empty] | 652.53 | 652.53 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | WLDN2NS01448LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139608 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/01447 | Brendan Meagher | 2021-07-24 02:14 | Stage 2 - Penneys Road to Moree | Culverts | 648.240, 6/2400x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | 648.240 - Installation of Pre-Cast Units | 2021-07-24 |  | 2021-07-20 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 |  |  |  | WLD/N2NS/01341, WLD/N2NS/01344 | [5 empty] | 648.24 | 648.24 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | WLDN2NS01447LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139607 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/01446 | Ryan Shenton | 2021-07-23 22:13 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Stage 2 - Type E3 Layer 2 (RMAR/WIDENINGS) - CH629.300 to CH629.800 | 2021-07-24 |  | 2021-08-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 629.3 | 629.8 | [13 empty] | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0861 Panda Results.pdf, N-21-179-684.pdf, Test Request 0838 Panda Results Retest.pdf, N-21-179-736.pdf, N-21-179-775.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139600
WLD/N2NS/01445 | Ryan Lloyd | 2021-07-23 08:15 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Insitu Concrete | Concrete | Ryan Lloyd | Piling for Bridgeworks at Croppa Bridge |  |  | 2021-07-31 10:00 |  |  |  | Planned | AMS/N2NS/00020 | ITP/N2NS/00025 | [10 empty] | 735 | 735 | [6 empty] | HWP/N2NS/00321 | [6 empty] | Chris Chant, Dan Kandamby, Danika Green, Laura Buckland |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139599 |  | Caporn Piling | PKG/N2NS/00025 | 7632-GS454019
WLD/N2NS/01444 | Ryan Lloyd | 2021-07-23 07:23 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Demolition | Other | Ryan Lloyd | Demolition Works at Croppa Creek Bridge |  |  | 2021-06-23 10:00 |  |  |  | Planned | [12 empty] | 735 | 735 | [13 empty] | Chris Chant, Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139597 |  | IRONBARK DEMOLITION PTY LTD
WLD/N2NS/01443 | Richard Doering | 2021-07-23 07:05 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type C3 - Insitu Stabilisation | 2021-07-23 |  | 2021-07-26 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00015 | [9 empty] | 655.39 | 655.5 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139595 |  |  |  | 7632-2C41552
WLD/N2NS/01442 | Ryan Shenton | 2021-07-23 06:44 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH686.300 to CH686.540 - Layer 1 - 400mm | 2021-07-23 |  | 2021-07-31 10:00 |  |  |  | Abandoned | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 686.3 | 686.54 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139594 |  |  |  | 7632-3C41552
WLD/N2NS/01441 | Ryan Shenton | 2021-07-23 06:44 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH686.300 to CH686.540 - Layer 1 - 400mm | 2021-07-23 |  | 2021-07-31 10:00 |  |  |  | Abandoned | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 686.3 | 686.54 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139593 |  |  |  | 7632-3C41552
WLD/N2NS/01440 | Richard Doering | 2021-07-23 06:44 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 Layer 1 Siding CH656.260 to 657.000 | 2021-07-23 |  | 2021-07-25 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 656.26 | 657 | [15 empty] | Test Request 0834 Panda Results.pdf, N-21-179-685.pdf, N-21-179-705.pdf, Test Request 0882 panda Results.pdf, N-21-179-780.pdf, N-21-179-779.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139592 |  |  |  | 7632-2C41552
WLD/N2NS/01439 | Ryan Shenton | 2021-07-23 06:43 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH686.300 to CH686.540 - Layer 1 - 400mm | 2021-07-23 |  | 2021-07-31 10:00 |  |  |  | Abandoned | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 686.3 | 686.54 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139591 |  |  |  | 7632-3C41552
WLD/N2NS/01438 | Ryan Shenton | 2021-07-23 06:43 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH686.300 to CH686.540 - Layer 1 - 400mm |  |  | 2021-07-31 10:00 |  |  |  | Abandoned | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 686.3 | 686.54 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139590 |  |  |  | 7632-3C41552
WLD/N2NS/01437 | Ryan Shenton | 2021-07-23 06:41 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH686.350 to CH686.490 - Layer 1 - 400mm | 2021-07-23 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 686.35 | 686.49 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR 857 Panda Results.pdf, TR 835 Panda Results.pdf, N-21-186-115.pdf, N-21-186-133.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139589 |  |  |  | 7632-3C41552
WLD/N2NS/01436 | Richard Doering | 2021-07-23 06:40 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 Layer 1 (Siding) CH657.000 to 657.700 | 2021-07-23 |  | 2021-07-24 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 657 | 657.7 | [15 empty] | Test Request 0833 B Panda Results.pdf, Test Request 0868 A panda Results.pdf, N-21-179-746.pdf, N-21-179-748.pdf, N-21-179-751.pdf, N-21-179-754.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139588 |  |  |  | 7632-2C41552
WLD/N2NS/01435 | Ryan Shenton | 2021-07-23 06:36 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type C3 - Stage 3 - CH686.350 to CH686.490 - Insitu Chew - 300mm | 2021-07-23 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00015 | [9 empty] | 686.35 | 686.49 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR 832 Panda Results.pdf, N-21-186-114.pdf, N-21-186-134.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139587 |  |  |  | 7632-2C41552
WLD/N2NS/01434 | Nabin Koirala | 2021-07-22 08:32 | Stage 2 - Penneys Road to Moree | Culverts | 633.780, 35/3000x2400, remove and rebuild | Culverts - Other | Other | Nabin Koirala | Precast Installation | 2021-07-24 |  | 2021-09-09 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00041 | [9 empty] | 633.78 | 633.78 | [13 empty] | Brendan Meagher, Emma Conroy, Keegan Baker, Maddie Dahlstrom, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139552
WLD/N2NS/01433 | Nabin Koirala | 2021-07-22 07:41 | Stage 2 - Penneys Road to Moree | Culverts | 627.280, 50/3000x2400, remove and rebuild | Culverts - Other | Other | Nabin Koirala | Cast-Insitu Apron Slabs | 2021-07-24 |  | 2021-12-31 11:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [9 empty] | 627.28 | 627.28 | [6 empty] | HWP/N2NS/00313 | [6 empty] | Emma Conroy, Frank Paraha, Keegan Baker, Maddie Dahlstrom |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139548
WLD/N2NS/01432 | Richard Doering | 2021-07-22 07:34 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 2 CH648.420 to CH649.150 | 2021-07-22 |  | 2021-07-23 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 648.42 | 649.15 | [15 empty] | Test Request 0920 panda Results.pdf, N-21-179-700.pdf, N-21-179-740.pdf, Test Request 0867 B Panda Results.pdf, Test Request 0867 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139547 |  |  |  | 7632-2C41552
WLD/N2NS/01431 | Richard Doering | 2021-07-22 07:31 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 2 CH650.340 to CH650.680 | 2021-07-22 |  | 2021-07-23 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 650.34 | 650.68 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139546 |  |  |  | 7632-2C41552
WLD/N2NS/01430 | Ryan Shenton | 2021-07-22 06:32 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH681.030 to CH682.450 - Layer 1 - 400mm | 2021-07-22 |  | 2021-08-05 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 681.03 | 682.45 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | N-21-186-112.pdf, TR 865 Panda Results.pdf, N-21-186-113.pdf, Test Request 0837 Panda Results.pdf, N-21-186-132.pdf, N-21-186-137.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/139542 |  |  |  | 7632-3C41552
WLD/N2NS/01429 | Richard Doering | 2021-07-21 07:29 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 2 CH651.330 to 651.680 | 2021-07-21 |  | 2021-07-22 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 651.33 | 651.68 | [15 empty] | N-21-179-728.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129473 |  |  |  | 7632-2C41552
WLD/N2NS/01428 | Kallen Doong | 2021-07-21 07:28 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH640.668 to CH641.100 - Layer 2 - 400mm | 2021-07-27 |  | 2021-08-11 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 640.67 | 641.1 | [6 empty] | HWP/N2NS/00336 | [6 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0823 Panda Results.pdf, E3 Stabilised Layer 2 WLD-N2NS-01428.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129472 |  |  |  | 7632-2C41552
WLD/N2NS/01427 | Ryan Shenton | 2021-07-21 07:15 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH681.450 to CH682.220 - Layer 1 - 400mm | 2021-07-21 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 681.45 | 682.22 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0821 Panda results.pdf, Test Request 814 Panda Results.pdf, Test Request 0814 Panda Results.pdf, N-21-186-117.pdf, N-21-186-129.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129469 |  |  |  | 7632-3C41552
WLD/N2NS/01426 | Kallen Doong | 2021-07-20 08:06 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Stage 2 - Type E3 Layer 2 (RMAR/WIDENINGS) - CH628.080 to CH628.475 | 2021-07-24 |  | 2021-08-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 628.09 | 628.48 | [13 empty] | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0862 Panda Results.pdf, TR 811 Panda Results.pdf, N-21-179-687.pdf, N-21-179-729.pdf, N-21-179-730.pdf, N-21-179-774.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129420
WLD/N2NS/01425 | Kallen Doong | 2021-07-20 07:58 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH640.415 to CH640.662 - Layer 2 - 400mm | 2021-07-27 |  | 2021-08-11 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 640.42 | 640.66 | [6 empty] | HWP/N2NS/00336 | [6 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0810 Panda Results.pdf, Test Request 0802 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129419 |  |  |  | 7632-2C41552
WLD/N2NS/01424 | Ryan Shenton | 2021-07-20 07:55 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH682.220 to CH682.860 - Layer 1 - 400mm | 2021-07-20 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 682.22 | 682.86 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR 803 Panda Results.pdf, N-21-186-123.pdf, N-21-186-139.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129418 |  |  |  | 7632-3C41552
WLD/N2NS/01423 | Ben Foster | 2021-07-19 22:45 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 25th July to 31st July 2021 TOTAL QTY - 1254.26 Tonnes | 2021-07-27 |  | 2021-07-31 10:00 | Benjamin Philip | 2021-08-11 | 2021-08-10 23:41 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 |  |  |  |  | WLD/N2NS/00259 | [5 empty] | 0 | 0 | Ben Foster | 2021-08-10 23:19 | [5 empty] | Lot closed |  | 2021-08-10 23:41 | [5 empty] | 1028301.pdf, 1028304 1028308.pdf, 5441.pdf, 1028313 1028314.pdf, 1028319.pdf, 1028318.pdf, 5442 1028316.pdf, 1070120.pdf, 1028311 1028312.pdf, 1070114.pdf, 1028321 1028322.pdf, 1070123.pdf, 1028326 1028327.pdf, 1028323 1028324.pdf, 1028344 & 1028345.pdf, 1028333 & 1028334.pdf, 1028338.pdf, 5444 & 5445.pdf, 1028346 & 1028347.pdf, 1028339.pdf, 1028335 & 1028336.pdf, 1028330.pdf, 1070174.pdf, 1070150.pdf, 1070170.pdf, 1070159.pdf, 1028341 & 1028342.pdf, 1028299 & 5439.pdf, 50913 643 1028297.pdf, 50914 643 1028295 and 643 1028296.pdf, 2CH-202108-0001-00077225-F.pdf, 2AT-202107-0183-00077226-F.pdf, 2GA-202108-0009-00077250-F.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129348 |  | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551 |  | 2021-08-11 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/01422 | Jarryd Davis | 2021-07-19 21:56 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Jake Mossman | Capping Placement CH 631.2 - 631.565 Mainline | 2021-07-20 |  | 2021-07-28 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 631.16 | 631.57 | [6 empty] | HWP/N2NS/00306 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Jarryd Davis, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129341 |  |  |  | 7632-1C47051
WLD/N2NS/01421 | Richard Doering | 2021-07-19 07:39 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 2 CH650.700 to 651.330 | 2021-07-19 |  | 2021-07-20 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 650.7 | 651.33 | [15 empty] | Test Request 0816 Panda Results.pdf, N-21-179-671.pdf, Test Request 0829 panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129333 |  |  |  | 7632-2C41552
WLD/N2NS/01420 | Kallen Doong | 2021-07-19 07:37 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH639.595 to CH640.080 - Layer 2 - 400mm | 2021-07-27 |  | 2021-08-05 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 639.6 | 640.08 | [6 empty] | HWP/N2NS/00336 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0806 Panda Results.pdf, Test Request 0792 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129332 |  |  |  | 7632-2C41552
WLD/N2NS/01419 | Richard Doering | 2021-07-19 07:37 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type C3 - Insitu Stabilisation - Maintenance Siding Turnout CH657.205 to 657.405 | 2021-07-19 |  | 2021-07-20 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00015 | [9 empty] | 657.21 | 657.41 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129331 |  |  |  | 7632-2C41552
WLD/N2NS/01418 | Ryan Shenton | 2021-07-19 06:42 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH682.760 to CH683.680 - Layer 1 - 400mm | 2021-07-19 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 682.76 | 683.68 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR 790 Panda Results.pdf, N-21-186-116.pdf, N-21-186-136.pdf, Test Request 0807 Panda Result.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129329 |  |  |  | 7632-3C41552
WLD/N2NS/01417 | Ryan Shenton | 2021-07-19 04:20 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type C3 - Stage 3 - CH682.760 to CH682.800 - Insitu Chew - 300mm | 2021-07-19 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00015 | [9 empty] | 682.76 | 682.8 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR 789 Panda Results.pdf, N-21-186-111.pdf, N-21-186-131.pdf, Test Request 0808 Panda Result.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129319 |  |  |  | 7632-2C41552
WLD/N2NS/01416 | Ryan Shenton | 2021-07-19 03:19 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Cut Inc Ground Preparation - CH686.080 - CH686.500 | 2021-07-19 |  | 2021-07-30 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 686.08 | 686.5 | [6 empty] | HWP/N2NS/00309 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | N-21-186-124.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129315 |  |  |  | 7632-3C41220
WLD/N2NS/01415 | Kallen Doong | 2021-07-18 07:35 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH639.140 to CH639.595 - Layer 2 - 400mm | 2021-07-23 |  | 2021-08-05 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 639.14 | 639.6 | [6 empty] | HWP/N2NS/00336 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR 780 Panda Results.pdf, Test request 0791 Panda Results.pdf, N-21-179-651.pdf, N-21-179-739.pdf, N-21-179-726.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129297 |  |  |  | 7632-2C41552
WLD/N2NS/01414 | Kallen Doong | 2021-07-18 06:45 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH634.494 to CH634.550 - Layer 1 - 400mm | 2021-07-19 |  | 2021-08-03 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 634.49 | 634.55 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0776 Panda Results.pdf, N-21-179-660.pdf, Test request 0787 Panda Results.pdf, N-21-184-3.pdf, N-21-179-759.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129296 |  |  |  | 7632-2C41552
WLD/N2NS/01413 | Ryan Shenton | 2021-07-18 06:37 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH683.680 to CH684.525 - Layer 1 - 400mm | 2021-07-18 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 683.68 | 684.53 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 788 Panda Results.pdf, Test Request 0775 Panda Results.pdf, N-21-186-107.pdf, N-21-186-130.pdf, N-21-186-126.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129295 |  |  |  | 7632-3C41552
WLD/N2NS/01412 | Kallen Doong | 2021-07-18 06:33 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH634.564 to CH634.863 - Layer 2 - 400mm | 2021-07-18 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 634.56 | 634.86 | [6 empty] | HWP/N2NS/00323 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0774 Panda Results.pdf, N-21-179-658.pdf, Test Request 0777 Panda Results.pdf, N-21-179-737.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129294 |  |  |  | 7632-2C41552
WLD/N2NS/01411 | Jasmine Daly-Hayes | 2021-07-18 06:00 | Stage 2 - Penneys Road to Moree | Bridgeworks | Bridge - 641.540, Gurley Creek (9m ¦ 13 spans) | Bridgeworks - Structural Steel and Metalwork | Other | Ryan Lloyd | Post Tensioning at Gurley Creek | 2021-07-19 |  | 2021-08-08 10:00 |  |  |  | Open | AMS/N2NS/00014 | ITP/N2NS/00026 | [10 empty] | 641 | 642 | [6 empty] | HWP/N2NS/00460, HWP/N2NS/00461 | [6 empty] | Chris Chant, Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  | Order 9846 SRG - Trans4m Delivery 1 (2).pdf, N2NS-SUR-087-1-A.pdf, N2NS-SUR-082-1-A.pdf, N2NS-SUR-080-1-A.pdf, N2NS-SUR-086-1-A.pdf, N2NS-SUR-083-1-A.pdf, N2NS-SUR-054-1-A.pdf, N2NS-SUR-089-1-A.pdf, N2NS-SUR-085-1-A.pdf, N2NS-SUR-053-1-A.pdf, N2NS-SUR-088-1-A.pdf, N2NS-SUR-078-1-A.pdf, N2NS-SUR-081-1-A.pdf, N2NS-SUR-084-1-A.pdf, N2NS-SUR-079-1-A.pdf, 5-0018-260-PVP-00-TP-0014, Item 5.1 - Concrete Strength Before Stressing.pdf, 5-0018-260-PVP-00-TP-0014, Item 4.1 - Post Tensioning Supervisor.pdf, 5-0018-260-PVP-00-TP-0014, Item 5.3 - Stressing Operations - Gurley Creek Bridge (BR07).pdf, 5-0018-260-PVP-00-TP-0014, Item 5.1 - Concrete Strength Before Stressing - Gurley Creek Bridge (BR07)-01.pdf, 5-0018-260-PVP-00-TP-0014, Item 4.2 - Stress Bar Conformity Records - Gurley Creek and Gil Gil Creek.pdf, 210802 - Post Tensioning Field Form - BR07.pdf, 210810 - Post Tensioning Field Form - BR07.pdf, 210806 - Post Tensioning Field Form - BR07.pdf, 210811 - Post Tensioning Field Form - BR07.pdf, 210807 - Post Tensioning Field Form - BR07.pdf, 210730 - Post Tensioning Field Form - BR07.pdf, 210801 - Post Tensioning Field Form - BR07.pdf, Technical Memo - Stressing Extension v1.pdf, 210803 - Post Tensioning Field Form - BR07.pdf, Grout Tube Methodology - RFI.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129293
WLD/N2NS/01410 | Ryan Shenton | 2021-07-18 00:12 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Cut Inc Ground Preparation - CH681.000 - CH681.800 | 2021-07-18 |  | 2021-07-30 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 681 | 681.8 | [6 empty] | HWP/N2NS/00298 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_4560.JPG, IMG_4557.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129292 |  |  |  | 7632-3C41220
WLD/N2NS/01409 | Kallen Doong | 2021-07-17 07:48 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type C3 - Stage 2 - CH634479 to CH634565 - Insitu Chew - 250mm | 2021-07-19 |  | 2021-08-04 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00015 | [9 empty] | 634.48 | 634.57 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0766 Panda Results.pdf, N-21-179-638.pdf, Test Request 0786 Panda Results.pdf, N-21-179-741.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129291 |  |  |  | 7632-2C41552
WLD/N2NS/01408 | Nabin Koirala | 2021-07-17 07:12 | Stage 2 - Penneys Road to Moree | Culverts | 627.280, 50/3000x2400, remove and rebuild | Drainage - Other | Other | Keegan Baker | Excavation and Foundation Preparation for Wing Walls |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 627.29 | 627.8 | [6 empty] | HWP/N2NS/00179, HWP/N2NS/00300 | [6 empty] | Brendan Meagher, Emma Conroy, Keegan Baker, Maddie Dahlstrom |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129290
WLD/N2NS/01407 | Nabin Koirala | 2021-07-17 06:25 | Stage 2 - Penneys Road to Moree | Culverts | 638.140, 5/2400x1200, remove and rebuild | Drainage - Other | Other | Keegan Baker | Cast In-situ - Cut off Walls | 2021-07-24 |  | 2021-07-19 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00038 | [9 empty] | 638.14 | 638.14 | [6 empty] | HWP/N2NS/00297 | [6 empty] | Brendan Meagher, Emma Conroy, Keegan Baker, Maddie Dahlstrom |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129289
WLD/N2NS/01406 | Ryan Shenton | 2021-07-17 05:20 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH684.525 to CH685.020 - Layer 1 - 400mm | 2021-07-17 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 684.5 | 685 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 772 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129288 |  |  |  | 7632-3C41552
WLD/N2NS/01405 | Ryan Shenton | 2021-07-17 05:12 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Kallen Doong | Type C3 - Stage 3 - CH684.880 to CH684.920 - Insitu Chew - 300mm | 2021-07-17 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00015 | [9 empty] | 684.88 | 684.92 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | N-21-186-104.pdf, N-21-186-128.pdf, Test Request 0773 Panda Result.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129287 |  |  |  | 7632-2C41552
WLD/N2NS/01404 | Hayden Murphy | 2021-07-17 03:17 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Insitu Treatments/Stabilisation | Roadworks | Hayden Murphy | LX555 - Stabilisation of Subgrade on Western Side | 2021-07-17 |  | 2021-07-24 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00027 | PER/N2NS/00048 | [8 empty] | 636.28 | 636.32 | [6 empty] | HWP/N2NS/00310 | [6 empty] | Ahmad Alwan, Aziz Kamaoui, Jeramy Smith, Loui Tannous |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129286
WLD/N2NS/01403 | Kallen Doong | 2021-07-16 07:39 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH638.900 to CH639.250 - Layer 2 - 400mm | 2021-07-18 |  | 2021-08-05 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 638.9 | 639.25 | [6 empty] | HWP/N2NS/00336 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR 764 Panda Results.pdf, Test Request 0752 Panda Results.pdf, N-21-179-639.pdf, N-21-179-738.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129281 |  |  |  | 7632-2C41552
WLD/N2NS/01402 | Ryan Shenton | 2021-07-16 06:47 | Stage 3 - Camurra North to North Star | Earthworks | Other (Specify Location in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Type E3 - Stage 3 - CH685.000 to CH635.900 - Layer 1 - 400mm | 2021-07-16 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 685 | 685.9 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0748 Panda Results.pdf, N-21-186-103.pdf, N-21-186-127.pdf, N-21-186-125.pdf, Test Request 0757 Panda Result.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129275 |  |  |  | 7632-3C41552
WLD/N2NS/01401 | Miaya Tighe | 2021-07-16 06:31 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Arjan Sidhu | Capping Placement CH 633.855 - 634.45Mainline |  |  | 2021-08-01 10:00 |  |  |  | Planned | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 633.86 | 634.45 | [13 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129273 |  |  |  | 7632-1C47051
WLD/N2NS/01400 | Miaya Tighe | 2021-07-16 06:17 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Jake Mossman | Capping placement CH 626.1 - 626.64 Mainline | 2021-07-16 |  | 2021-07-28 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 626.1 | 626.64 | [6 empty] | HWP/N2NS/00439, HWP/N2NS/00440, HWP/N2NS/00455 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Jarryd Davis, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129272 |  |  |  | 7632-1C47051
WLD/N2NS/01399 | Miaya Tighe | 2021-07-16 06:03 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Jake Mossman | Capping placement CH630.6 - 630.910 Mainline | 2021-07-16 |  | 2021-07-30 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 630.6 | 630.91 | [6 empty] | HWP/N2NS/00314 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129270 |  |  |  | 7632-2C47051
WLD/N2NS/01398 | Ryan Shenton | 2021-07-16 02:17 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Cut Inc Ground Preparation - CH681.800 - CH683.000 | 2021-07-16 |  | 2021-07-30 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 681.8 | 683 | [6 empty] | HWP/N2NS/00296 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_4537.JPG, IMG_4532.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129261 |  |  |  | 7632-3C41220
WLD/N2NS/01397 | Miaya Tighe | 2021-07-16 02:07 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Jake Mossman | Capping placement CH 627.760 - 628.9 | 2021-07-16 |  | 2021-07-18 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 627.76 | 628.9 | [6 empty] | HWP/N2NS/00304 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129260 |  |  |  | 7632-1C47051
WLD/N2NS/01396 | Miaya Tighe | 2021-07-15 21:56 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Capping | Earthworks | Arjan Sidhu | JCQ Runnymede Capping Supply - 4000T Stockpile 14 | 2021-07-16 |  | 2021-08-13 10:00 | Benjamin Philip | 2021-07-16 | 2021-07-16 05:09 | Closed | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 625.55 | 667 | Miaya Tighe | 2021-07-15 21:57 | [5 empty] | Lot closed |  | 2021-07-16 05:09 |  |  |  | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  | N-21-193-9.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129244 | 2021-07-29 18:40 |  |  |  |  | 2021-07-17 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/01395 | James Martin | 2021-07-15 00:13 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - Stage 2 - CH653.XXX to CH655.XXX - Layer 3 of 3 | 2021-08-03 |  | 2021-07-16 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 1 | 2 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | N-21-179-615.pdf, N-21-179-659.pdf, Test Request 0739 Panda Results.pdf, N-21-179-735.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129211 |  |  |  | 7632-2C41552
WLD/N2NS/01394 | James Martin | 2021-07-14 23:59 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - Stage 2 - CH653.XXX to CH655.XXX - Layer 3 of 3 |  |  | 2021-07-15 10:00 |  |  |  | Planned | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 1 | 2 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129210 |  |  |  | 7632-2C41552
WLD/N2NS/01393 | Ben Foster | 2021-07-14 22:14 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 18th July to 24th July 2021 TOTAL QTY - 1195.26 Tonnes | 2021-07-15 |  | 2021-07-24 10:00 | Benjamin Philip | 2021-08-08 | 2021-08-08 00:17 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 |  |  |  |  | WLD/N2NS/00259 | [5 empty] | 0 | 0 | Ben Foster | 2021-08-03 05:06 | [5 empty] | Lot closed |  | 2021-08-08 00:17 | [5 empty] | 1028255 & 1028256.pdf, 1028264.pdf, 1136067.pdf, 1070025.pdf, 5434.pdf, 1136000.pdf, 1028273.pdf, 1028270 1028271.pdf, 1028272.pdf, 1028268 1028269.pdf, 1028265 1028266.pdf, 1136104.pdf, 1070062.pdf, 1028277.pdf, 1070036.pdf, 1070028.pdf, 1070059.pdf, 1136122.pdf, 1028287.pdf, 5438 1028290.pdf, 1070094.pdf, 1028297.pdf, 1028295 1028296.pdf, 1028286.pdf, 1028274 1028275.pdf, 1028284 1028285.pdf, 1028276.pdf, 1136156 1136157.pdf, 1028291 1028292.pdf, 5435 5436.pdf, 1070073.pdf, 1070061.pdf, Job 50919.pdf, 5438.pdf, 1028299.pdf, 1028290.pdf, 2GA-202107-0369-00077153-F.pdf, 2CH-202107-0017-00077145-F.pdf, 2AT-202107-0117-00077148-F.pdf, 1028290.pdf, 5438.pdf, 1070050.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129204 |  | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551 |  | 2021-08-16 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/01392 | Kallen Doong | 2021-07-14 07:38 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH638.120 to CH638.500 - Layer 2 - 400mm | 2021-07-16 |  | 2021-08-04 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/01332 | [5 empty] | 638.12 | 638.5 | [6 empty] | HWP/N2NS/00336 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0750 Panda Results.pdf, Test Request 0734 Panda Results.pdf, N-21-179-613.pdf, N-21-179-727.pdf, E3 Stabilised Layer 2 WLD-N2NS-01392.pdf, FFB127D3-5A45-4DB0-ACA0-EA58384CA705.JPG, A924018D-7557-4FC4-8259-8E28C0E764A1.JPG, wldn2ns001392.pdf, lot map 1392.pdf, N-21-179-669.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129186 |  |  |  | 7632-2C41552
WLD/N2NS/01391 | Kallen Doong | 2021-07-14 07:27 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH634.863 to CH634.957 - Layer 2 - 400mm | 2021-07-17 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 634.86 | 634.96 | [6 empty] | HWP/N2NS/00323 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR 765 Panda Results.pdf, Test Request 0795 Panda Results.pdf, N-21-179-616.pdf, N-21-179-733.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129184 |  |  |  | 7632-2C41552
WLD/N2NS/01390 | Nabin Koirala | 2021-07-14 06:39 | Stage 2 - Penneys Road to Moree | Culverts | 653.150, 1/600x600, remove and rebuild | Culverts - Other | Other | Frank Paraha | 653.150 - Excavation & Foundation Preparation - Wingwalls | 2021-07-18 |  | 2021-07-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 |  |  |  | WLD/N2NS/00571, WLD/N2NS/00708, WLD/N2NS/01450 | [5 empty] | 653.15 | 653.15 | [6 empty] | HWP/N2NS/00292 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Maddie Dahlstrom, Patrick Coria |  | WLDN2NS001390LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129171 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2C41460
WLD/N2NS/01389 | Ben Foster | 2021-07-14 06:38 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Cut Inc Ground Preparation - CH683.000 - CH683.750 | 2021-07-17 |  | 2021-07-15 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 683 | 683.75 | [13 empty] | Ben Foster |  | IMG_4514.JPG, IMG_4513.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129169 |  |  |  | 7632-3C41220
WLD/N2NS/01388 | Nabin Koirala | 2021-07-14 06:37 | Stage 2 - Penneys Road to Moree | Culverts | 652.715, 1/1800x600, remove and rebuild | Culverts - Other | Earthworks | Frank Paraha | 652.715 - Excavation & Foundation Preparation - Wingwalls | 2021-07-24 |  | 2021-07-26 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 |  |  |  | WLD/N2NS/00572, WLD/N2NS/01062, WLD/N2NS/01449 | [5 empty] | 652.72 | 652.72 | [6 empty] | HWP/N2NS/00293, HWP/N2NS/00317 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Maddie Dahlstrom, Patrick Coria |  | WLDN2NS01388LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129168 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2C41460
WLD/N2NS/01387 | Nabin Koirala | 2021-07-14 06:34 | Stage 2 - Penneys Road to Moree | Culverts | 652.530, 2/1800x600, remove and rebuild | Culverts - Other | Earthworks | Frank Paraha | 652.530 - Excavation & Foundation Preparation | 2021-07-24 |  | 2021-07-01 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 |  |  |  | WLD/N2NS/00573, WLD/N2NS/01334, WLD/N2NS/01448 | [5 empty] | 652.53 | 652.53 | [6 empty] | HWP/N2NS/00294, HWP/N2NS/00295, HWP/N2NS/00318 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Maddie Dahlstrom, Patrick Coria |  | WLDN2NS01387LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129167 |  |  |  | 7632-2C41460
WLD/N2NS/01386 | Miaya Tighe | 2021-07-13 23:18 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Earthworks - Filling | Earthworks | Arjan Sidhu | Matpol Structural Fill - Stockpile SF5A 8000T | 2021-07-14 |  | 2021-08-13 10:00 | Lorne Jenks | 2021-07-14 | 2021-07-14 04:13 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 | [9 empty] | 625.55 | 666 | Miaya Tighe | 2021-07-13 23:20 | [5 empty] | Lot closed |  | 2021-07-14 04:13 |  |  |  | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  | N-21-238-6.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129073 | 2021-07-29 18:40 |  |  |  |  | 2021-07-17 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/01385 | Miaya Tighe | 2021-07-13 23:14 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Earthworks - Filling | Earthworks | Arjan Sidhu | Matpol Structural Fill - Stockpile SF4A 8000T | 2021-07-14 |  | 2021-08-13 10:00 | Benjamin Philip | 2021-07-16 | 2021-07-16 05:24 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 | [9 empty] | 625.55 | 666 | Miaya Tighe | 2021-07-14 04:29 | [5 empty] | Lot closed |  | 2021-07-16 05:24 |  |  |  | Arjan Sidhu, Brett Jenkins, Jake Mossman, Miaya Tighe |  | N-21-238-5.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129072 | 2021-07-29 18:40 |  |  |  |  | 2021-07-17 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/01384 | Miaya Tighe | 2021-07-13 23:07 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Arjan Sidhu | Capping Placement CH 628.9 - 629.5 Mainline only | 2021-07-15 |  | 2021-08-13 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 628.9 | 629.5 | [6 empty] | HWP/N2NS/00290 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Jarryd Davis, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129067 |  |  |  | 7632-2C47051
WLD/N2NS/01383 | Kallen Doong | 2021-07-13 07:09 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH641.690 to CH641.880 - Layer 2 - 400mm |  |  | 2021-08-11 10:00 |  |  |  | Planned | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 641.69 | 641.88 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129037 |  |  |  | 7632-2C41552
WLD/N2NS/01382 | Kallen Doong | 2021-07-13 07:03 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH641.100 to CH641.530 - Layer 2 - 400mm | 2021-07-14 |  | 2021-08-11 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 641.1 | 641.53 | [6 empty] | HWP/N2NS/00336 | [6 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0732 Panda Results.pdf, Test Request 0719 Panda Results.pdf, N-21-179-623.pdf, N-21-179-585.pdf, N-21-179-667.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129036 |  |  |  | 7632-2C41552
WLD/N2NS/01381 | James Martin | 2021-07-13 06:47 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - Stage 2 - CH6XX to CH6XX - Layer 2 - 400mm | 2021-08-02 |  | 2021-07-14 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 1 | 2 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0720 Panda Results.pdf, Test Request 0751 Panda Results.pdf, N-21-179-734.pdf, N-21-179-612.pdf, N-21-179-732.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129033 |  |  |  | 7632-2C41552
WLD/N2NS/01380 | James Martin | 2021-07-13 06:42 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH683.750 - CH684.600 | 2021-07-13 |  | 2021-07-14 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 683.75 | 684.6 | [6 empty] | HWP/N2NS/00289 | [8 empty] | IMG_4508.JPG, IMG_4507.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/129031 |  |  |  | 7632-3C41220
WLD/N2NS/01379 | Miaya Tighe | 2021-07-12 21:54 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Capping | Earthworks | Jake Mossman | JCQ Runnymede Capping Supply - 4000T Stockpile 15 | 2021-07-13 |  | 2021-08-13 10:00 | Lorne Jenks | 2021-07-13 | 2021-07-13 06:45 | Closed | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 625.55 | 667 | Miaya Tighe | 2021-07-12 21:55 | [5 empty] | Lot closed |  | 2021-07-13 06:45 |  |  |  | Arjan Sidhu, Brett Jenkins, Miaya Tighe |  | RU Capping Lot 15-21 18-6-21.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128968 | 2021-07-29 18:40 |  |  |  |  | 2021-07-17 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/01378 | Aziz Kamaoui | 2021-07-12 07:51 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Aziz Kamaoui | Cast In-Situ Base Slabs, End Structures and Cut Off Walls - LX555 DDR2 | 2021-07-12 |  | 2021-07-19 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00038 | [9 empty] | 636.3 | 636.3 | [6 empty] | HWP/N2NS/00287 | [8 empty] | WLDN2NS01378- Checklist.pdf, WLDN2NS01378.pdf, Survey Report.pdf, Precast Concrete Headwall.pdf, Concrete Pour Record.pdf, N-21-179-626.pdf, Lot Map.pdf, 555DDR2_2.JPG, 555DDR2_1.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128958
WLD/N2NS/01377 | James Martin | 2021-07-12 07:31 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH684.600 - CH685.370 | 2021-07-12 |  | 2021-07-13 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 684.6 | 685.37 | [6 empty] | HWP/N2NS/00285 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128957 |  |  |  | 7632-3C41220
WLD/N2NS/01376 | Kallen Doong | 2021-07-12 06:32 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH641.690 to CH641.730 - Layer 1 - 400mm | 2021-07-12 |  | 2021-08-02 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 641.69 | 641.73 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0711 Panda Results.pdf, N-21-179-602.pdf, N-21-179-650.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128952 |  |  |  | 7632-2C41552
WLD/N2NS/01375 | James Martin | 2021-07-12 06:14 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - Stage 2 - CH6XX to CH6XX - Layer 2 - 400mm | 2021-08-02 |  | 2021-07-13 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 1 | 2 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0738 Panda Results.pdf, Test Request 0710 Panda Results.pdf, N-21-179-624.pdf, N-21-179-657.pdf, N-21-179-586.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128948 |  |  |  | 7632-2C41552
WLD/N2NS/01374 | Nabin Koirala | 2021-07-12 02:11 | Stage 2 - Penneys Road to Moree | Culverts | 655.980, 5/3000x1200, remove and rebuild (RRA) | Drainage - Other | Earthworks | Frank Paraha | 655.980 - Excavation & Foundation Preparation | 2021-07-24 |  | 2021-08-05 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 655.98 | 655.98 | [6 empty] | HWP/N2NS/00454 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Maddie Dahlstrom, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128933 |  |  |  | 7632-2C41460
WLD/N2NS/01373 | Nabin Koirala | 2021-07-12 02:11 | Stage 2 - Penneys Road to Moree | Culverts | 655.270, 6/3000x1200, remove and rebuild (RRA) | Drainage - Other | Other | Frank Paraha | 655.270 - Excavation & Foundation Preparation |  |  | 2021-08-07 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 655.27 | 655.27 | [6 empty] | HWP/N2NS/00403, HWP/N2NS/00414 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Maddie Dahlstrom, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128932 |  |  |  | 7632-2C41460
WLD/N2NS/01372 | Nabin Koirala | 2021-07-12 02:10 | Stage 2 - Penneys Road to Moree | Culverts | 654.525, 1/1800x900, remove and rebuild | Drainage - Other | Earthworks | Frank Paraha | 654.525 - Excavation & Foundation Preparation | 2021-07-24 |  | 2021-07-08 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 654.53 | 654.53 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Maddie Dahlstrom, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128931 |  |  |  | 7632-2C41460
WLD/N2NS/01371 | Nabin Koirala | 2021-07-12 02:10 | Stage 2 - Penneys Road to Moree | Culverts | 653.700, 1/2400x900, remove and rebuild | Drainage - Other | Other | Frank Paraha | 653.700 - Excavation & Foundation Preparation |  |  | 2021-08-14 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 653.7 | 653.7 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Maddie Dahlstrom, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128930 |  |  |  | 7632-2C41460
WLD/N2NS/01370 | Nabin Koirala | 2021-07-12 02:09 | Stage 2 - Penneys Road to Moree | Culverts | 653.620, 6/2400x900, remove and rebuild | Drainage - Other | Earthworks | Frank Paraha | 653.620 - Excavation & Foundation Preparation |  |  | 2021-08-07 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 653.62 | 653.62 | [6 empty] | HWP/N2NS/00415 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Maddie Dahlstrom, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128929 |  |  |  | 7632-2C41460
WLD/N2NS/01369 | Nabin Koirala | 2021-07-12 02:08 | Stage 2 - Penneys Road to Moree | Culverts | 649,700 NEW | Drainage - Other | Earthworks | Frank Paraha | 649.700 - Excavation & Foundation Preparation | 2021-07-24 |  | 2021-07-14 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 649.7 | 649.7 | [6 empty] | HWP/N2NS/00365 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Maddie Dahlstrom, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128928 |  |  |  | 7632-2C41460
WLD/N2NS/01368 | Nabin Koirala | 2021-07-12 02:07 | Stage 2 - Penneys Road to Moree | Culverts | 648.395, 10/3000x2400, remove and rebuild | Drainage - Other | Earthworks | Frank Paraha | 648.395 - Excavation & Foundation Preparation |  |  | 2021-08-07 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 648.4 | 648.4 | [6 empty] | HWP/N2NS/00395 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Maddie Dahlstrom, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128927 |  |  |  | 7632-2C41460
WLD/N2NS/01367 | Miaya Tighe | 2021-07-11 22:04 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Capping | Earthworks | Jake Mossman | JCQ Runnymede Capping Supply - 4000T Stockpile 17 | 2021-07-12 |  | 2021-08-12 10:00 | Lorne Jenks | 2021-07-12 | 2021-07-11 22:55 | Closed | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 625.55 | 667 | Miaya Tighe | 2021-07-11 22:05 | [5 empty] | Lot closed |  | 2021-07-11 22:55 | [5 empty] | RU Capping Lot 17-21 8-7-21.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128913 | 2021-07-29 18:40 |  |  |  |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/01366 | Miaya Tighe | 2021-07-11 21:52 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Capping | Earthworks | Jake Mossman | JCQ Runnymede Capping Supply - 4000T Stockpile 16 | 2021-07-12 |  | 2021-08-12 10:00 | Lorne Jenks | 2021-07-12 | 2021-07-11 22:59 | Closed | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 625.55 | 667 | Miaya Tighe | 2021-07-11 21:54 | [5 empty] | Lot closed |  | 2021-07-11 22:59 |  |  |  | Arjan Sidhu, Brett Jenkins, Miaya Tighe |  | RU Capping Lot 16-21 5-7-21.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128912 | 2021-07-29 18:40 |  |  |  |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/01365 | Nabin Koirala | 2021-07-11 07:27 | Stage 3 - Camurra North to North Star | Culverts | 709.740, 5/2400x900, remove and rebuild | Culverts - Other | Other | Nabin Koirala | Cast-In Situ Base Slab |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00038 | [9 empty] | 709.74 | 709.74 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Maddie Dahlstrom |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128898
WLD/N2NS/01364 | Nabin Koirala | 2021-07-11 07:27 | Stage 3 - Camurra North to North Star | Culverts | 708.445, 13/3000x1200, remove and rebuild (RRA) | Culverts - Other | Other | Nabin Koirala | Cast-In Situ Base Slab |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00038 | [9 empty] | 708.45 | 708.45 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Maddie Dahlstrom |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128897
WLD/N2NS/01363 | Nabin Koirala | 2021-07-11 07:26 | Stage 3 - Camurra North to North Star | Culverts | 707.575, 8/1800x600, remove and rebuild (RRA) | Culverts - Other | Other | Nabin Koirala | Cast-In Situ Base Slab |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00038 | [9 empty] | 707.58 | 707.58 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Maddie Dahlstrom |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128896
WLD/N2NS/01362 | Nabin Koirala | 2021-07-11 07:26 | Stage 3 - Camurra North to North Star | Culverts | 707.405, 2/1800x600, remove and rebuild (RRA) | Culverts - Other | Other | Nabin Koirala | Cast-In Situ Base Slab |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00038 | [9 empty] | 707.41 | 707.41 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Maddie Dahlstrom |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128895
WLD/N2NS/01361 | Nabin Koirala | 2021-07-11 07:25 | Stage 3 - Camurra North to North Star | Culverts | 706.695, 3/1200x600, remove and rebuild (RRA) | Culverts - Other | Other | Nabin Koirala | Cast-In Situ Base Slab |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00038 | [9 empty] | 706.7 | 706.7 | [6 empty] | HWP/N2NS/00269 | [6 empty] | Brendan Meagher, Emma Conroy, George Yousef, Maddie Dahlstrom |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128894
WLD/N2NS/01360 | Nabin Koirala | 2021-07-11 07:24 | Stage 3 - Camurra North to North Star | Culverts | 706.695, 3/1200x600, remove and rebuild (RRA) | Culverts - Other | Other | Nabin Koirala | Cast-In Situ Base Slab |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00038 | [9 empty] | 706.7 | 706.7 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Maddie Dahlstrom |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128893
WLD/N2NS/01359 | Nabin Koirala | 2021-07-11 07:24 | Stage 3 - Camurra North to North Star | Culverts | 711.640, 15/3000x1500, remove and rebuild | Culverts - Other | Other | Nabin Koirala | Cast-In Situ Base Slab |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00038 | [9 empty] | 711.64 | 711.64 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Maddie Dahlstrom |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128892
WLD/N2NS/01358 | James Martin | 2021-07-11 07:22 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - Stage 2 - CH647.220 to CH647.700 - Layer 1 - 400mm | 2021-08-02 |  | 2021-07-12 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 647.22 | 647.7 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0701 Panda Results.pdf, N-21-179-601.pdf, N-21-179-649.pdf, N-21-179-596.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128891 |  |  |  | 7632-2C41552
WLD/N2NS/01357 | James Martin | 2021-07-11 07:12 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH685.370 - CH685.920 | 2021-07-11 |  | 2021-07-12 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 685.37 | 685.92 | [6 empty] | HWP/N2NS/00266 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128890 |  |  |  | 7632-3C41220
WLD/N2NS/01356 | James Martin | 2021-07-11 06:59 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH646.500 - CH646.940 | 2021-07-11 |  | 2021-07-11 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 646.5 | 646.94 | [6 empty] | HWP/N2NS/00263, HWP/N2NS/00264, HWP/N2NS/00265 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | N-21-179-611.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128889 |  |  |  | 7632-2C41220
WLD/N2NS/01355 | Kallen Doong | 2021-07-11 05:59 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH634.957 to CH635.190 - Layer 2 - 400mm | 2021-07-14 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 634.96 | 635.19 | [6 empty] | HWP/N2NS/00323 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0731 Panda Results.pdf, N-21-179-654.pdf, N-21-179-588.pdf, N-21-179-668.pdf, Test Request 0718 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128887 |  |  |  | 7632-2C41552
WLD/N2NS/01354 | Kallen Doong | 2021-07-11 05:53 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH635.660 to CH635.720 - Layer 2 - 400mm | 2021-07-14 |  | 2021-07-30 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 635.66 | 635.72 | [6 empty] | HWP/N2NS/00323 | [6 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0717 Panda Results.pdf, N-21-179-608.pdf, N-21-179-652.pdf, Test Request 0699 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128886 |  |  |  | 7632-2C41552
WLD/N2NS/01353 | Kallen Doong | 2021-07-11 05:44 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH633.590 to CH634.167 - Layer 1 - 400mm | 2021-07-12 |  | 2021-07-30 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 633.59 | 634.17 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | 26B0F16E-1524-4D08-97CE-13D6FCA40CC7.JPG, 52B0D9D7-746D-402F-98CF-34CEFED5605A.JPG, Test Request 0779 Panda Results.pdf, Test Request 0778 Panda Report.msg, N-21-179-578.pdf, N-21-179-577.pdf, N-21-179-647.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128885 |  |  |  | 7632-2C41552
WLD/N2NS/01352 | Kallen Doong | 2021-07-11 05:05 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH641.080 to CH641.100 - Layer 1 - 400mm | 2021-07-12 |  | 2021-08-02 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 641.08 | 641.1 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0714 Panda Results.pdf, N-21-179-632.pdf, N-21-179-600.pdf, Test Request 0695 Panda Results.pdf, N-21-179-648.pdf, N-21-179-663.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128884 |  |  |  | 7632-2C41552
WLD/N2NS/01351 | Nabin Koirala | 2021-07-11 02:20 | Stage 2 - Penneys Road to Moree | Culverts | 655.980, 5/3000x1200, remove and rebuild (RRA) | Culverts - Other | Other | Frank Paraha | 655.980 - Demolition of Existing Structures | 2021-07-24 |  | 2021-07-01 10:00 | Sarah Brooks | 2021-08-04 | 2021-08-04 03:18 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 655.98 | 655.98 | Maddie Dahlstrom | 2021-08-04 01:40 | [5 empty] | Lot closed |  | 2021-08-04 03:18 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, Keegan Baker, Maddie Dahlstrom, Patrick Coria |  | WLDN2NS01351LM.pdf, WLDN2NS01351 Checklist.pdf, IMG_0385.jpg, IMG_0386.jpg, IMG_0389.jpg, IMG_0387.jpg, IMG_0390.jpg, IMG_0384.jpg, IMG_0388.jpg | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128883 |  |  |  | 7632-2S41011 |  | 2021-08-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/01350 | Nabin Koirala | 2021-07-11 02:12 | Stage 2 - Penneys Road to Moree | Culverts | 655.270, 6/3000x1200, remove and rebuild (RRA) | Culverts - Other | Other | Frank Paraha | 655.270 - Demolition of Existing Structures |  |  | 2021-08-04 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 655.27 | 655.27 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Keegan Baker, Maddie Dahlstrom, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128882 |  |  |  | 7632-2S41011
WLD/N2NS/01349 | Nabin Koirala | 2021-07-11 02:11 | Stage 2 - Penneys Road to Moree | Culverts | 654.525, 1/1800x900, remove and rebuild | Culverts - Other | Other | Frank Paraha | 654.525 - Demolition of Existing Structures | 2021-07-24 |  | 2021-07-05 10:00 | Sarah Brooks | 2021-08-04 | 2021-08-03 23:32 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 654.53 | 654.53 | Maddie Dahlstrom | 2021-08-03 22:29 | [5 empty] | Lot closed |  | 2021-08-03 23:32 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, Keegan Baker, Maddie Dahlstrom, Patrick Coria |  | WLDN2NS01349LM.pdf, WLDN2NS01349 Checklist.pdf, IMG_0375.jpg, IMG_0377.jpg, IMG_0376.jpg | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128881 |  |  |  | 7632-2S41011 |  | 2021-08-16 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/01348 | Nabin Koirala | 2021-07-11 02:11 | Stage 2 - Penneys Road to Moree | Culverts | 653.700, 1/2400x900, remove and rebuild | Culverts - Other | Other | Frank Paraha | 653.700 - Demolition of Existing Structures |  |  | 2021-08-09 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 653.7 | 653.7 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Keegan Baker, Maddie Dahlstrom, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128880 |  |  |  | 7632-2S41011
WLD/N2NS/01347 | Nabin Koirala | 2021-07-11 02:10 | Stage 2 - Penneys Road to Moree | Culverts | 653.620, 6/2400x900, remove and rebuild | Culverts - Other | Other | Frank Paraha | 653.620 - Demolition of Existing Structures |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 653.62 | 653.62 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Keegan Baker, Maddie Dahlstrom, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128879 |  |  |  | 7632-2S41011
WLD/N2NS/01346 | Nabin Koirala | 2021-07-11 02:10 | Stage 2 - Penneys Road to Moree | Culverts | 648.635, 6/2400x900, remove and rebuild | Culverts - Other | Other | Frank Paraha | 648.635 - Demolition of Existing Structures | 2021-07-24 |  | 2021-07-07 10:00 |  |  | 2021-08-03 06:25 | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 648.64 | 648.64 | Maddie Dahlstrom | 2021-08-03 06:21 | [5 empty] | Reopened lot | No checklist attached | 2021-08-16 03:02 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, Keegan Baker, Maddie Dahlstrom, Patrick Coria |  | WLDN2NS01346 CHECKLIST.pdf, WLDN2NS01346LM.pdf, IMG_0320.JPG, IMG_0319.JPG, IMG_0322.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128878 |  |  |  | 7632-2S41011 |  | 2021-08-16 | Mike Harris | ARTC Rejected
WLD/N2NS/01345 | Nabin Koirala | 2021-07-11 02:09 | Stage 2 - Penneys Road to Moree | Culverts | 648.395, 10/3000x2400, remove and rebuild | Culverts - Other | Other | Frank Paraha | 648.395 - Demolition of Existing Structures |  |  | 2021-08-04 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 648.4 | 648.4 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Keegan Baker, Maddie Dahlstrom, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128877 |  |  |  | 7632-2S41011
WLD/N2NS/01344 | Nabin Koirala | 2021-07-11 02:09 | Stage 2 - Penneys Road to Moree | Culverts | 648.240, 6/2400x900, remove and rebuild | Culverts - Other | Other | Frank Paraha | 648.240 - Demolition of Existing Structures | 2021-07-24 |  | 2021-07-08 10:00 | Sarah Brooks | 2021-08-04 | 2021-08-04 05:41 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 |  |  |  | WLD/N2NS/01341, WLD/N2NS/01447 | [5 empty] | 648.24 | 648.24 | Maddie Dahlstrom | 2021-08-04 04:57 | [5 empty] | Lot closed |  | 2021-08-04 05:41 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, Keegan Baker, Maddie Dahlstrom, Patrick Coria |  | WLDN2NS01344LM.pdf, WLDN2NS01344 Checklist.pdf, IMG_0308.jpg, IMG_0307.jpg, IMG_0303.jpg, IMG_0309.jpg, IMG_0305.jpg, IMG_0302.jpg, IMG_0306.jpg, IMG_0310.jpg, IMG_0304.jpg | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128876 |  |  |  | 7632-2S41011 |  | 2021-08-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/01343 | Nabin Koirala | 2021-07-11 02:08 | Stage 2 - Penneys Road to Moree | Culverts | 647.925, 4/2400x1200, remove and rebuild | Culverts - Other | Other | Frank Paraha | 647.925 - Demolition of Existing Structures | 2021-07-24 |  | 2021-07-08 10:00 | Sarah Brooks | 2021-08-02 | 2021-08-02 02:09 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 647.93 | 647.93 | Sarah Brooks | 2021-08-02 02:09 | [5 empty] | Lot closed |  | 2021-08-02 02:09 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, Keegan Baker, Maddie Dahlstrom, Patrick Coria |  | WLDN2NS01343LM.pdf, MicrosoftTeams-image (4).png, MicrosoftTeams-image (5).png, WLDN2NS01343.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128875 |  |  |  | 7632-2S41011 |  | 2021-08-02 | Sarah Brooks | Submitted to ARTC for Review
WLD/N2NS/01342 | Nabin Koirala | 2021-07-11 01:37 | Stage 2 - Penneys Road to Moree | Culverts | 656,240 New | Culverts - Other | Earthworks | Frank Paraha | 656.240 - Excavation & Foundation Preparation | 2021-07-11 |  | 2021-07-12 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 |  |  |  | WLD/N2NS/00101 | [5 empty] | 656.24 | 656.24 | [6 empty] | HWP/N2NS/00378 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Maddie Dahlstrom, Patrick Coria |  | WLDN2NS01342LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128874 |  |  |  | 7632-2C41460
WLD/N2NS/01341 | Nabin Koirala | 2021-07-11 00:29 | Stage 2 - Penneys Road to Moree | Culverts | 648.240, 6/2400x900, remove and rebuild | Culverts - Other | Earthworks | Frank Paraha | 648.240 - Excavation & Foundation Preparation - Base Slab | 2021-07-11 |  | 2021-07-24 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 |  |  |  | WLD/N2NS/01344, WLD/N2NS/01447 | [5 empty] | 648.24 | 648.24 | [6 empty] | HWP/N2NS/00361, HWP/N2NS/00362 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, Maddie Dahlstrom, Patrick Coria |  | WLDN2NS01341LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128873 |  |  |  | 7632-2C41460
WLD/N2NS/01340 | Ganan Ganeshanantham | 2021-07-10 05:57 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Manufacture of Precast Rail Large & Small Concrete Box Culvert and Wing Walls - July 2021 | 2021-07-10 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058 | [9 empty] | MIX/N2NS/00001 | 0 | 0 |  |  |  | PNC/N2NS/00099, PNC/N2NS/00100, PNC/N2NS/00101, PNC/N2NS/00102, PNC/N2NS/00103, PNC/N2NS/00105, PNC/N2NS/00106, PNC/N2NS/00107, PNC/N2NS/00108, PNC/N2NS/00110, PNC/N2NS/00112, PNC/N2NS/00113, PNC/N2NS/00114, PNC/N2NS/00115, PNC/N2NS/00116, PNC/N2NS/00117, PNC/N2NS/00118, PNC/N2NS/00120, PNC/N2NS/00122, PNC/N2NS/00124, PNC/N2NS/00125, PNC/N2NS/00126, PNC/N2NS/00128, PNC/N2NS/00129, PNC/N2NS/00131, PNC/N2NS/00132, PNC/N2NS/00133, PNC/N2NS/00134, PNC/N2NS/00135, PNC/N2NS/00137, PNC/N2NS/00140, PNC/N2NS/00141 | Closed, Closed, Closed, Closed, Closed, Closed, Closed, Closed, Closed, Closed, Closed, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Open, Pending Disposition Approval, Pending Disposition Approval | [11 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128872 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/01339 | Arjan Sidhu | 2021-07-10 04:05 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Earthworks - Filling | Earthworks | Arjan Sidhu | Matpol Structural Fill - Stock Pile SF3B. First 8000T | 2021-07-10 |  | 2021-06-30 10:00 | Lorne Jenks | 2021-07-10 | 2021-07-10 04:52 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 | [9 empty] | 625.55 | 666 | Arjan Sidhu | 2021-07-10 04:15 | [5 empty] | Lot closed |  | 2021-07-10 04:52 |  |  |  | Brett Jenkins, Jake Mossman, Miaya Tighe |  | N-21-238-4.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128871 | 2021-07-29 18:40 |  |  |  |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/01338 | Arjan Sidhu | 2021-07-10 04:05 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Earthworks - Filling | Earthworks | Arjan Sidhu | Matpol Structural Fill - Stock Pile SF3A. Additional 20000T | 2021-07-10 |  | 2021-06-30 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 | [9 empty] | 625.55 | 666 | [13 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Jarryd Davis, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128870
WLD/N2NS/01337 | Arjan Sidhu | 2021-07-10 04:05 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Earthworks - Filling | Earthworks | Arjan Sidhu | Matpol Structural Fill - Stock Pile SF3A. Additional 20000T | 2021-07-10 |  | 2021-06-30 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 | [9 empty] | 625.55 | 666 | [13 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Jarryd Davis, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128869
WLD/N2NS/01336 | Kallen Doong | 2021-07-09 07:21 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH640.380 to CH641.080 - Layer 1 - 400mm | 2021-07-10 |  | 2021-08-12 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 640.38 | 641.08 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | 605B7156-6766-4D96-A566-11EA5494B0BB.JPG, 40D40395-5959-4876-9DE9-83423AD64D2A.JPG, N-21-179-598.pdf, TR 691 Panda Results.pdf, N-21-179-635.pdf, Test Request 0693 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128855 |  |  |  | 7632-2C41552
WLD/N2NS/01335 | Emma Conroy | 2021-07-09 04:26 | Stage 2 - Penneys Road to Moree | Culverts | 652.715, 1/1800x600, remove and rebuild | Drainage - Other | Other | Frank Paraha | (DELETE OR REPURPOSE) Cast Un-Situ base Slab |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00038 | [9 empty] | 652.72 | 652.72 | [13 empty] | Emma Conroy, Keegan Baker, Maddie Dahlstrom, Nabin Koirala |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128834 |  | MCS CIVIL (NSW) PTY LTD
WLD/N2NS/01334 | Emma Conroy | 2021-07-09 04:25 | Stage 2 - Penneys Road to Moree | Culverts | 652.530, 2/1800x600, remove and rebuild | Culverts - Installation of Box Culverts | Concrete | Frank Paraha | 652.530 - Cast In Situ Base Slab | 2021-07-24 |  | 2021-07-08 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00038 |  |  |  | WLD/N2NS/00573, WLD/N2NS/01387, WLD/N2NS/01448 |  |  |  |  | MIX/N2NS/00007 | 652.53 | 652.53 | [13 empty] | Emma Conroy, Keegan Baker, Maddie Dahlstrom, Nabin Koirala |  | WLDN2NS01334LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128833 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/01333 | Emma Conroy | 2021-07-09 04:25 | Stage 2 - Penneys Road to Moree | Culverts | 649.185, 2/1800x600, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | 649.185 - Cast In Situ Base Slab | 2021-07-24 |  | 2021-07-07 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00038 |  |  |  | WLD/N2NS/00089, WLD/N2NS/00575 | [5 empty] | 649.19 | 649.19 | [6 empty] | HWP/N2NS/00243 | [6 empty] | Emma Conroy, Keegan Baker, Maddie Dahlstrom, Nabin Koirala |  | WLDN2NS01333LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128832 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/01332 | Ben Foster | 2021-07-08 22:39 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 11th July to 17th July 2021 TOTAL QTY - 665.98 Tonnes | 2021-07-09 |  | 2021-07-17 10:00 | Sarah Brooks | 2021-08-02 | 2021-08-02 04:58 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 |  |  |  |  | WLD/N2NS/00259 | [5 empty] | 0 | 0 | Ben Foster | 2021-08-01 23:46 | [5 empty] | Lot closed |  | 2021-08-02 04:58 | [5 empty] | 1069900.pdf, 1069926.pdf, 1069916.pdf, 1028252 & 1028253.pdf, 1069955.pdf, 1135927.pdf, 1069931.pdf, 1028256 & 1028257.pdf, 1069953.pdf, 1135939.pdf, 1135992.pdf, 1136018.pdf, 1136005.pdf, 1070004.pdf, 1135989.pdf, 55974.pdf, 5433.pdf, 2GA-202107-0295-00077103-F.pdf, 2CH-202107-0011-00077087-F.pdf, 2AT-202107-0087-00077118-F.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128793 |  | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551 |  | 2021-08-16 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/01331 | Ben Foster | 2021-07-08 22:37 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 4th July to 10th July 2021 TOTAL QTY - 580.75 Tonnes | 2021-07-09 |  | 2021-07-10 10:00 | Sarah Brooks | 2021-08-02 | 2021-08-02 04:57 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 |  |  |  |  | WLD/N2NS/00259, WLD/N2NS/01322 | [5 empty] | 0 | 0 | Ben Foster | 2021-08-01 23:45 | [5 empty] | Lot closed |  | 2021-08-02 04:57 | [5 empty] | 1028248 & 1028250.pdf, 1135676.pdf, 1135672.pdf, 1135665.pdf, 5430.pdf, 5431.pdf, 1069843.pdf, 5432.pdf, 1135549.pdf, 1135723.pdf, 1028242.pdf, 1069878.pdf, 1069876.pdf, 1135718.pdf, 1135547 (2).pdf, 2CH-202107-0007-00077053-F.pdf, 2GA-202107-0211-00077059-F.pdf, 2AT-202107-0075-00077037-F.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128792 |  | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551 |  | 2021-08-16 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/01330 | James Martin | 2021-07-08 04:43 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH685.920 - CH686.080 | 2021-07-08 |  | 2021-07-08 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 685.92 | 686.08 | [6 empty] | HWP/N2NS/00261 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128747 |  |  |  | 7632-3C41220
WLD/N2NS/01329 | Ryan Shenton | 2021-07-07 22:48 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH641.100 to CH641.520 - Layer 1 - 400mm | 2021-07-08 |  | 2021-07-23 10:00 | Benjamin Philip | 2021-08-17 | 2021-08-17 04:55 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00599 | [5 empty] | 641.1 | 641.52 | Benjamin Philip | 2021-08-17 04:55 | [5 empty] | Lot closed |  | 2021-08-17 04:55 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | 538C0C03-9B2F-45BC-8376-E84F98A39F6D.JPG, 344EC4D4-A0F9-445E-B1E3-7B98783A7990.JPG, N-21-179-587.pdf, N-21-179-599.pdf, Test Request 0696 Panda Results.pdf, N-21-179-637.pdf, TR 687 Panda Results.pdf, E3 Stabilised Layer 1 WLD-N2NS-01329.pdf, lot map 1329.pdf, wldn2ns01329.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128731 |  |  |  | 7632-2C41552 |  | 2021-08-17 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/01328 | Ryan Shenton | 2021-07-07 22:19 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type C3 - Stage 2 - CH641.080 to CH641.140 - Insitu Chew - 300mm | 2021-07-16 |  | 2021-07-19 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00015 | [9 empty] | 641.08 | 641.14 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | 36D12C9E-36D0-47EF-B5E2-C34611B4FBD6.JPG, 10677D13-A8C7-4832-BD80-186A85CB96C7.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128729 |  |  |  | 7632-2C41552
WLD/N2NS/01327 | Frank Paraha | 2021-07-07 09:07 | Stage 2 - Penneys Road to Moree | Culverts | 647.925, 4/2400x1200, remove and rebuild | Culverts - Other | Earthworks | Frank Paraha | 647.925 - Excavation & Foundation Preparation | 2021-07-07 |  | 2021-07-10 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 647.93 | 647.93 | [6 empty] | HWP/N2NS/00354, HWP/N2NS/00360 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128724 |  |  |  | 7632-2C41460
WLD/N2NS/01326 | Arjan Sidhu | 2021-07-07 08:16 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Arjan Sidhu | Capping Placement - CH 629500 to 630600 | 2021-07-07 |  | 2021-07-20 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 629.5 | 630.6 |  |  |  | PNC/N2NS/00123 | Disposition Rejected | [8 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Jarryd Davis, Miaya Tighe |  | IMG_0481.JPG, IMG_0478.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128723 |  |  |  | 7632-2C47051
WLD/N2NS/01325 | Richard Doering | 2021-07-07 07:55 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 2 CH652.700 to CH653.180 | 2021-07-07 |  | 2021-07-08 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 652.7 | 653.18 | [15 empty] | Test Request 0704 Panda Results.pdf, N-21-179-564.pdf, N-21-179-634.pdf, N-21-179-580.pdf, Test Request 0677 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128722 |  |  |  | 7632-2C41552
WLD/N2NS/01324 | Richard Doering | 2021-07-07 07:52 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type C3 - Insitu Stabilisation | 2021-07-07 |  | 2021-07-06 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00015 | [9 empty] | 648.03 | 648.15 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128721 |  |  |  | 7632-2C41552
WLD/N2NS/01323 | Ryan Shenton | 2021-07-07 07:17 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH633.860 to CH634.530 - Layer 1 - 400mm | 2021-07-07 |  | 2021-07-23 10:00 | Benjamin Philip | 2021-08-17 | 2021-08-17 04:29 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00599 | [5 empty] | 633.86 | 634.53 | Benjamin Philip | 2021-08-17 04:29 | [5 empty] | Lot closed |  | 2021-08-17 04:29 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | 96E79214-D586-4E73-AAF1-BD3C23E3C097.JPG, 97C727E5-2424-4017-A664-14FD0896B461.JPG, N-21-179-636.pdf, Test Request 0694 Panda Results.pdf, N-21-179-579.pdf, Test Request 0697 Panda Results 1.pdf, E3 Stabilised Layer 1 WLD-N2NS-01323.pdf, wldn2ns01323.pdf, lot map 1323.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128718 |  |  |  | 7632-2C41552 |  | 2021-08-17 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/01322 | Frank Paraha | 2021-07-07 05:26 | Stage 2 - Penneys Road to Moree | Culverts | 647.315, 10/3000x1200, remove and rebuild | Culverts - Other | Earthworks | Frank Paraha | 647.315 - Excavation & Foundation Preparation | 2021-07-07 |  | 2021-07-11 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 |  |  |  | WLD/N2NS/00082, WLD/N2NS/00569, WLD/N2NS/01331 | [5 empty] | 647.32 | 647.32 | [6 empty] | HWP/N2NS/00256, HWP/N2NS/00357 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS01322LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128703 |  |  |  | 7632-2C41460
WLD/N2NS/01321 | James Martin | 2021-07-07 05:20 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH686.500 - CH687.210 | 2021-08-15 |  | 2021-07-08 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 686.5 | 687.21 | [6 empty] | HWP/N2NS/00257, HWP/N2NS/00259, HWP/N2NS/00260 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128702 |  |  |  | 7632-3C41220
WLD/N2NS/01320 | Miaya Tighe | 2021-07-06 22:37 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Basecourse | Other | Arjan Sidhu | JCQ Runnymede DGB20 Stockpile 6 4000T | 2021-07-07 |  | 2021-07-15 10:00 | Lorne Jenks | 2021-07-07 | 2021-07-07 00:58 | Closed | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 625.55 | 666 | Miaya Tighe | 2021-07-06 22:40 | [5 empty] | Lot closed |  | 2021-07-07 00:58 |  |  |  | Arjan Sidhu, Brett Jenkins, Jake Mossman |  | RU DGB20 Lot6-21 29-4-21.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128684 | 2021-07-29 18:40 |  |  |  |  | 2021-07-07 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/01319 | Richard Doering | 2021-07-06 07:12 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 1 CH647.700 to CH648.150 | 2021-07-06 |  | 2021-07-07 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 647.7 | 658.15 | [15 empty] | Test Request 0703 Panda Results.pdf, Test Request 0665 Panda Results.pdf, N-21-179-633.pdf, N-21-179-581.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128658 |  |  |  | 7632-2C41552
WLD/N2NS/01318 | Richard Doering | 2021-07-05 23:27 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Richard Doering | Cut inc Ground Preparation CH646.940 to CH647.110 | 2021-07-06 |  | 2021-07-08 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 646.94 | 647.11 | [6 empty] | HWP/N2NS/00253 | [8 empty] | N-21-179-711.pdf, N-21-179-789.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128600 |  |  |  | 7632-2C41220
WLD/N2NS/01317 | James Martin | 2021-07-05 22:34 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH687.210 - CH687.470 | 2021-07-06 |  | 2021-07-06 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 687.21 | 687.47 | [6 empty] | HWP/N2NS/00252 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128596 |  |  |  | 7632-3C41220
WLD/N2NS/01316 | James Martin | 2021-07-05 22:25 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH688.320 - CH688.540 | 2021-07-06 |  | 2021-07-06 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 688.32 | 688.54 | [6 empty] | HWP/N2NS/00251 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128595 |  |  |  | 7632-3C41220
WLD/N2NS/01315 | Keegan Baker | 2021-07-05 08:18 | Stage 2 - Penneys Road to Moree | Culverts | 648.635, 6/2400x900, remove and rebuild | Culverts - Other | Earthworks | Frank Paraha | 648.635 - Excavation & Foundation Preparation | 2021-07-11 |  | 2021-07-28 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 648.64 | 648.64 | [6 empty] | HWP/N2NS/00363, HWP/N2NS/00364 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128592 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/01314 | Keegan Baker | 2021-07-05 07:43 | Stage 2 - Penneys Road to Moree | Culverts | 640,080, 5/2400x900, new build | Culverts - Other | Concrete | Keegan Baker | 640.080 - Cast-In-situ Cut-off Walls | 2021-07-24 |  | 2021-08-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 640.08 | 640.08 | [6 empty] | HWP/N2NS/00249 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128581
WLD/N2NS/01313 | Keegan Baker | 2021-07-05 07:37 | Stage 2 - Penneys Road to Moree | Culverts | 639.160, 14/1800x600, new build | Culverts - Other | Concrete | Keegan Baker | 639.160 - Cast-In-situ Cut-off Walls |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 639.16 | 639.16 | [6 empty] | HWP/N2NS/00248 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128580
WLD/N2NS/01312 | Ryan Shenton | 2021-07-05 07:12 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH635.660 to CH635.720 - Layer 1 - 400mm | 2021-07-11 |  | 2021-07-23 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 635.66 | 635.72 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR 668 Panda Results.pdf, Test Request 0655 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128576 |  |  |  | 7632-2C41552
WLD/N2NS/01311 | Richard Doering | 2021-07-05 07:02 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 1 CH648.150 to CH648.700 | 2021-07-05 |  | 2021-07-06 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 648.15 | 648.7 | [15 empty] | Test Request 0702 Panda Results.pdf, Test Request 0656 Panda Results.pdf, N-21-179-604.pdf, N-21-179-562.pdf, N-21-179-541.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128575 |  |  |  | 7632-2C41552
WLD/N2NS/01310 | Ryan Shenton | 2021-07-05 06:38 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type C3 - Stage 2 - CH635660 to CH635720 - Insitu Chew - 250mm | 2021-07-17 |  | 2021-07-19 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00015 | [9 empty] | 635.66 | 635.72 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128573 |  |  |  | 7632-2C41552
WLD/N2NS/01309 | Jeramy Smith | 2021-07-05 01:05 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 750.098, LX3167, Private (Type 1, 6m, steel, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Aziz Kamaoui | Pavement Marking- LX3167 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 750 | 750.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128507
WLD/N2NS/01308 | Jeramy Smith | 2021-07-05 01:05 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 756.426, LX3169, Private (Type 1, 6m, steel, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Ahmad Alwan | Pavement Marking- LX3169 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 756.31 | 756.51 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128506
WLD/N2NS/01307 | Jeramy Smith | 2021-07-05 01:04 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 758.252, LX923, NS Road (Type 4, rubber, sealed), RX-5 | Ancillary Works - Linemarking | Roadworks | Hayden Murphy | Pavement Marking- LX923 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 758.14 | 758.34 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128505
WLD/N2NS/01306 | Jeramy Smith | 2021-07-05 01:03 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 752.749, LX3168, Private (Type 1, 6m, steel, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Aziz Kamaoui | Pavement Marking- LX3168 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 752.63 | 752.83 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128504
WLD/N2NS/01305 | Jeramy Smith | 2021-07-05 01:02 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 755.578, LX922, NS - Croppa Ck Road (Type 4, rubber, sealed), RX-5 | Ancillary Works - Linemarking | Roadworks | Ahmad Alwan | Pavement Marking- LX922 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 755.47 | 755.67 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128503
WLD/N2NS/01304 | Jeramy Smith | 2021-07-05 01:02 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 747.052, LX3166, Private (Type 1, 6m, rubber, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Hayden Murphy | Pavement Marking- LX3166 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 746.96 | 747.16 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128502
WLD/N2NS/01303 | Jeramy Smith | 2021-07-05 01:01 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 749.254, LX4378, North Star Lxing (Type 1, 4.5m, rubber, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Aziz Kamaoui | Pavement Marking- LX4378 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 749.15 | 749.35 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128501
WLD/N2NS/01302 | Jeramy Smith | 2021-07-05 01:00 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 744.977, LX3165, Private (Type 1, 6m, rubber, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX3165 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 744.87 | 745.06 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128500
WLD/N2NS/01301 | Jeramy Smith | 2021-07-05 01:00 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 732.555, LX3164, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX3164 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 732.46 | 732.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128499
WLD/N2NS/01300 | Jeramy Smith | 2021-07-05 00:59 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 742.842, LX921, Tumba Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX921 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 742.74 | 742.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128498
WLD/N2NS/01299 | Jeramy Smith | 2021-07-05 00:58 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 739.332, LX920, Murgo Access Road (Type 2, rubber, sealed at crossing), RX-2 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX920 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 739.22 | 739.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128497
WLD/N2NS/01298 | Jeramy Smith | 2021-07-05 00:58 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 736.453, LX919, Murgo Access Road (Type 2, rubber, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX919 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 736.34 | 736.54 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128496
WLD/N2NS/01297 | Jeramy Smith | 2021-07-05 00:57 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 733.944, LX918, Buckie Road (Type 4, rubber, sealed), RX-5 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX918 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 733.82 | 734.02 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128495
WLD/N2NS/01296 | Jeramy Smith | 2021-07-05 00:56 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 727.422, LX3162, Private (Type 1, 12.0m, rubber, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX3162 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 727.43 | 727.63 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128494
WLD/N2NS/01295 | Jeramy Smith | 2021-07-05 00:55 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX917 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128493
WLD/N2NS/01294 | Jeramy Smith | 2021-07-05 00:53 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 721.145, LX3161, Private (Type 1, 4.5m, rubber, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX3161 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 721.05 | 721.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128492
WLD/N2NS/01293 | Jeramy Smith | 2021-07-05 00:52 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 724.905, LX916, Crooble-Croopa Creek (Type 3, rubber, sealed at crossing), RX-2 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX916 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 724.79 | 724.99 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128491
WLD/N2NS/01292 | Jeramy Smith | 2021-07-05 00:52 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - In BOQ... LX3160, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX3160 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 716.26 | 716.46 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128490
WLD/N2NS/01291 | Jeramy Smith | 2021-07-05 00:51 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 718.865, LX915, Crooble-Croopa Creek (Type 3, 7m, rubber, sealed at crossing), RX-5 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX915 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 718.74 | 718.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128489
WLD/N2NS/01290 | Jeramy Smith | 2021-07-05 00:50 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 717.020, LX913, Gil Gil Creek Road (Type 3, 7m, rubber, sealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX913 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 716.95 | 717.15 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128488
WLD/N2NS/01289 | Jeramy Smith | 2021-07-05 00:50 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 710.961, LX912, Alma Lane (Type 3, 7m, rubber, sealed at crossing), RX-2 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX912 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 710.85 | 711.05 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128487
WLD/N2NS/01288 | Jeramy Smith | 2021-07-05 00:47 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX911 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 706.46 | 706.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128486
WLD/N2NS/01287 | Ryan Shenton | 2021-07-04 23:52 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH632.780 CH633.270 - Layer 2 - 400mm | 2021-07-05 |  | 2021-07-19 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 632.78 | 633.68 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0653 Panda Results.pdf, N-21-179-548.pdf, N-21-179-589.pdf, Test Request 0652 Panda Results.pdf, Test Request 0652 Panda Results.pdf, CF0E3D20-DDFA-4B0C-B47C-A7AF4D380C73.JPG, 283F103B-3B0C-47CD-9A94-66DA047A8681.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128482 |  |  |  | 7632-2C41552
WLD/N2NS/01286 | Jeramy Smith | 2021-07-04 23:41 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 704.694, LX3156, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX3156 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 704.59 | 704.79 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128478
WLD/N2NS/01285 | Jeramy Smith | 2021-07-04 23:41 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 700.939, LX910, Calimpa-County Boundary Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX910 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 700.83 | 701.03 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128477
WLD/N2NS/01284 | Jeramy Smith | 2021-07-04 23:40 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 693.959, LX909, Private (Type 3, 4.5m, rubber, sealed at crossing), RX-2 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX909 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 693.87 | 694.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128476
WLD/N2NS/01283 | Jeramy Smith | 2021-07-04 23:39 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 689.505, LX3153, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX3153 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 689.41 | 689.61 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128474
WLD/N2NS/01282 | Jeramy Smith | 2021-07-04 23:37 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 686.451, LX1842, Roydon Road (Type 2, 4.5m, rubber, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX1842 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 686.38 | 686.58 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128473
WLD/N2NS/01281 | Jeramy Smith | 2021-07-04 23:36 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX1841 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 686.29 | 686.49 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128471
WLD/N2NS/01280 | Jeramy Smith | 2021-07-04 23:36 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 684.899, LX3152, Private (Type 1, 6m, steel, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking- LX3152 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 684.72 | 684.92 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128470
WLD/N2NS/01279 | Jeramy Smith | 2021-07-04 23:25 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 750.098, LX3167, Private (Type 1, 6m, steel, unsealed), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX3167 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 750 | 750.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128464
WLD/N2NS/01278 | Jeramy Smith | 2021-07-04 23:23 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 756.426, LX3169, Private (Type 1, 6m, steel, unsealed), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX3169 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 756.31 | 756.51 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128463
WLD/N2NS/01277 | Jeramy Smith | 2021-07-04 23:22 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 758.252, LX923, NS Road (Type 4, rubber, sealed), RX-5 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX923 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 758.14 | 758.34 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128462
WLD/N2NS/01276 | Jeramy Smith | 2021-07-04 23:21 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 752.749, LX3168, Private (Type 1, 6m, steel, unsealed), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX3168 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 752.63 | 752.63 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128460
WLD/N2NS/01275 | Jeramy Smith | 2021-07-04 23:20 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 755.578, LX922, NS - Croppa Ck Road (Type 4, rubber, sealed), RX-5 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX922 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 755.45 | 755.67 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128459
WLD/N2NS/01274 | Jeramy Smith | 2021-07-04 23:19 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 747.052, LX3166, Private (Type 1, 6m, rubber, unsealed), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX3166 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 746.96 | 747.16 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128458
WLD/N2NS/01273 | Jeramy Smith | 2021-07-04 23:18 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 749.254, LX4378, North Star Lxing (Type 1, 4.5m, rubber, unsealed), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX4378 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 749.15 | 749.35 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128457
WLD/N2NS/01272 | Jeramy Smith | 2021-07-04 23:17 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 744.977, LX3165, Private (Type 1, 6m, rubber, unsealed), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX3165 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 744.87 | 745.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128456
WLD/N2NS/01271 | Jeramy Smith | 2021-07-04 23:16 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 732.555, LX3164, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX3164 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 732.46 | 732.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128455
WLD/N2NS/01270 | Jeramy Smith | 2021-07-04 23:16 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 742.842, LX921, Tumba Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX921 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 742.74 | 742.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128454
WLD/N2NS/01269 | Jeramy Smith | 2021-07-04 23:15 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 739.332, LX920, Murgo Access Road (Type 2, rubber, sealed at crossing), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX920 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 739.22 | 739.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128453
WLD/N2NS/01268 | Jeramy Smith | 2021-07-04 23:14 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 736.453, LX919, Murgo Access Road (Type 2, rubber, unsealed), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX919 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 736.34 | 736.54 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128452
WLD/N2NS/01267 | Jeramy Smith | 2021-07-04 23:13 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 733.944, LX918, Buckie Road (Type 4, rubber, sealed), RX-5 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX918 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 733.82 | 734.02 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128451
WLD/N2NS/01266 | Jeramy Smith | 2021-07-04 23:12 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 727.422, LX3162, Private (Type 1, 12.0m, rubber, unsealed), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX3162 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 727.43 | 727.63 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128450
WLD/N2NS/01265 | Jeramy Smith | 2021-07-04 23:11 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX917 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128449
WLD/N2NS/01264 | Jeramy Smith | 2021-07-04 23:10 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 721.145, LX3161, Private (Type 1, 4.5m, rubber, unsealed), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX3161 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 721.05 | 721.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128447
WLD/N2NS/01263 | Jeramy Smith | 2021-07-04 23:10 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 724.905, LX916, Crooble-Croopa Creek (Type 3, rubber, sealed at crossing), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX916 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 724.79 | 724.99 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128446
WLD/N2NS/01262 | Jeramy Smith | 2021-07-04 23:08 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - In BOQ... LX3160, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX3160 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 716.26 | 716.46 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128445
WLD/N2NS/01261 | Jeramy Smith | 2021-07-04 23:07 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 718.865, LX915, Crooble-Croopa Creek (Type 3, 7m, rubber, sealed at crossing), RX-5 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX915 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 718.74 | 718.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128444
WLD/N2NS/01260 | Jeramy Smith | 2021-07-04 23:06 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 717.020, LX913, Gil Gil Creek Road (Type 3, 7m, rubber, sealed), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX913 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 716.95 | 717.15 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128443
WLD/N2NS/01259 | Jeramy Smith | 2021-07-04 23:05 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 710.961, LX912, Alma Lane (Type 3, 7m, rubber, sealed at crossing), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX912 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 710.85 | 711.05 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128442
WLD/N2NS/01258 | Jeramy Smith | 2021-07-04 23:04 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX911 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 706.46 | 706.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128441
WLD/N2NS/01257 | Jeramy Smith | 2021-07-04 23:04 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 704.694, LX3156, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX3156 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 704.59 | 704.79 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128440
WLD/N2NS/01256 | Jeramy Smith | 2021-07-04 23:03 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 700.939, LX910, Calimpa-County Boundary Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX910 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 700.83 | 701.03 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128439
WLD/N2NS/01255 | Jeramy Smith | 2021-07-04 22:53 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 693.959, LX909, Private (Type 3, 4.5m, rubber, sealed at crossing), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX909 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 693.87 | 694.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128437
WLD/N2NS/01254 | Jeramy Smith | 2021-07-04 22:53 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 689.505, LX3153, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX3153 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 689.41 | 689.61 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128436
WLD/N2NS/01253 | Jeramy Smith | 2021-07-04 22:52 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 686.451, LX1842, Roydon Road (Type 2, 4.5m, rubber, unsealed), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX1842 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 686.38 | 686.58 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128435
WLD/N2NS/01252 | Jeramy Smith | 2021-07-04 22:51 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX1841 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 686.29 | 686.49 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128434
WLD/N2NS/01251 | Jeramy Smith | 2021-07-04 22:51 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 684.899, LX3152, Private (Type 1, 6m, steel, unsealed), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX3152 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 684.72 | 684.92 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128433
WLD/N2NS/01250 | Jeramy Smith | 2021-07-04 22:49 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 750.098, LX3167, Private (Type 1, 6m, steel, unsealed), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX3167 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 750 | 750.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128432
WLD/N2NS/01249 | Jeramy Smith | 2021-07-04 22:48 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 756.426, LX3169, Private (Type 1, 6m, steel, unsealed), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX3169 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 756.31 | 756.51 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128431
WLD/N2NS/01248 | Jeramy Smith | 2021-07-04 22:45 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 758.252, LX923, NS Road (Type 4, rubber, sealed), RX-5 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX923 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 758.14 | 758.34 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128430
WLD/N2NS/01247 | Jeramy Smith | 2021-07-04 22:44 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 752.749, LX3168, Private (Type 1, 6m, steel, unsealed), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX3168 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 782.63 | 782.83 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128429
WLD/N2NS/01246 | Jeramy Smith | 2021-07-04 22:43 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 755.578, LX922, NS - Croppa Ck Road (Type 4, rubber, sealed), RX-5 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX922 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 755.47 | 755.67 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128428
WLD/N2NS/01245 | Jeramy Smith | 2021-07-04 22:42 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 747.052, LX3166, Private (Type 1, 6m, rubber, unsealed), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX3166 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 746.96 | 747.16 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128427
WLD/N2NS/01244 | Jeramy Smith | 2021-07-04 22:42 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 749.254, LX4378, North Star Lxing (Type 1, 4.5m, rubber, unsealed), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX4378 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 749.15 | 749.35 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128426
WLD/N2NS/01243 | Jeramy Smith | 2021-07-04 22:41 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 744.977, LX3165, Private (Type 1, 6m, rubber, unsealed), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX3165 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 744.87 | 745.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128425
WLD/N2NS/01242 | Jeramy Smith | 2021-07-04 22:40 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 732.555, LX3164, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX3164 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 732.46 | 732.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128424
WLD/N2NS/01241 | Jeramy Smith | 2021-07-04 22:39 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 742.842, LX921, Tumba Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX921 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 742.74 | 742.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128423
WLD/N2NS/01240 | Jeramy Smith | 2021-07-04 22:38 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 739.332, LX920, Murgo Access Road (Type 2, rubber, sealed at crossing), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX920 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 739.22 | 739.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128422
WLD/N2NS/01239 | Jeramy Smith | 2021-07-04 22:37 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 736.453, LX919, Murgo Access Road (Type 2, rubber, unsealed), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX919 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 736.34 | 736.54 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128421
WLD/N2NS/01238 | Jeramy Smith | 2021-07-04 22:36 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 733.944, LX918, Buckie Road (Type 4, rubber, sealed), RX-5 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX918 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 733.82 | 734.02 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128420
WLD/N2NS/01237 | Jeramy Smith | 2021-07-04 22:35 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 727.422, LX3162, Private (Type 1, 12.0m, rubber, unsealed), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX3162 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 727.43 | 727.63 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128419
WLD/N2NS/01236 | Jeramy Smith | 2021-07-04 22:32 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX917 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128418
WLD/N2NS/01235 | Jeramy Smith | 2021-07-04 22:31 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 721.145, LX3161, Private (Type 1, 4.5m, rubber, unsealed), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX3161 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 721.05 | 721.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128417
WLD/N2NS/01234 | Jeramy Smith | 2021-07-04 22:30 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 724.905, LX916, Crooble-Croopa Creek (Type 3, rubber, sealed at crossing), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX916 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 724.79 | 724.99 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128416
WLD/N2NS/01233 | Jeramy Smith | 2021-07-04 22:29 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - In BOQ... LX3160, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX3160 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 716.26 | 716.46 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128415
WLD/N2NS/01232 | Jeramy Smith | 2021-07-04 22:28 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 718.865, LX915, Crooble-Croopa Creek (Type 3, 7m, rubber, sealed at crossing), RX-5 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX915 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 718.74 | 718.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128414
WLD/N2NS/01231 | Jeramy Smith | 2021-07-04 22:27 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 717.020, LX913, Gil Gil Creek Road (Type 3, 7m, rubber, sealed), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX913 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 716.95 | 717.15 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128413
WLD/N2NS/01230 | Jeramy Smith | 2021-07-04 22:26 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 710.961, LX912, Alma Lane (Type 3, 7m, rubber, sealed at crossing), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX912 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 710.85 | 711.05 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128412
WLD/N2NS/01229 | Jeramy Smith | 2021-07-04 22:25 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX911 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 706.46 | 706.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128411
WLD/N2NS/01228 | Jeramy Smith | 2021-07-04 22:24 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 704.694, LX3156, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX3156 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 704.59 | 704.79 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128410
WLD/N2NS/01227 | Jeramy Smith | 2021-07-04 22:23 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 700.939, LX910, Calimpa-County Boundary Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX910 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 700.83 | 701.03 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128409
WLD/N2NS/01226 | Jeramy Smith | 2021-07-04 22:22 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 693.959, LX909, Private (Type 3, 4.5m, rubber, sealed at crossing), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX909 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 700.83 | 701.03 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128408
WLD/N2NS/01225 | Jeramy Smith | 2021-07-04 22:21 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 689.505, LX3153, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX3153 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 689.41 | 689.61 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128407
WLD/N2NS/01224 | Jeramy Smith | 2021-07-04 22:21 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 686.451, LX1842, Roydon Road (Type 2, 4.5m, rubber, unsealed), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX1842 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 686.38 | 686.58 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128406
WLD/N2NS/01223 | Jeramy Smith | 2021-07-04 22:20 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX1841 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 686.29 | 686.49 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128405
WLD/N2NS/01222 | Jeramy Smith | 2021-07-04 22:19 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 684.899, LX3152, Private (Type 1, 6m, steel, unsealed), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX3152 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 684.72 | 684.92 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128404
WLD/N2NS/01221 | Jeramy Smith | 2021-07-04 22:17 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 750.098, LX3167, Private (Type 1, 6m, steel, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX3167 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 750 | 750.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128403
WLD/N2NS/01220 | Jeramy Smith | 2021-07-04 22:17 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 756.426, LX3169, Private (Type 1, 6m, steel, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX3169 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 756.31 | 756.51 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128402
WLD/N2NS/01219 | Jeramy Smith | 2021-07-04 22:16 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 758.252, LX923, NS Road (Type 4, rubber, sealed), RX-5 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX923 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 758.14 | 758.34 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128401
WLD/N2NS/01218 | Jeramy Smith | 2021-07-04 22:15 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 752.749, LX3168, Private (Type 1, 6m, steel, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX3168 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 752.63 | 752.83 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128400
WLD/N2NS/01217 | Jeramy Smith | 2021-07-04 22:14 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 755.578, LX922, NS - Croppa Ck Road (Type 4, rubber, sealed), RX-5 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX922 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 755.47 | 755.67 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128399
WLD/N2NS/01216 | Jeramy Smith | 2021-07-04 22:13 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 747.052, LX3166, Private (Type 1, 6m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX3166 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 746.96 | 747.16 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128398
WLD/N2NS/01215 | Jeramy Smith | 2021-07-04 22:12 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 749.254, LX4378, North Star Lxing (Type 1, 4.5m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX4378 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 749.15 | 749.35 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128397
WLD/N2NS/01214 | Jeramy Smith | 2021-07-04 22:12 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 744.977, LX3165, Private (Type 1, 6m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX3165 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 744.87 | 745.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128396
WLD/N2NS/01213 | Jeramy Smith | 2021-07-04 22:11 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 732.555, LX3164, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX3164 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 732.46 | 732.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128395
WLD/N2NS/01212 | Jeramy Smith | 2021-07-04 22:10 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 742.842, LX921, Tumba Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX921 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 742.74 | 742.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128394
WLD/N2NS/01211 | Jeramy Smith | 2021-07-04 22:09 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 739.332, LX920, Murgo Access Road (Type 2, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX920 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 739.22 | 739.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128393
WLD/N2NS/01210 | Jeramy Smith | 2021-07-04 22:08 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 736.453, LX919, Murgo Access Road (Type 2, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX919 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 736.34 | 736.54 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128392
WLD/N2NS/01209 | Jeramy Smith | 2021-07-04 22:07 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 733.944, LX918, Buckie Road (Type 4, rubber, sealed), RX-5 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX918 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 733.82 | 734.02 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128391
WLD/N2NS/01208 | Jeramy Smith | 2021-07-04 22:06 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 727.422, LX3162, Private (Type 1, 12.0m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX3162 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 727.43 | 727.63 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128390
WLD/N2NS/01207 | Jeramy Smith | 2021-07-04 22:05 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX917 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128388
WLD/N2NS/01206 | Jeramy Smith | 2021-07-04 22:05 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 721.145, LX3161, Private (Type 1, 4.5m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX3161 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 721.05 | 721.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128387
WLD/N2NS/01205 | Jeramy Smith | 2021-07-04 22:04 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 724.905, LX916, Crooble-Croopa Creek (Type 3, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX916 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 724.79 | 724.99 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128386
WLD/N2NS/01204 | Jeramy Smith | 2021-07-04 22:03 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - In BOQ... LX3160, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX3160 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 716.26 | 716.46 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128385
WLD/N2NS/01203 | Jeramy Smith | 2021-07-04 22:02 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 718.865, LX915, Crooble-Croopa Creek (Type 3, 7m, rubber, sealed at crossing), RX-5 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX915 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 718.74 | 718.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128384
WLD/N2NS/01202 | Jeramy Smith | 2021-07-04 22:01 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 717.020, LX913, Gil Gil Creek Road (Type 3, 7m, rubber, sealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX913 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 716.95 | 717.15 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128383
WLD/N2NS/01201 | Jeramy Smith | 2021-07-04 22:00 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 710.961, LX912, Alma Lane (Type 3, 7m, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX912 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 710.85 | 711.05 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128382
WLD/N2NS/01200 | Jeramy Smith | 2021-07-04 21:59 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX911 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 706.46 | 706.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128381
WLD/N2NS/01199 | Jeramy Smith | 2021-07-04 21:59 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 704.694, LX3156, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX3156 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 704.59 | 704.79 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128380
WLD/N2NS/01198 | Jeramy Smith | 2021-07-04 21:58 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 700.939, LX910, Calimpa-County Boundary Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX910 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 700.83 | 701.03 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128378
WLD/N2NS/01197 | Jeramy Smith | 2021-07-04 21:57 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 693.959, LX909, Private (Type 3, 4.5m, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX909 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 693.87 | 694.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128377
WLD/N2NS/01196 | Jeramy Smith | 2021-07-04 21:56 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 689.505, LX3153, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX3135 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 689.41 | 689.61 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128375
WLD/N2NS/01195 | Jeramy Smith | 2021-07-04 21:54 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 689.505, LX3153, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX3153 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 689.41 | 689.61 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128373
WLD/N2NS/01194 | Jeramy Smith | 2021-07-04 21:54 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 686.451, LX1842, Roydon Road (Type 2, 4.5m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX1842 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 686.38 | 686.58 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128372
WLD/N2NS/01193 | Jeramy Smith | 2021-07-04 21:53 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX1841 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 686.29 | 686.49 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128370
WLD/N2NS/01192 | Jeramy Smith | 2021-07-04 21:52 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 684.899, LX3152, Private (Type 1, 6m, steel, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX3152 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 684.72 | 684.92 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128368
WLD/N2NS/01191 | Jeramy Smith | 2021-07-04 21:50 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 750.098, LX3167, Private (Type 1, 6m, steel, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX3167 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 750 | 750.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128367
WLD/N2NS/01190 | Jeramy Smith | 2021-07-04 21:48 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 756.426, LX3169, Private (Type 1, 6m, steel, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX3169 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 756.31 | 756.51 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128366
WLD/N2NS/01189 | Jeramy Smith | 2021-07-04 21:48 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 758.252, LX923, NS Road (Type 4, rubber, sealed), RX-5 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX923 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 758.14 | 758.34 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128365
WLD/N2NS/01188 | Jeramy Smith | 2021-07-04 21:47 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 752.749, LX3168, Private (Type 1, 6m, steel, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX3168 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 752.63 | 752.83 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128364
WLD/N2NS/01187 | Jeramy Smith | 2021-07-04 21:46 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 755.578, LX922, NS - Croppa Ck Road (Type 4, rubber, sealed), RX-5 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX922 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 755.47 | 755.67 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128363
WLD/N2NS/01186 | Jeramy Smith | 2021-07-04 21:45 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 747.052, LX3166, Private (Type 1, 6m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX3166 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 746.96 | 747.16 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128362
WLD/N2NS/01185 | Jeramy Smith | 2021-07-04 21:44 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 749.254, LX4378, North Star Lxing (Type 1, 4.5m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX4378 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 749.15 | 749.35 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128361
WLD/N2NS/01184 | Jeramy Smith | 2021-07-04 21:44 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 744.977, LX3165, Private (Type 1, 6m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX3165 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 744.87 | 745.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128360
WLD/N2NS/01183 | Jeramy Smith | 2021-07-04 21:43 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 732.555, LX3164, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX3164 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 732.46 | 732.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128359
WLD/N2NS/01182 | Jeramy Smith | 2021-07-04 21:42 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 742.842, LX921, Tumba Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX921 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 742.74 | 742.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128358
WLD/N2NS/01181 | Jeramy Smith | 2021-07-04 21:41 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 739.332, LX920, Murgo Access Road (Type 2, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX920 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 739.22 | 739.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128357
WLD/N2NS/01180 | Jeramy Smith | 2021-07-04 21:41 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 736.453, LX919, Murgo Access Road (Type 2, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX919 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 736.34 | 736.54 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128356
WLD/N2NS/01179 | Jeramy Smith | 2021-07-04 21:40 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 733.944, LX918, Buckie Road (Type 4, rubber, sealed), RX-5 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX918 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 733.82 | 734.02 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128355
WLD/N2NS/01178 | Jeramy Smith | 2021-07-04 21:39 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 727.422, LX3162, Private (Type 1, 12.0m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX3162 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 727.43 | 727.63 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128354
WLD/N2NS/01177 | Jeramy Smith | 2021-07-04 21:38 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX917 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128353
WLD/N2NS/01176 | Jeramy Smith | 2021-07-04 21:38 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 721.145, LX3161, Private (Type 1, 4.5m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX3161 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 721.05 | 721.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128352
WLD/N2NS/01175 | Jeramy Smith | 2021-07-04 21:37 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 724.905, LX916, Crooble-Croopa Creek (Type 3, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX916 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 724.79 | 724.99 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128351
WLD/N2NS/01174 | Jeramy Smith | 2021-07-04 21:36 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - In BOQ... LX3160, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX3160 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 716.26 | 716.46 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128350
WLD/N2NS/01173 | Jeramy Smith | 2021-07-04 21:35 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 718.865, LX915, Crooble-Croopa Creek (Type 3, 7m, rubber, sealed at crossing), RX-5 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX915 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 718.74 | 718.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128349
WLD/N2NS/01172 | Jeramy Smith | 2021-07-04 21:34 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 717.020, LX913, Gil Gil Creek Road (Type 3, 7m, rubber, sealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX913 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 716.95 | 717.15 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128348
WLD/N2NS/01171 | Jeramy Smith | 2021-07-04 21:33 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 710.961, LX912, Alma Lane (Type 3, 7m, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX912 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 710.85 | 710.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128347
WLD/N2NS/01170 | Jeramy Smith | 2021-07-04 21:32 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX911 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 706.46 | 706.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128346
WLD/N2NS/01169 | Jeramy Smith | 2021-07-04 21:31 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 704.694, LX3156, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX3156 |  |  | 2021-08-05 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 704.59 | 704.79 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128345
WLD/N2NS/01168 | Richard Doering | 2021-07-04 07:43 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 1 CH648.700 to CH649.350 | 2021-07-03 |  | 2021-07-05 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 648.7 | 649.35 | [15 empty] | N-21-179-542.pdf, N-21-179-547.pdf, N-21-179-590.pdf, Test Request 0648 Panda Results.pdf, Test Request 0675 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128344 |  |  |  | 7632-2C41552
WLD/N2NS/01167 | James Martin | 2021-07-04 06:32 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH687.940 - CH688.320 | 2021-07-04 |  | 2021-07-05 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 687.94 | 688.32 | [6 empty] | HWP/N2NS/00247 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128341 |  |  |  | 7632-3C41220
WLD/N2NS/01166 | Arjan Sidhu | 2021-07-04 05:03 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Earthworks - Filling | Earthworks | Arjan Sidhu | Matpol Structural Fill - Stock Pile SF3A. Additional 20000T | 2021-07-04 |  | 2021-06-30 10:00 | Lorne Jenks | 2021-07-05 | 2021-07-05 01:09 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 | [9 empty] | 625.55 | 666 | Arjan Sidhu | 2021-07-04 05:08 | [5 empty] | Lot closed |  | 2021-07-05 01:09 |  |  |  | Brett Jenkins, Jake Mossman, Miaya Tighe |  | N-21-238-3_SF3A_Combined_20000t.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128340 | 2021-07-29 18:40 |  |  |  |  | 2021-07-06 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/01165 | Arjan Sidhu | 2021-07-04 00:55 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Arjan Sidhu | Capping Placement - CH 636.35 - CH636.7 | 2021-07-04 |  | 2021-07-06 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 636.35 | 636.7 | [6 empty] | HWP/N2NS/00245, HWP/N2NS/00258 | [6 empty] | Arjan Sidhu, Brett Jenkins, Jake Mossman, Jarryd Davis, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128332 |  |  |  | 7632-2C47051
WLD/N2NS/01164 | Richard Doering | 2021-07-03 07:22 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 1 CH649.480 to CH650.000 | 2021-07-03 |  | 2021-07-04 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 649.48 | 650 | [15 empty] | Test Request 0666 Panda Results.pdf, N-21-179-540.pdf, N-21-179-591.pdf, N-21-179-549.pdf, Test Request 0642 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128330 |  |  |  | 7632-2C41552
WLD/N2NS/01163 | Richard Doering | 2021-07-02 07:39 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 2 CH653.180 to CH653.580 | 2021-07-02 |  | 2021-07-04 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 653.18 | 653.58 | [15 empty] | Test Request 0657 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128321 |  |  |  | 7632-2C41552
WLD/N2NS/01162 | Jeramy Smith | 2021-07-02 06:25 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 700.939, LX910, Calimpa-County Boundary Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX910 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 700.83 | 701.03 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128319
WLD/N2NS/01161 | Jeramy Smith | 2021-07-02 06:24 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 693.959, LX909, Private (Type 3, 4.5m, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX909 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 693.87 | 694.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128318
WLD/N2NS/01160 | Jeramy Smith | 2021-07-02 06:24 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 689.505, LX3153, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX3153 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 689.41 | 689.61 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128317
WLD/N2NS/01159 | Jeramy Smith | 2021-07-02 06:23 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 686.451, LX1842, Roydon Road (Type 2, 4.5m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX1842 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 686.38 | 686.58 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128316
WLD/N2NS/01158 | Jeramy Smith | 2021-07-02 06:22 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX1841 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 686.29 | 686.49 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128315
WLD/N2NS/01157 | Jeramy Smith | 2021-07-02 06:21 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 684.899, LX3152, Private (Type 1, 6m, steel, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX3152 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 684.72 | 684.92 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128314
WLD/N2NS/01156 | Jeramy Smith | 2021-07-02 06:09 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 750.098, LX3167, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX3167 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 750 | 750.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128313
WLD/N2NS/01155 | Jeramy Smith | 2021-07-02 06:08 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 756.426, LX3169, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX3169 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 756.31 | 756.51 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128312
WLD/N2NS/01154 | Jeramy Smith | 2021-07-02 06:07 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 758.252, LX923, NS Road (Type 4, rubber, sealed), RX-5 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX923 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 758.14 | 758.34 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128311
WLD/N2NS/01153 | Jeramy Smith | 2021-07-02 06:06 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 752.749, LX3168, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX3168 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 752.63 | 752.83 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128310
WLD/N2NS/01152 | Jeramy Smith | 2021-07-02 06:05 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 755.578, LX922, NS - Croppa Ck Road (Type 4, rubber, sealed), RX-5 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX922 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 755.47 | 755.67 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128308
WLD/N2NS/01151 | Jeramy Smith | 2021-07-02 06:03 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 747.052, LX3166, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX3166 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 746.96 | 747.16 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128307
WLD/N2NS/01150 | Jeramy Smith | 2021-07-02 06:02 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 749.254, LX4378, North Star Lxing (Type 1, 4.5m, rubber, unsealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX4378 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 749.15 | 749.35 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128306
WLD/N2NS/01149 | Jeramy Smith | 2021-07-02 06:02 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 744.977, LX3165, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX3165 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 744.87 | 745.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128305
WLD/N2NS/01148 | Jeramy Smith | 2021-07-02 06:01 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 732.555, LX3164, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX3164 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 732.46 | 732.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128304
WLD/N2NS/01147 | Jeramy Smith | 2021-07-02 05:48 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 742.842, LX921, Tumba Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX921 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 742.74 | 742.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128302
WLD/N2NS/01146 | Jeramy Smith | 2021-07-02 05:46 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 739.332, LX920, Murgo Access Road (Type 2, rubber, sealed at crossing), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX920 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 739.22 | 739.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128301
WLD/N2NS/01145 | Jeramy Smith | 2021-07-02 05:45 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 736.453, LX919, Murgo Access Road (Type 2, rubber, unsealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX919 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 736.34 | 736.54 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128300
WLD/N2NS/01144 | Jeramy Smith | 2021-07-02 05:30 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 733.944, LX918, Buckie Road (Type 4, rubber, sealed), RX-5 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX918 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 733.82 | 734.02 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128299
WLD/N2NS/01143 | Jeramy Smith | 2021-07-02 05:28 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 727.422, LX3162, Private (Type 1, 12.0m, rubber, unsealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX3162 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 727.43 | 727.63 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128298
WLD/N2NS/01142 | Jeramy Smith | 2021-07-02 05:28 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX917 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128297
WLD/N2NS/01141 | Jeramy Smith | 2021-07-02 05:27 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 721.145, LX3161, Private (Type 1, 4.5m, rubber, unsealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX3161 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 721.05 | 721.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128296
WLD/N2NS/01140 | Jeramy Smith | 2021-07-02 05:26 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 724.905, LX916, Crooble-Croopa Creek (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX916 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 724.79 | 724.99 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128295
WLD/N2NS/01139 | Jeramy Smith | 2021-07-02 05:26 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - In BOQ... LX3160, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX3160 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 716.26 | 716.46 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128294
WLD/N2NS/01138 | Jeramy Smith | 2021-07-02 05:24 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 718.865, LX915, Crooble-Croopa Creek (Type 3, 7m, rubber, sealed at crossing), RX-5 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX915 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 718.74 | 718.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128293
WLD/N2NS/01137 | Jeramy Smith | 2021-07-02 05:23 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 717.020, LX913, Gil Gil Creek Road (Type 3, 7m, rubber, sealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX913 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 716.95 | 717.15 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128292
WLD/N2NS/01136 | Jeramy Smith | 2021-07-02 05:21 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 710.961, LX912, Alma Lane (Type 3, 7m, rubber, sealed at crossing), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX912 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 710.85 | 711.05 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128290
WLD/N2NS/01135 | Jeramy Smith | 2021-07-02 05:20 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX911 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 706.46 | 706.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128289
WLD/N2NS/01134 | Jeramy Smith | 2021-07-02 05:19 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 704.694, LX3156, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX3156 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 704.59 | 704.79 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128288
WLD/N2NS/01133 | Jeramy Smith | 2021-07-02 05:19 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 700.939, LX910, Calimpa-County Boundary Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX910 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 700.83 | 701.03 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128287
WLD/N2NS/01132 | Jeramy Smith | 2021-07-02 05:18 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 693.959, LX909, Private (Type 3, 4.5m, rubber, sealed at crossing), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX909 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 693.87 | 694.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128286
WLD/N2NS/01131 | Jeramy Smith | 2021-07-02 05:17 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 689.505, LX3153, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX3153 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 689.41 | 689.61 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128285
WLD/N2NS/01130 | Jeramy Smith | 2021-07-02 05:16 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 686.451, LX1842, Roydon Road (Type 2, 4.5m, rubber, unsealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX1842 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 686.38 | 686.58 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128284
WLD/N2NS/01129 | Jeramy Smith | 2021-07-02 05:16 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX1841 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 686.29 | 686.49 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128283
WLD/N2NS/01128 | Jeramy Smith | 2021-07-02 05:06 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 750.098, LX3167, Private (Type 1, 6m, steel, unsealed), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX3167 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 749.1 | 750.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128282
WLD/N2NS/01127 | Jeramy Smith | 2021-07-02 05:05 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 756.426, LX3169, Private (Type 1, 6m, steel, unsealed), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX3169 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 756.31 | 756.51 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128281
WLD/N2NS/01126 | Jeramy Smith | 2021-07-02 05:03 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 758.252, LX923, NS Road (Type 4, rubber, sealed), RX-5 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX923 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 758.14 | 758.34 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128280
WLD/N2NS/01125 | Jeramy Smith | 2021-07-02 05:02 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 752.749, LX3168, Private (Type 1, 6m, steel, unsealed), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX3168 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 752.63 | 752.83 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128279
WLD/N2NS/01124 | Jeramy Smith | 2021-07-02 05:01 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 755.578, LX922, NS - Croppa Ck Road (Type 4, rubber, sealed), RX-5 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX922 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 755.47 | 755.67 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128278
WLD/N2NS/01123 | Jeramy Smith | 2021-07-02 05:00 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 747.052, LX3166, Private (Type 1, 6m, rubber, unsealed), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX3166 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 747.15 | 749.35 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128277
WLD/N2NS/01122 | Jeramy Smith | 2021-07-02 04:58 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 749.254, LX4378, North Star Lxing (Type 1, 4.5m, rubber, unsealed), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX4378 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 749.15 | 749.35 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128276
WLD/N2NS/01121 | Frank Paraha | 2021-07-02 04:48 | Stage 2 - Penneys Road to Moree | Culverts | 627.430, 30/3000x2100, remove and rebuild | Culverts - Headwalls, Wingwalls and Cut Off Walls | Concrete | Keegan Baker | 627.430 - Cast In Situ Apron Slab | 2021-07-02 |  | 2021-08-08 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 |  |  |  | WLD/N2NS/00037, WLD/N2NS/00527, WLD/N2NS/00528, WLD/N2NS/00661 |  |  |  |  | MIX/N2NS/00007 | 627.43 | 627.43 | [6 empty] | HWP/N2NS/00244, HWP/N2NS/00284 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128275 |  |  |  | 7632-2S72200
WLD/N2NS/01120 | Jeramy Smith | 2021-07-02 02:34 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 744.977, LX3165, Private (Type 1, 6m, rubber, unsealed), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX3165 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 744.87 | 745.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128269
WLD/N2NS/01119 | Jeramy Smith | 2021-07-02 02:32 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 732.555, LX3164, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX3164 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 732.46 | 732.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128268
WLD/N2NS/01118 | Jeramy Smith | 2021-07-02 02:30 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 742.842, LX921, Tumba Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX921 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 742.74 | 742.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128267
WLD/N2NS/01117 | Jeramy Smith | 2021-07-02 02:30 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 736.453, LX919, Murgo Access Road (Type 2, rubber, unsealed), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX919 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 736.34 | 736.54 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128265
WLD/N2NS/01116 | Jeramy Smith | 2021-07-02 02:29 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 733.944, LX918, Buckie Road (Type 4, rubber, sealed), RX-5 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX918 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 733.82 | 734.02 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128263
WLD/N2NS/01115 | Jeramy Smith | 2021-07-02 02:28 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 727.422, LX3162, Private (Type 1, 12.0m, rubber, unsealed), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX3162 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 727.43 | 727.63 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128262
WLD/N2NS/01114 | Jeramy Smith | 2021-07-02 02:26 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX917 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128260
WLD/N2NS/01113 | Jeramy Smith | 2021-07-02 02:25 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 721.145, LX3161, Private (Type 1, 4.5m, rubber, unsealed), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX3161 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 721.05 | 721.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128259
WLD/N2NS/01112 | Jeramy Smith | 2021-07-02 02:24 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 724.905, LX916, Crooble-Croopa Creek (Type 3, rubber, sealed at crossing), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX916 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 724.79 | 742.99 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128258
WLD/N2NS/01111 | Jeramy Smith | 2021-07-02 02:23 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - In BOQ... LX3160, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX3160 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 716.26 | 716.46 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128256
WLD/N2NS/01110 | Jeramy Smith | 2021-07-02 02:23 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 718.865, LX915, Crooble-Croopa Creek (Type 3, 7m, rubber, sealed at crossing), RX-5 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX915 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 718.74 | 718.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128255
WLD/N2NS/01109 | Jeramy Smith | 2021-07-02 02:22 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 717.020, LX913, Gil Gil Creek Road (Type 3, 7m, rubber, sealed), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX913 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 716.95 | 717.15 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128254
WLD/N2NS/01108 | Jeramy Smith | 2021-07-02 02:21 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 710.961, LX912, Alma Lane (Type 3, 7m, rubber, sealed at crossing), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX912 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 710.85 | 711.05 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128253
WLD/N2NS/01107 | Jeramy Smith | 2021-07-02 02:20 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX911 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 706.46 | 706.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128252
WLD/N2NS/01106 | Jeramy Smith | 2021-07-02 02:20 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 704.694, LX3156, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX3156 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 704.59 | 704.79 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128251
WLD/N2NS/01105 | Jeramy Smith | 2021-07-02 02:19 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 700.939, LX910, Calimpa-County Boundary Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX910 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 700.83 | 701.03 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128250
WLD/N2NS/01104 | Jeramy Smith | 2021-07-02 02:18 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 693.959, LX909, Private (Type 3, 4.5m, rubber, sealed at crossing), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX909 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 693.87 | 694.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128249
WLD/N2NS/01103 | Jeramy Smith | 2021-07-02 02:17 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 689.505, LX3153, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX3153 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 689.41 | 689.61 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128248
WLD/N2NS/01102 | Jeramy Smith | 2021-07-02 02:16 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 686.451, LX1842, Roydon Road (Type 2, 4.5m, rubber, unsealed), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX1842 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 686.29 | 686.49 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128247
WLD/N2NS/01101 | Jeramy Smith | 2021-07-02 02:16 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX1841 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 686.29 | 686.49 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128246
WLD/N2NS/01100 | Jeramy Smith | 2021-07-02 02:15 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 684.899, LX3152, Private (Type 1, 6m, steel, unsealed), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX3152 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 684.72 | 684.92 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128245
WLD/N2NS/01099 | Jeramy Smith | 2021-07-02 02:13 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 750.098, LX3167, Private (Type 1, 6m, steel, unsealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX3167 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 750 | 750.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128244
WLD/N2NS/01098 | Jeramy Smith | 2021-07-02 02:12 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 756.426, LX3169, Private (Type 1, 6m, steel, unsealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX3169 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 756.31 | 756.51 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128243
WLD/N2NS/01097 | Jeramy Smith | 2021-07-02 02:11 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 758.252, LX923, NS Road (Type 4, rubber, sealed), RX-5 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX923 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 758.14 | 758.34 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128242
WLD/N2NS/01096 | Jeramy Smith | 2021-07-02 02:10 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 752.749, LX3168, Private (Type 1, 6m, steel, unsealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX3168 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 752.63 | 752.83 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128241
WLD/N2NS/01095 | Jeramy Smith | 2021-07-02 02:09 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 755.578, LX922, NS - Croppa Ck Road (Type 4, rubber, sealed), RX-5 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX922 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 755.47 | 755.67 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128240
WLD/N2NS/01094 | Jeramy Smith | 2021-07-02 02:09 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 747.052, LX3166, Private (Type 1, 6m, rubber, unsealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX3166 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 746.96 | 747.16 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128239
WLD/N2NS/01093 | Jeramy Smith | 2021-07-02 02:08 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 749.254, LX4378, North Star Lxing (Type 1, 4.5m, rubber, unsealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX4378 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 749.15 | 749.35 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128238
WLD/N2NS/01092 | Jeramy Smith | 2021-07-02 02:07 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 744.977, LX3165, Private (Type 1, 6m, rubber, unsealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX3165 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 744.87 | 745.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128236
WLD/N2NS/01091 | Jeramy Smith | 2021-07-02 02:06 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 732.555, LX3164, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX3164 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 732.46 | 732.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128235
WLD/N2NS/01090 | Jeramy Smith | 2021-07-02 02:05 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 742.842, LX921, Tumba Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX921 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 742.74 | 742.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128234
WLD/N2NS/01089 | Jeramy Smith | 2021-07-02 02:04 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 739.332, LX920, Murgo Access Road (Type 2, rubber, sealed at crossing), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX920 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 739.22 | 739.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128233
WLD/N2NS/01088 | Jeramy Smith | 2021-07-02 02:03 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 736.453, LX919, Murgo Access Road (Type 2, rubber, unsealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX919 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 736.34 | 736.54 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128232
WLD/N2NS/01087 | Jeramy Smith | 2021-07-02 02:02 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 733.944, LX918, Buckie Road (Type 4, rubber, sealed), RX-5 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX918 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 733.82 | 734.02 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128231
WLD/N2NS/01086 | Jeramy Smith | 2021-07-02 02:02 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 727.422, LX3162, Private (Type 1, 12.0m, rubber, unsealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX3162 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 727.43 | 727.63 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128230
WLD/N2NS/01085 | Jeramy Smith | 2021-07-02 02:01 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX917 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128229
WLD/N2NS/01084 | Jeramy Smith | 2021-07-02 01:59 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 721.145, LX3161, Private (Type 1, 4.5m, rubber, unsealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX3161 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 721.05 | 721.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128226
WLD/N2NS/01083 | Jeramy Smith | 2021-07-02 01:57 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 724.905, LX916, Crooble-Croopa Creek (Type 3, rubber, sealed at crossing), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX916 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 724.79 | 724.99 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128225
WLD/N2NS/01082 | Jeramy Smith | 2021-07-02 01:57 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - In BOQ... LX3160, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX3160 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 716.26 | 716.46 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128224
WLD/N2NS/01081 | Jeramy Smith | 2021-07-02 01:56 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 718.865, LX915, Crooble-Croopa Creek (Type 3, 7m, rubber, sealed at crossing), RX-5 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX915 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 718.74 | 718.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128223
WLD/N2NS/01080 | Jeramy Smith | 2021-07-02 01:55 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 717.020, LX913, Gil Gil Creek Road (Type 3, 7m, rubber, sealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX913 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 716.95 | 717.15 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128222
WLD/N2NS/01079 | Jeramy Smith | 2021-07-02 01:54 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 710.961, LX912, Alma Lane (Type 3, 7m, rubber, sealed at crossing), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX912 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 710.85 | 711.05 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128221
WLD/N2NS/01078 | Jeramy Smith | 2021-07-02 01:53 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX911 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 706.46 | 706.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128220
WLD/N2NS/01077 | Jeramy Smith | 2021-07-02 01:52 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 704.694, LX3156, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX3156 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 704.59 | 704.89 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128217
WLD/N2NS/01076 | Jeramy Smith | 2021-07-02 01:51 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 700.939, LX910, Calimpa-County Boundary Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX910 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 700.83 | 701.03 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128216
WLD/N2NS/01075 | Jeramy Smith | 2021-07-02 01:51 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 693.959, LX909, Private (Type 3, 4.5m, rubber, sealed at crossing), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX909 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 693.87 | 694.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128215
WLD/N2NS/01074 | Jeramy Smith | 2021-07-02 01:50 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 689.505, LX3153, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX3153 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 689.41 | 689.61 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128214
WLD/N2NS/01073 | Jeramy Smith | 2021-07-02 01:49 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 686.451, LX1842, Roydon Road (Type 2, 4.5m, rubber, unsealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX1842 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 686.38 | 686.58 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128212
WLD/N2NS/01072 | Jeramy Smith | 2021-07-02 01:48 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX1841 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 686.29 | 686.49 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128211
WLD/N2NS/01071 | Jeramy Smith | 2021-07-02 01:47 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 682.850, LX3151, Private (Type 1, 6m, steel, unsealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX3152 |  |  | 2021-07-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 684.72 | 684.92 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128210
WLD/N2NS/01070 | Jeramy Smith | 2021-07-02 01:45 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 750.098, LX3167, Private (Type 1, 6m, steel, unsealed), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX3167 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 750 | 750.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128209
WLD/N2NS/01069 | Jeramy Smith | 2021-07-02 01:44 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 756.426, LX3169, Private (Type 1, 6m, steel, unsealed), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX3169 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 756.31 | 756.51 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128208
WLD/N2NS/01068 | Jeramy Smith | 2021-07-02 01:44 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 758.252, LX923, NS Road (Type 4, rubber, sealed), RX-5 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX923 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 758.14 | 758.34 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128207
WLD/N2NS/01067 | Jeramy Smith | 2021-07-02 01:42 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 752.749, LX3168, Private (Type 1, 6m, steel, unsealed), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX3168 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 752.63 | 752.83 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128206
WLD/N2NS/01066 | Jeramy Smith | 2021-07-02 01:41 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 747.052, LX3166, Private (Type 1, 6m, rubber, unsealed), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX3166 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 746.96 | 747.16 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128205
WLD/N2NS/01065 | Jeramy Smith | 2021-07-02 01:40 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 749.254, LX4378, North Star Lxing (Type 1, 4.5m, rubber, unsealed), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX4378 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 749.15 | 749.35 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128204
WLD/N2NS/01064 | Jeramy Smith | 2021-07-02 01:39 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 744.977, LX3165, Private (Type 1, 6m, rubber, unsealed), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX3165 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 144.87 | 145.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128203
WLD/N2NS/01063 | Jeramy Smith | 2021-07-02 01:38 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 732.555, LX3164, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX3164 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 732.46 | 732.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128202
WLD/N2NS/01062 | Frank Paraha | 2021-07-02 01:33 | Stage 2 - Penneys Road to Moree | Culverts | 652.715, 1/1800x600, remove and rebuild | Culverts - Installation of Box Culverts | Concrete | Frank Paraha | 652.715 - Cast In Situ Base Slab | 2021-07-02 |  | 2021-08-08 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 |  |  |  | WLD/N2NS/00567, WLD/N2NS/00572, WLD/N2NS/01388, WLD/N2NS/01449 |  |  |  |  | MIX/N2NS/00007 | 652.72 | 652.72 | [6 empty] | HWP/N2NS/00241 | [6 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS01062LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128201 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/01061 | Richard Doering | 2021-07-02 01:09 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 2 of 3 - 300mm CH653.730 to CH654.550 | 2021-07-02 |  | 2021-07-03 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 653.73 | 654.55 | [13 empty] | James Martin |  | Test Request 0649 Panda Results.pdf, Test Request 0628 Panda Results.pdf, N-21-179-593.pdf, N-21-179-563.pdf, N-21-179-546.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128196 |  |  |  | 7632-2C41552
WLD/N2NS/01060 | Jeramy Smith | 2021-07-02 00:47 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 742.842, LX921, Tumba Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX921 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 742.74 | 742.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128191
WLD/N2NS/01059 | Jeramy Smith | 2021-07-02 00:46 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 739.332, LX920, Murgo Access Road (Type 2, rubber, sealed at crossing), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX920 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 739.22 | 739.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128189
WLD/N2NS/01058 | Jeramy Smith | 2021-07-02 00:45 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 736.453, LX919, Murgo Access Road (Type 2, rubber, unsealed), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX919 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 736.34 | 736.54 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128188
WLD/N2NS/01057 | Jeramy Smith | 2021-07-02 00:44 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 733.944, LX918, Buckie Road (Type 4, rubber, sealed), RX-5 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX918 |  |  | 2021-08-02 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 733.82 | 734.02 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128187
WLD/N2NS/01056 | Kallen Doong | 2021-06-30 06:54 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH633.270 to CH633.680 - Layer 2 - 400mm | 2021-07-05 |  | 2021-07-23 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 632.78 | 633.68 | [6 empty] | HWP/N2NS/00328 | [6 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR 630 Panda Results.pdf, TR 809 Panda Results.pdf, 7EE83AB1-5052-46BC-B062-42D563EEA7CA.JPG, N-21-179-845.pdf, N-21-179-850.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128056 |  |  |  | 7632-2C41552
WLD/N2NS/01055 | Richard Doering | 2021-06-30 04:34 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 2 of 3 - 300mm Layer CH654.550 to CH655.200 | 2021-06-30 |  | 2021-07-01 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 654.55 | 655.2 | [15 empty] | N-21-179-552.pdf, Test request 0615 Panda Results.pdf, N-21-179-528.pdf, Test Request 0615 Panda Results.pdf, N-21-179-595.pdf, Test Request 0643 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128048 |  |  |  | 7632-2C41552
WLD/N2NS/01054 | Jeramy Smith | 2021-06-30 03:10 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 727.422, LX3162, Private (Type 1, 12.0m, rubber, unsealed), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX3162 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 727.43 | 727.63 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128033
WLD/N2NS/01053 | Jeramy Smith | 2021-06-30 03:09 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX917 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128032
WLD/N2NS/01052 | Jeramy Smith | 2021-06-30 03:08 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 721.145, LX3161, Private (Type 1, 4.5m, rubber, unsealed), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX3161 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 721.05 | 721.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128031
WLD/N2NS/01051 | Jeramy Smith | 2021-06-30 03:06 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 724.905, LX916, Crooble-Croopa Creek (Type 3, rubber, sealed at crossing), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX916 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 724.79 | 724.99 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128029
WLD/N2NS/01050 | Jeramy Smith | 2021-06-30 03:05 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - In BOQ... LX3160, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX3160 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 716.26 | 716.46 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128028
WLD/N2NS/01049 | Jeramy Smith | 2021-06-30 03:05 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 718.865, LX915, Crooble-Croopa Creek (Type 3, 7m, rubber, sealed at crossing), RX-5 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX915 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 718.74 | 718.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128027
WLD/N2NS/01048 | Jeramy Smith | 2021-06-30 03:04 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 717.020, LX913, Gil Gil Creek Road (Type 3, 7m, rubber, sealed), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX913 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 716.95 | 717.15 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128026
WLD/N2NS/01047 | Jeramy Smith | 2021-06-30 03:03 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 710.961, LX912, Alma Lane (Type 3, 7m, rubber, sealed at crossing), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX912 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 710.85 | 711.05 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128025
WLD/N2NS/01046 | Jeramy Smith | 2021-06-30 01:49 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX911 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 706.46 | 706.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128018
WLD/N2NS/01045 | Jeramy Smith | 2021-06-30 01:48 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 704.694, LX3156, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX3156 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 704.59 | 704.79 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128017
WLD/N2NS/01044 | Jeramy Smith | 2021-06-30 01:46 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 700.939, LX910, Calimpa-County Boundary Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX910 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 700.83 | 701.03 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128016
WLD/N2NS/01043 | Jeramy Smith | 2021-06-30 01:45 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 693.959, LX909, Private (Type 3, 4.5m, rubber, sealed at crossing), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX909 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 693.87 | 694.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128015
WLD/N2NS/01042 | Jeramy Smith | 2021-06-30 01:44 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 689.505, LX3153, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX3153 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 689.41 | 689.61 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128014
WLD/N2NS/01041 | Jeramy Smith | 2021-06-30 01:43 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 686.451, LX1842, Roydon Road (Type 2, 4.5m, rubber, unsealed), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX1842 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 686.38 | 686.58 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128013
WLD/N2NS/01040 | Jeramy Smith | 2021-06-30 01:43 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX1841 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 686.29 | 686.49 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128012
WLD/N2NS/01039 | Jeramy Smith | 2021-06-30 01:42 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 684.899, LX3152, Private (Type 1, 6m, steel, unsealed), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX3152 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 684.72 | 684.92 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128011
WLD/N2NS/01038 | Jeramy Smith | 2021-06-30 01:22 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 758.252, LX923, NS Road (Type 4, rubber, sealed), RX-5 | Utilities - Conduit and Pit Installation | Roadworks | Jeramy Smith | Conduit and Pit Installation- LX923 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00021 | CHK/N2NS/00045 | [9 empty] | 758.14 | 758.34 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128010
WLD/N2NS/01037 | Jeramy Smith | 2021-06-30 01:21 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 755.578, LX922, NS - Croppa Ck Road (Type 4, rubber, sealed), RX-5 | Utilities - Conduit and Pit Installation | Roadworks | Jeramy Smith | Conduit and Pit Installation- LX922 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00021 | CHK/N2NS/00045 | [9 empty] | 755.47 | 755.67 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128009
WLD/N2NS/01036 | Jeramy Smith | 2021-06-30 01:20 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 733.944, LX918, Buckie Road (Type 4, rubber, sealed), RX-5 | Utilities - Conduit and Pit Installation | Roadworks | Jeramy Smith | Conduit and Pit Installation- LX918 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00021 | CHK/N2NS/00045 | [9 empty] | 733.82 | 734.02 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128008
WLD/N2NS/01035 | Jeramy Smith | 2021-06-30 01:19 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Utilities - Conduit and Pit Installation | Roadworks | Jeramy Smith | Conduit and Pit Installation- LX917 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00021 | CHK/N2NS/00045 | [9 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128007
WLD/N2NS/01034 | Jeramy Smith | 2021-06-30 01:19 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 718.865, LX915, Crooble-Croopa Creek (Type 3, 7m, rubber, sealed at crossing), RX-5 | Utilities - Conduit and Pit Installation | Roadworks | Jeramy Smith | Conduit and Pit Installation- LX915 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00021 | CHK/N2NS/00045 | [9 empty] | 718.74 | 718.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128006
WLD/N2NS/01033 | Jeramy Smith | 2021-06-30 01:18 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Utilities - Conduit and Pit Installation | Roadworks | Jeramy Smith | Conduit and Pit Installation- LX911 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00021 | CHK/N2NS/00045 | [9 empty] | 706.46 | 706.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128005
WLD/N2NS/01032 | Jeramy Smith | 2021-06-30 01:14 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 750.098, LX3167, Private (Type 1, 6m, steel, unsealed), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX3167 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 750 | 750.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128004
WLD/N2NS/01031 | Jeramy Smith | 2021-06-30 01:13 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 758.252, LX923, NS Road (Type 4, rubber, sealed), RX-5 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX923 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 758.14 | 758.34 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128002
WLD/N2NS/01030 | Jeramy Smith | 2021-06-30 01:12 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 752.749, LX3168, Private (Type 1, 6m, steel, unsealed), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX3168 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 752.63 | 752.83 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128001
WLD/N2NS/01029 | Jeramy Smith | 2021-06-30 01:11 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 755.578, LX922, NS - Croppa Ck Road (Type 4, rubber, sealed), RX-5 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX922 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 755.47 | 755.67 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/128000
WLD/N2NS/01028 | Jeramy Smith | 2021-06-30 01:10 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 747.052, LX3166, Private (Type 1, 6m, rubber, unsealed), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX3166 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 746.96 | 747.16 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127999
WLD/N2NS/01027 | Jeramy Smith | 2021-06-30 01:09 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 749.254, LX4378, North Star Lxing (Type 1, 4.5m, rubber, unsealed), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX4378 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 749.15 | 749.35 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127998
WLD/N2NS/01026 | Jeramy Smith | 2021-06-30 01:08 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 744.977, LX3165, Private (Type 1, 6m, rubber, unsealed), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX3165 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 744.87 | 745.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127997
WLD/N2NS/01025 | Jeramy Smith | 2021-06-30 01:07 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 732.555, LX3164, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX3164 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 732.46 | 732.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127996
WLD/N2NS/01024 | Jeramy Smith | 2021-06-30 01:06 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 742.842, LX921, Tumba Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX921 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 742.74 | 742.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127995
WLD/N2NS/01023 | Jeramy Smith | 2021-06-30 01:05 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 739.332, LX920, Murgo Access Road (Type 2, rubber, sealed at crossing), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX920 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 739.22 | 739.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127994
WLD/N2NS/01022 | Jeramy Smith | 2021-06-30 01:03 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 736.453, LX919, Murgo Access Road (Type 2, rubber, unsealed), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX919 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 736.34 | 736.54 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127993
WLD/N2NS/01021 | Jeramy Smith | 2021-06-30 01:02 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 733.944, LX918, Buckie Road (Type 4, rubber, sealed), RX-5 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX918 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 733.82 | 734.02 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127992
WLD/N2NS/01020 | Jeramy Smith | 2021-06-30 01:02 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX917 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127991
WLD/N2NS/01019 | Jeramy Smith | 2021-06-30 01:01 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 721.145, LX3161, Private (Type 1, 4.5m, rubber, unsealed), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX3161 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 721.05 | 721.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127990
WLD/N2NS/01018 | Jeramy Smith | 2021-06-30 01:00 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 724.905, LX916, Crooble-Croopa Creek (Type 3, rubber, sealed at crossing), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX916 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 724.79 | 724.99 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127989
WLD/N2NS/01017 | Jeramy Smith | 2021-06-30 01:00 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - In BOQ... LX3160, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX3160 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 716.26 | 716.46 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127988
WLD/N2NS/01016 | Jeramy Smith | 2021-06-30 00:58 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 717.020, LX913, Gil Gil Creek Road (Type 3, 7m, rubber, sealed), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX913 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 716.95 | 717.15 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127987
WLD/N2NS/01015 | Jeramy Smith | 2021-06-30 00:57 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 710.961, LX912, Alma Lane (Type 3, 7m, rubber, sealed at crossing), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX912 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 710.85 | 711.05 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127985
WLD/N2NS/01014 | Jeramy Smith | 2021-06-30 00:57 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX911 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 706.46 | 706.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127984
WLD/N2NS/01013 | Jeramy Smith | 2021-06-30 00:56 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 704.694, LX3156, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX3156 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 704.59 | 705.79 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127983
WLD/N2NS/01012 | Jeramy Smith | 2021-06-30 00:55 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 700.939, LX910, Calimpa-County Boundary Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX910 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 700.83 | 701.03 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127982
WLD/N2NS/01011 | Jeramy Smith | 2021-06-30 00:54 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 693.959, LX909, Private (Type 3, 4.5m, rubber, sealed at crossing), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX909 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 693.87 | 694.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127981
WLD/N2NS/01010 | Jeramy Smith | 2021-06-30 00:52 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 689.505, LX3153, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX3153 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 689.41 | 689.61 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127980
WLD/N2NS/01009 | Jeramy Smith | 2021-06-30 00:52 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 686.451, LX1842, Roydon Road (Type 2, 4.5m, rubber, unsealed), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX1842 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 686.38 | 686.58 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127979
WLD/N2NS/01008 | Jeramy Smith | 2021-06-30 00:51 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX1841 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 686.29 | 686.49 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127978
WLD/N2NS/01007 | Jeramy Smith | 2021-06-30 00:50 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 684.899, LX3152, Private (Type 1, 6m, steel, unsealed), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX3152 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 684.72 | 684.92 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127977
WLD/N2NS/01006 | Jeramy Smith | 2021-06-30 00:35 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 750.098, LX3167, Private (Type 1, 6m, steel, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX3167 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 750 | 750.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127975
WLD/N2NS/01005 | Jeramy Smith | 2021-06-30 00:34 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 758.252, LX923, NS Road (Type 4, rubber, sealed), RX-5 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX923 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 758.14 | 758.34 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127974
WLD/N2NS/01004 | Jeramy Smith | 2021-06-30 00:33 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 752.749, LX3168, Private (Type 1, 6m, steel, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX3168 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 752.63 | 752.83 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127973
WLD/N2NS/01003 | Jeramy Smith | 2021-06-30 00:32 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 755.578, LX922, NS - Croppa Ck Road (Type 4, rubber, sealed), RX-5 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX922 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 755.47 | 755.67 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127972
WLD/N2NS/01002 | Jeramy Smith | 2021-06-30 00:31 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 747.052, LX3166, Private (Type 1, 6m, rubber, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX3166 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 746.96 | 747.16 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127971
WLD/N2NS/01001 | Jeramy Smith | 2021-06-30 00:30 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 749.254, LX4378, North Star Lxing (Type 1, 4.5m, rubber, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX4378 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 749.15 | 749.35 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127970
WLD/N2NS/01000 | Jeramy Smith | 2021-06-30 00:29 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 744.977, LX3165, Private (Type 1, 6m, rubber, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX3165 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 744.87 | 745.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127969
WLD/N2NS/00999 | Jeramy Smith | 2021-06-30 00:28 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 732.555, LX3164, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX3164 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 732.46 | 732.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127968
WLD/N2NS/00998 | Jeramy Smith | 2021-06-30 00:27 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 742.842, LX921, Tumba Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX921 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 742.74 | 742.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127967
WLD/N2NS/00997 | Jeramy Smith | 2021-06-30 00:26 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 739.332, LX920, Murgo Access Road (Type 2, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX920 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 739.22 | 739.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127966
WLD/N2NS/00996 | Jeramy Smith | 2021-06-30 00:25 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 736.453, LX919, Murgo Access Road (Type 2, rubber, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX919 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 736.34 | 736.54 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127965
WLD/N2NS/00995 | Jeramy Smith | 2021-06-30 00:24 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 733.944, LX918, Buckie Road (Type 4, rubber, sealed), RX-5 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX918 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 733.82 | 734.02 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127964
WLD/N2NS/00994 | Jeramy Smith | 2021-06-30 00:23 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX917 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127963
WLD/N2NS/00993 | Jeramy Smith | 2021-06-30 00:22 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 721.145, LX3161, Private (Type 1, 4.5m, rubber, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX3161 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 721.05 | 721.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127962
WLD/N2NS/00992 | Jeramy Smith | 2021-06-30 00:22 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 724.905, LX916, Crooble-Croopa Creek (Type 3, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX916 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 724.79 | 724.99 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127960
WLD/N2NS/00991 | Jeramy Smith | 2021-06-30 00:21 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - In BOQ... LX3160, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX3160 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 716.26 | 716.46 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127959
WLD/N2NS/00990 | Jeramy Smith | 2021-06-30 00:20 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 717.020, LX913, Gil Gil Creek Road (Type 3, 7m, rubber, sealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX913 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 716.95 | 717.15 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127958
WLD/N2NS/00989 | Jeramy Smith | 2021-06-30 00:19 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 710.961, LX912, Alma Lane (Type 3, 7m, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX912 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 710.85 | 710.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127957
WLD/N2NS/00988 | Jeramy Smith | 2021-06-30 00:18 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX911 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 706.46 | 706.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127956
WLD/N2NS/00987 | Jeramy Smith | 2021-06-30 00:18 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 704.694, LX3156, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX3156 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 704.59 | 704.79 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127955
WLD/N2NS/00986 | Jeramy Smith | 2021-06-30 00:17 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 700.939, LX910, Calimpa-County Boundary Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX910 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 700.83 | 701.03 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127954
WLD/N2NS/00985 | Jeramy Smith | 2021-06-30 00:16 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 693.959, LX909, Private (Type 3, 4.5m, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX909 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 693.87 | 694.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127953
WLD/N2NS/00984 | Jeramy Smith | 2021-06-30 00:15 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 689.505, LX3153, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX3153 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 689.41 | 689.61 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127952
WLD/N2NS/00983 | Jeramy Smith | 2021-06-30 00:14 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 686.451, LX1842, Roydon Road (Type 2, 4.5m, rubber, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX1842 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 686.38 | 686.58 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127951
WLD/N2NS/00982 | Jeramy Smith | 2021-06-30 00:13 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX1841 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 686.29 | 686.49 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127950
WLD/N2NS/00981 | Jeramy Smith | 2021-06-30 00:12 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 684.899, LX3152, Private (Type 1, 6m, steel, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX3152 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 684.72 | 684.92 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127949
WLD/N2NS/00980 | Jeramy Smith | 2021-06-30 00:01 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 750.098, LX3167, Private (Type 1, 6m, steel, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX3167 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 749.1 | 750.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127948
WLD/N2NS/00979 | Jeramy Smith | 2021-06-29 23:59 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 758.252, LX923, NS Road (Type 4, rubber, sealed), RX-5 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX923 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 758.14 | 758.34 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127947
WLD/N2NS/00978 | Jeramy Smith | 2021-06-29 23:58 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 752.749, LX3168, Private (Type 1, 6m, steel, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX3168 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 752.63 | 752.83 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127946
WLD/N2NS/00977 | Jeramy Smith | 2021-06-29 23:57 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 755.578, LX922, NS - Croppa Ck Road (Type 4, rubber, sealed), RX-5 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX922 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 755.47 | 755.67 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127945
WLD/N2NS/00976 | Jeramy Smith | 2021-06-29 23:57 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 747.052, LX3166, Private (Type 1, 6m, rubber, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX3166 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 746.96 | 747.16 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127944
WLD/N2NS/00975 | Jeramy Smith | 2021-06-29 23:56 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 749.254, LX4378, North Star Lxing (Type 1, 4.5m, rubber, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX4378 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 749.15 | 749.35 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127943
WLD/N2NS/00974 | Jeramy Smith | 2021-06-29 23:55 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 744.977, LX3165, Private (Type 1, 6m, rubber, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX3165 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 744.87 | 745.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127942
WLD/N2NS/00973 | Jeramy Smith | 2021-06-29 23:54 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 732.555, LX3164, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX3164 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 732.46 | 732.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127941
WLD/N2NS/00972 | Jeramy Smith | 2021-06-29 23:53 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 742.842, LX921, Tumba Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX921 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 742.74 | 742.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127940
WLD/N2NS/00971 | Jeramy Smith | 2021-06-29 23:52 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 739.332, LX920, Murgo Access Road (Type 2, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX920 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 739.22 | 739.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127939
WLD/N2NS/00970 | Jeramy Smith | 2021-06-29 23:51 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 736.453, LX919, Murgo Access Road (Type 2, rubber, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX919 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 736.34 | 736.54 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127938
WLD/N2NS/00969 | Jeramy Smith | 2021-06-29 23:48 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 733.944, LX918, Buckie Road (Type 4, rubber, sealed), RX-5 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX918 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 733.82 | 734.02 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127937
WLD/N2NS/00968 | Jeramy Smith | 2021-06-29 23:47 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX917 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127936
WLD/N2NS/00967 | Jeramy Smith | 2021-06-29 23:45 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 721.145, LX3161, Private (Type 1, 4.5m, rubber, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX3161 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 721.05 | 721.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127935
WLD/N2NS/00966 | Jeramy Smith | 2021-06-29 23:44 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 724.905, LX916, Crooble-Croopa Creek (Type 3, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX916 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 724.79 | 724.99 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127934
WLD/N2NS/00965 | Jeramy Smith | 2021-06-29 23:43 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - In BOQ... LX3160, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX3160 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 716.26 | 716.46 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127933
WLD/N2NS/00964 | Jeramy Smith | 2021-06-29 23:42 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 717.020, LX913, Gil Gil Creek Road (Type 3, 7m, rubber, sealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX913 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 716.95 | 717.15 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127932
WLD/N2NS/00963 | Jeramy Smith | 2021-06-29 23:41 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 710.961, LX912, Alma Lane (Type 3, 7m, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX912 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 710.85 | 711.05 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127931
WLD/N2NS/00962 | Jeramy Smith | 2021-06-29 23:40 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 704.694, LX3156, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX3156 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 704.59 | 704.79 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127929
WLD/N2NS/00961 | Jeramy Smith | 2021-06-29 23:37 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX911 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 706.46 | 706.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127928
WLD/N2NS/00960 | Jeramy Smith | 2021-06-29 23:37 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 700.939, LX910, Calimpa-County Boundary Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX910 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 700.83 | 701.03 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127927
WLD/N2NS/00959 | Jeramy Smith | 2021-06-29 23:36 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 693.959, LX909, Private (Type 3, 4.5m, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX909 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 693.87 | 694.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127926
WLD/N2NS/00958 | Jeramy Smith | 2021-06-29 23:35 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 689.505, LX3153, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX3153 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 689.41 | 689.61 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127925
WLD/N2NS/00957 | Jeramy Smith | 2021-06-29 23:34 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX1841 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 686.38 | 686.58 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127924
WLD/N2NS/00956 | Jeramy Smith | 2021-06-29 23:33 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX1841 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 686.29 | 686.49 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127923
WLD/N2NS/00955 | Jeramy Smith | 2021-06-29 23:31 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 684.899, LX3152, Private (Type 1, 6m, steel, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX3152 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 684.72 | 684.92 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127922
WLD/N2NS/00954 | Jeramy Smith | 2021-06-29 23:21 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 750.098, LX3167, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX3167 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 749.1 | 750.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127921
WLD/N2NS/00953 | Jeramy Smith | 2021-06-29 23:20 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 756.426, LX3169, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX3169 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 756.31 | 756.51 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127920
WLD/N2NS/00952 | Jeramy Smith | 2021-06-29 23:18 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 758.252, LX923, NS Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX923 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 758.14 | 758.34 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127919
WLD/N2NS/00951 | Jeramy Smith | 2021-06-29 23:17 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 752.749, LX3168, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX3168 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 752.63 | 752.83 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127918
WLD/N2NS/00950 | Jeramy Smith | 2021-06-29 23:15 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 755.578, LX922, NS - Croppa Ck Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX922 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 755.47 | 755.67 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127917
WLD/N2NS/00949 | Jeramy Smith | 2021-06-29 23:13 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 747.052, LX3166, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX3166 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 746.96 | 747.16 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127916
WLD/N2NS/00948 | Jeramy Smith | 2021-06-29 23:13 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 749.254, LX4378, North Star Lxing (Type 1, 4.5m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX4378 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 749.15 | 749.35 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127915
WLD/N2NS/00947 | Jeramy Smith | 2021-06-29 23:11 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 744.977, LX3165, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX3165 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 744.87 | 745.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127914
WLD/N2NS/00946 | Jeramy Smith | 2021-06-29 23:10 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 732.555, LX3164, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX3164 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 732.46 | 732.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127913
WLD/N2NS/00945 | Jeramy Smith | 2021-06-29 23:09 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 742.842, LX921, Tumba Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX921 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 742.74 | 742.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127912
WLD/N2NS/00944 | Jeramy Smith | 2021-06-29 23:08 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 739.332, LX920, Murgo Access Road (Type 2, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX920 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 739.22 | 739.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127911
WLD/N2NS/00943 | Jeramy Smith | 2021-06-29 23:07 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 736.453, LX919, Murgo Access Road (Type 2, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX919 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 736.34 | 736.54 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127910
WLD/N2NS/00942 | Jeramy Smith | 2021-06-29 23:06 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 733.944, LX918, Buckie Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX918 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 733.82 | 734.02 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127909
WLD/N2NS/00941 | Jeramy Smith | 2021-06-29 23:03 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 727.422, LX3162, Private (Type 1, 12.0m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX3162 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 727.43 | 727.63 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127908
WLD/N2NS/00940 | Jeramy Smith | 2021-06-29 23:02 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX917 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127907
WLD/N2NS/00939 | Jeramy Smith | 2021-06-29 23:01 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 721.145, LX3161, Private (Type 1, 4.5m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX3161 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 721.05 | 721.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127906
WLD/N2NS/00938 | Jeramy Smith | 2021-06-29 23:00 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 724.905, LX916, Crooble-Croopa Creek (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX916 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 724.79 | 724.99 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127905
WLD/N2NS/00937 | Jeramy Smith | 2021-06-29 22:59 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - In BOQ... LX3160, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX3160 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 716.26 | 716.46 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127904
WLD/N2NS/00936 | Jeramy Smith | 2021-06-29 22:59 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 718.865, LX915, Crooble-Croopa Creek (Type 3, 7m, rubber, sealed at crossing), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX915 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 718.74 | 718.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127903
WLD/N2NS/00935 | Jeramy Smith | 2021-06-29 22:58 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 717.020, LX913, Gil Gil Creek Road (Type 3, 7m, rubber, sealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX913 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 716.95 | 717.15 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127902
WLD/N2NS/00934 | Jeramy Smith | 2021-06-29 22:57 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 710.961, LX912, Alma Lane (Type 3, 7m, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX912 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 710.85 | 711.05 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127901
WLD/N2NS/00933 | Jeramy Smith | 2021-06-29 22:56 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX911 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 706.46 | 706.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127900
WLD/N2NS/00932 | Jeramy Smith | 2021-06-29 22:55 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 704.694, LX3156, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX3156 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 704.59 | 704.79 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127899
WLD/N2NS/00931 | Jeramy Smith | 2021-06-29 22:54 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 700.939, LX910, Calimpa-County Boundary Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX910 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 700.83 | 701.03 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127898
WLD/N2NS/00930 | Jeramy Smith | 2021-06-29 22:54 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 693.959, LX909, Private (Type 3, 4.5m, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX909 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 693.87 | 694.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127897
WLD/N2NS/00929 | Jeramy Smith | 2021-06-29 22:53 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 689.505, LX3153, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX3153 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 689.41 | 689.61 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127896
WLD/N2NS/00928 | Jeramy Smith | 2021-06-29 22:52 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 686.451, LX1842, Roydon Road (Type 2, 4.5m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX1842 |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 686.38 | 686.58 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127895
WLD/N2NS/00927 | Jeramy Smith | 2021-06-29 22:51 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX1841 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 686.29 | 686.49 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127894
WLD/N2NS/00926 | Jeramy Smith | 2021-06-29 22:50 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 684.899, LX3152, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX3152 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 684.72 | 684.92 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127893
WLD/N2NS/00925 | Ahmad Alwan | 2021-06-29 07:25 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Ancillary Works | Roadworks | Aziz Kamaoui | Cast In-Situ Base Slabs, End Structures and Cut Off Walls - LX1828 DDR2 | 2021-06-29 |  | 2021-07-01 10:00 | Benjamin Philip | 2021-08-17 | 2021-08-17 01:25 | Closed | AMS/N2NS/00004 | ITP/N2NS/00016 |  |  |  |  | WLD/N2NS/00415 | [5 empty] | 627.75 | 627.95 | Benjamin Philip | 2021-08-17 01:25 |  |  |  |  | HWP/N2NS/00224 | Lot closed |  | 2021-08-17 01:25 | [5 empty] | IMG_8077.JPG, IMG_8078.JPG, WLDN2NS00925.pdf, WLDN2NS00925-LC.pdf, N-12-179-556.pdf, N-21-179-556.pdf, N-21-179-280.pdf, Concrete Pour Record.pdf, Precast Concrete Headwall.pdf, Lot Map.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127874 | [5 empty] | 2021-08-17 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00924 | Kallen Doong | 2021-06-29 07:15 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH632085 to CH632780 - Layer 2 - 400mm | 2021-06-30 |  | 2021-07-22 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 632.09 | 632.78 | [6 empty] | HWP/N2NS/00430 | [6 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | A318018D-D4CA-4833-A4B8-4E72A6BB7089.JPG, 950D81A3-77C1-4CC3-84BF-597B3C513072.JPG, N-21-179-493.pdf, N-21-179-566.pdf, Test Request 0605 Panda Results.pdf, N-21-179-770.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127869 |  |  |  | 7632-2C41552
WLD/N2NS/00923 | Nabin Koirala | 2021-06-29 07:04 | Stage 2 - Penneys Road to Moree | Culverts | 638.920, 14/1800x600, new build | Culverts - Other | Other | Keegan Baker | 638.920 - Cast-In-situ Cut-off Walls | 2021-07-01 |  | 2021-08-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [9 empty] | 638.92 | 638.92 | [6 empty] | HWP/N2NS/00225 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127863
WLD/N2NS/00922 | Nabin Koirala | 2021-06-29 07:01 | Stage 2 - Penneys Road to Moree | Culverts | 637.290, 1/1800x900, remove and rebuild | Drainage - Other | Concrete | Keegan Baker | Cast In situ Cut- off wall | 2021-07-24 |  | 2021-12-01 11:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 637.29 | 637.29 | [6 empty] | HWP/N2NS/00226 | [6 empty] | Emma Conroy, Keegan Baker, Maddie Dahlstrom |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127862
WLD/N2NS/00921 | Richard Doering | 2021-06-29 06:57 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 1 CH657.240 to CH657.740 | 2021-06-29 |  | 2021-06-30 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 657.24 | 657.74 | [15 empty] | Test Request 0632 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127859 |  |  |  | 7632-2C41552
WLD/N2NS/00920 | Hayden Murphy | 2021-06-29 06:45 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Ahmad Alwan | LX1828 -DDR1 Headwalls Installation (single DN525) | 2021-06-29 |  | 2021-07-08 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00038, CHK/N2NS/00040, CHK/N2NS/00042 | [9 empty] | 627.75 | 627.95 | [6 empty] | HWP/N2NS/00224 | [6 empty] | Ahmad Alwan, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127853
WLD/N2NS/00919 | Hayden Murphy | 2021-06-29 06:44 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Ahmad Alwan | LX1828 -DDR2 Headwalls Installation (single DN600) | 2021-06-29 |  | 2021-06-07 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00038, CHK/N2NS/00040, CHK/N2NS/00042 | [9 empty] | 627.75 | 627.95 | [6 empty] | HWP/N2NS/00224 | [6 empty] | Ahmad Alwan, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127852
WLD/N2NS/00918 | Jeramy Smith | 2021-06-29 06:27 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 750.098, LX3167, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX3167 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 750.1 | 750.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127848
WLD/N2NS/00917 | Jeramy Smith | 2021-06-29 06:26 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 756.426, LX3169, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX3169 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 756.31 | 756.51 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127847
WLD/N2NS/00916 | Jeramy Smith | 2021-06-29 06:25 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 758.252, LX923, NS Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX923 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 758.14 | 758.34 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127844
WLD/N2NS/00915 | Jeramy Smith | 2021-06-29 06:24 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 752.749, LX3168, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX3168 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 752.83 | 752.83 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127843
WLD/N2NS/00914 | Jeramy Smith | 2021-06-29 06:24 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 755.578, LX922, NS - Croppa Ck Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX922 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 755.47 | 755.67 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127842
WLD/N2NS/00913 | Jeramy Smith | 2021-06-29 06:23 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 747.052, LX3166, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX3166 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 746.96 | 747.16 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127841
WLD/N2NS/00912 | Jeramy Smith | 2021-06-29 06:22 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 749.254, LX4378, North Star Lxing (Type 1, 4.5m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX4378 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 749.15 | 749.35 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127840
WLD/N2NS/00911 | Jeramy Smith | 2021-06-29 06:21 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 744.977, LX3165, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX3165 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 744.87 | 745.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127839
WLD/N2NS/00910 | Jeramy Smith | 2021-06-29 06:20 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 732.555, LX3164, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX3164 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 732.46 | 732.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127837
WLD/N2NS/00909 | Jeramy Smith | 2021-06-29 06:19 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 742.842, LX921, Tumba Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX921 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 742.74 | 742.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127836
WLD/N2NS/00908 | Jeramy Smith | 2021-06-29 06:19 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 739.332, LX920, Murgo Access Road (Type 2, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX920 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 739.22 | 739.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127835
WLD/N2NS/00907 | Jeramy Smith | 2021-06-29 06:18 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 736.453, LX919, Murgo Access Road (Type 2, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX919 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 736.34 | 736.54 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127834
WLD/N2NS/00906 | Jeramy Smith | 2021-06-29 06:17 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 733.944, LX918, Buckie Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX918 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 733.82 | 734.02 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127833
WLD/N2NS/00905 | Jeramy Smith | 2021-06-29 06:16 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 727.422, LX3162, Private (Type 1, 12.0m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX3162 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 727.43 | 727.63 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127832
WLD/N2NS/00904 | Jeramy Smith | 2021-06-29 06:15 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX917 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127831
WLD/N2NS/00903 | Jeramy Smith | 2021-06-29 06:14 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 721.145, LX3161, Private (Type 1, 4.5m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX3161 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 720.95 | 721.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127830
WLD/N2NS/00902 | Jeramy Smith | 2021-06-29 05:49 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 724.905, LX916, Crooble-Croopa Creek (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX916 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 724.79 | 725.09 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127829
WLD/N2NS/00901 | Jeramy Smith | 2021-06-29 05:48 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - In BOQ... LX3160, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX3160 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 716.26 | 716.46 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127828
WLD/N2NS/00900 | Jeramy Smith | 2021-06-29 05:47 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 718.865, LX915, Crooble-Croopa Creek (Type 3, 7m, rubber, sealed at crossing), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX915 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 718.74 | 718.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127827
WLD/N2NS/00899 | Jeramy Smith | 2021-06-29 05:46 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 717.020, LX913, Gil Gil Creek Road (Type 3, 7m, rubber, sealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX913 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 716.95 | 717.15 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127826
WLD/N2NS/00898 | Jeramy Smith | 2021-06-29 05:44 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX912 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 710.85 | 711.05 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127825
WLD/N2NS/00897 | Jeramy Smith | 2021-06-29 05:43 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX911 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 706.46 | 706.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127824
WLD/N2NS/00896 | Jeramy Smith | 2021-06-29 05:42 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 704.694, LX3156, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX3156 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 704.59 | 704.79 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127823
WLD/N2NS/00895 | Jeramy Smith | 2021-06-29 05:42 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 700.939, LX910, Calimpa-County Boundary Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX910 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 700.83 | 701.03 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127822
WLD/N2NS/00894 | Jeramy Smith | 2021-06-29 05:41 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 693.959, LX909, Private (Type 3, 4.5m, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX909 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 693.87 | 694.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127821
WLD/N2NS/00893 | Jeramy Smith | 2021-06-29 05:40 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 689.505, LX3153, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX3153 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 689.41 | 689.61 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127819
WLD/N2NS/00892 | Jeramy Smith | 2021-06-29 05:39 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 686.451, LX1842, Roydon Road (Type 2, 4.5m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX1842 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 686.38 | 686.58 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127818
WLD/N2NS/00891 | Jeramy Smith | 2021-06-29 05:38 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX1841 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 686.29 | 686.49 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127817
WLD/N2NS/00890 | Jeramy Smith | 2021-06-29 05:37 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 684.899, LX3152, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX3152 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 684.72 | 684.92 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127816
WLD/N2NS/00889 | Jeramy Smith | 2021-06-29 04:36 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Ancillary Works | Roadworks | Aziz Kamaoui | Cast In-Situ Base Slabs, End Structures and Cut Off Walls - LX555 DDR1 | 2021-07-12 |  | 2021-07-29 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 636.2 | 636.4 | [6 empty] | HWP/N2NS/00246 | [8 empty] | WLDN2NS00889-Checklist.pdf, WLDN2NS00889.pdf, Survey Report.pdf, Concrete Pour Record.pdf, Precast Concrete Headwall.pdf, N-21-179-609.pdf, Lot Map.pdf, 555DDR1_1.JPG, 555DDR1_2.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127812
WLD/N2NS/00888 | Jeramy Smith | 2021-06-29 04:35 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Ancillary Works | Roadworks | Aziz Kamaoui | Cast In-Situ Base Slabs, End Structures and Cut Off Walls - LX3066 | 2021-07-06 |  | 2021-07-29 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | [10 empty] | 634.39 | 634.59 | [6 empty] | HWP/N2NS/00305 | [9 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127811
WLD/N2NS/00887 | Jeramy Smith | 2021-06-29 04:34 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Ahmad Alwan | Cast In-Situ Base Slabs, End Structures and Cut Off Walls - LX553 | 2021-07-06 |  | 2021-07-29 10:00 | Benjamin Philip | 2021-08-18 | 2021-08-18 01:11 | Closed | AMS/N2NS/00004 | ITP/N2NS/00016 | [10 empty] | 631.05 | 631.25 | Benjamin Philip | 2021-08-18 01:11 |  |  |  |  | HWP/N2NS/00449 | Lot closed |  | 2021-08-18 01:11 | [5 empty] | IMG_8080.JPG, IMG_8082.JPG, WLDN2NS00887.pdf, WLDN2NS00887- Checklist.pdf, Survey Report.pdf, Precast Concrete Headwall.pdf, N-21-179-644.pdf, Concrete Pour Record.pdf, Lot Map.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127810 | [5 empty] | 2021-08-18 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00886 | Jeramy Smith | 2021-06-29 04:34 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Ancillary Works | Roadworks | Ahmad Alwan | Cast In-Situ Base Slabs, End Structures and Cut Off Walls - LX1828 DDR1 |  |  | 2021-07-29 10:00 | Benjamin Philip | 2021-08-17 | 2021-08-17 01:31 | Closed | AMS/N2NS/00004 | ITP/N2NS/00016 |  |  |  |  | WLD/N2NS/00058 | [5 empty] | 627.75 | 627.95 | Benjamin Philip | 2021-08-17 01:31 |  |  |  |  | HWP/N2NS/00224 | Lot closed |  | 2021-08-17 01:31 | [5 empty] | IMG_8080.JPG, IMG_8079.JPG, WLDN2NS00886- Checklist.pdf, WLDN2NS00886.pdf, N-21-179-556.pdf, N-21-179-271.pdf, Concrete Pour Record.pdf, Precast Concrete Headwall.pdf, Lot Map.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127809 | [5 empty] | 2021-08-17 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00885 | Jeramy Smith | 2021-06-29 04:30 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 750.098, LX3167, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX3167 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 749.95 | 750.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127808
WLD/N2NS/00884 | Jeramy Smith | 2021-06-29 04:29 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 756.426, LX3169, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX3169 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 756.31 | 756.51 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127807
WLD/N2NS/00883 | Jeramy Smith | 2021-06-29 04:28 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 758.252, LX923, NS Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX923 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 758.14 | 758.34 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127806
WLD/N2NS/00882 | Jeramy Smith | 2021-06-29 04:27 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 752.749, LX3168, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX3168 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 752.63 | 752.83 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127805
WLD/N2NS/00881 | Jeramy Smith | 2021-06-29 04:26 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 755.578, LX922, NS - Croppa Ck Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX922 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 755.47 | 755.67 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127804
WLD/N2NS/00880 | Jeramy Smith | 2021-06-29 04:25 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 747.052, LX3166, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX3166 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 746.96 | 747.16 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127802
WLD/N2NS/00879 | Jeramy Smith | 2021-06-29 04:24 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 749.254, LX4378, North Star Lxing (Type 1, 4.5m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX4378 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 749.15 | 749.35 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127801
WLD/N2NS/00878 | Jeramy Smith | 2021-06-29 04:22 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 744.977, LX3165, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX3165 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 744.87 | 745.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127800
WLD/N2NS/00877 | Jeramy Smith | 2021-06-29 04:22 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 732.555, LX3164, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX3164 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 732.46 | 732.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127799
WLD/N2NS/00876 | Jeramy Smith | 2021-06-29 04:20 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 739.332, LX920, Murgo Access Road (Type 2, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX921 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 742.74 | 742.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127798
WLD/N2NS/00875 | Jeramy Smith | 2021-06-29 04:19 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 739.332, LX920, Murgo Access Road (Type 2, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX920 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 739.22 | 739.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127797
WLD/N2NS/00874 | Jeramy Smith | 2021-06-29 04:17 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 736.453, LX919, Murgo Access Road (Type 2, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX919 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 736.34 | 736.54 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127796
WLD/N2NS/00873 | Jeramy Smith | 2021-06-29 04:16 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 733.944, LX918, Buckie Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX918 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 733.82 | 734.02 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127795
WLD/N2NS/00872 | Jeramy Smith | 2021-06-29 04:13 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 727.422, LX3162, Private (Type 1, 12.0m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX3162 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 727.43 | 727.63 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127794
WLD/N2NS/00871 | Jeramy Smith | 2021-06-29 04:12 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX917 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127793
WLD/N2NS/00870 | Jeramy Smith | 2021-06-29 04:11 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 721.145, LX3161, Private (Type 1, 4.5m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX3161 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 721.05 | 721.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127792
WLD/N2NS/00869 | Jeramy Smith | 2021-06-29 04:10 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 724.905, LX916, Crooble-Croopa Creek (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX916 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 724.79 | 724.99 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127791
WLD/N2NS/00868 | Jeramy Smith | 2021-06-29 04:09 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - In BOQ... LX3160, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX3160 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 716.26 | 716.46 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127790
WLD/N2NS/00867 | Jeramy Smith | 2021-06-29 04:08 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 718.865, LX915, Crooble-Croopa Creek (Type 3, 7m, rubber, sealed at crossing), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX915 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 718.74 | 718.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127788
WLD/N2NS/00866 | Jeramy Smith | 2021-06-29 04:07 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 717.020, LX913, Gil Gil Creek Road (Type 3, 7m, rubber, sealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX913 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 716.95 | 717.15 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127787
WLD/N2NS/00865 | Jeramy Smith | 2021-06-29 04:05 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX912 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 710.85 | 711.05 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127786
WLD/N2NS/00864 | Jeramy Smith | 2021-06-29 04:05 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX911 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 706.46 | 706.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127785
WLD/N2NS/00863 | Jeramy Smith | 2021-06-29 04:03 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 704.694, LX3156, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX3156 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 704.59 | 704.79 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127784
WLD/N2NS/00862 | Jeramy Smith | 2021-06-29 04:02 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 700.939, LX910, Calimpa-County Boundary Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX910 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 700.83 | 701.03 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127782
WLD/N2NS/00861 | Jeramy Smith | 2021-06-29 04:01 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 693.959, LX909, Private (Type 3, 4.5m, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX909 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 693.87 | 694.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127781
WLD/N2NS/00860 | Jeramy Smith | 2021-06-29 04:00 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 689.505, LX3153, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX3153 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 689.41 | 689.61 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127780
WLD/N2NS/00859 | Jeramy Smith | 2021-06-29 03:59 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 686.451, LX1842, Roydon Road (Type 2, 4.5m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX1842 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 686.38 | 686.58 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127779
WLD/N2NS/00858 | Jeramy Smith | 2021-06-29 03:58 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX1841 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 686.29 | 686.49 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127778
WLD/N2NS/00857 | Jeramy Smith | 2021-06-29 03:56 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 750.098, LX3167, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX3167 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 749.95 | 750.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127777
WLD/N2NS/00856 | Jeramy Smith | 2021-06-29 03:54 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 756.426, LX3169, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX3169 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 756.31 | 756.51 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127776
WLD/N2NS/00855 | Jeramy Smith | 2021-06-29 03:53 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 752.749, LX3168, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX3168 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 752.63 | 752.83 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127775
WLD/N2NS/00854 | Jeramy Smith | 2021-06-29 03:52 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 755.578, LX922, NS - Croppa Ck Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX922 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 755.47 | 755.67 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127774
WLD/N2NS/00853 | Jeramy Smith | 2021-06-29 03:51 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 747.052, LX3166, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX3166 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 746.96 | 747.16 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127773
WLD/N2NS/00852 | Jeramy Smith | 2021-06-29 03:49 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 749.254, LX4378, North Star Lxing (Type 1, 4.5m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX4378 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 749.15 | 749.35 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127772
WLD/N2NS/00851 | Jeramy Smith | 2021-06-29 03:48 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 744.977, LX3165, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX3165 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 744.87 | 745.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127770
WLD/N2NS/00850 | Jeramy Smith | 2021-06-29 03:47 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 732.555, LX3164, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX3164 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 732.46 | 732.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127769
WLD/N2NS/00849 | Jeramy Smith | 2021-06-29 03:46 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 742.842, LX921, Tumba Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX921 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 742.74 | 742.93 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127768
WLD/N2NS/00848 | Jeramy Smith | 2021-06-29 03:45 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 739.332, LX920, Murgo Access Road (Type 2, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX920 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 739.22 | 739.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127767
WLD/N2NS/00847 | Jeramy Smith | 2021-06-29 03:44 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 736.453, LX919, Murgo Access Road (Type 2, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX919 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 736.34 | 736.55 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127766
WLD/N2NS/00846 | Jeramy Smith | 2021-06-29 03:43 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 733.944, LX918, Buckie Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX918 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 733.82 | 734.02 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127765
WLD/N2NS/00845 | Jeramy Smith | 2021-06-29 03:42 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 727.422, LX3162, Private (Type 1, 12.0m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX3162 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 727.43 | 727.63 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127764
WLD/N2NS/00844 | Jeramy Smith | 2021-06-29 03:42 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX917 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127763
WLD/N2NS/00843 | Jeramy Smith | 2021-06-29 03:41 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 721.145, LX3161, Private (Type 1, 4.5m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX3161 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 721.05 | 721.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127762
WLD/N2NS/00842 | Jeramy Smith | 2021-06-29 03:40 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - In BOQ... LX3160, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX916 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 724.79 | 724.99 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127761
WLD/N2NS/00841 | Jeramy Smith | 2021-06-29 03:39 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - In BOQ... LX3160, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX3160 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 716.26 | 716.46 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127760
WLD/N2NS/00840 | Jeramy Smith | 2021-06-29 03:38 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 718.865, LX915, Crooble-Croopa Creek (Type 3, 7m, rubber, sealed at crossing), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX915 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 718.74 | 718.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127759
WLD/N2NS/00839 | Jeramy Smith | 2021-06-29 03:37 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 717.020, LX913, Gil Gil Creek Road (Type 3, 7m, rubber, sealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX913 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 716.95 | 717.15 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127758
WLD/N2NS/00838 | Jeramy Smith | 2021-06-29 03:35 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 710.961, LX912, Alma Lane (Type 3, 7m, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX912 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 710.85 | 711.05 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127757
WLD/N2NS/00837 | Jeramy Smith | 2021-06-29 03:34 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX911 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 706.46 | 704.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127756
WLD/N2NS/00836 | Jeramy Smith | 2021-06-29 03:33 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 704.694, LX3156, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX3156 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 704.59 | 704.79 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127755
WLD/N2NS/00835 | Jeramy Smith | 2021-06-29 03:32 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 700.939, LX910, Calimpa-County Boundary Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX910 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 700.83 | 701.03 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127754
WLD/N2NS/00834 | Jeramy Smith | 2021-06-29 03:31 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 693.959, LX909, Private (Type 3, 4.5m, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX909 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 693.87 | 694.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127753
WLD/N2NS/00833 | Jeramy Smith | 2021-06-29 03:29 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 689.505, LX3153, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX3153 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 689.41 | 689.61 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127752
WLD/N2NS/00832 | Jeramy Smith | 2021-06-29 03:29 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 686.451, LX1842, Roydon Road (Type 2, 4.5m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX1842 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 686.38 | 686.58 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127751
WLD/N2NS/00831 | Jeramy Smith | 2021-06-29 03:28 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX1841 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 686.29 | 686.49 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127750
WLD/N2NS/00830 | Jeramy Smith | 2021-06-29 03:27 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 684.899, LX3152, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX3152 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 684.72 | 684.92 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127749
WLD/N2NS/00829 | Jeramy Smith | 2021-06-29 03:24 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 750.098, LX3167, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX3167 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 749.95 | 750.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127748
WLD/N2NS/00828 | Jeramy Smith | 2021-06-29 03:23 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 756.426, LX3169, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX3169 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 756.31 | 756.51 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127747
WLD/N2NS/00827 | Jeramy Smith | 2021-06-29 03:22 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 758.252, LX923, NS Road (Type 4, rubber, sealed), RX-5 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX923 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 758.14 | 758.34 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127746
WLD/N2NS/00826 | Jeramy Smith | 2021-06-29 03:21 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 752.749, LX3168, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX3168 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 752.63 | 752.83 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127745
WLD/N2NS/00825 | Jeramy Smith | 2021-06-29 03:20 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 755.578, LX922, NS - Croppa Ck Road (Type 4, rubber, sealed), RX-5 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX922 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 755.47 | 755.67 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127744
WLD/N2NS/00824 | Jeramy Smith | 2021-06-29 03:19 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 747.052, LX3166, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX3166 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 748.96 | 745.16 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127743
WLD/N2NS/00823 | Jeramy Smith | 2021-06-29 03:18 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 749.254, LX4378, North Star Lxing (Type 1, 4.5m, rubber, unsealed), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX4378 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 749.15 | 749.35 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127742
WLD/N2NS/00822 | Jeramy Smith | 2021-06-29 03:17 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 744.977, LX3165, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX3165 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 744.87 | 745.06 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127741
WLD/N2NS/00821 | Jeramy Smith | 2021-06-29 03:17 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 732.555, LX3164, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX3164 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 732.46 | 732.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127740
WLD/N2NS/00820 | Jeramy Smith | 2021-06-29 03:14 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 742.842, LX921, Tumba Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX921 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 742.74 | 742.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127739
WLD/N2NS/00819 | Jeramy Smith | 2021-06-29 03:14 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 739.332, LX920, Murgo Access Road (Type 2, rubber, sealed at crossing), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX920 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 739.22 | 739.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127738
WLD/N2NS/00818 | Jeramy Smith | 2021-06-29 03:13 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 736.453, LX919, Murgo Access Road (Type 2, rubber, unsealed), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX919 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 736.34 | 736.54 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127737
WLD/N2NS/00817 | Jeramy Smith | 2021-06-29 03:12 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 733.944, LX918, Buckie Road (Type 4, rubber, sealed), RX-5 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX918 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 733.82 | 734.02 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127736
WLD/N2NS/00816 | Jeramy Smith | 2021-06-29 03:11 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 727.422, LX3162, Private (Type 1, 12.0m, rubber, unsealed), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX3162 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 727.43 | 727.63 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127735
WLD/N2NS/00815 | Jeramy Smith | 2021-06-29 03:10 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX917 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127734
WLD/N2NS/00814 | Jeramy Smith | 2021-06-29 03:10 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX917 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127733
WLD/N2NS/00813 | Jeramy Smith | 2021-06-29 03:09 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 721.145, LX3161, Private (Type 1, 4.5m, rubber, unsealed), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX3161 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 721.05 | 721.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127732
WLD/N2NS/00812 | Jeramy Smith | 2021-06-29 03:08 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 724.905, LX916, Crooble-Croopa Creek (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX916 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 724.79 | 724.99 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127731
WLD/N2NS/00811 | Jeramy Smith | 2021-06-29 03:08 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - In BOQ... LX3160, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX3160 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 716.26 | 716.46 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127730
WLD/N2NS/00810 | Jeramy Smith | 2021-06-29 03:07 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 718.865, LX915, Crooble-Croopa Creek (Type 3, 7m, rubber, sealed at crossing), RX-5 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX915 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 718.74 | 718.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127729
WLD/N2NS/00809 | Jeramy Smith | 2021-06-29 03:06 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 717.020, LX913, Gil Gil Creek Road (Type 3, 7m, rubber, sealed), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX913 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 717.05 | 717.15 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127728
WLD/N2NS/00808 | Jeramy Smith | 2021-06-29 03:05 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 710.961, LX912, Alma Lane (Type 3, 7m, rubber, sealed at crossing), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX912 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 710.85 | 711.05 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127727
WLD/N2NS/00807 | Jeramy Smith | 2021-06-29 03:05 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX911 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 706.46 | 706.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127726
WLD/N2NS/00806 | Jeramy Smith | 2021-06-29 03:04 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 704.694, LX3156, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX3156 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 704.59 | 704.79 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127725
WLD/N2NS/00805 | Jeramy Smith | 2021-06-29 01:56 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 700.939, LX910, Calimpa-County Boundary Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX910 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 700.83 | 701.03 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127721
WLD/N2NS/00804 | Jeramy Smith | 2021-06-29 01:55 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 693.959, LX909, Private (Type 3, 4.5m, rubber, sealed at crossing), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX909 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 693.87 | 694.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127720
WLD/N2NS/00803 | Jeramy Smith | 2021-06-29 01:55 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 689.505, LX3153, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX3153 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 689.41 | 689.61 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127719
WLD/N2NS/00802 | Jeramy Smith | 2021-06-29 01:54 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 686.451, LX1842, Roydon Road (Type 2, 4.5m, rubber, unsealed), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX1842 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 686.38 | 686.58 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127718
WLD/N2NS/00801 | Jeramy Smith | 2021-06-29 01:53 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX1841 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 686.29 | 686.49 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127717
WLD/N2NS/00800 | Jeramy Smith | 2021-06-29 01:52 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 684.899, LX3152, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX3152 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 684.72 | 684.92 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127716
WLD/N2NS/00799 | Jeramy Smith | 2021-06-29 01:47 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 750.098, LX3167, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX3167 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 750.1 | 750.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127715
WLD/N2NS/00798 | Jeramy Smith | 2021-06-29 01:46 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 756.426, LX3169, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX3169 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 756.31 | 756.51 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127714
WLD/N2NS/00797 | Jeramy Smith | 2021-06-29 01:45 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 758.252, LX923, NS Road (Type 4, rubber, sealed), RX-5 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX923 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 758.14 | 758.34 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127713
WLD/N2NS/00796 | Jeramy Smith | 2021-06-29 01:45 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 752.749, LX3168, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX3168 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 752.63 | 752.83 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127711
WLD/N2NS/00795 | Jeramy Smith | 2021-06-29 01:44 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 755.578, LX922, NS - Croppa Ck Road (Type 4, rubber, sealed), RX-5 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX922 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 755.47 | 755.67 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127710
WLD/N2NS/00794 | Jeramy Smith | 2021-06-29 01:43 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 747.052, LX3166, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX3166 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 746.96 | 747.16 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127708
WLD/N2NS/00793 | Jeramy Smith | 2021-06-29 01:42 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 749.254, LX4378, North Star Lxing (Type 1, 4.5m, rubber, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX4378 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 749.15 | 749.35 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127707
WLD/N2NS/00792 | Jeramy Smith | 2021-06-29 01:41 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 744.977, LX3165, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX3165 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 744.86 | 745.06 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127706
WLD/N2NS/00791 | Jeramy Smith | 2021-06-29 01:40 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 732.555, LX3164, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX3164 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 735.46 | 732.66 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127705
WLD/N2NS/00790 | Jeramy Smith | 2021-06-29 01:39 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 742.842, LX921, Tumba Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX921 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 742.74 | 742.93 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127704
WLD/N2NS/00789 | Jeramy Smith | 2021-06-29 01:39 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 739.332, LX920, Murgo Access Road (Type 2, rubber, sealed at crossing), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX920 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 739.22 | 739.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127703
WLD/N2NS/00788 | Jeramy Smith | 2021-06-29 01:38 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 736.453, LX919, Murgo Access Road (Type 2, rubber, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Hayden Murphy | Clearing and Grubbing- LX919 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 736.24 | 736.44 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127702
WLD/N2NS/00787 | Jeramy Smith | 2021-06-29 01:37 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 733.944, LX918, Buckie Road (Type 4, rubber, sealed), RX-5 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX918 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 733.82 | 734.02 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127701
WLD/N2NS/00786 | Jeramy Smith | 2021-06-29 01:36 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 727.422, LX3162, Private (Type 1, 12.0m, rubber, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX3162 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 727.43 | 727.63 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127700
WLD/N2NS/00785 | Jeramy Smith | 2021-06-29 01:36 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 730.335, LX917, Myall Downs Road (Type 4, rubber, sealed), RX-5 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX917 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 730.22 | 730.42 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127698
WLD/N2NS/00784 | Jeramy Smith | 2021-06-29 01:35 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 721.145, LX3161, Private (Type 1, 4.5m, rubber, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX3161 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 721.05 | 721.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127697
WLD/N2NS/00783 | Jeramy Smith | 2021-06-29 01:34 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 724.905, LX916, Crooble-Croopa Creek (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX916 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 724.79 | 725.09 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127696
WLD/N2NS/00782 | Jeramy Smith | 2021-06-29 01:33 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - In BOQ... LX3160, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX3160 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 716.26 | 716.46 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127695
WLD/N2NS/00781 | Jeramy Smith | 2021-06-29 01:32 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 718.865, LX915, Crooble-Croopa Creek (Type 3, 7m, rubber, sealed at crossing), RX-5 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX915 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 718.74 | 718.94 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127694
WLD/N2NS/00780 | Jeramy Smith | 2021-06-29 01:32 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 717.020, LX913, Gil Gil Creek Road (Type 3, 7m, rubber, sealed), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX913 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 717.05 | 717.15 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127693
WLD/N2NS/00779 | Jeramy Smith | 2021-06-29 01:31 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 710.961, LX912, Alma Lane (Type 3, 7m, rubber, sealed at crossing), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX912 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 710.85 | 710.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127692
WLD/N2NS/00778 | Jeramy Smith | 2021-06-29 01:30 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 706.550, LX911, County Boundary Road (Type 4, rubber, sealed), RX-5 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX911 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 706.45 | 706.65 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127691
WLD/N2NS/00777 | Jeramy Smith | 2021-06-29 01:29 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 704.694, LX3156, Private (Type 1, 6.0m, steel, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX3156 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 704.59 | 704.79 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127689
WLD/N2NS/00776 | Jeramy Smith | 2021-06-29 01:28 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 700.939, LX910, Calimpa-County Boundary Road (Type 3, 7m, rubber, sealed at crossing), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX910 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 700.83 | 700.93 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127688
WLD/N2NS/00775 | Jeramy Smith | 2021-06-29 01:27 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 693.959, LX909, Private (Type 3, 4.5m, rubber, sealed at crossing), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX909 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 693.87 | 694.07 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127687
WLD/N2NS/00774 | Jeramy Smith | 2021-06-29 01:26 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 689.505, LX3153, Private (Type 1, 4.5m, steel, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX3153 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 689.41 | 689.61 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127686
WLD/N2NS/00773 | Jeramy Smith | 2021-06-29 01:25 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 686.451, LX1842, Roydon Road (Type 2, 4.5m, rubber, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX1842 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 686.35 | 686.55 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127685
WLD/N2NS/00772 | Jeramy Smith | 2021-06-29 01:24 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 686.387, LX1841, Aff Land Pty (Type 2, 6m, rubber, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX1841 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 686.29 | 686.49 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127684
WLD/N2NS/00771 | Jeramy Smith | 2021-06-29 01:22 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 727.422, LX3162, Private (Type 1, 12.0m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX3162 |  |  | 2021-07-29 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 727.32 | 727.52 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127683
WLD/N2NS/00770 | Kallen Doong | 2021-06-28 08:22 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH631640 to CH632085 - Layer 2 - 400mm | 2021-06-29 |  | 2021-07-21 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 631.64 | 632.09 | [6 empty] | HWP/N2NS/00432 | [6 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | FDDA2EB3-9B74-418B-8DC6-BA050402D8E0.JPG, 15FF00E5-F1BF-4228-977E-60B38AD48035.JPG, Test Request 0599 Panda Results.pdf, Test Request 0601 Panda Results.pdf, N-21-179-849.pdf, N-21-179-847.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127669 |  |  |  | 7632-2C41552
WLD/N2NS/00769 | Richard Doering | 2021-06-28 07:40 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Richard Doering | Type E3 - Layer 1 CH656.580 to CH657.240 | 2021-06-28 |  | 2021-06-29 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 656.58 | 657.24 | [15 empty] | Test Request 0629 Panda Results.pdf, N-21-179-567.pdf, Test Request 0595 Panda Results.pdf, N-21-179-551.pdf, Test Request 0595 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127667 |  |  |  | 7632-2C41552
WLD/N2NS/00768 | Ryan Shenton | 2021-06-28 07:11 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Stage 2 - CH641.690 to CH641.870 - Cut Incl. Ground Preparation | 2021-06-28 |  | 2021-07-08 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 641.69 | 641.87 | [6 empty] | HWP/N2NS/00233 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_4426.JPG, IMG_4427.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127664 |  |  |  | 7632-2C41220
WLD/N2NS/00767 | Nabin Koirala | 2021-06-28 07:01 | Stage 2 - Penneys Road to Moree | Culverts | 639.740, 60/2400x900, remove and rebuild | Culverts - Other | Other | Keegan Baker | Excavation and Foundation Preparation of Drainage Structures |  |  | 2021-12-31 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 639.74 | 639.74 | [6 empty] | HWP/N2NS/00230, HWP/N2NS/00301 | [9 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127663
WLD/N2NS/00766 | Jeramy Smith | 2021-06-28 04:29 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 648.100, LX3067, Private (Type 1, 9.20m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Ahmad Alwan | LX3067- Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 648 | 648.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127655
WLD/N2NS/00765 | Jeramy Smith | 2021-06-28 04:28 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 649.350, LX1829, Crown access (Type 2, 6m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Ahmad Alwan | LX1829- Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 649.25 | 649.45 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127654
WLD/N2NS/00764 | Jeramy Smith | 2021-06-28 04:27 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 641.060, LX556, Private (Type 2, 4.50m, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Ahmad Alwan | LX556- Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 641.06 | 641.16 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127653
WLD/N2NS/00763 | Jeramy Smith | 2021-06-28 04:26 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Ahmad Alwan | LX555- Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 636.2 | 636.4 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127652
WLD/N2NS/00762 | Jeramy Smith | 2021-06-28 04:25 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 635.600, LX554, Gurley Creek Road (Type 4, rubber, sealed), RX-5 | Pavements - Prime/Primer Seal | Roadworks | Ahmad Alwan | LX554- Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 635.5 | 635.7 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127651
WLD/N2NS/00761 | Jeramy Smith | 2021-06-28 04:24 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Ahmad Alwan | LX3066- Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 634.39 | 634.59 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127650
WLD/N2NS/00760 | Jeramy Smith | 2021-06-28 04:23 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Ahmad Alwan | LX553 - Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 631.05 | 631.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127649
WLD/N2NS/00759 | Jeramy Smith | 2021-06-28 04:22 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Ahmad Alwan | LX1828 - Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 627.75 | 627.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127648
WLD/N2NS/00758 | Jeramy Smith | 2021-06-28 04:17 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 648.100, LX3067, Private (Type 1, 9.20m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Roadworks | Jeramy Smith | Upper Zone Formation (UZF)- LX3067 | 2021-08-08 |  | 2021-07-28 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 648 | 648.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127647
WLD/N2NS/00757 | Jeramy Smith | 2021-06-28 04:17 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 649.350, LX1829, Crown access (Type 2, 6m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Roadworks | Aziz Kamaoui | Upper Zone Formation (UZF)- LX1829 | 2021-08-19 |  | 2021-07-28 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 649.25 | 649.45 | [6 empty] | HWP/N2NS/00436 | [6 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127646
WLD/N2NS/00756 | Jeramy Smith | 2021-06-28 04:16 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 641.060, LX556, Private (Type 2, 4.50m, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Roadworks | Aziz Kamaoui | Upper Zone Formation (UZF)- LX556 | 2021-08-19 |  | 2021-07-28 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 641.06 | 641.16 | [6 empty] | HWP/N2NS/00462 | [6 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127645
WLD/N2NS/00755 | Jeramy Smith | 2021-06-28 04:15 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 635.600, LX554, Gurley Creek Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Roadworks | Aziz Kamaoui | Upper Zone Formation (UZF)- LX554 | 2021-08-15 |  | 2021-07-28 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 635.5 | 635.7 | [6 empty] | HWP/N2NS/00350 | [6 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127644
WLD/N2NS/00754 | Jeramy Smith | 2021-06-28 04:14 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Roadworks | Ahmad Alwan | Upper Zone Formation (UZF)- LX3066 | 2021-07-12 |  | 2021-07-28 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 634.39 | 634.59 | [6 empty] | HWP/N2NS/00271, HWP/N2NS/00327 | [6 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127643
WLD/N2NS/00753 | Jeramy Smith | 2021-06-28 04:14 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Roadworks | Hayden Murphy | Upper Zone Formation (UZF)- LX553 | 2021-07-06 |  | 2021-07-28 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 631.05 | 631.25 | [6 empty] | HWP/N2NS/00254, HWP/N2NS/00311 | [6 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  | 1.jpg, 2.jpg, N-21-179-683.pdf, Survey Report.pdf, Lot Map.pdf, WLDN2NS00753-LC.pdf, WLDN2NS0000753- Checklist (1).pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127642
WLD/N2NS/00752 | Jeramy Smith | 2021-06-28 04:09 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Roadworks | Hayden Murphy | Upper Zone Formation (UZF)- LX1828 | 2021-07-12 |  | 2021-07-28 10:00 | Benjamin Philip | 2021-08-16 | 2021-08-16 05:44 | Closed | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 627.75 | 627.95 | Benjamin Philip | 2021-08-16 05:44 |  |  |  |  | HWP/N2NS/00286 | Lot closed |  | 2021-08-16 05:44 |  |  |  | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  | WLDN2NS00752- Checklist.pdf, WLDN2NS00752- Lot Confromance.pdf, Test Report..pdf, Test Report.pdf, Material Test Report.pdf, Survey Report..pdf, Survey Report.pdf, Subgrade Confromance.pdf, Lot Map.pdf, 0823B93E-D954-4E26-AA43-BB1831A948E1.jpeg, 80C9C175-FE79-433A-9FD2-8FD0F898C6EA.jpeg | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127641 | [5 empty] | 2021-08-16 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00751 | Jeramy Smith | 2021-06-28 03:58 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 648.100, LX3067, Private (Type 1, 9.20m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Roadworks | Ahmad Alwan | Embankment Foundation (Subgrade)- LX3067 | 2021-08-06 |  | 2021-07-28 10:00 | Benjamin Philip | 2021-08-18 | 2021-08-18 00:14 | Closed | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 648 | 648.2 | Benjamin Philip | 2021-08-18 00:14 |  |  |  |  | HWP/N2NS/00448 | Lot closed |  | 2021-08-18 00:14 |  |  |  | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  | 2.jpg, 1.jpg, WLDN2NS00751-LC.pdf, N-21-179-795.pdf, Lot Map.pdf, WLDN2NS00751- Checklist.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127639 | [5 empty] | 2021-08-18 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00750 | Jeramy Smith | 2021-06-28 03:57 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 649.350, LX1829, Crown access (Type 2, 6m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Roadworks | Ahmad Alwan | Embankment Foundation (Subgrade)- LX1829 | 2021-08-06 |  | 2021-07-28 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 649.25 | 649.45 | [6 empty] | HWP/N2NS/00389 | [6 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127636
WLD/N2NS/00749 | Jeramy Smith | 2021-06-28 03:55 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 641.060, LX556, Private (Type 2, 4.50m, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Roadworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX556 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 641.06 | 641.16 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127634
WLD/N2NS/00748 | Jeramy Smith | 2021-06-28 03:55 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Roadworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX555 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 636.2 | 636.4 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127633
WLD/N2NS/00747 | Jeramy Smith | 2021-06-28 03:54 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 635.600, LX554, Gurley Creek Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Roadworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX554 | 2021-08-15 |  | 2021-07-28 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 635.5 | 635.7 | [6 empty] | HWP/N2NS/00326, HWP/N2NS/00431, HWP/N2NS/00434 | [6 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127631
WLD/N2NS/00746 | Jeramy Smith | 2021-06-28 03:52 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Roadworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX3066 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 634.39 | 634.59 | [6 empty] | HWP/N2NS/00288 | [6 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127630
WLD/N2NS/00745 | Jeramy Smith | 2021-06-28 03:51 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Roadworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX553 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 631.05 | 631.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127629
WLD/N2NS/00744 | Jeramy Smith | 2021-06-28 03:49 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Roadworks | Jeramy Smith | Embankment Foundation (Subgrade) |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 627.75 | 627.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127628
WLD/N2NS/00743 | Jeramy Smith | 2021-06-28 03:46 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Loui Tannous | LX555- RMS Embankment | 2021-08-15 |  | 2021-07-28 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 636.2 | 636.4 | [6 empty] | HWP/N2NS/00132, HWP/N2NS/00250 | [6 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127627
WLD/N2NS/00742 | Jeramy Smith | 2021-06-28 03:39 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Ancillary Works - Other | Other | Ahmad Alwan | Headwall Installation- LX533 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 631.05 | 631.25 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127626
WLD/N2NS/00741 | Jeramy Smith | 2021-06-28 03:33 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Ancillary Works - Other | Other | Ahmad Alwan | Headwall Installation- LX3066 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 634.39 | 634.59 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127625
WLD/N2NS/00740 | Jeramy Smith | 2021-06-28 03:30 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Drainage - Reinforced Concrete Pipes | Other | Ahmad Alwan | LX 3066- Excavation and Foundation Preparation of Drainage Structures | 2021-07-06 |  | 2021-07-28 10:00 | Benjamin Philip | 2021-08-17 | 2021-08-17 01:18 | Closed | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 634.39 | 634.59 | Benjamin Philip | 2021-08-17 01:18 |  |  |  |  | HWP/N2NS/00236, HWP/N2NS/00238 | Lot closed |  | 2021-08-17 01:18 |  |  |  | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  | 2.jpg, 1.jpg, WLDN2NS00740.pdf, WLDN2NS00740-LC.pdf, N-21-179-529.pdf, Test Report.pdf, Lot Map.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127624 | [5 empty] | 2021-08-17 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00739 | Jeramy Smith | 2021-06-28 03:28 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Ancillary Works - Other | Other | Ahmad Alwan | LX 553 - Excavation and Foundation Preparation of Drainage Structures | 2021-07-06 |  | 2021-07-28 10:00 | Benjamin Philip | 2021-07-28 | 2021-07-27 23:52 | Closed | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 631.05 | 631.25 | Benjamin Philip | 2021-07-27 23:52 |  |  |  |  | HWP/N2NS/00237, HWP/N2NS/00239 | Lot closed |  | 2021-07-27 23:52 |  |  |  | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  | IMG_0638.JPG, IMG_0639.JPG, IMG_0640.JPG, WLDN2NS00739- Checklist.pdf, WLDN2NS00739- Lot Conformance.pdf, Test Report.pdf, Lot Map.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127623 | 2021-07-29 18:40 |  |  |  |  | 2021-07-30 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00738 | Jeramy Smith | 2021-06-28 03:25 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 648.100, LX3067, Private (Type 1, 9.20m, rubber, unsealed), RX-2 | Earthworks - Insitu Treatments/Stabilisation | Roadworks | Jeramy Smith | Insitu Stabilisation- LX3067 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00027 | [9 empty] | 648 | 648.2 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127621
WLD/N2NS/00737 | Jeramy Smith | 2021-06-28 03:24 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 649.350, LX1829, Crown access (Type 2, 6m, rubber, unsealed), RX-2 | Earthworks - Insitu Treatments/Stabilisation | Roadworks | Jeramy Smith | Insitu Stabilisation- LX1829 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00027 | [9 empty] | 649.25 | 649.45 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127620
WLD/N2NS/00736 | Jeramy Smith | 2021-06-28 03:22 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Insitu Treatments/Stabilisation | Roadworks | Hayden Murphy | Insitu Stabilisation- LX553 | 2021-06-28 |  | 2021-07-28 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00027 | [9 empty] | 631.05 | 631.25 | [6 empty] | HWP/N2NS/00311 | [6 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127619
WLD/N2NS/00735 | Patrick Coria | 2021-06-28 02:49 | Stage 2 - Penneys Road to Moree | Culverts | 640,080, 5/2400x900, new build | Bridgeworks - Other | Concrete | Keegan Baker | 640.080 - Cast Insitu - Cut Off Walls - Upstream and Downstream | 2021-06-28 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 640.08 | 640.08 | [13 empty] | Brendan Meagher, Emma Conroy, Keegan Baker, Maddie Dahlstrom, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127617
WLD/N2NS/00734 | Patrick Coria | 2021-06-28 02:46 | Stage 2 - Penneys Road to Moree | Culverts | 637.290, 1/1800x900, remove and rebuild | Culverts - Other | Other | Keegan Baker | 637.290 - Backfill of Culverts | 2021-06-28 |  | 2021-08-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00037 | [9 empty] | 637.29 | 637.29 | [6 empty] | HWP/N2NS/00340, HWP/N2NS/00375, HWP/N2NS/00382 | [6 empty] | Brendan Meagher, Emma Conroy, Keegan Baker, Maddie Dahlstrom, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127616
WLD/N2NS/00733 | Jeramy Smith | 2021-06-28 01:15 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 684.899, LX3152, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Jeramy Smith | Clearing and Grubbing- LX3152 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 684.72 | 684.92 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127603
WLD/N2NS/00732 | Jeramy Smith | 2021-06-28 01:02 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 682.850, LX3151, Private (Type 1, 6m, steel, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Jeramy Smith | Pavement Marking |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 682.75 | 682.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127594
WLD/N2NS/00731 | Jeramy Smith | 2021-06-28 00:58 | Stage 3 - Camurra North to North Star | Trackwork | Level Crossing - 682.850, LX3151, Private (Type 1, 6m, steel, unsealed), RX-2 | Trackwork - Track Signage | Roadworks | Jeramy Smith | Signage Installation TfNSW- LX3151 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | [9 empty] | 682.75 | 682.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127593
WLD/N2NS/00730 | Jeramy Smith | 2021-06-28 00:51 | Stage 3 - Camurra North to North Star | Fencing | Level Crossing - 682.850, LX3151, Private (Type 1, 6m, steel, unsealed), RX-2 | Fencing - Fencing and Gates | Roadworks | Jeramy Smith | Fencing Installation TFNSW- LX3151 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 | [10 empty] | 682.75 | 682.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127591
WLD/N2NS/00729 | Jeramy Smith | 2021-06-28 00:47 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 682.850, LX3151, Private (Type 1, 6m, steel, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application of Sprayed Bituminous Surfacing) - LX3151 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00021 | [9 empty] | 682.75 | 682.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127590
WLD/N2NS/00728 | Jeramy Smith | 2021-06-28 00:44 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 682.850, LX3151, Private (Type 1, 6m, steel, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Jeramy Smith | Prime, Primerseal & Seal (Application and Incorporation of Aggregate) - LX3151 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020 | [9 empty] | 682.75 | 682.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127588
WLD/N2NS/00727 | Jeramy Smith | 2021-06-28 00:40 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 684.899, LX3152, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Jeramy Smith | Capping- LX3152 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 684.72 | 684.92 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127587
WLD/N2NS/00726 | Jeramy Smith | 2021-06-28 00:37 | Stage 3 - Camurra North to North Star | Ancillary Works | Level Crossing - 682.850, LX3151, Private (Type 1, 6m, steel, unsealed), RX-2 | Ancillary Works | Roadworks | Jeramy Smith | Construction of General Concrete Structures- LX3151 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 682.75 | 682.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127585
WLD/N2NS/00725 | Jeramy Smith | 2021-06-28 00:32 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 682.850, LX3151, Private (Type 1, 6m, steel, unsealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Jeramy Smith | Subsoil Drains, inc Precast Pits- LX3151 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 682.75 | 682.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127584
WLD/N2NS/00724 | Jeramy Smith | 2021-06-28 00:28 | Stage 3 - Camurra North to North Star | Pavements | Level Crossing - 682.850, LX3151, Private (Type 1, 6m, steel, unsealed), RX-2 | Pavements - Other | Roadworks | Jeramy Smith | Unbound Pavements- LX3151 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 682.75 | 682.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127583
WLD/N2NS/00723 | Jeramy Smith | 2021-06-28 00:25 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 682.850, LX3151, Private (Type 1, 6m, steel, unsealed), RX-2 | Drainage - Headwalls, Wingwalls and Cut Off Walls | Roadworks | Jeramy Smith | Headwall Installation- LX3151 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 682.75 | 682.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127582
WLD/N2NS/00722 | Jeramy Smith | 2021-06-28 00:22 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 682.850, LX3151, Private (Type 1, 6m, steel, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Excavation and Foundation Preparation of Drainage Structures- LX3151 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 682.75 | 682.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127581
WLD/N2NS/00721 | Jeramy Smith | 2021-06-28 00:18 | Stage 3 - Camurra North to North Star | Drainage | Level Crossing - 682.850, LX3151, Private (Type 1, 6m, steel, unsealed), RX-2 | Drainage - Installation of Culverts | Roadworks | Jeramy Smith | Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill- LX3151 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 682.75 | 682.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127580
WLD/N2NS/00720 | Jeramy Smith | 2021-06-28 00:11 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 682.850, LX3151, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Select Material Zone- LX3151 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 682.75 | 682.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127579
WLD/N2NS/00719 | Jeramy Smith | 2021-06-28 00:09 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 682.850, LX3151, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Upper Zone Formation (UZF)- LX3151 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 682.75 | 682.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127578
WLD/N2NS/00718 | Jeramy Smith | 2021-06-28 00:06 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 682.850, LX3151, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | Embankment Foundation (Subgrade)- LX3151 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 682.75 | 682.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127577
WLD/N2NS/00717 | Jeramy Smith | 2021-06-28 00:02 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 682.850, LX3151, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Jeramy Smith | RMS Embankments- LX3151 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 682.75 | 682.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127576
WLD/N2NS/00716 | Jeramy Smith | 2021-06-27 23:52 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 682.850, LX3151, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Topsoil Removal | Earthworks | Jeramy Smith | Strip Topsoil- LX3151 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 682.75 | 682.95 | [13 empty] | Ahmad Alwan, Aziz Kamaoui, Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127575
WLD/N2NS/00715 | Jeramy Smith | 2021-06-27 23:44 | Stage 3 - Camurra North to North Star | Earthworks | Level Crossing - 682.850, LX3151, Private (Type 1, 6m, steel, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Earthworks | Jeramy Smith | Clearing and Grubbing- LX3151 |  |  | 2021-07-28 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 682.75 | 682.95 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127574
WLD/N2NS/00714 | Shane Aberdeen | 2021-06-27 21:06 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Delivery of Precast Large & Small Concrete Box Culvert and Wing Walls - Week Ending 27 June 2021 | 2021-06-28 |  | 2021-06-27 10:00 | Shane Aberdeen | 2021-06-28 | 2021-06-27 21:07 | Closed | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058, ITP/N2NS/00059, ITP/N2NS/00060 | [9 empty] | MIX/N2NS/00001 | 0 | 0 | Shane Aberdeen | 2021-06-27 21:07 | [5 empty] | Lot closed |  | 2021-06-27 21:07 | [5 empty] | 27 June 2021 Precast Units Delivered Register.pdf, 20210627 CoCs.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127567 | 2021-06-29 19:15 | Holcim Australia Pty Ltd | PKG/N2NS/00006 |  |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00713 | Richard Doering | 2021-06-27 05:36 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Richard Doering | Type E3 - Layer 1 CH656.000 to CH656.580 | 2021-06-27 |  | 2021-06-28 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 656 | 656.58 | [13 empty] | James Martin, Paddy Montgomery, Tahlor Swan |  | N-21-179-482.pdf, N-21-179-491.pdf, N-21-179-565.pdf, Test Request 0584 Panda Results.pdf, N-21-179-846.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127562 |  |  |  | 7632-2C41552
WLD/N2NS/00712 | Kallen Doong | 2021-06-27 04:57 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH631155 to CH631175 - Foundation Treatment - 300mm | 2021-07-02 |  | 2021-07-21 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 631.15 | 631.18 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR580 Panda.pdf, N-21-179-492.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127561 |  |  |  | 7632-2C41552
WLD/N2NS/00711 | Kallen Doong | 2021-06-27 04:53 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH631510 to CH631640 - Layer 2 - 400mm | 2021-06-28 |  | 2021-07-21 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 631.51 | 631.64 | [6 empty] | HWP/N2NS/00432 | [6 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 0597 Panda Results.pdf, N-21-179-487.pdf, TR 579 Panda Results.pdf, BB28349F-97BB-4356-80A2-73A062B306BC.JPG, 22188515-0611-4B8A-B437-C1092252CD67.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127560 |  |  |  | 7632-2C41552
WLD/N2NS/00710 | Nabin Koirala | 2021-06-27 03:53 | Stage 2 - Penneys Road to Moree | Culverts | 631.140, 3/1800x900, remove and rebuild | Bridgeworks - Other | Concrete | Keegan Baker | Cast Insitu - Cut Off Walls - Upstream and Downstream 631.140 | 2021-06-30 |  | 2021-12-31 11:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 631.14 | 631.14 | [6 empty] | HWP/N2NS/00222, HWP/N2NS/00391, HWP/N2NS/00408 | [6 empty] | Brendan Meagher, Emma Conroy, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127559
WLD/N2NS/00709 | Ben Foster | 2021-06-26 20:58 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 27th June to 3rd July 2021 TOTAL QTY - 750.1 Tonnes | 2021-06-28 |  | 2021-07-03 10:00 | Lorne Jenks | 2021-07-14 | 2021-07-14 04:22 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 |  |  |  |  | WLD/N2NS/00259 | [5 empty] | 0 | 0 | Ben Foster | 2021-07-14 04:15 | [5 empty] | Lot closed |  | 2021-07-14 04:22 | [5 empty] | 55248.pdf, 1069767.pdf, 1069749.pdf, 1135431.pdf, 1069775.pdf, 1069773.pdf, 1135442.pdf, 1069765.pdf, 1135452.pdf, 1069785.pdf, 1069793.pdf, 1135481.pdf, 1069803.pdf, 1028236.pdf, 1135547.pdf, 1028235.pdf, 1135531.pdf, 1069824.pdf, 1028233.pdf, 2GA-202107-0005-00076996-F.pdf, 2CH-202107-0003-00076988-F.pdf, 1135480.pdf, 2AT-202107-0005-00077007-F.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127557 | 2021-07-29 18:40 | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551 |  | 2021-07-17 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00708 | Frank Paraha | 2021-06-26 06:40 | Stage 2 - Penneys Road to Moree | Culverts | 653.150, 1/600x600, remove and rebuild | Culverts - Installation of Box Culverts | Concrete | Frank Paraha | 653.150 - Cast In Situ Base Slab | 2021-07-25 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 |  |  |  | WLD/N2NS/00566, WLD/N2NS/00571, WLD/N2NS/01390, WLD/N2NS/01450 |  |  |  |  | MIX/N2NS/00007 | 653.15 | 653.15 | [6 empty] | HWP/N2NS/00217 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS00708LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127556 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/00707 | Richard Doering | 2021-06-26 04:02 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Richard Doering | Type E3 - Layer 1 CH655.475 to 656.000 | 2021-06-26 |  | 2021-06-27 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 655.48 | 656 | [15 empty] | N-21-179-513.pdf, N-21-179-480.pdf, TR 575 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127555 |  |  |  | 7632-2C41552
WLD/N2NS/00706 | Richard Doering | 2021-06-26 03:27 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type C3 - Insitu Stabilisation | 2021-06-26 |  | 2021-06-27 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00015 | [9 empty] | 657.54 | 657.64 | [13 empty] | James Martin, Paddy Montgomery, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127554 |  |  |  | 7632-2C41552
WLD/N2NS/00705 | Richard Doering | 2021-06-26 03:21 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Richard Doering | Cut inc Ground Prep | 2021-06-26 |  | 2021-06-26 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 657.57 | 657.74 | [6 empty] | HWP/N2NS/00214 | [6 empty] | James Martin, Paddy Montgomery, Richard Doering, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127553 |  |  |  | 7632-2C41220
WLD/N2NS/00704 | Richard Doering | 2021-06-26 02:58 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type C3 - Insitu Stabilisation - CH655.380 to 655.480 | 2021-06-21 | 2021-06-23 | 2021-06-23 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00015 | [9 empty] | 655.38 | 655.48 | [13 empty] | James Martin, Paddy Montgomery, Richard Doering, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127552 |  |  |  | 7632-2C41552
WLD/N2NS/00703 | Ryan Shenton | 2021-06-26 01:56 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Stage 2 - CH641.390 to CH641.529 - Cut Incl. Ground Preparation | 2021-06-26 |  | 2021-08-06 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 641.39 | 641.53 | [6 empty] | HWP/N2NS/00215 | [6 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_4401.JPG, IMG_4406.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127551 |  |  |  | 7632-2C41220
WLD/N2NS/00702 | Kallen Doong | 2021-06-25 07:35 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Stage 2 - Type E3 Layer 2 (SF) - CH630895 to CH630631510 | 2021-06-26 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 |  |  |  | WLD/N2NS/00519 | [5 empty] | 630.9 | 631.51 | [6 empty] | HWP/N2NS/00432 | [6 empty] | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | 816E46EB-4705-4AB5-8422-CBF1C006702E.JPG, 6599BD63-26B3-465B-89F8-6319543AB311.JPG, Test Request 0576 Panda Results.pdf, N-21-179-466.pdf, TR 569 Panda Results.pdf, Test Request 0749 Panda Results.pdf, N-21-179-614.pdf, N-21-179-664.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127538
WLD/N2NS/00701 | Richard Doering | 2021-06-25 07:02 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Richard Doering | Cut inc Ground Prep | 2021-06-25 |  | 2021-06-27 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 658 | 658 | [6 empty] | HWP/N2NS/00214 | [6 empty] | James Martin, Kallen Doong, Paddy Montgomery, Ryan Shenton, Tahlor Swan |  | N-21-179-475.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127535 |  |  |  | 7632-2C41220
WLD/N2NS/00700 | Kallen Doong | 2021-06-24 07:23 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Stage 2 - Type E3 Layer 2 (SF) - CH630431 to CH630780 | 2021-07-06 |  | 2021-07-08 10:00 | Benjamin Philip | 2021-07-20 | 2021-07-19 23:49 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 |  |  |  | WLD/N2NS/00519, WLD/N2NS/00649 | [5 empty] | 630.43 | 630.78 | Benjamin Philip | 2021-07-19 23:49 |  |  |  |  | HWP/N2NS/00232 | Lot closed |  | 2021-07-19 23:49 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0566.pdf, TR0566 Panda.pdf, TR0566 A.pdf, TR0568 Panda.pdf, ACE2E9F3-2D2D-4C93-AAB4-312C8D16AD41.JPG, D21F28C4-F1E7-49AE-AB4D-3DFE8304724D.JPG, lot map 700.pdf, E3 Stabilised Layer 2 WLD-N2NS-00700.pdf, wldn2ns00700.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127475 | 2021-07-29 18:40 |  |  |  |  | 2021-07-22 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00699 | James Martin | 2021-06-24 01:48 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH656.910 - CH657.180 | 2021-06-24 |  | 2021-06-24 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 656.91 | 657.18 | [6 empty] | HWP/N2NS/00282 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | WLDN2NS00699 - 1.JPG, WLDN2NS00699 - 2.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127434 |  |  |  | 7632-2C41220
WLD/N2NS/00698 | James Martin | 2021-06-24 01:39 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH656.570 - CH656.910 | 2021-06-24 |  | 2021-06-23 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 656.57 | 656.91 | [6 empty] | HWP/N2NS/00281 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_1307.JPG, IMG_1305.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127433 |  |  |  | 7632-2C41220
WLD/N2NS/00697 | James Martin | 2021-06-24 01:36 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH647.460 - CH647.645 | 2021-06-24 |  | 2021-06-23 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 647.46 | 647.65 | [6 empty] | HWP/N2NS/00270 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_1311.JPG, IMG_1309.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127432 |  |  |  | 7632-2C41220
WLD/N2NS/00696 | James Martin | 2021-06-24 01:34 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH656.000 - CH656.220 (Siding/Loop) | 2021-06-24 |  | 2021-06-22 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 656 | 656.22 | [6 empty] | HWP/N2NS/00283 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_1297.JPG, IMG_1298.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127431 |  |  |  | 7632-2C41220
WLD/N2NS/00695 | Kallen Doong | 2021-06-24 01:32 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Stage 2 - Type E3 Layer 2 (SF) - CH630101 to CH630431 | 2021-06-24 |  | 2021-07-06 10:00 | Benjamin Philip | 2021-07-16 | 2021-07-16 06:25 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 |  |  |  | WLD/N2NS/00519, WLD/N2NS/00649 | [5 empty] | 630.1 | 630.43 | Benjamin Philip | 2021-07-16 06:25 |  |  |  |  | HWP/N2NS/00232 | Lot closed |  | 2021-07-16 06:25 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0562.pdf, TR0562 Panda.pdf, TR0565 Panda.pdf, TR0562 A.pdf, E3 Stabilised Layer 2 WLD-N2NS-00695.pdf, E3DD4B91-B591-43F4-B49F-F72D1A8BBEEC.JPG, 7175AD78-B316-4615-A3B7-68323906B8F9.JPG, wldn2ns00695.pdf, lot map 695.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127430 | 2021-07-29 18:40 |  |  |  |  | 2021-07-22 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00694 | James Martin | 2021-06-24 01:32 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH655.950 - CH656.570 | 2021-06-22 |  | 2021-06-22 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 655.95 | 656.57 | [6 empty] | HWP/N2NS/00280 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_1301.JPG, IMG_1296.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127429 |  |  |  | 7632-2C41220
WLD/N2NS/00693 | James Martin | 2021-06-24 01:29 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH647.700 - CH648.280 | 2021-06-22 |  | 2021-06-22 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 647.7 | 648.28 | [6 empty] | HWP/N2NS/00272 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_1293.JPG, IMG_1294.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127428 |  |  |  | 7632-2C41220
WLD/N2NS/00692 | Brendan Meagher | 2021-06-23 07:30 | Stage 2 - Penneys Road to Moree | Culverts | 650.690, 2/2400x900, remove and rebuild | Culverts - Demolition | Other | Frank Paraha | 650.690 - Demolition of Existing Structures | 2021-06-23 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-06-28 | 2021-06-27 22:33 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 650.69 | 650.69 | Frank Paraha | 2021-06-27 06:32 | [5 empty] | Lot closed |  | 2021-06-27 22:33 |  |  |  | Emma Conroy, Frank Paraha, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | Lot Conformance Report - 650.690 Demo (Lot 692).pdf, Completed Checklist - 650.690 Demo (Lot 692).pdf, Lot Map - 650.690 Demo (Lot 692).pdf, 650.690 & 650.330 Demo - CMP's.JPG, 650.690 & 650.330 Demo - CMP's (2).JPG, 650.690 & 650.330 Demo - CMP's (4).JPG, 650.690 & 650.330 Demo - Concrete & CMP's.JPG, 650.690.JPG, 650.690 & 650.330 Demo - Concrete (2).JPG, 650.690 & 650.330 Demo - Concrete.JPG, 650.690 & 650.330 Demo - Concrete (3).JPG, 650.690 & 650.330 Demo - CMP's (3).JPG, 650.690 & 650.330 Demo - Concrete & CMP's (2).JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127402 | 2021-06-29 19:15 |  |  | 7632-2C41010 |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00691 | Brendan Meagher | 2021-06-23 07:29 | Stage 2 - Penneys Road to Moree | Culverts | 650.330, 1/2400x900, remove and rebuild | Culverts - Demolition | Other | Frank Paraha | 650.330 - Demolition of Existing Structures | 2021-06-23 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-06-27 | 2021-06-27 03:28 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 650.33 | 650.33 | Frank Paraha | 2021-06-27 03:06 | [5 empty] | Lot closed |  | 2021-06-27 03:28 |  |  |  | Emma Conroy, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | Lot Conformance Report - 650.330 Demo (Lot 691).pdf, Completed Checklist - 650.330 Demo (Lot 691).pdf, Lot Map - 650.330 Demo (Lot 691).pdf, IMG_1488.JPG, IMG_1481.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127401 | 2021-06-29 19:15 |  |  | 7632-2C41010 |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00690 | Nabin Koirala | 2021-06-23 01:21 | Stage 3 - Camurra North to North Star | Culverts | 711.770, 11/3000x1200, remove and rebuild | Culverts - Other | Concrete | Nabin Koirala | Cast Insitu - Base Slab - 711.770 | 2021-07-11 |  | 2021-12-31 11:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 711.77 | 711.77 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Maddie Dahlstrom |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127376
WLD/N2NS/00689 | Brendan Meagher | 2021-06-23 00:43 | Stage 3 - Camurra North to North Star | Culverts | 706.505, 1/3000x1100, remove and rebuild (RRA) | Culverts - Other | Other | Nabin Koirala | Excavation and Foundation Preparation of Drainage Structures - 706.505 | 2021-07-11 |  | 2021-06-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00040 | [9 empty] | 706.51 | 706.51 | [6 empty] | HWP/N2NS/00197 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127375
WLD/N2NS/00688 | Loui Tannous | 2021-06-23 00:17 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Ahmad Alwan | LX555- Upper Zone Formation (UZF) (Eastern Side) to Subgrade - along control line LX0555 LX side V1 only | 2021-06-23 |  | 2021-06-14 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 636.2 | 636.4 | [6 empty] | HWP/N2NS/00104, HWP/N2NS/00105 | [6 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  | Test Report.pdf, Test Report,.pdf, LX555 Subgrade Conformance Side.pdf, Survey Report (2).pdf, Lot Map (2).pdf, 555-2.JPG, 555-1.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127374
WLD/N2NS/00687 | James Martin | 2021-06-22 06:53 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - CH655.500 to CH655.475 - Layer 1 | 2021-06-24 |  | 2021-06-23 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 655 | 655.48 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR 574 Panda Results.pdf, N-21-179-501.pdf, N-21-179-457.pdf, N-21-179-500.pdf, TR 559 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127360 |  |  |  | 7632-2C41552
WLD/N2NS/00686 | Arjan Sidhu | 2021-06-22 06:47 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Earthworks - Filling | Earthworks | Arjan Sidhu | Matpol Structural Fill - Stock Pile SF3A. 6000T | 2021-06-22 |  | 2021-06-30 10:00 | Lorne Jenks | 2021-06-23 | 2021-06-22 20:52 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 | [9 empty] | 625.55 | 666 | Arjan Sidhu | 2021-06-22 06:50 | [5 empty] | Lot closed |  | 2021-06-22 20:52 |  |  |  | Brett Jenkins, Jake Mossman, Miaya Tighe |  | N-21-238-1.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127359 | 2021-06-29 19:15 |  |  |  |  | 2021-07-06 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00685 | Kallen Doong | 2021-06-22 06:38 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Stage 2 - Type E3 Layer 2 (SF Siding) - CH629550 to CH630101 | 2021-06-22 |  | 2021-07-07 10:00 | Benjamin Philip | 2021-07-17 | 2021-07-17 04:14 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 |  |  |  | WLD/N2NS/00519, WLD/N2NS/00649 | [5 empty] | 629.55 | 630.1 | Benjamin Philip | 2021-07-17 04:14 |  |  |  |  | HWP/N2NS/00232 | Lot closed |  | 2021-07-17 04:14 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0552 Panda .pdf, TR0552 A.pdf, TR0557 Panda.pdf, TR0552 B.pdf, E3 Stabilised Layer 2 WLD-N2NS-00685.pdf, wldn2ns00685.pdf, lot map 685.pdf, 5195248F-FE00-46FE-8D6A-A49997BE4D81.JPG, D7C0706C-7488-4455-BD54-13765A89BCB2.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127358 | 2021-07-29 18:40 |  |  |  |  | 2021-07-22 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00684 | Brendan Meagher | 2021-06-22 02:25 | Stage 2 - Penneys Road to Moree | Culverts | 635.410, 2/2400x900, remove and rebuild (RRA) | Culverts - Rock Protection | Other | Keegan Baker | 635.410 - Scour Protection | 2021-06-23 |  | 2021-07-16 10:00 | Benjamin Philip | 2021-06-27 | 2021-06-27 03:50 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00009 | [9 empty] | 631.58 | 631.58 | Nabin Koirala | 2021-06-27 02:47 | [5 empty] | Lot closed |  | 2021-06-27 03:50 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | Checklist.pdf, 635.410_lOT MAP.pdf, 635.410 (IMG_0738.JPG, 635.410 (IMG_0751).JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127338 | 2021-06-29 19:15 |  |  |  |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00683 | Brendan Meagher | 2021-06-21 22:27 | Stage 2 - Penneys Road to Moree | Culverts | 631.580, 1/600x600, remove and rebuild | Culverts - Rock Protection | Other | Keegan Baker | 631.580 - Scour Protection | 2021-06-23 |  | 2021-07-16 10:00 | Benjamin Philip | 2021-06-27 | 2021-06-26 23:20 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00009 | [9 empty] | 631.58 | 631.58 | Nabin Koirala | 2021-06-26 07:43 | [5 empty] | Lot closed |  | 2021-06-26 23:20 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | Checklist.pdf, 631.580_Lot Map.pdf, 631.580 (IMG_0738.JPG, 631.580 (IMG_0739).JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127300 | 2021-06-29 19:15 |  |  |  |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00682 | Shane Aberdeen | 2021-06-21 18:16 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Delivery of Precast Large & Small Concrete Box Culvert and Wing Walls - Week Ending 20 June 2021 | 2021-06-22 |  | 2021-06-20 10:00 | Shane Aberdeen | 2021-06-22 | 2021-06-21 18:18 | Closed | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058, ITP/N2NS/00059, ITP/N2NS/00060 | [9 empty] | MIX/N2NS/00001 | 0 | 0 | Shane Aberdeen | 2021-06-21 21:54 | [5 empty] | Lot closed |  | 2021-06-21 21:54 | [5 empty] | 20 June 2021 Precast Units Delivered Register.pdf, 20210620 CoCs.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127290 | 2021-06-29 19:15 | Holcim Australia Pty Ltd | PKG/N2NS/00006 |  |  | 2021-07-06 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00681 | Kallen Doong | 2021-06-21 07:22 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Stage 2 - Type E3 Layer 2 (SF) - CH629724 to CH630101 | 2021-06-22 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-07-20 | 2021-07-19 21:24 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 |  |  |  | WLD/N2NS/00519, WLD/N2NS/00649 | [5 empty] | 629.72 | 630.1 | Benjamin Philip | 2021-07-19 21:24 |  |  |  |  | HWP/N2NS/00232 | Lot closed |  | 2021-07-19 21:24 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | A1BE5DFA-E371-4F0C-8C75-7857662482F3.JPG, 71D62A54-4B09-45CE-B178-A5B101987462.JPG, TR0546 Panda.pdf, TR0546 NUC.pdf, TR0560 Panda.pdf, E3 Stabilised Layer 2 WLD-N2NS-00681.pdf, TR0546 A.pdf, wldn2ns00681.pdf, lot map 681.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127280 | 2021-07-29 18:40 |  |  |  |  | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00680 | James Martin | 2021-06-21 07:21 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - CH649.350 to CH650.230 - Layer 1 | 2021-06-22 |  | 2021-06-22 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 649.35 | 650.23 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Day 0 Compaction.pdf, Day 3 Pandas.pdf, Day 7 UCS.pdf, Day 0 Pandas.pdf, Day 0 Gradings.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127279 |  |  |  | 7632-2C41552
WLD/N2NS/00679 | Nabin Koirala | 2021-06-21 05:52 | Stage 3 - Camurra North to North Star | Culverts | 711.410, 10/2400x900, new build | Culverts - Other | Other | Nabin Koirala | Excavation and Foundation Preparation for Wingwalls |  |  | 2021-12-01 11:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 711.41 | 711.41 | [6 empty] | HWP/N2NS/00210 | [6 empty] | Emma Conroy, Maddie Dahlstrom |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127271
WLD/N2NS/00678 | Brendan Meagher | 2021-06-21 04:23 | Stage 2 - Penneys Road to Moree | Culverts | 627.760, 10/2400x1200, new build | Culverts - Other | Concrete | Keegan Baker | 627.760 - Cast In Situ Concrete Cut-Off Wall | 2021-06-23 |  | 2021-07-24 10:00 | Benjamin Philip | 2021-07-27 | 2021-07-26 21:40 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 627.76 | 627.76 | Maddie Dahlstrom | 2021-07-26 04:16 |  |  |  |  | HWP/N2NS/00211 | Lot closed |  | 2021-07-26 21:40 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | Lot Conformance & Checklist.pdf, N-21-179-444 (Downstream Compressive Strength Test Results).pdf, WLD N2NS 678_SWR489_Culvert 627760 Cutoff Wall Asbuilt.pdf, Lot Map.pdf, IMG_0399.JPG, IMG_0398.JPG, IMG_0394.JPG, N-21-179-444.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127268 | 2021-07-29 18:40 |  |  | 7632-2S72200 |  | 2021-07-29 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00677 | James Martin | 2021-06-20 22:46 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH648.280 - CH649.040 | 2021-06-21 |  | 2021-06-20 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 648.28 | 649.04 | [6 empty] | HWP/N2NS/00273 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_1274.JPG, IMG_1273.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127239 |  |  |  | 7632-2C41220
WLD/N2NS/00676 | James Martin | 2021-06-20 22:44 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - CH650.230 to CH651.100 - Layer 1 | 2021-06-21 |  | 2021-06-21 10:00 | Benjamin Philip | 2021-08-16 | 2021-08-16 02:59 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00015 |  |  |  | WLD/N2NS/00649 | [5 empty] | 650.23 | 651.1 | Benjamin Philip | 2021-08-16 02:59 | [5 empty] | Lot closed |  | 2021-08-16 02:59 |  |  |  | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | E3 Stabilised Layer 1 WLD-N2NS-00676.pdf, TR 556 Panda Results.pdf, N-21-179-450.pdf, N-21-179-495.pdf, TR 537 Panda Results.pdf, lot map 676.pdf, wldn2ns00676.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127238 |  |  |  | 7632-2C41552 |  | 2021-08-16 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00675 | Patrick Coria | 2021-06-20 21:34 | Stage 2 - Penneys Road to Moree | Culverts | 633.780, 35/3000x2400, remove and rebuild | Drainage - Other | Earthworks | Keegan Baker | 633.780 - Excavation and Foundation Preparation of Drainage Structure |  |  | 2021-07-09 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 633.78 | 633.78 | [6 empty] | HWP/N2NS/00213, HWP/N2NS/00316, HWP/N2NS/00319 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127237
WLD/N2NS/00674 | Kallen Doong | 2021-06-20 07:44 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Stage 2 - Type E3 Layer 2 (SF Mainline) - CH629550 to CH629724 | 2021-06-21 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-07-17 | 2021-07-17 04:23 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 |  |  |  | WLD/N2NS/00519, WLD/N2NS/00649 | [5 empty] | 629.55 | 629.72 | Benjamin Philip | 2021-07-17 04:23 |  |  |  |  | HWP/N2NS/00232 | Lot closed |  | 2021-07-17 04:23 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | F0086F4F-17C8-44B3-AD38-FF15111CB75D.JPG, C973BCB1-D8AA-4D2A-B9BB-061983F39BCE.JPG, TR0535 Panda.pdf, TR0535 NUC.pdf, TR0545 Panda.pdf, TR0535 A.pdf, E3 Stabilised Layer 2 WLD-N2NS-00674.pdf, lot map 674.pdf, wldn2ns00674.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127227 | 2021-07-29 18:40 |  |  |  |  | 2021-07-22 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00673 | Kallen Doong | 2021-06-20 07:33 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH629034 to CH629234 Siding - Layer 2 - 400mm | 2021-06-21 |  | 2021-06-30 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00649 | [5 empty] | 629.03 | 629.23 | [6 empty] | HWP/N2NS/00232 | [6 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | D59F5938-4CC0-4E6F-9289-6762CAEC83B3.JPG, F08CB6C9-1538-4280-8A14-BB52C1484F48.JPG, TR0534.pdf, TR0534 PSD ATTERBERG.pdf, TR0534 Panda.pdf, TR0534 A (1).pdf, TR0548 Panda.pdf, wldn2ns00673.pdf, Lot Map 673.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127226 |  |  |  | 7632-2C41552
WLD/N2NS/00672 | Brendan Meagher | 2021-06-20 06:15 | Stage 2 - Penneys Road to Moree | Culverts | 635.410, 2/2400x900, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Keegan Baker | Installation of Precast Culvert 635.410 | 2021-06-23 |  | 2021-06-30 10:00 | Lorne Jenks | 2021-07-11 | 2021-07-11 05:07 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 | [9 empty] | 635.15 | 635.15 | Lorne Jenks | 2021-07-11 05:07 | [5 empty] | Lot closed |  | 2021-07-11 05:07 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | WLDN2NS00672LM.pdf, 635.410 (IMG_0738.JPG, 635.410 (IMG_0749).JPG, 635.410 (IMG_0751).JPG, 635.410 (IMG_0750).JPG, S66 Balo St21071115271.pdf, LLP0039_N2NS_00672_0.pdf, S66 Balo St21071115281.pdf, S66 Balo St21071115282.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127225 | 2021-07-29 18:40 |  |  |  |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00671 | Brendan Meagher | 2021-06-20 06:11 | Stage 2 - Penneys Road to Moree | Culverts | 635.145, 6/1800x600, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Keegan Baker | Installation of Precast Culvert 635.145 | 2021-06-23 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-06-27 | 2021-06-27 04:19 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 | [9 empty] | 635.15 | 635.15 | Nabin Koirala | 2021-06-27 02:16 | [5 empty] | Lot closed |  | 2021-06-27 04:19 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | 635.145_Precast+Lot Map.pdf, EXP0039_N2NS_00411_0.pdf_635145.pdf, 635.145 (IMG_0752).JPG, 635.145 (IMG_0755).JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127224 | 2021-06-29 19:15 |  |  |  |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00670 | Brendan Meagher | 2021-06-20 06:09 | Stage 2 - Penneys Road to Moree | Culverts | 631.580, 1/600x600, remove and rebuild | Culverts - Installation of Box Culverts | Other | Keegan Baker | Installation of Precast Culvert 631.580 | 2021-06-23 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-06-27 | 2021-06-27 04:21 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 | [9 empty] | 630.93 | 630.93 | Nabin Koirala | 2021-06-27 02:29 | [5 empty] | Lot closed |  | 2021-06-27 04:21 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | 631.580_Precast+Lot Map.pdf, EXP0035_N2NS_00410_0.pdf_631.580.pdf, 631.580 (IMG_0745).JPG, 631.580 (IMG_0739).JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127223 | 2021-06-29 19:15 |  |  |  |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00669 | Brendan Meagher | 2021-06-20 06:05 | Stage 2 - Penneys Road to Moree | Culverts | 631.140, 3/1800x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Keegan Baker | Installation of Precast Culvert 631.140 | 2021-06-23 |  | 2021-06-30 10:00 | Lorne Jenks | 2021-07-10 | 2021-07-10 05:11 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 | [9 empty] | 630.93 | 630.93 | Lorne Jenks | 2021-07-10 05:11 | [5 empty] | Lot closed |  | 2021-07-10 05:11 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | WLDN2NS00669LM.pdf, 631.140 (IMG_0736).JPG, 631.140 (IMG_0735.JPG, 631.140 (IMG_0737).JPG, 631.140.pdf, S66 Balo St21071016010.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127222 | 2021-07-29 18:40 |  |  |  |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00668 | Brendan Meagher | 2021-06-20 06:02 | Stage 2 - Penneys Road to Moree | Culverts | 630.925, 2/600x600, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Keegan Baker | Installation of Precast Culvert 630.925 | 2021-06-23 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-06-27 | 2021-06-27 04:26 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 | [9 empty] | 630.93 | 630.93 | Nabin Koirala | 2021-06-27 02:34 | [5 empty] | Lot closed |  | 2021-06-27 04:26 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | 630.925_Precast+Lot Map.pdf, Survey As_Built_EXP0036_N2NS_00409_0.pdf_630.925.pdf, 630.925 (IMG_0747).JPG, 630.925 (IMG_0746).JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127221 | 2021-06-29 19:15 |  |  |  |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00667 | Keegan Baker | 2021-06-20 05:46 | Stage 2 - Penneys Road to Moree | Culverts | 650.690, 2/2400x900, remove and rebuild | Culverts - Other | Other | Frank Paraha | 650.690 - Excavation & Foundation Preparation | 2021-06-23 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 650.69 | 650.69 | [6 empty] | HWP/N2NS/00204, HWP/N2NS/00207 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127220 |  |  |  | 7632-2C41460
WLD/N2NS/00666 | Keegan Baker | 2021-06-20 05:45 | Stage 2 - Penneys Road to Moree | Culverts | 650.330, 1/2400x900, remove and rebuild | Culverts - Other | Other | Frank Paraha | 650.330 - Excavation & Foundation Preparation | 2021-06-23 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 650.33 | 650.33 | [6 empty] | HWP/N2NS/00203 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127219 |  |  |  | 7632-2C41460
WLD/N2NS/00665 | James Martin | 2021-06-19 07:02 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - CH651.100 to CH651.700 - Layer 1 | 2021-06-20 |  | 2021-06-20 10:00 | Benjamin Philip | 2021-08-16 | 2021-08-16 02:39 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00649 | [5 empty] | 651.1 | 651.7 | Benjamin Philip | 2021-08-16 02:39 | [5 empty] | Lot closed |  | 2021-08-16 02:39 |  |  |  | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | E3 Stabilised Layer 1 WLD-N2NS-00665.pdf, TR553 Panda Results.pdf, N-21-179-488.pdf, Test Request 0522 Panda Results.pdf, N-21-179-426.pdf, wldn2ns00665.pdf, lot map 665.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127207 |  |  |  | 7632-2C41552 |  | 2021-08-16 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00664 | James Martin | 2021-06-19 06:51 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH655.530 - CH655.950 | 2021-06-19 |  | 2021-06-19 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 655.53 | 655.95 | [6 empty] | HWP/N2NS/00279 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | WLDN2NS00664 - 1.JPG, WLDN2NS00664 - 2.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127205 |  |  |  | 7632-2C41220
WLD/N2NS/00663 | James Martin | 2021-06-19 06:46 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH649.040 - CH650.650 | 2021-06-19 |  | 2021-06-19 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 649.04 | 649.65 | [6 empty] | HWP/N2NS/00274 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | WLDN2NS00663 - 1.JPG, WLDN2NS00663 - 2.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127204 |  |  |  | 7632-2C41220
WLD/N2NS/00662 | Brendan Meagher | 2021-06-19 05:52 | Stage 2 - Penneys Road to Moree | Culverts | 627.760, 10/2400x1200, new build | Culverts - Installation of Box Culverts | Other | Keegan Baker | Installation of Pre Cast Culverts and Wingwalls at 627.760 | 2021-06-23 |  | 2021-06-20 10:00 | Lorne Jenks | 2021-07-10 | 2021-07-10 05:08 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 | [9 empty] | 627.76 | 627.76 | Lorne Jenks | 2021-07-10 05:08 | [5 empty] | Lot closed |  | 2021-07-10 05:08 | [5 empty] | WLDN2NS00662LM.pdf, 627.760 (IMG_0730).JPG, 627.760 (IMG_0728).JPG, 627.760 (IMG_0731).JPG, 627.760 (IMG_0726).JPG, 627.760 (IMG_0732).JPG, 627.760 (IMG_0727).JPG, WLDN2NS00662LM.pdf, 627.760 (IMG_0733.JPG, 627.760 (IMG_0734).JPG, 627.760 (IMG_0729).JPG, EXP0044_N2NS_00661_0.pdf, S66 Balo St21071016020.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127203 | 2021-07-29 18:40 |  |  |  |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00661 | Brendan Meagher | 2021-06-19 04:47 | Stage 2 - Penneys Road to Moree | Culverts | 627.430, 30/3000x2100, remove and rebuild | Culverts - Installation of Box Culverts | Other | Keegan Baker | 627.430 - Installation of Pre Cast Culverts and Wingwalls | 2021-06-23 |  | 2021-06-20 10:00 | Benjamin Philip | 2021-07-19 | 2021-07-19 07:21 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 |  |  |  | WLD/N2NS/01121 | [5 empty] | 627.43 | 627.43 | Benjamin Philip | 2021-07-19 07:21 | [5 empty] | Lot closed |  | 2021-07-19 07:21 | [5 empty] | WLDN2NS00661 Checklist.pdf, EXP0044_N2NS_00661_0.pdf_As-builts.pdf, WLDN2NS00661LM.pdf, 627.430 (IMG_0762).JPG, 627.430 (IMG_0765).JPG, 627.430 (IMG_0764).JPG, 627.430 (IMG_0763).JPG, 627.430 (IMG_0761).JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127202 | 2021-07-29 18:40 |  |  |  |  | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00660 | Nabin Koirala | 2021-06-19 04:43 | Stage 3 - Camurra North to North Star | Culverts | 706.505, 1/3000x1100, remove and rebuild (RRA) | Culverts - Other | Other | Nabin Koirala | Demolition of Existing Structures Culvert 706.505 | 2021-06-21 |  | 2021-12-31 11:00 | Lorne Jenks | 2021-06-23 | 2021-06-23 00:54 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 706.51 | 706.51 | Maddie Dahlstrom | 2021-06-21 04:45 | [5 empty] | Lot closed |  | 2021-06-23 00:54 |  |  |  | Brendan Meagher, Emma Conroy, George Yousef, Maddie Dahlstrom |  | IMG_0797.JPG, IMG_0799.JPG, IMG_0796.JPG, WLDN2NS00660.pdf, WLDN2NS00660.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127201 | 2021-06-29 19:15 |  |  |  |  | 2021-07-06 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00659 | James Martin | 2021-06-19 00:35 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Excavation (Cut) | Earthworks | James Martin | Cut Inc Ground Preparation - CH649.650 - CH650.950 | 2021-06-18 |  | 2021-06-26 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 649.65 | 650.95 | [6 empty] | HWP/N2NS/00275 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | WLDN2NS00659 - 2.JPG, WLDN2N200659 - 1.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127200 |  |  |  | 7632-2C41220
WLD/N2NS/00658 | Kallen Doong | 2021-06-18 07:54 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Stage 2 - CH641.150 to CH641.400 - General Fill |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 641.15 | 641.4 | [13 empty] | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | ADD5F5FC-0B60-4518-8AC9-B2555D4D812E.JPG, AC297388-E53B-4CB7-887B-F93F0804E940.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127198
WLD/N2NS/00657 | James Martin | 2021-06-18 07:46 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - CH651.700 to CH652.350 - Layer 1 | 2021-06-19 |  | 2021-06-19 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 651.7 | 652.35 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Day 0 Pandas.pdf, Day 7 UCS.pdf, Day 0 Compaction.pdf, Day 0 Gradings.pdf, Day 3 Pandas.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127197 |  |  |  | 7632-2C41552
WLD/N2NS/00656 | Kallen Doong | 2021-06-18 07:17 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH629.034 to CH629.350 Mainline - Layer 2 - 400mm | 2021-07-06 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-07-17 | 2021-07-17 04:49 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00648 | [5 empty] | 629.03 | 629.35 | Benjamin Philip | 2021-07-17 04:49 |  |  |  |  | HWP/N2NS/00232 | Lot closed |  | 2021-07-17 04:49 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0512 A.pdf, TR0512.pdf, TR0512 NUC.pdf, TR0520 Panda.pdf, E3 Stabilised Layer 2 WLD-N2NS-00656.pdf, lot map656.pdf, 7554CE1C-8A32-495C-B50C-B32C437396A5.JPG, D9B53813-FD42-4828-A432-56D4C4C4083E.JPG, wldn2ns00656.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127193 | 2021-07-29 18:40 |  |  | 7632-2C41552 |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00655 | Patrick Coria | 2021-06-18 03:49 | Stage 2 - Penneys Road to Moree | Culverts | 637.170, 1/1800x600, remove and rebuild | Drainage - Other | Other | Keegan Baker | 637.170 - Backfill of Reinforced Concrete Box Culverts | 2021-06-23 |  | 2021-06-25 10:00 | Benjamin Philip | 2021-07-20 | 2021-07-19 21:06 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00004 | [9 empty] | 637.17 | 637.17 | Benjamin Philip | 2021-07-19 21:06 | [5 empty] | Lot closed |  | 2021-07-19 21:06 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | N-21-179-443.pdf, N-21-179-446.pdf, Lot Map- chainage 637.170.pdf, 637.170 (IMG_0769).JPG, S66 Balo St21063009520.pdf, Culvert 637170 Transition Structural Fill_WLD N2NS 655_SWR419.pdf, IMG_0952.JPG, IMG_0953.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127142 | 2021-07-29 18:40 |  |  |  |  | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00654 | Patrick Coria | 2021-06-18 03:49 | Stage 2 - Penneys Road to Moree | Culverts | 636.705, 4/600x600, remove and rebuild (RRA) | Drainage - Other | Other | Keegan Baker | 636.705 - Backfill of Reinforced Concrete Box Culverts | 2021-06-23 |  | 2021-06-25 10:00 | Benjamin Philip | 2021-07-20 | 2021-07-19 21:09 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00004 | [9 empty] | 636.71 | 636.71 | Benjamin Philip | 2021-07-19 21:09 | [5 empty] | Lot closed |  | 2021-07-19 21:09 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | S66 Balo St21062909260.pdf, N-21-179-447.pdf, 636.705 (IMG_0768).JPG, 636.705 (IMG_0767).JPG, 636.705 (IMG_0766).JPG, Lot Map - chainage 636.705.pdf, N-21-179-433.pdf, Culvert 636705 Transition Structural Fill_WLD N2NS 654_SWR418.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127141 | 2021-07-29 18:40 |  |  |  |  | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00653 | Patrick Coria | 2021-06-18 03:47 | Stage 2 - Penneys Road to Moree | Culverts | 635.410, 2/2400x900, remove and rebuild (RRA) | Drainage - Other | Other | Keegan Baker | 635.410 - Backfill of Reinforced Concrete Box Culverts | 2021-06-23 |  | 2021-06-25 10:00 | Benjamin Philip | 2021-07-20 | 2021-07-19 21:02 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00004 | [9 empty] | 635.41 | 635.41 | Benjamin Philip | 2021-07-19 21:02 | [5 empty] | Lot closed |  | 2021-07-19 21:02 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | N-21-179-429.pdf, 635.410 (IMG_0751).JPG, 635.410 (IMG_0750).JPG, 635.410 (IMG_0738.JPG, Lot Map- chainage 635.410 (00653) .pdf, S66 Balo St21062910590.pdf, Culvert 635410 Transition Structural Fill_WLD N2NS 653_SWR417.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127139 | 2021-07-29 18:40 |  |  |  |  | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00652 | Patrick Coria | 2021-06-18 03:46 | Stage 2 - Penneys Road to Moree | Culverts | 635.145, 6/1800x600, remove and rebuild (RRA) | Drainage - Other | Other | Keegan Baker | 635.145 - Backfill of Reinforced Concrete Box Culverts | 2021-06-23 |  | 2021-06-25 10:00 | Benjamin Philip | 2021-07-20 | 2021-07-19 21:16 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00004 | [9 empty] | 635.15 | 635.15 | Benjamin Philip | 2021-07-19 21:16 | [5 empty] | Lot closed |  | 2021-07-19 21:16 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS00652 Checklist.pdf, N-21-179-431.pdf, N-21-179-416.pdf, Culvert 635145 Transition Structural Fill_WLD N2NS 652_SWR416.pdf, WLDNSNS00652LM.pdf, 635.145 (IMG_0755).JPG, 635.145 (IMG_0754).JPG, 635.145 (IMG_0752).JPG, 635.145 (IMG_0753).JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127138 | 2021-07-29 18:40 |  |  |  |  | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00651 | Keegan Baker | 2021-06-18 03:09 | Stage 2 - Penneys Road to Moree | Culverts | 637.170, 1/1800x600, remove and rebuild | Culverts - Other | Concrete | Keegan Baker | 637.170 - Cast In Situ Concrete Cut-Off Wall | 2021-06-18 |  | 2021-07-24 10:00 | Benjamin Philip | 2021-08-12 | 2021-07-25 22:50 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 636.71 | 636.71 | Maddie Dahlstrom | 2021-08-11 04:32 |  |  |  |  | HWP/N2NS/00199 | Lot closed |  | 2021-08-12 02:14 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | N-21-179-412 (002) (Compressive Strength Test Result).pdf, WLD N2NS 651_SWR407_Culvert 637170 Cutoff Wall Asbuilt.pdf, Lot Map.pdf, IMG_0575.jpg, IMG_0574.jpg, WLDN2NS00651.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127128 | 2021-07-29 18:40 |  |  | 7632-2S72200 |  | 2021-08-14 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00650 | Keegan Baker | 2021-06-18 03:06 | Stage 2 - Penneys Road to Moree | Culverts | 636.705, 4/600x600, remove and rebuild (RRA) | Culverts - Other | Concrete | Keegan Baker | 636.705 - Cast In Situ Concrete Cut-Off Wall | 2021-06-18 |  | 2021-07-24 10:00 | Benjamin Philip | 2021-07-26 | 2021-07-26 02:34 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 636.71 | 636.71 | Emma Conroy | 2021-07-25 22:30 |  |  |  |  | HWP/N2NS/00198 | Lot closed |  | 2021-07-26 02:34 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | N-21-179-412 (002) (Compressive Strength Test Result).pdf, WLD N2NS 650_SWR406_Culvert 636705 Cutoff Wall Asbuilt.pdf, Lot Map.pdf, IMG_0358.JPG, IMG_0576.jpg, Signed Lot Conformance & Checklist.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127127 | 2021-07-29 18:40 |  |  | 7632-2S72200 |  | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00649 | Ben Foster | 2021-06-17 21:34 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 20th June to 26th June 2021 Estimated QTY for JUNE PC - 578.79 Tonnes | 2021-06-18 |  | 2021-06-26 10:00 | Benjamin Philip | 2021-07-20 | 2021-07-19 23:50 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 |  |  |  |  | WLD/N2NS/00673, WLD/N2NS/00674, WLD/N2NS/00681, WLD/N2NS/00685, WLD/N2NS/00695 | [5 empty] | 0 | 0 | Ben Foster | 2021-07-19 21:07 | [5 empty] | Lot closed |  | 2021-07-19 23:50 | [5 empty] | 1028202 1028203.pdf, 1028206 1028207.pdf, 1135243.pdf, 1028218.pdf, 1069690.pdf, 1135252.pdf, 1135302.pdf, 8607.pdf, 1135292.pdf, 1028216 1028217.pdf, 1135363.pdf, 1069743.pdf, 1069727.pdf, 1028223.pdf, 2GA-202106-0404-00076927-F.pdf, 2CH-202106-0017-00076908-F.pdf, 2AT-202106-0133-00076929-F.pdf, 1069716.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127091 | 2021-07-29 18:40 | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551 |  | 2021-07-22 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00648 | Ben Foster | 2021-06-17 21:25 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 13th June to 19th June 2021 TOTAL QTY - 300.73 Tonnes | 2021-06-18 |  | 2021-06-19 10:00 | Lorne Jenks | 2021-07-10 | 2021-07-09 21:45 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 0 | 0 | Ben Foster | 2021-07-09 04:18 | [5 empty] | Lot closed |  | 2021-07-09 21:45 | [5 empty] | 1028201.pdf, 1135184.pdf, 08603.pdf, 1028190.pdf, 05419.pdf, 1028182.pdf, 1028180.pdf, 1009841.pdf, 1028196 1028197.pdf, 2AT-202106-0135-00076888-F.pdf, 2GA-202106-0329-00076892-F.pdf, 2CH-202106-0013-00076868-F.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127090 | 2021-07-29 18:40 | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551 |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00647 | James Martin | 2021-06-17 07:33 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - CH652.350 to CH652.920 - Layer 1 | 2021-06-19 |  | 2021-06-18 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 652.35 | 652.92 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Day 3 Pandas.pdf, Day 0 Compaction.pdf, Day 0 Gradings.pdf, Day 0 Pandas.pdf, Day 7 UCS.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127027 |  |  |  | 7632-2C41552
WLD/N2NS/00646 | James Martin | 2021-06-17 06:23 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH650.950 - CH651.250 | 2021-06-17 |  | 2021-06-17 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 650.95 | 651.25 | [6 empty] | HWP/N2NS/00276 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | WLDN2N200646 - 2.JPG, WLDN2N200646 - 1.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127025 |  |  |  | 7632-2C41220
WLD/N2NS/00645 | Harris Ahmad | 2021-06-17 04:22 | Stage 3 - Camurra North to North Star | Trackwork | Main Alignment (Specify Chainage in Lot) | Trackwork - Sleeper Installation | Track | Harris Ahmad | Installation of sleepers - CH66...... |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00009 | [11 empty] | 625.7 | 627.14 | [13 empty] | Callum Todd, Chelsea Carter, Semir Basic |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127012
WLD/N2NS/00644 | James Martin | 2021-06-17 02:45 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH651.410 - CH651.750 | 2021-06-17 |  | 2021-06-17 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 651.41 | 651.75 | [6 empty] | HWP/N2NS/00277 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | WLDN2N200644 - 2.JPG, WLDN2NS00644 - 1.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127005 |  |  |  | 7632-2C41220
WLD/N2NS/00643 | James Martin | 2021-06-17 02:43 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut Inc Ground Preparation - CH655.310 - CH655.530 | 2021-06-17 |  | 2021-06-17 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 655.31 | 655.53 | [6 empty] | HWP/N2NS/00278 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | WLDN2NS00643 - 2.JPG, WLDN2NS00643 -1.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/127004 |  |  |  | 7632-2C41220
WLD/N2NS/00642 | James Martin | 2021-06-17 01:40 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - CH652.920 to CH653.800 - Layer 1 | 2021-06-17 |  | 2021-06-17 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 652.92 | 653.8 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Day 7 UCS.pdf, Day 0 Compaction.pdf, Day 0 Pandas.pdf, Day 3 Pandas.pdf, Day 0 Gradings.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126994 |  |  |  | 7632-2C41552
WLD/N2NS/00641 | James Martin | 2021-06-16 07:54 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type E3 - CH653.800 to CH654.380 - Layer 1/Insitu | 2021-06-16 |  | 2021-06-25 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 653.8 | 654.38 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Day 3 Pandas.pdf, Day 7 UCS (2).pdf, Day 7 UCS.pdf, Day 0 Pandas.pdf, Day 0 Compaction.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126963 |  |  |  | 7632-2C41552
WLD/N2NS/00640 | Keegan Baker | 2021-06-16 07:26 | Stage 2 - Penneys Road to Moree | Culverts | 631.580, 1/600x600, remove and rebuild | Drainage - Other | Other | Keegan Baker | 631.580 - Backfill of Reinforced Concrete Box Culverts | 2021-06-23 |  | 2021-07-16 10:00 | Benjamin Philip | 2021-07-20 | 2021-07-19 20:59 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00004 | [9 empty] | 631.58 | 631.58 | Benjamin Philip | 2021-07-19 20:59 | [5 empty] | Lot closed |  | 2021-07-19 20:59 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS00640 Checklist.pdf, Culvert 631580 Transition Structural Fill_WLD N2NS 640_SWR415.pdf, WLDN2NS00640LM.pdf, 631.580 (IMG_0744).JPG, 631.580 (IMG_0745).JPG, 631.580 (IMG_0739).JPG, 631.580 (IMG_0742).JPG, 631.580 (IMG_0743).JPG, N-21-179-430.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126958 | 2021-07-29 18:40 |  |  |  |  | 2021-07-29 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00639 | Keegan Baker | 2021-06-16 07:11 | Stage 2 - Penneys Road to Moree | Culverts | 630.925, 2/600x600, remove and rebuild (RRA) | Drainage - Other | Other | Keegan Baker | 630.925 - Backfill of Reinforced Concrete Box Culverts | 2021-06-23 |  | 2021-06-22 10:00 | Benjamin Philip | 2021-07-20 | 2021-07-19 22:39 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00004 | [9 empty] | 630.93 | 630.93 | Benjamin Philip | 2021-07-19 22:39 | [5 empty] | Lot closed |  | 2021-07-19 22:39 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS00639 Checklist.pdf, Culvert 630925 Transition Structural Fill_WLD N2NS 639_SWR414.pdf, WLDN2NS00639LM.pdf, 630.925 (IMG_0748).JPG, 630.925 (IMG_0746).JPG, 630.925 (IMG_0747).JPG, N-21-179-415.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126957 | 2021-07-29 18:40 |  |  |  |  | 2021-07-29 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00638 | Ryan Shenton | 2021-06-16 05:29 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Stage 2 - Type E3 Layer 2 (SF) (350mm) - CH629.490 to CH630.140 |  |  | 2021-06-30 10:00 |  |  |  | Planned | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00519 | [5 empty] | 629.49 | 630.14 | [13 empty] | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126945
WLD/N2NS/00637 | Shane Aberdeen | 2021-06-15 22:45 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Delivery of Precast Large & Small Concrete Box Culvert and Wing Walls - Week Ending 13 June 2021 | 2021-06-16 |  | 2021-06-13 10:00 | Shane Aberdeen | 2021-06-16 | 2021-06-15 22:47 | Closed | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058, ITP/N2NS/00059, ITP/N2NS/00060 | [9 empty] | MIX/N2NS/00001 | 0 | 0 | Shane Aberdeen | 2021-06-15 22:47 | [5 empty] | Lot closed |  | 2021-06-15 22:47 | [5 empty] | 20210613 CoCs.pdf, 13 June 2021 Precast Units Delivered Register.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126876 | 2021-06-29 19:15 |  |  |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00636 | Richard Doering | 2021-06-15 07:04 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Richard Doering | Type E3 - CH654.380 to CH654.700 - Layer 1/Insitu | 2021-06-15 |  | 2021-06-16 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 654.38 | 654.7 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126857 |  |  |  | 7632-2C41552
WLD/N2NS/00635 | Hayden Murphy | 2021-06-15 01:50 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 635.600, LX554, Gurley Creek Road (Type 4, rubber, sealed), RX-5 | Temporary Works - Access Points - Other | Roadworks | Hayden Murphy | Temporary Road - LX554 Gurley Creek Road | 2021-06-16 |  | 2021-06-23 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 635.6 | 635.7 | [13 empty] | Aziz Kamaoui, Grant Mills, Jeramy Smith |  | WLDN2NS00635.pdf, RU DGB20 Lot5-21 26-4-21.pdf, N-21-179-270 Copy.pdf, N-21-179-262.pdf, Temporary Works Site Validation Form.docx, DGB 20 dockets 4.pdf, DGB 20 dockets.pdf, DGB 20 dockets 3.pdf, DGB 20 dockets 2.pdf, WLDN2NS00635.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126844
WLD/N2NS/00634 | Arjan Sidhu | 2021-06-15 01:31 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Earthworks - Filling | Earthworks | Arjan Sidhu | Structural Fill Tookey pit stockpile 2 additional 2000T | 2021-06-15 |  | 2021-06-21 10:00 | Sarah Brooks | 2021-06-16 | 2021-06-16 00:56 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 | [9 empty] | 625.55 | 666 | Arjan Sidhu | 2021-06-15 01:41 | [5 empty] | Lot closed |  | 2021-06-16 00:56 |  |  |  | Arjan Sidhu, Jake Mossman, Miaya Tighe |  | N-21-179-156_Combined.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126842 | 2021-06-29 19:15 |  |  |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00633 | Jeramy Smith | 2021-06-14 21:32 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Ahmad Alwan | LX555 DDR2 - Excavation for RCP's- 4 Barrel excluding Headwalls | 2021-06-15 |  | 2021-06-14 10:00 | Lorne Jenks | 2021-07-12 | 2021-07-12 07:05 | Closed | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 636.2 | 636.4 | Lorne Jenks | 2021-07-12 07:05 |  |  |  |  | HWP/N2NS/00111, HWP/N2NS/00159 | Lot closed |  | 2021-07-12 07:05 |  |  |  | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  | S66 Balo Re21071212491.pdf, S66 Balo Re21071212490.pdf, S66 Balo Re21071212480.pdf, S66 Balo Re21071212492.pdf, WLD-N2NS-00633.pdf, 00633-Lot Confromance.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126786 | 2021-07-29 18:40 |  |  |  |  | 2021-07-17 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00632 | Keegan Baker | 2021-06-14 01:30 | Stage 2 - Penneys Road to Moree | Culverts | 635.410, 2/2400x900, remove and rebuild (RRA) | Culverts - Other | Concrete | Keegan Baker | 635.410 - Cast In Situ Concrete Cut-Off Wall | 2021-06-14 |  | 2021-07-10 10:00 | Benjamin Philip | 2021-07-27 | 2021-07-27 01:19 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 635.41 | 635.41 | Benjamin Philip | 2021-07-27 01:18 |  |  |  |  | HWP/N2NS/00191 | Lot closed |  | 2021-07-27 01:19 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | Signed Lot Conformance & Checklist.pdf, N-21-179-421 (Concrete Test Results).pdf, WLD N2NS 601_SWR405_Culvert 635410 Cutoff Wall Asbuilt.pdf, Lot Map.pdf, IMG_0338.JPG, IMG_0337.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126766 | 2021-07-29 18:40 |  |  | 7632-2S72200 |  | 2021-07-30 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00631 | Arjan Sidhu | 2021-06-10 22:08 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Capping | Earthworks | Arjan Sidhu | JCQ Runnymede Capping Supply - 4000T Stockpile 13 | 2021-06-11 |  | 2021-07-30 10:00 | Benjamin Philip | 2021-07-21 | 2021-06-12 03:08 | Closed | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 625.55 | 667 | Benjamin Philip | 2021-07-20 20:39 | [5 empty] | Lot closed |  | 2021-07-20 20:40 |  |  |  | Arjan Sidhu, Brett Jenkins, Jake Mossman, Jarryd Davis, Miaya Tighe |  | RU Capping Lot 13-21 9-6-21_1.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126526 | 2021-07-29 18:40 |  |  |  |  | 2021-07-22 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00630 | Shane Aberdeen | 2021-06-09 20:34 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Delivery of Precast Large & Small Concrete Box Culvert and Wing Walls - Week ending 06 June 2021 | 2021-06-10 |  | 2021-06-06 10:00 | Shane Aberdeen | 2021-06-10 | 2021-06-09 20:38 | Closed | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058, ITP/N2NS/00059, ITP/N2NS/00060 | [9 empty] | MIX/N2NS/00001 | 0 | 0 | Shane Aberdeen | 2021-06-09 20:38 | [5 empty] | Lot closed |  | 2021-06-09 20:38 | [5 empty] | 20210606 CoCs.pdf, 06 June 2021 Precast Units Delivered Register.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126404 | 2021-06-29 19:15 | Holcim Australia Pty Ltd | PKG/N2NS/00006 |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00629 | Jeramy Smith | 2021-06-09 05:44 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Ahmad Alwan | LX555 DDR1 - Excavation for RCP's - Single Barrel | 2021-06-09 |  | 2021-06-14 10:00 | Benjamin Philip | 2021-08-16 | 2021-08-16 05:08 | Closed | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 636.2 | 636.4 | Benjamin Philip | 2021-08-16 05:03 |  |  |  |  | HWP/N2NS/00111, HWP/N2NS/00112 | Lot closed |  | 2021-08-16 05:08 |  |  |  | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  | Test Report.pdf, Lot Map.pdf, 555DDR1 Asbuilt Report.pdf, WLDN2NS00629- Checklist.pdf, WLDN2NS00629-LC.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126386 | [5 empty] | 2021-08-16 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00628 | Nabin Koirala | 2021-06-09 01:08 | Stage 2 - Penneys Road to Moree | Culverts | 627.760, 10/2400x1200, new build | Culverts - Demolition | Other | Keegan Baker | Demolition of Existing Culvert - 627.760 |  |  | 2021-06-26 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 627.76 | 627.76 | [13 empty] | Brendan Meagher, Emma Conroy, George Yousef, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126368
WLD/N2NS/00627 | Kallen Doong | 2021-06-08 06:36 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH628990 to CH629290 - Layer 2 - 400mm | 2021-07-06 |  | 2021-06-18 10:00 | Benjamin Philip | 2021-07-17 | 2021-07-17 04:53 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00648 | [5 empty] | 628.99 | 629.03 | Benjamin Philip | 2021-07-17 04:53 |  |  |  |  | HWP/N2NS/00232 | Lot closed |  | 2021-07-17 04:53 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0503 C.pdf, TR0503 B.pdf, TR0503 Panda.pdf, TR0503 Panda A.pdf, TR0509 Panda .pdf, wldn2ns00627.pdf, lot map 627.pdf, 1F3CFD76-5857-4226-8B46-86A51CE8049A.JPG, C95EB739-C68B-45F5-989A-D1C58A113632.JPG, WAE EX STG2 LOT 627 CH628990-629030.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126319 | 2021-07-29 18:40 |  |  | 7632-2C41552 |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00626 | Ryan Shenton | 2021-06-08 02:57 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Excavation (Cut) | Earthworks | Ryan Shenton | Cut Inc Ground Preparation - CH640.280 - CH640.800 | 2021-06-08 |  | 2021-06-22 10:00 | Lorne Jenks | 2021-07-12 | 2021-07-12 01:05 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 640.28 | 640.8 | Lorne Jenks | 2021-07-12 01:04 |  |  |  |  | HWP/N2NS/00267, HWP/N2NS/00268 | Lot closed |  | 2021-07-12 01:05 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Tahlor Swan |  | IMG_4175.JPG, IMG_4176.JPG, lot map 626.pdf, IMG_4384.JPG, Excavation Foundation Ch 640280 to Ch 640800 Lot WLD-N2NS-00626.pdf, TR0611.pdf, TR0591.pdf, TR0582 Panda .pdf, wldn2ns00626.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126238 | 2021-07-29 18:40 |  |  | 7632-2C41220 |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00625 | Kallen Doong | 2021-06-07 08:02 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Stage 2 - Type E3 Layer 2 (SF) - CH629350 to CH629550 | 2021-06-16 |  | 2021-06-12 10:00 | Benjamin Philip | 2021-07-17 | 2021-07-17 05:18 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 |  |  |  | WLD/N2NS/00519, WLD/N2NS/00648 | [5 empty] | 629.35 | 629.55 | Benjamin Philip | 2021-07-17 05:18 |  |  |  |  | HWP/N2NS/00232 | Lot closed |  | 2021-07-17 05:18 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | 9E8104BC-3DA5-4F1F-9964-50B0D5C4D7DF.JPG, D20B2423-2A01-4BE6-ACA5-912B59391924.JPG, TR0510 Panda.pdf, TR0502 Panda.pdf, TR0502 Compac.pdf, TR0502 C.pdf, TR0502 B.pdf, TR0508 B.pdf, TR0508 A.pdf, TR0508 PSD ATT.pdf, TR0521 Panda.pdf, WAE EX STG2 LOT 625 CH629355-629550.pdf, wldn2ns00625.pdf, lot map 625.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126196 | 2021-07-29 18:40 |  |  |  |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00624 | Kallen Doong | 2021-06-07 07:35 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH628880 to CH628990 - Layer 2 - 400mm | 2021-06-08 |  | 2021-06-16 10:00 | Benjamin Philip | 2021-07-22 | 2021-07-22 00:51 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00599 | [5 empty] | 628.88 | 628.99 | Benjamin Philip | 2021-07-22 00:51 |  |  |  |  | HWP/N2NS/00232 | Lot closed |  | 2021-07-22 00:51 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_4329.JPG, IMG_4328.JPG, TR0427.pdf, TR0427 A.pdf, TR 427 Panda Results.pdf, N-21-179-512.pdf, WAE EX STG2 LOT 624 CH628880-628990.pdf, wldn2ns00624.pdf, lot map 624.pdf, Test Request 0463 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126191 | 2021-07-29 18:40 |  |  | 7632-2C41552 |  | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00623 | Ryan Shenton | 2021-06-07 07:00 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH637.820 to CH638.120 - Layer 2 - 400mm | 2021-06-07 |  | 2021-06-21 10:00 | Benjamin Philip | 2021-08-11 | 2021-08-11 05:47 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00599 | [5 empty] | 637.63 | 637.94 | Benjamin Philip | 2021-08-11 05:46 |  |  |  |  | HWP/N2NS/00255 | Lot closed |  | 2021-08-11 05:47 |  |  |  | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0425B.pdf, TR0425.pdf, TR0425 A.pdf, Test Request 425 Panda Results.pdf, TR0465 Panda.pdf, E3 Stabilised Layer 2 WLD-N2NS-00623.pdf, lot map 623.pdf, wldn2ns00623.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126183 |  |  |  | 7632-2C41552 |  | 2021-08-14 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00622 | Frank Paraha | 2021-06-07 05:45 | Stage 2 - Penneys Road to Moree | Culverts | 635.145, 6/1800x600, remove and rebuild (RRA) | Culverts - Other | Concrete | Nabin Koirala | 635.145 - Cast In Situ Cut Off Wall | 2021-06-07 |  | 2021-07-10 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 |  |  |  | WLD/N2NS/00405, WLD/N2NS/00411 |  |  |  |  | MIX/N2NS/00007 | 635.15 | 635.15 | [6 empty] | HWP/N2NS/00189, HWP/N2NS/00376 | [6 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126175 |  |  |  | 7632-2S72200
WLD/N2NS/00621 | Frank Paraha | 2021-06-07 05:31 | Stage 2 - Penneys Road to Moree | Culverts | 631.580, 1/600x600, remove and rebuild | Culverts - Other | Concrete | Nabin Koirala | 631.580 - Cast In Situ Apron Slab | 2021-06-07 |  | 2021-06-26 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 |  |  |  | WLD/N2NS/00404, WLD/N2NS/00410 |  |  |  |  | MIX/N2NS/00007 | 631.58 | 631.58 | [6 empty] | HWP/N2NS/00186 | [6 empty] | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126170 |  |  |  | 7632-2S72200
WLD/N2NS/00620 | Shane Aberdeen | 2021-06-07 05:28 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Delivery of Precast Rail Large & Small Concrete Box Culvert and Wing Walls - May 2021 | 2021-06-07 |  | 2021-05-31 10:00 | Shane Aberdeen | 2021-06-08 | 2021-06-07 22:34 | Closed | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058, ITP/N2NS/00059, ITP/N2NS/00060 | [9 empty] | MIX/N2NS/00001 | 0 | 0 | Shane Aberdeen | 2021-06-07 22:34 | [5 empty] | Lot closed |  | 2021-06-07 22:34 | [5 empty] | CoCs 029 to 057.pdf, May 2021 Precast Units Delivered Register.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126167 | 2021-06-29 19:15 | Holcim Australia Pty Ltd | PKG/N2NS/00006 |  |  | 2021-06-08 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00619 | Shane Aberdeen | 2021-06-07 05:25 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Delivery of Precast Rail Large & Small Concrete Box Culvert and Wing Walls - April 2021 | 2021-06-07 |  | 2021-04-30 10:00 | Shane Aberdeen | 2021-06-07 | 2021-06-07 05:26 | Closed | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058 | [9 empty] | MIX/N2NS/00001 | 0 | 0 | Shane Aberdeen | 2021-06-07 05:26 | [5 empty] | Lot closed |  | 2021-06-07 05:26 | [5 empty] | CoCs 011 to 029.pdf, April 2021 Precast Units Delivered Register.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126165 | 2021-06-29 19:15 | Holcim Australia Pty Ltd | PKG/N2NS/00006 |  |  | 2021-06-08 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00618 | Shane Aberdeen | 2021-06-07 02:48 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Delivery of Precast Rail Large & Small Concrete Box Culvert and Wing Walls - March 2021 | 2021-06-07 |  | 2021-03-31 11:00 | Shane Aberdeen | 2021-06-07 | 2021-06-07 02:50 | Closed | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058 | [9 empty] | MIX/N2NS/00001 | 0 | 0 | Shane Aberdeen | 2021-06-07 02:50 | [5 empty] | Lot closed |  | 2021-06-07 05:23 | [5 empty] | CoCs 001 to 010.pdf, March 2021 Precast Units Delivered Register.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126133 | 2021-06-29 19:15 | Holcim Australia Pty Ltd | PKG/N2NS/00006 |  |  | 2021-07-06 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00617 | Jeramy Smith | 2021-06-06 23:34 | Stage 2 - Penneys Road to Moree | Temporary Works - Other | Other (Specify Location in Lot) | Temporary Works - Compounds and Laydowns - Other | Other | Ahmad Alwan | Level Crossing 554, Gurley Creek Rd - (Temporary Road) |  |  | 2021-07-07 10:00 |  |  |  | Planned | AMS/N2NS/00004 | [11 empty] | 635.5 | 635.7 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126100
WLD/N2NS/00616 | Jeramy Smith | 2021-06-06 23:29 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Ancillary Works - Other | Other | Ahmad Alwan | Level Crossing 555, GrainCorp- Headwall Installation- DDR2 |  |  | 2021-07-07 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 636.2 | 636.4 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126099
WLD/N2NS/00615 | Jeramy Smith | 2021-06-06 23:28 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Ancillary Works - Other | Other | Ahmad Alwan | Level Crossing 555, GrainCorp- Headwall Installation- DDR1 |  |  | 2021-07-07 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 636.2 | 636.4 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126098
WLD/N2NS/00614 | Jeramy Smith | 2021-06-06 23:27 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Ancillary Works - Other | Other | Ahmad Alwan | LX 1828 DDR2 - Excavation and Foundation Preparation of Drainage Structures | 2021-06-23 |  | 2021-07-07 10:00 | Benjamin Philip | 2021-07-28 | 2021-07-27 23:44 | Closed | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00040 | [9 empty] | 627.75 | 627.95 | Benjamin Philip | 2021-07-27 23:44 |  |  |  |  | HWP/N2NS/00145, HWP/N2NS/00157, HWP/N2NS/00158 | Lot closed |  | 2021-07-27 23:44 |  |  |  | Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  | Test Report.pdf, Survey Report.pdf, Lot Map.pdf, WLDN2NS00614- Checklist.pdf, WLDN2NS00614- LC.pdf, IMG_8078.JPG, IMG_8079.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126097 | 2021-07-29 18:40 |  |  |  |  | 2021-07-30 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00613 | Jeramy Smith | 2021-06-06 23:26 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Ancillary Works - Other | Other | Ahmad Alwan | Level Crossing 1828, Waterloo- Headwall Installation- DDR1 |  |  | 2021-07-07 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 627.75 | 627.95 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126096
WLD/N2NS/00612 | Jeramy Smith | 2021-06-06 23:21 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 648.100, LX3067, Private (Type 1, 9.20m, rubber, unsealed), RX-2 | Landscaping - Other | Earthworks | Ahmad Alwan | LX3067 - Tycannah South SMZ | 2021-08-16 |  | 2021-07-07 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 649.25 | 649.45 | [6 empty] | HWP/N2NS/00435 | [6 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126094
WLD/N2NS/00611 | Jeramy Smith | 2021-06-06 23:19 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 649.350, LX1829, Crown access (Type 2, 6m, rubber, unsealed), RX-2 | Landscaping - Other | Earthworks | Ahmad Alwan | Level Crossing 1829, Tycannah - SMZ |  |  | 2021-07-07 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 649.25 | 649.45 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126093
WLD/N2NS/00610 | Jeramy Smith | 2021-06-06 23:12 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 641.060, LX556, Private (Type 2, 4.50m, rubber, sealed at crossing), RX-2 | Landscaping - Other | Earthworks | Ahmad Alwan | Level Crossing 556, Pad 2- SMZ |  |  | 2021-07-07 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 641.06 | 641.16 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126092
WLD/N2NS/00609 | Jeramy Smith | 2021-06-06 23:08 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Landscaping - Other | Earthworks | Ahmad Alwan | Level Crossing 555, Graincorp- SMZ | 2021-07-12 |  | 2021-07-07 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 634.39 | 643.59 | [6 empty] | HWP/N2NS/00366 | [6 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126090
WLD/N2NS/00608 | Jeramy Smith | 2021-06-06 23:06 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Landscaping - Other | Earthworks | Ahmad Alwan | Level Crossing 3066, Turners Rd- SMZ | 2021-07-23 |  | 2021-07-07 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 634.39 | 634.59 | [6 empty] | HWP/N2NS/00349 | [6 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126089
WLD/N2NS/00607 | Jeramy Smith | 2021-06-06 23:04 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 635.600, LX554, Gurley Creek Road (Type 4, rubber, sealed), RX-5 | Pavements - Level Crossing Pavement | Earthworks | Ahmad Alwan | Level Crossing 554- Gurley Creek Road- SMZ | 2021-08-07 |  | 2021-07-07 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 635.5 | 635.7 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126088
WLD/N2NS/00606 | Jeramy Smith | 2021-06-06 23:03 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Landscaping - Other | Earthworks | Ahmad Alwan | Level Crossing 553 - Kanimbla Road- SMZ | 2021-07-26 |  | 2021-07-07 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 631.05 | 631.25 | [6 empty] | HWP/N2NS/00322, HWP/N2NS/00433 | [6 empty] | Aziz Kamaoui, Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126087
WLD/N2NS/00605 | Jeramy Smith | 2021-06-06 23:02 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Landscaping - Other | Earthworks | Ahmad Alwan | Level Crossing 1828 - SMZ | 2021-07-19 |  | 2021-07-07 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00029 | [9 empty] | 627.75 | 627.95 | [6 empty] | HWP/N2NS/00312 | [6 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126086
WLD/N2NS/00604 | Jeramy Smith | 2021-06-06 22:56 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 635.600, LX554, Gurley Creek Road (Type 4, rubber, sealed), RX-5 | Earthworks - Clearing & Grubbing | Earthworks | Ahmad Alwan | Level Crossing 554 - Gurley Creek Road (Southern Side) | 2021-06-08 |  | 2021-07-07 10:00 | Benjamin Philip | 2021-08-17 | 2021-07-27 | Closed | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010, CHK/N2NS/00011 |  |  |  | WLD/N2NS/00061 | [5 empty] | 635.5 | 635.7 | Benjamin Philip | 2021-08-16 21:00 |  |  |  |  | HWP/N2NS/00139, HWP/N2NS/00188 | Lot closed |  | 2021-08-16 21:00 |  |  |  | Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  | Survey Report.pdf, Lot Map.pdf, 554-2.JPG, 554-1.JPG, WLDN2NS00604- LC.pdf, WLDN2NS00604- Checklists.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126085 | 2021-07-29 18:40 |  |  |  |  | 2021-08-17 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00603 | Jeramy Smith | 2021-06-06 22:53 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Landscaping - Topsoil | Earthworks | Ahmad Alwan | Level Crossing 553 - Kanimbla Road (HWY Section) | 2021-07-19 |  | 2021-07-07 10:00 | Benjamin Philip | 2021-07-27 | 2021-07-27 00:13 | Closed | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010, CHK/N2NS/00011 | [9 empty] | 631.05 | 631.25 | Jeramy Smith | 2021-07-26 23:30 |  |  |  |  | HWP/N2NS/00302, HWP/N2NS/00303 | Lot closed |  | 2021-07-27 00:13 |  |  |  | Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  | Survey Report.pdf, Lot Map.pdf, 648975412.jpg, fff.jpg, WLDN2NS00603- Checklist.pdf, WLDN2NS00603- LC.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126084 | 2021-07-29 18:40 |  |  |  |  | 2021-07-30 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00602 | Kallen Doong | 2021-06-06 07:42 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH628579 to CH628880 - Layer 2 - 400mm | 2021-06-15 |  | 2021-06-13 10:00 | Benjamin Philip | 2021-07-17 | 2021-07-17 05:12 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 628.58 | 628.88 | Benjamin Philip | 2021-07-17 05:12 |  |  |  |  | HWP/N2NS/00232 | Lot closed |  | 2021-07-17 05:12 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_4333.JPG, IMG_4331.JPG, TR0416.pdf, TR0416A (1).pdf, TR0416B.pdf, WAE EX STG2 LOT 602 CH628580-628880.pdf, Test Request 0426 Panda Results.pdf, wldn2ns00602.pdf, TR0433 Panda.pdf, lot map 602.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126078 | 2021-07-29 18:40 |  |  | 7632-2C41552 |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00601 | Nabin Koirala | 2021-06-06 05:02 | Stage 2 - Penneys Road to Moree | Culverts | 630.925, 2/600x600, remove and rebuild (RRA) | Culverts - Other | Concrete | Nabin Koirala | Concrete pour for Cut - off walls 630.925 | 2021-06-22 |  | 2021-06-19 10:00 | Benjamin Philip | 2021-07-27 | 2021-07-10 06:07 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 630.92 | 630.92 | Benjamin Philip | 2021-07-26 21:41 |  |  |  |  | HWP/N2NS/00182 | Lot closed |  | 2021-07-26 21:41 |  |  |  | Emma Conroy, Keegan Baker, Maddie Dahlstrom |  | S66 Balo St21071016330.pdf, 9985A403-CE27-4AAD-B286-443A2AB6B6CD.JPG, 73D2A274-5A31-4DCA-93AD-C3C05BD016A1.JPG, S66 Balo St21071016330.pdf, 630.925_Cut-off Wall Lot Map 7.pdf, WLDN2NS00601 CHECKLIST.pdf, N-21-179-374.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126077 | 2021-07-29 18:40 |  |  |  |  | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00600 | Nabin Koirala | 2021-06-05 07:09 | Stage 2 - Penneys Road to Moree | Culverts | 627.280, 50/3000x2400, remove and rebuild | Culverts - Demolition | Other | Nabin Koirala | Demolition of Existing Culverts 627.280 | 2021-06-22 |  | 2021-06-06 10:00 | Lorne Jenks | 2021-07-09 | 2021-07-09 06:10 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 627.28 | 627.28 | Lorne Jenks | 2021-07-09 06:10 | [5 empty] | Lot closed |  | 2021-07-09 06:10 |  |  |  | Emma Conroy, Frank Paraha, Keegan Baker, Maddie Dahlstrom |  | Signed Checklist & Lot Conformance.pdf, Lot Map.pdf, IMG_0026.JPG, IMG_0032.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126076 | 2021-07-29 18:40 |  |  |  |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00599 | Ben Foster | 2021-06-04 23:29 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 6th June to 12th June 2021 TOTAL QTY - 352.01 Tonnes | 2021-06-06 | 2021-06-12 | 2021-06-12 10:00 | Benjamin Philip | 2021-06-25 | 2021-06-25 05:30 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 0 | 0 | Ben Foster | 2021-06-24 06:48 | [5 empty] | Lot closed |  | 2021-06-25 05:30 | [5 empty] | 1028161 & 1028162.pdf, 1028155.pdf, 1028174 & 1028175.pdf, 1028171 & 1028172.pdf, 1028170.pdf, 1028176-1028177.pdf, 1028160.pdf, 1135009.pdf, 1028179.pdf, 2AT-202106-0087-00076802-F.pdf, 2CH-202106-0007-00076850-F.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126075 | 2021-06-29 19:15 | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551 |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00598 | Ben Foster | 2021-06-04 22:19 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 30th May to 5th June 2021 TOTAL QTY - 418.84 Tonnes | 2021-06-05 | 2021-06-05 | 2021-06-05 10:00 | Lorne Jenks | 2021-07-10 | 2021-06-25 05:32 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 |  |  |  |  | WLD/N2NS/00547, WLD/N2NS/00579, WLD/N2NS/00580, WLD/N2NS/00584, WLD/N2NS/00586 | [5 empty] | 0 | 0 | Lorne Jenks | 2021-07-09 06:05 | [5 empty] | Lot closed |  | 2021-07-09 21:47 |  |  |  | Paddy Montgomery |  | 1028130.pdf, 1069434.pdf, 1028114.pdf, 1028148.pdf, 1028142.pdf, 1028137.pdf, 1028141.pdf, 1028143.pdf, 1028144.pdf, 1028158.pdf, 1069465.pdf, 2AT-202106-0041-00076766-F.pdf, 2CH-202106-0001-00076709-F.pdf, 2CH-202106-0003-00076772-F.pdf, 1028150.pdf, 1028149.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126074 | 2021-07-29 18:40 | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551 |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00597 | Ryan Shenton | 2021-06-04 07:16 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH635.190 to CH635.400 - Layer 2 - 400mm | 2021-06-04 |  | 2021-06-18 10:00 | Sarah Brooks | 2021-08-02 | 2021-08-02 02:03 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00598 | [5 empty] | 635.19 | 635.4 | Sarah Brooks | 2021-08-02 02:03 |  |  |  |  | HWP/N2NS/00323 | Lot closed |  | 2021-08-02 02:03 |  |  |  | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0398.pdf, Test Request 398 Panda Results.pdf, TR0399 Panda Results.pdf, TR0398 A.pdf, E3 Stabilised Fill Layer 2 Ch 635190 to Ch 635400 Lot WLD-N2NS-00597.pdf, 366F7182-E76C-4E93-8912-A87D034899C6.JPG, 6E10DDB6-3583-4D33-9421-6C310E3CC4F8.JPG, wldn2ns00597.pdf, lot map 597.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126071 |  |  |  | 7632-2C41552 |  | 2021-08-02 | Sarah Brooks | Submitted to ARTC for Review
WLD/N2NS/00596 | Ryan Shenton | 2021-06-04 05:58 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Stage 2 - CH641.140 to CH641.390 - Cut Incl. Ground Preparation | 2021-06-04 |  | 2021-06-18 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 641.15 | 641.4 |  |  |  | PNC/N2NS/00086 | Closed |  | HWP/N2NS/00181, HWP/N2NS/00216 | [6 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_4375.JPG, IMG_4377.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126063 |  |  |  | 7632-2C41220
WLD/N2NS/00595 | Miaya Tighe | 2021-06-03 06:05 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Capping | Earthworks | Arjan Sidhu | JCQ Runnymede Capping Supply - 4000T Stockpile 12 | 2021-06-03 |  | 2021-07-03 10:00 | Sarah Brooks | 2021-06-03 | 2021-06-03 06:23 | Closed | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 625.55 | 667 | Miaya Tighe | 2021-06-03 06:06 | [5 empty] | Lot closed |  | 2021-06-03 06:23 |  |  |  | Brett Jenkins, Jake Mossman, Miaya Tighe |  | RU Capping Lot 12-21 3-6-21.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126013 | 2021-06-29 19:15 |  |  |  |  | 2021-06-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00594 | Miaya Tighe | 2021-06-03 05:59 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Capping | Earthworks | Arjan Sidhu | JCQ Runnymede Capping Supply - 4000T Stockpile 11 | 2021-06-03 |  | 2021-07-03 10:00 | Lorne Jenks | 2021-07-13 | 2021-06-03 06:22 | Closed | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 625.55 | 667 | Miaya Tighe | 2021-07-12 22:20 | [5 empty] | Lot closed |  | 2021-07-13 06:49 |  |  |  | Brett Jenkins, Jake Mossman, Miaya Tighe |  | RU Capping Lot 11-21 17-5-21.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126012 | 2021-07-29 18:40 |  |  |  |  | 2021-07-17 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00593 | Miaya Tighe | 2021-06-03 05:54 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Arjan Sidhu | Capping Installation Penneys Road to Culvert 627.280: CH 625.9 - CH 626.1 | 2021-06-28 |  | 2021-07-09 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 |  |  |  | WLD/N2NS/00070 | [5 empty] | 625.9 | 626.1 | [6 empty] | HWP/N2NS/00223, HWP/N2NS/00438 | [6 empty] | Arjan Sidhu, Jake Mossman, Jarryd Davis, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/126009 |  |  |  | 7632-2C47051
WLD/N2NS/00592 | James Martin | 2021-06-03 02:31 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Topsoil Removal | Earthworks | James Martin | Topsoil Removal - Stage 2 - CH633840 to CH635700 | 2021-06-03 |  | 2021-06-05 10:00 | Lorne Jenks | 2021-07-14 | 2021-07-14 03:54 | Closed | AMS/N2NS/00001 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 633.84 | 635.7 | Lorne Jenks | 2021-07-14 03:54 | [5 empty] | Lot closed |  | 2021-07-14 03:54 |  |  |  | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | wldn2ns00592.pdf, Stripped Topsoil Quantity Report Ch 633810 to CH 635707 Lot WLD-N2NS-00592.pdf, lot map 592.pdf, 64B3EBE9-2DA9-4983-9CF3-5EEA29EB457B.JPG, C02E54B2-099A-4E64-9FE7-3DA454D9EC79.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125988 | 2021-07-29 18:40 |  |  | 7632-2C41190 |  | 2021-07-17 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00591 | James Martin | 2021-06-02 23:59 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | James Martin | Type E3 - Stage 2 - CH640060 to CH640280 - Layer 1 - 400mm | 2021-06-03 |  | 2021-06-04 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 640.06 | 640.28 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0388.pdf, test Request 388 Panda Results.pdf, Test Request 389 Panda Results.pdf, IMG_4142.JPG, IMG_4141.JPG, TR0388A.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125977 |  |  |  | 7632-2C41552
WLD/N2NS/00590 | James Martin | 2021-06-02 23:47 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | James Martin | Type E3 - Stage 2 - CH635.430 to CH635.660 - Layer 2 - 400mm | 2021-06-03 |  | 2021-06-04 10:00 | Sarah Brooks | 2021-08-03 | 2021-08-03 04:34 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00598 | [5 empty] | 635.43 | 635.66 | Sarah Brooks | 2021-08-03 04:34 |  |  |  |  | HWP/N2NS/00323 | Lot closed |  | 2021-08-03 04:34 |  |  |  | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Day 3 Pandas.pdf, Gradings.pdf, Day 7 UCS.pdf, Day 0 Compaction.pdf, Day 0 Pandas.pdf, E3 Stabilised Layer 2 Ch 635430 to Ch 635660Lot WLD-N2NS-00590.pdf, FC2F8F5E-F010-48D5-8510-7779EB45671A.JPG, 5F923B04-3CA2-4E8A-BBF9-68C5C6FA30C6.JPG, wldn2ns00590.pdf, lot map 590.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125975 |  |  |  | 7632-2C41552 |  | 2021-08-16 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00589 | James Martin | 2021-06-02 23:42 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH634550 to CH634700 - Layer 1 - 400mm | 2021-07-13 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 634.55 | 634.7 | [13 empty] | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | E3 Stabilised Layer 1 WLD-N2NS-00589.pdf, N-21-179-597.pdf, N-21-179-622.pdf, Test Request 0700 Panda Results.pdf, N-21-179-653.pdf, Test Request 0716 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125974 |  |  |  | 7632-2C41552
WLD/N2NS/00588 | Arjan Sidhu | 2021-06-02 23:36 | Stage 2 - Penneys Road to Moree | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Arjan Sidhu | Capping Placement - CH 635.750 - CH636.35 | 2021-06-06 |  | 2021-06-25 10:00 |  |  |  | Open | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023 | [9 empty] | 635.75 | 636.35 | [6 empty] | HWP/N2NS/00208 | [6 empty] | Arjan Sidhu, Jake Mossman, Jarryd Davis, Miaya Tighe |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125973 |  |  |  | 7632-2C47051
WLD/N2NS/00587 | James Martin | 2021-06-02 02:54 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | James Martin | Type E3 - Stage 2 - CH637.630 to CH637.940 - Layer 2 - 400mm | 2021-06-06 |  | 2021-06-21 10:00 | Lorne Jenks | 2021-07-14 | 2021-07-14 03:59 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00599 | [5 empty] | 637.63 | 637.94 | Lorne Jenks | 2021-07-14 03:59 |  |  |  |  | HWP/N2NS/00255 | Lot closed |  | 2021-07-14 03:59 |  |  |  | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_4159.JPG, IMG_4156.JPG, Test request 409 Panda Results.pdf, TR0423 Panda.pdf, TR0409A.pdf, TR0409.pdf, TR0409B.pdf, TR0409D.pdf, TR0409C.pdf, E3 Stabilised Fill Layer 2 Ch 637630 - Ch 637820 Lot WLD-N2NS-00587.pdf, wldn2ns00587.pdf, lot map 587.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125943 | 2021-07-29 18:40 |  |  | 7632-2C41552 |  | 2021-07-17 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00586 | Kallen Doong | 2021-06-01 07:16 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH628052 to CH628444 Maintenance Siding - Layer 2 - 400mm | 2021-07-01 |  | 2021-06-06 10:00 | Lorne Jenks | 2021-07-08 | 2021-07-08 00:41 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00598 | [5 empty] | 628.05 | 628.44 | Lorne Jenks | 2021-07-08 00:41 |  |  |  |  | HWP/N2NS/00232 | Lot closed |  | 2021-07-08 00:41 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Test Request 402 Panda Results.pdf, TR0392D.pdf, Test Request 392 Panda results.pdf, TR0392C.pdf, TR0392B.pdf, TR0392 A.pdf, E3 Stabilised Fill Layer 2 Ch 628052 to Ch 628444 Lot WLD-N2NS-00586.pdf, wldn2ns00586.pdf, lot map 586.pdf, 586b.jpg, 586a.jpg | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125888 | 2021-07-29 18:40 |  |  |  |  | 2021-07-19 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00585 | Keegan Baker | 2021-06-01 07:13 | Stage 2 - Penneys Road to Moree | Culverts | 631.140, 3/1800x900, remove and rebuild | Drainage - Other | Earthworks | Keegan Baker | 631.140 - Excavation and Foundation Preparation of Drainage Structure | 2021-06-23 |  | 2021-06-22 10:00 | Lorne Jenks | 2021-07-12 | 2021-07-12 01:45 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 631.14 | 631.14 | Maddie Dahlstrom | 2021-07-12 01:43 |  |  |  |  | HWP/N2NS/00178, HWP/N2NS/00205 | Lot closed |  | 2021-07-12 01:45 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | Signed Lot Conformance & Checklist.pdf, Test Request 0375 Panda Results (631.140 Panda).pdf, N-21-179-286 - Post Stabe Compaction.pdf, WLD N2NS 585_SWR422_Culvert 631140 Unsuitable Removal.pdf, Lot Map.pdf, IMG_0365.JPG, 631.140.png | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125887 | 2021-07-29 18:40 |  |  |  |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00584 | James Martin | 2021-06-01 06:54 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | James Martin | Type E3 - Stage 2 - CH638900 to CH640060 - Layer 1 - 400mm | 2021-06-01 |  | 2021-06-02 10:00 | Lorne Jenks | 2021-07-09 | 2021-07-09 06:07 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00598 | [5 empty] | 638.9 | 640.06 | Lorne Jenks | 2021-07-09 06:06 | [5 empty] | Lot closed |  | 2021-07-09 06:07 |  |  |  | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Day 0 Pandas.pdf, Day 3 Pandas.pdf, Day 7 UCS (3).pdf, Gradings.pdf, Day 0 Compaction.pdf, Day 7 UCS.pdf, Day 7 UCS (2).pdf, E3 Stabilised Fill Layer 1 Ch 638900 to Ch 640060 Lot WLD-N2NS-00584.pdf, WLDN2NS00584 - 2.JPG, WLDN2NS00584 - 1.JPG, wldn2ns00584.pdf, lot 584.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125885 | 2021-07-29 18:40 |  |  | 7632-2C41552 |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00583 | Keegan Baker | 2021-06-01 06:43 | Stage 2 - Penneys Road to Moree | Culverts | 631.140, 3/1800x900, remove and rebuild | Culverts - Demolition | Other | Keegan Baker | 631.140 - Demolition of Existing Culvert | 2021-06-01 |  | 2021-05-11 10:00 | Lorne Jenks | 2021-06-24 | 2021-06-23 21:18 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 631.14 | 631.14 | Keegan Baker | 2021-06-20 08:19 | [5 empty] | Lot closed |  | 2021-06-23 21:18 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala |  | Lot Map.pdf, IMG_0366.JPG, IMG_0132.JPG, WLD-N2NS 00583 - signed checklistpdf.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125884 | 2021-06-29 19:15 |  |  |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00582 | Johannes Mason | 2021-06-01 01:54 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Bridgeworks | Offsite Manufacture/Supply - Prestressed Concrete Deck and Kerb Units | Concrete | Johannes Mason | Manufacture of Precast Pre-stressed Deck Units - August 2021 | 2021-06-01 |  | 2021-08-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00062 | [9 empty] | MIX/N2NS/00002 | 0 | 0 | [6 empty] | HWP/N2NS/00173, HWP/N2NS/00174 | [9 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125869 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/00581 | Johannes Mason | 2021-06-01 01:53 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Bridgeworks | Offsite Manufacture/Supply - Prestressed Concrete Deck and Kerb Units | Concrete | Johannes Mason | Manufacture of Precast Pre-stressed Deck Units - July 2021 | 2021-06-01 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00062 | [9 empty] | MIX/N2NS/00002 | 0 | 0 | [6 empty] | HWP/N2NS/00171, HWP/N2NS/00172, HWP/N2NS/00173, HWP/N2NS/00174 | [9 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125868 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/00580 | Kallen Doong | 2021-05-31 07:32 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH630942 to CH631565 - Layer 1 - 400mm | 2021-06-28 |  | 2021-06-09 10:00 | Benjamin Philip | 2021-06-28 | 2021-06-28 04:10 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00598 | [5 empty] | 630.94 | 631.57 | Benjamin Philip | 2021-06-28 04:10 | [5 empty] | Lot closed |  | 2021-06-28 04:10 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0366A.pdf, TR0366.pdf, TR0366 Panda.pdf, TR0366 C.pdf, TR0366 B.pdf, E3 Stabilised Fill Layer 1 Conformance Report Ch 630940 to Ch 631560 Lot WLD-N2NS-00580.pdf, Test Request 370 Panda Results.pdf, 64F9F396-711D-41E7-BF8A-CC7439E6F29A.JPG, F9834E10-5436-400A-B698-501057E6B089.JPG, wldn2ns00580.pdf, lot map 580.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125831 | 2021-06-29 19:15 |  |  | 7632-2C41552 |  | 2021-07-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00579 | Kallen Doong | 2021-05-31 07:14 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH630.493 to CH630.748 - Layer 1 - Siding - 400mm | 2021-06-01 |  | 2021-06-09 10:00 | Lorne Jenks | 2021-06-15 | 2021-06-15 06:12 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00598 | [5 empty] | 630.49 | 630.75 | Paddy Montgomery | 2021-06-15 |  |  |  |  | HWP/N2NS/00184 | Lot closed |  | 2021-06-15 06:12 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | E3 Stabilised Layer 1 Ch 630493 to Ch 630748 Lot WLD-N2NS-00579.pdf, TR0363A.pdf, Test Request 371 Panda Results.pdf, TR0362 Panda.pdf, TR0362.pdf, IMG_4312.JPG, IMG_4311.JPG, wldn2ns00579.pdf, lot map 579.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125825 | 2021-06-29 19:15 |  |  | 7632-2C41552 |  | 2021-06-28 | Benjamin Philip | ARTC Accepted (Conforming)
WLD/N2NS/00578 | Maddie Dahlstrom | 2021-05-31 04:46 | Stage 2 - Penneys Road to Moree | Culverts | 647.155, 40/3000x2400, remove and rebuild | Culverts - Other | Earthworks | Frank Paraha | 647.155 - Excavation & Foundation Preparation (South) | 2021-07-24 |  | 2021-08-14 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 |  |  |  | WLD/N2NS/00081, WLD/N2NS/00570 | [5 empty] | 647.16 | 647.16 | [6 empty] | HWP/N2NS/00394 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125807 |  |  |  | 7632-2C41460
WLD/N2NS/00577 | Maddie Dahlstrom | 2021-05-31 04:44 | Stage 2 - Penneys Road to Moree | Culverts | 647.315, 10/3000x1200, remove and rebuild | Culverts - Other | Other | Frank Paraha | (DELETE OR REPURPOSE) Excavation & Foundation Prep of Drainage Structures |  |  | 2021-06-30 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 647.32 | 647.32 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125806
WLD/N2NS/00576 | Maddie Dahlstrom | 2021-05-31 04:43 | Stage 2 - Penneys Road to Moree | Culverts | 647.670, 10/3000x1500, remove and rebuild | Culverts - Other | Earthworks | Frank Paraha | 647.670 - Excavation & Foundation Preparation | 2021-07-24 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 647.67 | 647.67 | [6 empty] | HWP/N2NS/00358, HWP/N2NS/00359 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125805 |  |  |  | 7632-2C41460
WLD/N2NS/00575 | Maddie Dahlstrom | 2021-05-31 04:41 | Stage 2 - Penneys Road to Moree | Culverts | 649.185, 2/1800x600, remove and rebuild | Culverts - Other | Earthworks | Frank Paraha | 649.185 - Excavation & Foundation Preparation | 2021-06-24 |  | 2021-08-31 10:00 | Benjamin Philip | 2021-08-15 | 2021-08-04 22:18 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 |  |  |  | WLD/N2NS/00089, WLD/N2NS/00598, WLD/N2NS/01333 | [5 empty] | 649.19 | 649.19 | Maddie Dahlstrom | 2021-08-11 04:40 |  |  |  |  | HWP/N2NS/00160 | Lot closed |  | 2021-08-15 04:12 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS00575LM.pdf, WLDN2NS00575.pdf, IMG_0327.jpg, IMG_0326.jpg, IMG_0329.jpg, IMG_0332.jpg, IMG_0331.jpg, IMG_0330.jpg, IMG_0328.jpg, KPA Letter 274.pdf, N-21-179-277.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125804 |  |  |  | 7632-2S72150 |  | 2021-08-15 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00574 | Maddie Dahlstrom | 2021-05-31 04:40 | Stage 2 - Penneys Road to Moree | Culverts | 650,040 NEW | Culverts - Other | Earthworks | Frank Paraha | 650.040 - Excavation & Foundation Preparation | 2021-06-24 |  | 2021-06-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 650.04 | 650.04 | [6 empty] | HWP/N2NS/00161 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS00574LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125803 |  |  |  | 7632-2C41460
WLD/N2NS/00573 | Maddie Dahlstrom | 2021-05-31 04:38 | Stage 2 - Penneys Road to Moree | Culverts | 652.530, 2/1800x600, remove and rebuild | Culverts - Other | Earthworks | Frank Paraha | 652.530 - Excavation & Foundation Preparation | 2021-06-24 |  | 2021-06-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 |  |  |  | WLD/N2NS/01334, WLD/N2NS/01387, WLD/N2NS/01448 | [5 empty] | 652.53 | 652.53 | [6 empty] | HWP/N2NS/00162, HWP/N2NS/00242 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS00573LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125802 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/00572 | Maddie Dahlstrom | 2021-05-31 04:37 | Stage 2 - Penneys Road to Moree | Culverts | 652.715, 1/1800x600, remove and rebuild | Culverts - Other | Earthworks | Frank Paraha | 652.715 - Excavation & Foundation Preparation | 2021-06-25 |  | 2021-06-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 |  |  |  | WLD/N2NS/00567, WLD/N2NS/01062, WLD/N2NS/01388, WLD/N2NS/01449 | [5 empty] | 652.72 | 652.72 | [6 empty] | HWP/N2NS/00163 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS00572LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125801 |  |  |  | 7632-2S72150
WLD/N2NS/00571 | Maddie Dahlstrom | 2021-05-31 04:35 | Stage 2 - Penneys Road to Moree | Culverts | 653.150, 1/600x600, remove and rebuild | Culverts - Other | Other | Frank Paraha | 653.150 - Excavation & Foundation Preparation - Culvert Base | 2021-06-25 |  | 2021-06-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 |  |  |  | WLD/N2NS/00708, WLD/N2NS/01390, WLD/N2NS/01450 | [5 empty] | 653.15 | 653.15 | [6 empty] | HWP/N2NS/00164 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS00571LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125800 |  |  |  | 7632-2C41460
WLD/N2NS/00570 | Maddie Dahlstrom | 2021-05-31 04:32 | Stage 2 - Penneys Road to Moree | Culverts | 647.155, 40/3000x2400, remove and rebuild | Culverts - Demolition | Other | Frank Paraha | 647.155 - Demolition of Existing Structures (South) | 2021-07-11 |  | 2021-06-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 |  |  |  | WLD/N2NS/00578 | [5 empty] | 647.16 | 647.16 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS00570LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125799 |  |  |  | 7632-2S41011
WLD/N2NS/00569 | Maddie Dahlstrom | 2021-05-31 04:32 | Stage 2 - Penneys Road to Moree | Culverts | 647.315, 10/3000x1200, remove and rebuild | Culverts - Demolition | Other | Frank Paraha | 647.315 - Demolition of Existing Structures | 2021-07-07 |  | 2021-06-30 10:00 | Sarah Brooks | 2021-08-02 | 2021-08-02 02:12 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 |  |  |  | WLD/N2NS/00082, WLD/N2NS/01322 | [5 empty] | 647.32 | 647.32 | Maddie Dahlstrom | 2021-08-02 01:19 | [5 empty] | Lot closed |  | 2021-08-02 02:12 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS00569LM.pdf, IMG_0281.JPG, IMG_0286.JPG, IMG_0282.JPG, WLDN2NS00569.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125798 |  |  |  | 7632-2S41011 |  | 2021-08-02 | Sarah Brooks | Submitted to ARTC for Review
WLD/N2NS/00568 | Maddie Dahlstrom | 2021-05-31 04:30 | Stage 2 - Penneys Road to Moree | Culverts | 647.670, 10/3000x1500, remove and rebuild | Culverts - Demolition | Other | Frank Paraha | 647.670 - Demolition of Existing Structures | 2021-07-11 |  | 2021-07-15 10:00 | Sarah Brooks | 2021-08-02 | 2021-08-02 02:06 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 647.67 | 647.67 | Maddie Dahlstrom | 2021-08-01 23:18 | [5 empty] | Lot closed |  | 2021-08-02 02:06 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS00568LM.pdf, MicrosoftTeams-image (2).png, MicrosoftTeams-image (3).png, WLDN2NS00568.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125797 |  |  |  | 7632-2S41011 |  | 2021-08-02 | Sarah Brooks | Submitted to ARTC for Review
WLD/N2NS/00567 | Maddie Dahlstrom | 2021-05-31 04:28 | Stage 2 - Penneys Road to Moree | Culverts | 652.715, 1/1800x600, remove and rebuild | Culverts - Demolition | Other | Frank Paraha | 652.715 - Demolition of Existing Structures | 2021-06-19 |  | 2021-06-30 10:00 | Lorne Jenks | 2021-06-23 | 2021-06-23 00:09 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 652.71 | 652.72 | Maddie Dahlstrom | 2021-06-21 04:34 | [5 empty] | Lot closed |  | 2021-06-23 00:09 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | 652.715 Demo - Concrete.jpg, 652.715 Demo - CMP's.jpg, IMG_0592 (1).JPG, IMG_0593 (1).JPG, WLDN2NS00567.pdf, WLDN2NS00567.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125795 | 2021-06-29 19:15 |  |  | 7632-2S41011 |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00566 | Maddie Dahlstrom | 2021-05-31 04:27 | Stage 2 - Penneys Road to Moree | Culverts | 653.150, 1/600x600, remove and rebuild | Culverts - Demolition | Other | Frank Paraha | 653.150 - Demolition of Existing Structures | 2021-06-19 |  | 2021-06-30 10:00 | Lorne Jenks | 2021-06-23 | 2021-06-23 00:09 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 653.12 | 653.18 | Maddie Dahlstrom | 2021-06-21 04:40 | [5 empty] | Lot closed |  | 2021-06-23 00:09 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | 653.150 Demo - Concrete + Timber Sleepers.jpg, 653.150 Demo - Concrete.jpg, IMG_0590.JPG, IMG_0591.JPG, WLDN2NS00566.pdf, WlDN2NS00566.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125794 | 2021-06-29 19:15 |  |  | 7632-2S41011 |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00565 | Maddie Dahlstrom | 2021-05-31 03:02 | Stage 2 - Penneys Road to Moree | Culverts | 652.530, 2/1800x600, remove and rebuild | Culverts - Demolition | Other | Frank Paraha | 652.530 - Demolition of Existing Structures | 2021-06-16 |  | 2021-06-30 10:00 | Lorne Jenks | 2021-06-23 | 2021-06-23 01:36 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 652.53 | 652.53 | Maddie Dahlstrom | 2021-06-23 01:17 |  |  |  |  | HWP/N2NS/00192 | Lot closed |  | 2021-06-23 01:36 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | 652.530 Demo - CMP's.jpg, IMG_0609.JPG, IMG_0608.JPG, IMG_0607.JPG, IMG_0594.JPG, IMG_0606.JPG, IMG_0595.JPG, IMG_0592.JPG, WLDN2NS00565.pdf, WLDN2NS00565.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125789 | 2021-06-29 19:15 |  |  | 7632-2S41011 |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00564 | Maddie Dahlstrom | 2021-05-31 02:59 | Stage 2 - Penneys Road to Moree | Culverts | 649.185, 2/1800x600, remove and rebuild | Culverts - Demolition | Other | Frank Paraha | 649.185 - Demolition of Existing Structures | 2021-06-23 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-06-28 | 2021-06-27 23:31 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 649.19 | 649.19 | Frank Paraha | 2021-06-27 07:53 | [5 empty] | Lot closed |  | 2021-06-27 23:31 |  |  |  | Emma Conroy, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | 649.185 Demo - Timber (2).JPG, 649.185 Demo - CMP.JPG, 649.185 Demo - Timber.JPG, Lot Conformance Report - Lot 564 - 649.185 Demo.pdf, Completed Checklist - Lot 564 - 649.185 Demo.pdf, Lot Map - Lot 564 - 649.185 Demo.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125788 | 2021-06-29 19:15 |  |  |  |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00563 | James Martin | 2021-05-31 01:39 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | James Martin | Type E3 - CH638.500 to CH638.900 - Layer 2 | 2021-05-31 |  | 2021-05-31 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 638.5 | 638.9 | [6 empty] | HWP/N2NS/00336 | [8 empty] | Day 0 Pandas.pdf, Day 3 Pandas.pdf, Day 0 Compaction.pdf, Day 7 UCS.pdf, 50525FD5-C408-4060-B563-03CA45482FE3.JPG, F470C751-195E-427B-B221-E29F33A9EB32.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125776 |  |  |  | 7632-2C41552
WLD/N2NS/00562 | James Martin | 2021-05-31 00:50 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Stage 2 - CH634.550 to CH635.150 - Cut Incl. Ground Preparation | 2021-05-31 |  | 2021-05-31 10:00 | Benjamin Philip | 2021-07-04 | 2021-07-04 01:10 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 634.55 | 635.15 | James Martin | 2021-07-04 00:04 |  |  |  |  | HWP/N2NS/00156 | Lot closed |  | 2021-07-04 01:10 |  |  |  | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_1149.JPG, IMG_1148.JPG, IMG_1147.JPG, Excavation Foundation Ch 634550 to Ch 635190 Lot WLD-N2NS-00562.pdf, lot map 562.pdf, WLDN2NS00562 - Completed Checklist.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125768 | 2021-07-29 18:40 |  |  | 7632-2C41220 |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00561 | Keegan Baker | 2021-05-30 22:57 | Stage 2 - Penneys Road to Moree | Culverts | 627.280, 50/3000x2400, remove and rebuild | Drainage - Other | Earthworks | Keegan Baker | 627.280 - Excavation and Foundation Preparation of Drainage Structure | 2021-06-23 |  | 2021-06-22 10:00 | Benjamin Philip | 2021-08-15 | 2021-07-31 05:26 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 |  |  |  | WLD/N2NS/00599 | [5 empty] | 627.28 | 627.28 | Benjamin Philip | 2021-08-15 04:24 |  |  |  |  | HWP/N2NS/00165 | Lot closed |  | 2021-08-15 04:24 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | N-21-179-194 (DCP).pdf, TR0265 (DCP).pdf, Test Request 0265 Panda Results.pdf, 627.280.png, IMG_0170.JPG, N-21-179-317.pdf, Lot Map.pdf, Signed Lot Conformance & Checklist (7).pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125759 | [5 empty] | 2021-08-15 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00560 | Keegan Baker | 2021-05-30 06:03 | Stage 2 - Penneys Road to Moree | Culverts | 627.760, 10/2400x1200, new build | Drainage - Other | Earthworks | Keegan Baker | 627.760 - Excavation and Foundation Preparation of Drainage Structure | 2021-06-22 |  | 2021-06-30 10:00 | Lorne Jenks | 2021-07-12 | 2021-07-11 23:02 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 627.76 | 627.76 | Maddie Dahlstrom | 2021-07-11 22:07 |  |  |  |  | HWP/N2NS/00154, HWP/N2NS/00190 | Lot closed |  | 2021-07-11 23:02 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | Signed Lot Conformance & Checklist.pdf, Test Request 0348 Panda Results.pdf, N-21-179-285 (Compaction).pdf, WLD N2NS 560_SWR421_Culvert 627760 Unsuitable Removal .pdf, Lot Map.pdf, IMG_0280.JPG, 627.760.png | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125757 | 2021-07-29 18:40 |  |  |  |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00559 | James Martin | 2021-05-30 05:53 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Stage 2 - CH638.900 to CH640.280 - Cut Incl. Ground Preparation | 2021-05-30 |  | 2021-05-31 10:00 | Benjamin Philip | 2021-07-04 | 2021-07-04 01:06 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 638.9 | 640.28 | James Martin | 2021-07-04 00:09 |  |  |  |  | HWP/N2NS/00153 | Lot closed |  | 2021-07-04 01:06 |  |  |  | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_1154.JPG, IMG_1153.JPG, Excavation Foundation Ch 638900 to Ch 640280 Lot WLD-N2NS-00559.pdf, lot map 559.pdf, WLDN2NS00559 - Completed Checklist.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125756 | 2021-07-29 18:40 |  |  | 7632-2C41220 |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00558 | Nabin Koirala | 2021-05-30 05:39 | Stage 3 - Camurra North to North Star | Culverts | 711.510, 6/3000x1200, remove and rebuild | Culverts - Other | Concrete | Nabin Koirala | Concrete pour - Base Slab 711.510 | 2021-06-22 |  | 2021-06-03 10:00 | Benjamin Philip | 2021-07-19 | 2021-07-10 03:47 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 711.51 | 711.51 | Benjamin Philip | 2021-07-19 06:53 |  |  |  |  | HWP/N2NS/00152 | Lot closed |  | 2021-07-19 06:53 | [5 empty] | Concrete 28 Days Results _ N-21-186-74.pdf, LLP0037_N2NS_00558_0000.pdf, Concrete Pour Record.pdf, Lot COnformance Report.pdf, IMG_0649.JPG, IMG_0651.JPG, Lot Map_711.510 Cast In Situ Base Slab.pdf, Checklist WL 00558.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125755 | 2021-07-29 18:40 |  |  |  |  | 2021-08-01 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00557 | Nabin Koirala | 2021-05-29 22:32 | Stage 3 - Camurra North to North Star | Culverts | 709.740, 5/2400x900, remove and rebuild | Culverts - Other | Other | Nabin Koirala | Excavation and Foundation Preparation of Drainage Structures | 2021-07-11 |  | 2021-06-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00040 | [9 empty] | 709.74 | 709.74 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125754
WLD/N2NS/00556 | Nabin Koirala | 2021-05-29 22:32 | Stage 3 - Camurra North to North Star | Culverts | 708.445, 13/3000x1200, remove and rebuild (RRA) | Culverts - Other | Other | Nabin Koirala | Excavation and Foundation Preparation of Drainage Structures | 2021-07-11 |  | 2021-06-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00040 | [9 empty] | 707.45 | 708.45 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125753
WLD/N2NS/00555 | Nabin Koirala | 2021-05-29 22:31 | Stage 3 - Camurra North to North Star | Culverts | 707.575, 8/1800x600, remove and rebuild (RRA) | Culverts - Other | Other | Nabin Koirala | Excavation and Foundation Preparation of Drainage Structures | 2021-06-25 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-06-28 | 2021-06-27 23:39 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00040 | [9 empty] | 707.58 | 707.58 | Benjamin Philip | 2021-06-27 23:39 |  |  |  |  | HWP/N2NS/00194, HWP/N2NS/00202 | Lot closed |  | 2021-06-27 23:39 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | 707.575 _ Checklist.pdf, Test Request 0482 Culvert Ch 707.575.pdf, Test Request 0482 Panda Results.pdf, QAS.pdf, 707.575 707.405 706.695.pdf, IMG_0857.JPG, IMG_0856 (1).JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125752 | 2021-06-29 19:15 |  |  |  |  | 2021-07-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00554 | Nabin Koirala | 2021-05-29 22:30 | Stage 3 - Camurra North to North Star | Culverts | 707.405, 2/1800x600, remove and rebuild (RRA) | Culverts - Other | Other | Nabin Koirala | Excavation and Foundation Preparation of Drainage Structures | 2021-06-25 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-06-28 | 2021-06-27 23:36 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00040 | [9 empty] | 707.41 | 707.41 | Benjamin Philip | 2021-06-27 23:36 |  |  |  |  | HWP/N2NS/00193, HWP/N2NS/00201 | Lot closed |  | 2021-06-27 23:36 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | 707.405_Checklist.pdf, N-21-186-79.pdf, Test Request 0479 Panda Results Culvert Ch 707405.pdf, 707.575 707.405 706.695.pdf, QAS.pdf, IMG_0856.JPG, IMG_0746.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125751 | 2021-06-29 19:15 |  |  |  |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00553 | Nabin Koirala | 2021-05-29 22:30 | Stage 3 - Camurra North to North Star | Culverts | 706.695, 3/1200x600, remove and rebuild (RRA) | Culverts - Other | Other | Nabin Koirala | Excavation and Foundation Preparation of Drainage Structures | 2021-06-25 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-06-28 | 2021-06-27 23:42 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00040 | [9 empty] | 706.7 | 706.7 | Benjamin Philip | 2021-06-27 22:42 |  |  |  |  | HWP/N2NS/00195, HWP/N2NS/00200 | Lot closed |  | 2021-06-27 23:42 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | 706.695_ Checklist.pdf, Test Request 0479 Panda Results Culvert Ch 706695.pdf, N-21-186-80.pdf, 707.575 707.405 706.695.pdf, 706.695_QAS.pdf, IMG_0782.JPG, IMG_0783.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125750 | 2021-06-29 19:15 |  |  |  |  | 2021-07-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00552 | Nabin Koirala | 2021-05-29 07:14 | Stage 3 - Camurra North to North Star | Culverts | 709.740, 5/2400x900, remove and rebuild | Culverts - Demolition | Other | Nabin Koirala | Demolition of Existing Culverts | 2021-06-21 |  | 2021-05-31 10:00 | Lorne Jenks | 2021-06-23 | 2021-06-23 00:54 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 709.74 | 709.74 | Maddie Dahlstrom | 2021-06-21 05:04 | [5 empty] | Lot closed |  | 2021-06-23 00:54 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | Demo 1.JPG, Demo 2.JPG, WLDN2NS00552.pdf, WLDN2NS00552.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125745 | 2021-06-29 19:15 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00551 | Nabin Koirala | 2021-05-29 07:14 | Stage 3 - Camurra North to North Star | Culverts | 708.445, 13/3000x1200, remove and rebuild (RRA) | Culverts - Demolition | Other | Nabin Koirala | Demolition of Existing Culverts | 2021-06-21 |  | 2021-05-31 10:00 | Lorne Jenks | 2021-06-23 | 2021-06-23 00:38 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 708.45 | 708.45 | Maddie Dahlstrom | 2021-06-21 05:01 | [5 empty] | Lot closed |  | 2021-06-23 00:38 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | Demo 2.JPG, Demo 1.JPG, WLDN2NS00551.pdf, WLDN2NS00551.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125744 | 2021-06-29 19:15 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00550 | Nabin Koirala | 2021-05-29 07:13 | Stage 3 - Camurra North to North Star | Culverts | 707.575, 8/1800x600, remove and rebuild (RRA) | Culverts - Demolition | Other | Nabin Koirala | Demolition of Existing Culverts | 2021-06-21 |  | 2021-05-31 10:00 | Lorne Jenks | 2021-06-23 | 2021-06-23 00:47 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 707.58 | 707.58 | Lorne Jenks | 2021-06-23 00:46 | [5 empty] | Lot closed |  | 2021-06-23 00:47 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | IMG_0564.JPG, IMG_0567.JPG, IMG_0565.JPG, IMG_0566.JPG, WLDN2NS00550.pdf, WLDN2NS00550.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125743 | 2021-06-29 19:15 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00549 | Nabin Koirala | 2021-05-29 07:12 | Stage 3 - Camurra North to North Star | Culverts | 707.405, 2/1800x600, remove and rebuild (RRA) | Culverts - Demolition | Other | Nabin Koirala | Demolition of Existing Culverts | 2021-06-21 |  | 2021-05-31 10:00 | Lorne Jenks | 2021-06-23 | 2021-06-23 00:50 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 707.41 | 707.41 | Maddie Dahlstrom | 2021-06-21 04:54 | [5 empty] | Lot closed |  | 2021-06-23 00:50 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | Demo 2.JPG, Demo 1.JPG, WLDN2NS00549.pdf, WLDN2NS00549.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125742 | 2021-06-29 19:15 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00548 | Nabin Koirala | 2021-05-29 07:11 | Stage 3 - Camurra North to North Star | Culverts | 706.695, 3/1200x600, remove and rebuild (RRA) | Culverts - Demolition | Other | Nabin Koirala | Demolition of Existing Culverts | 2021-06-21 |  | 2021-05-31 10:00 | Lorne Jenks | 2021-06-23 | 2021-06-23 00:50 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 706.7 | 706.7 | Maddie Dahlstrom | 2021-06-21 04:48 | [5 empty] | Lot closed |  | 2021-06-23 00:50 |  |  |  | Brendan Meagher, Emma Conroy, Maddie Dahlstrom, Nabin Koirala |  | Demo 2.JPG, Demo 1.JPG, WLDN2NS00548.pdf, WLDN2NS00548.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125741 | 2021-06-29 19:15 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00547 | Kallen Doong | 2021-05-29 06:55 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH630.000 to CH630.493 - Layer 1 - Siding - 400mm | 2021-05-31 |  | 2021-06-09 10:00 | Benjamin Philip | 2021-06-29 | 2021-06-28 21:47 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00598 | [5 empty] | 630 | 630.49 | Benjamin Philip | 2021-06-28 21:47 |  |  |  |  | HWP/N2NS/00184 | Lot closed |  | 2021-06-28 21:47 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0352.pdf, TR0352 Panda.pdf, TR0352 A.pdf, 7E415EF5-46F4-479E-AC61-A92415DBEBE5.JPG, 97557C1C-68EE-4846-AB8D-6665EA3780A5.JPG, E3 Stabilised Layer 1 Ch 630000 to Ch 630493 Lot WLD-N2NS-00547.pdf, TR0563 Panda.pdf, wldn2ns00547.pdf, lot map 547.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125739 | 2021-06-29 19:15 |  |  | 7632-2C41552 |  | 2021-07-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00546 | Arjan Sidhu | 2021-05-29 01:49 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Earthfill | Roadworks | Arjan Sidhu | JCQ General Fill - Use as UZF R44 | 2021-05-29 |  | 2021-06-30 10:00 | Sarah Brooks | 2021-05-29 | 2021-05-29 02:10 | Closed | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025 | [9 empty] | 625.6 | 665 | Arjan Sidhu | 2021-05-29 01:58 | [5 empty] | Lot closed |  | 2021-05-29 02:10 | [5 empty] | N-21-193-7.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125736 | 2021-05-31 05:34 |  |  |  |  | 2021-06-06 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00545 | Kallen Doong | 2021-05-28 08:23 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Kallen Doong | Stage 2 - CH630.920 to CH631.530 - Cut Incl. Ground Preparation | 2021-06-09 |  | 2021-06-04 10:00 |  |  |  | Open | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 630.92 | 631.53 | [6 empty] | HWP/N2NS/00151 | [6 empty] | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | lot map 545.pdf, 1625989c-3429-4fa9-af9f-16c10101ff16.jpg, ebabded5-c7f0-4d30-bb9e-9807062f018b.jpg | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125732
WLD/N2NS/00544 | James Martin | 2021-05-28 08:01 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | James Martin | Type E3 - CH635170 to CH635700 - Layer 1 (Excluding Culvert 635.135 to 635.150) | 2021-05-28 |  | 2021-05-29 10:00 | Lorne Jenks | 2021-07-12 | 2021-07-11 23:24 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00540 | [5 empty] | 634.7 | 635.7 | Lorne Jenks | 2021-07-11 23:24 | [5 empty] | Lot closed |  | 2021-07-11 23:24 |  |  |  | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Day 3 Pandas.pdf, Day 7 UCS.pdf, Day 0 Pandas.pdf, Day 7 UCS (2).pdf, IMG_1177.JPG, IMG_1171.JPG, E3 Stabilised Fill Layer 1 Ch 635170 to Ch 635700 Lot WLD-N2NS-00544.pdf, lot map 544.pdf, Day 0 Compaction (6).pdf, wldn2ns00544.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125730 | 2021-07-29 18:40 |  |  | 7632-2C41552 |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00543 | Kallen Doong | 2021-05-28 07:53 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH629690 to CH630000 - Layer 1 - Siding - 400mm | 2021-05-29 |  | 2021-06-05 10:00 | Benjamin Philip | 2021-06-28 | 2021-06-28 04:40 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00540 | [5 empty] | 629.69 | 630 | Benjamin Philip | 2021-06-28 04:40 |  |  |  |  | HWP/N2NS/00184 | Lot closed |  | 2021-06-28 04:40 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | E3 Stabilised Layer 1 Ch 629690 to Ch 630000 Lot WLD-N2NS-00543.pdf, TR0339C.pdf, TR0339B.pdf, TR0339 Panda.pdf, TR0343 Panda.pdf, lot map 543.pdf, IMG_4075.JPG, IMG_4074.JPG, N-21-179-406.pdf, wldn2ns00543.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125727 | 2021-06-29 19:15 |  |  | 7632-2C41552 |  | 2021-07-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00542 | Kallen Doong | 2021-05-28 07:44 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH628690 to CH629690 - Layer 1 - Siding - 400mm | 2021-05-29 |  | 2021-06-02 10:00 | Benjamin Philip | 2021-06-28 | 2021-06-28 04:37 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00540 | [5 empty] | 628.69 | 629.69 | Benjamin Philip | 2021-06-28 04:27 |  |  |  |  | HWP/N2NS/00184 | Lot closed |  | 2021-06-28 04:37 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0338 D.pdf, TR0342 Panda.pdf, TR0338 C.pdf, TR0338 B.pdf, TR0338 A .pdf, TR0338.pdf, Test Request 394 Panda Results.pdf, TR0338E.pdf, E3 Stabilised Layer 1 Ch 628690 to Ch 629690 Lot WLD-N2NS-00542.pdf, lot map 542.pdf, IMG_4056.JPG, TR0338 Panda .pdf, wldn2ns00542.pdf, E4850BC0-B01B-4DA4-83DC-F5DABC5368F7.JPG, 4E7F0436-8787-4616-8EE0-947C1818E188.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125724 | 2021-06-29 19:15 |  |  | 7632-2C41552 |  | 2021-07-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00541 | James Martin | 2021-05-28 07:32 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Unsuitable Removal - CH638.500 Culvert base | 2021-05-28 |  | 2021-05-29 10:00 |  |  | 2021-08-03 23:36 | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 638.5 | 638.5 | Sarah Brooks | 2021-08-03 23:36 |  |  |  |  | HWP/N2NS/00148, HWP/N2NS/00149 | Reopened lot | WP release signature is not ARTC Inspector's signature | 2021-08-16 03:14 |  |  |  | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_1139.JPG, IMG_1140.JPG, IMG_1141.JPG, IMG_1138.JPG, WLD N2NS 541_SWR498_Culvert 638525 Unsuitable Removal Theoretical.pdf, wldn2ns00541.pdf, lot map 541.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125723 |  |  |  | 7632-2C41460 |  | 2021-08-16 | Mike Harris | ARTC Rejected
WLD/N2NS/00540 | Ben Foster | 2021-05-28 04:59 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 23rd May to 29th May 2021 TOTAL QTY - 795.00 Tonnes | 2021-05-28 | 2021-05-29 | 2021-05-29 10:00 | Benjamin Philip | 2021-06-09 | 2021-06-09 00:13 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 0 | 0 | Ben Foster | 2021-06-08 22:41 | [5 empty] | Lot closed |  | 2021-06-09 00:13 | [5 empty] | 1028082.pdf, 1028080.pdf, 1028078.pdf, 1028069.pdf, 1028068.pdf, 1069375.pdf, 1028107.pdf, 1028106.pdf, 1028104.pdf, 1009577.pdf, 1009576.pdf, 1028089 1028090.pdf, 1028112 1028111.pdf, 1009614 1009613.pdf, 1028102 1028103.pdf, 1028092 1028093.pdf, 1028086.pdf, 1028084 1028085.pdf, 1028072 1028073.pdf, 1028070 1028071.pdf, 1028108.pdf, 1028109.pdf, 2CH-202105-0019-00076663-F.pdf, 1009591.pdf, 1069362.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125714 | 2021-06-29 19:15 | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551 |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00539 | James Martin | 2021-05-27 07:06 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | James Martin | Type E3 - CH638.125 to CH638.500 - Layer 1 | 2021-05-27 | 2021-05-28 | 2021-05-28 10:00 | Lorne Jenks | 2021-06-24 | 2021-06-08 05:37 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00540 | [5 empty] | 638.13 | 638.5 | Paddy Montgomery | 2021-06-24 01:25 | [5 empty] | Lot closed |  | 2021-06-24 01:25 |  |  |  | Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Day 3 Pandas.pdf, Day 0 Pandas.pdf, Day 7 UCS.pdf, Day 0 Compaction.pdf, 2.JPG, 1.JPG, E3 Stabilised Fill Layer 1 Ch 638125 to Ch 638500 Lot WLD-N2NS-00539.pdf, wldn2ns00539.pdf, lot map 539.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125670 | 2021-06-29 19:15 |  |  | 7632-2C41552 |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00538 | Jeramy Smith | 2021-05-27 04:11 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Ahmad Alwan | LX555 DDR2 - Installation of Concrete Road Culverts- Pipes and RCBC's (Temp Silo/ GrainCorp) (Excluding Headwalls) | 2021-05-27 |  | 2021-07-27 10:00 | Lorne Jenks | 2021-07-13 | 2021-07-13 07:06 | Closed | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 636.1 | 636.4 | Lorne Jenks | 2021-07-13 07:05 |  |  |  |  | HWP/N2NS/00126 | Lot closed |  | 2021-07-13 07:06 |  |  |  | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  | ImageThumbnail (1).jpg, ImageThumbnail.jpg, N-21-179-341.pdf, Lot Map.pdf, WLDN2NS00538.pdf, Lot Conformance.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125653 | 2021-07-29 18:40 |  |  |  |  | 2021-07-17 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00537 | Jeramy Smith | 2021-05-27 04:09 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Ahmad Alwan | LX1828 - Installation of Concrete Road Culverts- Pipes and RCBC's (Waterloo) DDR1 ( 525mm) | 2021-05-27 |  | 2021-07-27 10:00 | Sarah Brooks | 2021-07-31 | 2021-07-31 05:36 | Closed | AMS/N2NS/00004 | ITP/N2NS/00030 | [10 empty] | 627.75 | 627.95 | Sarah Brooks | 2021-07-31 05:36 |  | PNC/N2NS/00085 | Closed |  | HWP/N2NS/00146 | Lot closed |  | 2021-07-31 05:36 |  |  |  | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  | Suurvey Report.pdf, Lot Map.pdf, Test Request.pdf, IMG_8078.JPG, IMG_8079.JPG, WLDN2NS00537- Scour Checklist.pdf, WLDN2NS00537- Checklist.pdf, WLDN2NS00537- LC.pdf, N-21-179-238- Test Report.pdf, N-21-179-271 Test Report.pdf, Scour Protection Lot Map.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125652 | [5 empty] | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00536 | Miaya Tighe | 2021-05-27 02:46 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Earthworks - Filling | Earthworks | Arjan Sidhu | Matpol quarry Stockpile 1 UZF | 2021-05-27 |  | 2021-06-24 10:00 | Benjamin Philip | 2021-07-25 | 2021-07-25 01:08 | Closed | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 625.55 | 667 | Benjamin Philip | 2021-07-25 01:08 | [5 empty] | Lot closed |  | 2021-07-25 01:08 | [5 empty] | N-21-179-212.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125638 | 2021-07-29 18:40 |  |  |  |  | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00535 | Miaya Tighe | 2021-05-27 02:29 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Trackwork - Bottom Ballast | Earthworks | Arjan Sidhu | Runnymede quarry Ballast Stockpile 6 5000T | 2021-05-27 |  | 2021-06-24 10:00 | Benjamin Philip | 2021-05-27 | 2021-05-27 03:17 | Closed | AMS/N2NS/00007 | ITP/N2NS/00007 | CHK/N2NS/00033 | [9 empty] | 625.55 | 666 | Miaya Tighe | 2021-05-27 02:33 | [5 empty] | Lot closed |  | 2021-05-27 03:17 | [5 empty] | RU Ballast SP6 17-5-21.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125636 | 2021-05-31 05:34 |  |  |  |  | 2021-06-06 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00534 | Ryan Shenton | 2021-05-27 02:08 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH628.444 to CH628.579 - Layer 2 - 400mm | 2021-05-27 |  | 2021-06-02 10:00 | Benjamin Philip | 2021-07-17 | 2021-07-17 04:28 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00599 | [5 empty] | 628.44 | 628.58 | Benjamin Philip | 2021-07-17 04:27 |  |  |  |  | HWP/N2NS/00232 | Lot closed |  | 2021-07-17 04:28 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | 736659EB-CB44-498E-A2E0-3A0A1A93460E.JPG, BF802DB3-49AE-42C2-BE9C-67354C843DF1.JPG, Test Request 403 Panda Results.pdf, TR0403A.pdf, TR0403B.pdf, TR0417 Panda Re-Test.pdf, TR0417 Panda.pdf, wldn2ns00534.pdf, lot map 534.pdf, E3 Stabilised Layer 2 WLD-N2NS-00534.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125623 | 2021-07-29 18:40 |  |  | 7632-2C41552 |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00533 | Ryan Shenton | 2021-05-27 00:09 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH627587 to CH627730 - Layer 2 - 400mm | 2021-05-27 |  | 2021-06-02 10:00 | Sarah Brooks | 2021-08-02 | 2021-08-02 02:01 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00540 | [5 empty] | 627.59 | 627.73 | Sarah Brooks | 2021-08-02 02:01 |  |  |  |  | HWP/N2NS/00348 | Lot closed |  | 2021-08-02 02:01 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | DA55EB3C-6E88-49D8-9483-89654DB39A1F.JPG, C784EC43-8FED-4D66-BDA9-EE5389E9BC2D.JPG, TR0324 Panda.pdf, TR0324 A.pdf, TR0324.pdf, TR0334 Panda.pdf, lot map 533.pdf, E3 Stabilised Layer 2 WLD-N2NS-00533.pdf, wldn2ns00533.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125618 |  |  |  | 7632-2C41552 |  | 2021-08-02 | Sarah Brooks | Submitted to ARTC for Review
WLD/N2NS/00532 | Ryan Shenton | 2021-05-26 23:59 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH625900 to CH625990 - Layer 2 - 400mm | 2021-05-27 |  | 2021-06-02 10:00 | Lorne Jenks | 2021-06-12 | 2021-06-12 05:51 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00540 | [5 empty] | 625.9 | 625.99 | Ryan Shenton | 2021-06-12 00:26 | [5 empty] | Lot closed |  | 2021-06-12 05:51 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | E3 Stabilised Fill Layer 2 Conformance Report Ch 625900 to Ch 625990 Lot WLD-N2NS-00532.pdf, wldn2ns00532.pdf, TR0323 Compaction.pdf, TR0323 Panda.pdf, TR0333 Panda.pdf, Test Request 396 Panda Results.pdf, TR0323.pdf, lot map 532.pdf, IMG_4243.JPG, IMG_4242.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125617 | 2021-06-29 19:15 |  |  | 7632-2C41552 |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00531 | Richard Doering | 2021-05-26 07:41 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - CH 637.660 to 638.125 - Layer 1 | 2021-05-27 | 2021-05-27 | 2021-05-27 10:00 | Lorne Jenks | 2021-07-13 | 2021-07-13 05:17 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00540 | [5 empty] | 637.66 | 638.13 | Lorne Jenks | 2021-07-13 05:17 | [5 empty] | Lot closed |  | 2021-07-13 05:17 |  |  |  | James Martin, Kallen Doong, Ryan Shenton |  | Day 3 Pandas.pdf, Day 0 Compaction.pdf, Day 3 Pandas (2).pdf, Day 0 Pandas.pdf, Day 7 UCS.pdf, E3 Stabilised Fill Layer 1 Ch 637660 to Ch 638125 Lot WLD-N2NS-00531.pdf, wldn2ns00531.pdf, lot map 531.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125595 | 2021-07-29 18:40 |  |  | 7632-2C41552 |  | 2021-07-17 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00530 | Ryan Shenton | 2021-05-26 07:11 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH628440 to CH628690 - Layer 1 - Siding - 400mm |  |  | 2021-06-02 10:00 |  |  |  | Abandoned | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 628.44 | 628.69 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | 54BEAAB6-484D-492F-9EA3-CCEF956FA990.JPG, 2504DEB6-B9AC-4610-8C7E-1AC399B1D5B0.JPG, Test Request 393 Panda Results.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125591 |  |  |  | 7632-2C41552
WLD/N2NS/00529 | Ryan Shenton | 2021-05-26 07:01 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH628040 to CH628444 - Layer 2 - 400mm | 2021-05-28 |  | 2021-06-02 10:00 | Lorne Jenks | 2021-07-13 | 2021-07-01 06:09 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00540 | [5 empty] | 628.04 | 628.44 | Paddy Montgomery | 2021-07-13 01:05 |  |  |  |  | HWP/N2NS/00232 | Lot closed |  | 2021-07-13 01:11 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | N-21-179-301.pdf, N-21-179-302.pdf, TR0315.pdf, TR0315 Panda.pdf, IMG_0775.jpg, IMG_0779.jpg, TR0332 Panda.pdf, wldn2ns00529.pdf, lot map 529.pdf, E3 Stabilised Fill Layer 2 WLD-N2NS-00529.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125589 | 2021-07-29 18:40 |  |  | 7632-2C41552 |  | 2021-07-17 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00528 | Keegan Baker | 2021-05-26 06:44 | Stage 2 - Penneys Road to Moree | Culverts | 627.430, 30/3000x2100, remove and rebuild | Drainage - Other | Earthworks | Keegan Baker | 627.430 - Excavation and Foundation Preparation of Drainage Structure | 2021-05-31 |  | 2021-06-22 10:00 | Lorne Jenks | 2021-07-12 | 2021-07-11 23:06 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 |  |  |  | WLD/N2NS/01121 | [5 empty] | 627.43 | 627.43 | Maddie Dahlstrom | 2021-07-11 21:43 |  |  |  |  | HWP/N2NS/00141, HWP/N2NS/00206 | Lot closed |  | 2021-07-11 23:06 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | Test Request 0322 Panda Results (627.430 Foundation Panda 1 of 2).pdf, Test Request 0322 Panda Results (627.430 Foundation Panda 2 of 2).pdf, N-21-179-317 (Lime Compaction Tests).pdf, N-21-179-248 (Wing DCPs).pdf, N-21-179-248 (Wing DCPs2).pdf, WLD N2NS 528_SWR267_Culvert 627430 Unsuitable Removal (Volume).pdf, Lot Map.pdf, WLDN2NS00528.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125588 | 2021-07-29 18:40 |  |  |  |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00527 | Brendan Meagher | 2021-05-26 03:53 | Stage 2 - Penneys Road to Moree | Culverts | 627.430, 30/3000x2100, remove and rebuild | Culverts - Demolition | Other | Keegan Baker | Demolition of Existing Culvert | 2021-05-31 |  | 2021-05-26 10:00 | Benjamin Philip | 2021-06-26 | 2021-06-23 22:45 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 627.43 | 627.43 | Keegan Baker | 2021-06-20 08:44 | [5 empty] | Lot closed |  | 2021-06-26 00:10 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom |  | Lot Map.pdf, IMG_0482.JPG, IMG_0245.JPG, IMG_0037.JPG, IMG_0058.JPG, IMG_0039.JPG, WLD-N2NS-00527 - COMPLETED CHECKLIST.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125576 | 2021-06-29 19:15 |  |  |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00526 | Brendan Meagher | 2021-05-26 03:44 | Stage 2 - Penneys Road to Moree | Culverts | 636.705, 4/600x600, remove and rebuild (RRA) | Culverts - Demolition | Earthworks | Keegan Baker | Demolition of Existing Culverts between 636.400 to 640.380 (Lot for Payment only - Culvert demolition quality covered under the culverts respective demolition lot) | 2021-05-28 | 2021-05-05 | 2021-05-05 10:00 |  |  |  | Abandoned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 636.4 | 640.38 | Brendan Meagher | 2021-05-30 07:57 | [5 empty] | Require additional info | To be abandoned | 2021-05-30 22:51 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125575
WLD/N2NS/00525 | Richard Doering | 2021-05-25 07:20 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Layer 2 - CH637.030 to CH637.630 | 2021-06-11 |  | 2021-05-26 10:00 | Benjamin Philip | 2021-08-09 | 2021-08-09 05:15 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00015 |  |  |  | WLD/N2NS/00540 | [5 empty] | 637.03 | 637.63 | Benjamin Philip | 2021-08-09 05:14 |  |  |  |  | HWP/N2NS/00255 | Lot closed |  | 2021-08-09 05:15 | [5 empty] | TR0310 B.pdf, TR0310.pdf, TR0310 Panda.pdf, TR0310 A.pdf, E3 Stabilised Fill Layer 2 Ch 637030 to Ch 637620 Lot WLD-N2NS-00525.pdf, Test Request 0319 Panda Results.pdf, C4399D7A-2C6E-4CBD-9A40-EF2F04EBF46B.JPG, 8B4F8718-F85D-466A-99B9-8911A4C849D6.JPG, wldn2ns00525.pdf, lot map 525.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125516 |  |  |  | 7632-2C41552 |  | 2021-08-09 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00524 | Ryan Shenton | 2021-05-24 07:49 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH628200 to CH628500 Maintenance Siding - Layer 1 - 400mm | 2021-05-24 |  | 2021-05-31 10:00 | Lorne Jenks | 2021-06-12 | 2021-06-12 06:26 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00540 | [5 empty] | 628.2 | 628.5 | Paddy Montgomery | 2021-06-11 04:51 | [5 empty] | Lot closed |  | 2021-06-12 06:26 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0307 Panda.pdf, TR0302.pdf, TR0302 Panda.pdf, TR0302 A.pdf, E3 Stabilised Layer 1 Ch 628250 to Ch 628440 Lot WLD-N2NS-00524.pdf, IMG_4115.JPG, IMG_4114.JPG, wldn2ns00524.pdf, lot map 524.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125449 | 2021-06-29 19:15 |  |  | 7632-2C41552 |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00523 | Ryan Shenton | 2021-05-24 07:37 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH637980 to CH638280 - Layer 2 - 400mm | 2021-05-24 |  | 2021-05-31 10:00 | Benjamin Philip | 2021-07-01 | 2021-07-01 06:14 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00540 | [5 empty] | 627.98 | 628.28 | Benjamin Philip | 2021-07-01 06:14 |  |  |  |  | HWP/N2NS/00232 | Lot closed |  | 2021-07-01 06:14 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | 50525FD5-C408-4060-B563-03CA45482FE3.JPG, F470C751-195E-427B-B221-E29F33A9EB32.JPG, TR0300.pdf, TR0300 C.pdf, TR0300 B.pdf, TR0300 A.pdf, E3 Stabilised Fill Layer 2 Ch 627760 to Ch 628040 Lot WLD-N2NS-00523.pdf, TR0314 Panda .pdf, Test Request 0300 Panda Results.pdf, wldn2ns00523.pdf, lot map 523.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125447 | 2021-07-29 18:40 |  |  | 7632-2C41552 |  | 2021-07-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00522 | Ryan Shenton | 2021-05-24 07:28 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH630770 to CH630900 - Layer 1 - 400mm | 2021-05-24 |  | 2021-05-31 10:00 | Lorne Jenks | 2021-07-09 | 2021-07-09 04:45 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00540 | [5 empty] | 630.77 | 630.9 | Lorne Jenks | 2021-07-09 04:45 | [5 empty] | Lot closed |  | 2021-07-09 04:45 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | E3 Stabilised Fill Layer 1 Conformance Report Ch 630770 to Ch 630935 Lot WLD-N2NS-00522.pdf, lot map 522.pdf, 497AC2C6-FBE6-4161-9A09-79FF9BAF7913.JPG, EB2A459B-CA35-4C6B-9614-15A6EACF058B.JPG, TR0305 Panda.pdf, Test Request 412 Panda Results.pdf, TR0412.pdf, N-21-179-520.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125446 | 2021-07-29 18:40 |  |  | 7632-2C41552 |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00521 | James Martin | 2021-05-24 07:14 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | James Martin | Type E3 - Stage 2 - CH636560 to CH637030 - Layer 2 - 400mm | 2021-05-24 |  | 2021-05-30 10:00 | Benjamin Philip | 2021-06-25 | 2021-06-25 05:51 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00540 | [5 empty] | 636.56 | 637.03 | Paddy Montgomery | 2021-06-22 21:54 |  |  |  |  | HWP/N2NS/00185 | Lot closed |  | 2021-06-25 05:51 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_4165.JPG, IMG_4276.JPG, E3 Stabilised Fill Layer 2 Conformance Report Ch 636560 to Ch 637030 Lot WLD-N2NS-00521.pdf, Day 3 Pandas.pdf, Gradings.pdf, Day 0 Compaction.pdf, Day 0 Pandas.pdf, Day 7 UCS.pdf, wldn2ns00521.pdf, lot map 521.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125440 | 2021-06-29 19:15 |  |  | 7632-2C41552 |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00520 | Miaya Tighe | 2021-05-24 03:51 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Earthworks - Filling | Earthworks | Arjan Sidhu | Structural Fill Tookey pit stockpile 1 additional 4000T | 2021-06-15 |  | 2021-06-21 10:00 | Sarah Brooks | 2021-06-16 | 2021-06-16 00:54 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 | [9 empty] | 625.55 | 666 | Arjan Sidhu | 2021-06-15 01:18 | [5 empty] | Lot closed |  | 2021-06-16 00:54 |  |  |  | Arjan Sidhu, Jake Mossman, Miaya Tighe |  | TR0154_SP1_NA51B and D.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125403 | 2021-06-29 19:15 |  |  |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00519 | Arjan Sidhu | 2021-05-24 01:40 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Structural Fill | Other | Arjan Sidhu | Material for use for Structural Fill and UZF. Stock piles 1 and 2 - 5000t each Source: Matpol Enterprises | 2021-05-24 |  | 2021-06-04 10:00 | Benjamin Philip | 2021-05-27 | 2021-05-25 06:52 | Closed | AMS/N2NS/00004, AMS/N2NS/00006 | ITP/N2NS/00003, ITP/N2NS/00016 | CHK/N2NS/00017, CHK/N2NS/00030 | [9 empty] | 625.6 | 665 | Arjan Sidhu | 2021-05-26 07:58 | [5 empty] | Lot closed |  | 2021-05-27 02:25 |  |  |  | Brett Jenkins, Jake Mossman, Miaya Tighe |  | External Test Results TR0154.pdf, N-21-179-156.pdf, N-21-179-155.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125386 | 2021-05-31 05:34 |  |  |  |  | 2021-06-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00518 | James Martin | 2021-05-24 00:18 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | James Martin | Type E3 - Stage 2 - CH631700 to CH632590 - Layer 1 - 400mm | 2021-05-24 |  | 2021-05-29 10:00 | Lorne Jenks | 2021-06-14 | 2021-06-14 01:58 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 631.7 | 632.59 | James Martin | 2021-06-14 01:05 | [5 empty] | Lot closed |  | 2021-06-14 01:58 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | E3 Stabilised Layer 1 Ch 631600 to Ch 632590 Lot WLD-N2NS-00518.pdf, IMG_1115.JPG, IMG_1114.JPG, Day 0 Compactions.pdf, Day 7 UCS.pdf, Day 0 Pandas Ch632.010.pdf, Day 3 Pandas.pdf, Day 0 Pandas Ch632.310.pdf, Gradings.pdf, WLDN2NS00518 - Completed Checklist.pdf, WLDN2NS00518 - Lot Map.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125378 | 2021-06-29 19:15 |  |  | 7632-2C41552 |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00517 | Keegan Baker | 2021-05-23 21:27 | Stage 2 - Penneys Road to Moree | Culverts | 635.410, 2/2400x900, remove and rebuild (RRA) | Drainage - Other | Earthworks | Keegan Baker | Excavation and Foundation Preparation of Drainage Structure 635.410 | 2021-05-31 |  | 2021-05-22 10:00 | Lorne Jenks | 2021-07-12 | 2021-07-11 23:49 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 635.41 | 635.41 | Maddie Dahlstrom | 2021-07-11 21:46 |  |  |  |  | HWP/N2NS/00131, HWP/N2NS/00138, HWP/N2NS/00147, HWP/N2NS/00150 | Lot closed |  | 2021-07-11 23:49 | [5 empty] | Lot Conformance & Checklist.pdf, N-21-179-229.pdf, Test Request 0286 Panda Results.pdf, N-21-179-229 (635.410 DCP).pdf, N-21-179-264 (635.410 Comp).pdf, WLD N2NS 517_SWR321_Culvert 635410 Unsuitable Removal.pdf, Lot Map.pdf, IMG_0238.JPG, IMG_0241.JPG, IMG_0239.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125360 | 2021-07-29 18:40 |  |  |  |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00516 | Ryan Shenton | 2021-05-23 05:54 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH630070 to CH630770 - Layer 1 - 400mm | 2021-05-23 |  | 2021-05-30 10:00 | Benjamin Philip | 2021-06-28 | 2021-06-28 04:13 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00540 | [5 empty] | 630.07 | 630.77 | Benjamin Philip | 2021-06-28 04:13 |  |  |  |  | HWP/N2NS/00184 | Lot closed |  | 2021-06-28 04:13 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | E3 Stabilised Layer 1 Ch 630070 to Ch 630770 Lot WLD-N2NS-00516.pdf, TR0297 Panda.pdf, TR0289A.pdf, TR0289 Panda 1.pdf, TR0289.pdf, TR0289 Panda.pdf, IMG_4309.JPG, IMG_4307.JPG, wldn2ns00516.pdf, TR0289C.pdf, lot map 516.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125353 | 2021-06-29 19:15 |  |  |  |  | 2021-07-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00515 | Ryan Shenton | 2021-05-22 05:40 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH625830 to CH625980 - Layer 1 - 400mm | 2021-06-01 |  | 2021-05-24 10:00 | Lorne Jenks | 2021-06-12 | 2021-06-12 06:54 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 625.83 | 625.98 | Paddy Montgomery | 2021-06-11 01:49 | [5 empty] | Lot closed |  | 2021-06-12 06:54 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0287 Panda.pdf, TR0282 Panda .pdf, TR0282A.pdf, TR0282.pdf, E3 Stabilised Fill Layer 1 Conformance Report Ch 625830 to Ch 625980 Lot WLD-N2NS-00515.pdf, lot map 515.pdf, IMG_4064.JPG, IMG_4066.JPG, wldn2ns00515.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125352 | 2021-06-29 19:15 |  |  |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00514 | Ryan Shenton | 2021-05-22 03:12 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Stage 2 - CH633530 to CH633700. - Cut Incl. Ground Preparation | 2021-05-22 |  | 2021-05-25 10:00 | Benjamin Philip | 2021-07-01 | 2021-07-01 06:23 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 633.53 | 633.7 | Benjamin Philip | 2021-07-01 06:22 |  |  |  |  | HWP/N2NS/00118 | Lot closed |  | 2021-07-01 06:23 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_4073.JPG, IMG_4072.JPG, Excavation Foundation Ch 633530 to Ch 633700 Lot WLD-N2NS-00514.pdf, wldn2ns00514.pdf, lot map 514.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125351 | 2021-07-29 18:40 |  |  |  |  | 2021-07-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00513 | James Martin | 2021-05-21 08:19 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | James Martin | Type E3 - Stage 2 - CH632590 to CH633460 - Layer 1 - 400mm | 2021-05-21 |  | 2021-05-23 10:00 | Lorne Jenks | 2021-06-13 | 2021-06-13 06:25 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00505 | [5 empty] | 632.59 | 633.46 | Ryan Shenton | 2021-06-13 05:49 | [5 empty] | Lot closed |  | 2021-06-13 06:25 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | E3 Stabilised Layer 1 Ch 632590 to Ch 633460 Lot WLD-N2NS-00513.pdf, IMG_1098.JPG, IMG_1096.JPG, Day 3 Pandas.pdf, Day 7 UCS.pdf, Day 0 Pandas.pdf, Day 0 Compaction.pdf, wldn2ns00513.pdf, lot map 513.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125344 | 2021-06-29 19:15 |  |  | 7632-2C41552 |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00512 | Ryan Shenton | 2021-05-21 06:43 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH629.337 to CH629.990 - Layer 1 - 400mm | 2021-05-21 |  | 2021-05-24 10:00 | Benjamin Philip | 2021-06-28 | 2021-06-28 04:44 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00505 | [5 empty] | 629.34 | 629.99 | Benjamin Philip | 2021-06-28 04:44 |  |  |  |  | HWP/N2NS/00184 | Lot closed |  | 2021-06-28 04:44 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0277A.pdf, TR0277.pdf, TR0277 Panda.pdf, E3 Stabilised Layer 1 Ch 629337 to Ch 629990 Lot WLD-N2NS-00512.pdf, lot map 512.pdf, Test Request 414 Panda Results.pdf, IMG_4076.JPG, IMG_4075.JPG, wldn2ns00512.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125342 | 2021-06-29 19:15 |  |  |  |  | 2021-07-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00511 | Jason Cheah | 2021-05-21 06:22 | Manufacture / Material Supply Lots | Offsite Manufacture | Other (Specify in Lot) | Signalling - Pre-wiring of SER / LX Huts | Other | Jason Cheah | Signalling Hut Fit Out and Prewiring |  |  | 2022-02-01 11:00 |  |  |  | Planned | [12 empty] | 0 | 0 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125341 |  | John Holland Rail | PKG/N2NS/00113 | 7632-GR84102
WLD/N2NS/00510 | Ryan Shenton | 2021-05-20 23:32 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Stage 2 - CH625.830 to CH625.980 - Cut Incl. Ground Preparation | 2021-05-21 |  | 2021-05-25 10:00 | Benjamin Philip | 2021-06-29 | 2021-06-28 23:05 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 625.83 | 625.98 | Benjamin Philip | 2021-06-28 23:05 |  |  |  |  | HWP/N2NS/00114 | Lot closed |  | 2021-06-28 23:05 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_4039.JPG, IMG_4038.JPG, wldn2ns00510.pdf, Foundation Excavation Ch 625830 to Ch 625980 Lot WLD-N2NS-00510.pdf, lot map 510.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125314 | 2021-06-29 19:15 |  |  |  |  | 2021-07-01 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00509 | Ryan Shenton | 2021-05-19 07:05 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH627.587 to CH627.950 - Layer 1 - 400mm | 2021-05-19 |  | 2021-05-26 10:00 | Lorne Jenks | 2021-06-13 | 2021-06-12 22:06 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00505 | [5 empty] | 627.59 | 627.91 | Ryan Shenton | 2021-06-12 05:15 | [5 empty] | Lot closed |  | 2021-06-12 22:06 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0252 Panda .pdf, TR0252A.pdf, TR0264 Panda.pdf, TR0252.pdf, E3 Stabilised Layer 1 Ch 627587 to Ch 627850 Lot WLD-N2NS-00509.pdf, IMG_4081.JPG, IMG_4016.JPG, wldn2ns00509.pdf, Lot Map 509.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125249 | 2021-06-29 19:15 |  |  |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00508 | Kallen Doong | 2021-05-18 07:05 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH627850 to CH628054 - Layer 1 - 400mm | 2021-05-18 |  | 2021-05-22 10:00 |  |  |  | Abandoned | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00505 | [5 empty] | 627.85 | 628.05 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | E3 Stabilised Layer 1 Ch 627850 to Ch 628050 Lot WLD-N2NS-00508.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125207
WLD/N2NS/00507 | Kallen Doong | 2021-05-18 06:42 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH626910 to CH627140 - Layer 2 - 400mm | 2021-05-18 |  | 2021-05-20 10:00 | Lorne Jenks | 2021-06-13 | 2021-06-09 05:36 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 626.91 | 627.14 | Ryan Shenton | 2021-06-12 03:54 |  |  |  |  | HWP/N2NS/00122 | Lot closed |  | 2021-06-12 22:26 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_3991.JPG, IMG_4033.JPG, wldn2ns00507.pdf, TR0234 Panda.pdf, TR0234A.pdf, TR0248 Panda.pdf, E3 Stabilised Fill Layer 2 Conformance Report Ch 626910 to Ch 627140 Lot WLD-N2NS-00507.pdf, lot map 507.pdf, TR0234.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125198 | 2021-06-29 19:15 |  |  |  |  | 2021-07-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00506 | Ryan Shenton | 2021-05-18 06:37 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Stage 2 - CH632.550 to CH633.530 - Cut Incl. Ground Preparation | 2021-05-18 |  | 2021-05-24 10:00 | Benjamin Philip | 2021-07-01 | 2021-07-01 06:19 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 632.55 | 633.53 | Benjamin Philip | 2021-07-01 06:18 |  |  |  |  | HWP/N2NS/00103 | Lot closed |  | 2021-07-01 06:19 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Excavation Foundation Ch 632550 to Ch 633530 Lot WLD-N2NS-00506.pdf, lot map 506.pdf, 0114ED12-C7A6-473E-97DF-F4088EC4F1D7.JPG, DD217DD0-3855-4E2D-8C73-6B0176338E53.JPG, wldn2ns00506.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125197 | 2021-07-29 18:40 |  |  |  |  | 2021-07-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00505 | Ben Foster | 2021-05-17 06:55 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 16th May to 22nd May 2021 TOTAL QTY - 761.18 Tonnes | 2021-05-17 |  | 2021-05-22 10:00 | Sarah Brooks | 2021-06-05 | 2021-06-04 22:49 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 |  |  |  |  | WLD/N2NS/00458 | [5 empty] | 0 | 0 | Ben Foster | 2021-06-04 22:17 | [5 empty] | Lot closed |  | 2021-06-04 22:49 | [5 empty] | 1028067.pdf, 1028059.pdf, 1028058.pdf, 1028065.pdf, 1028064.pdf, 1028060.pdf, 1009558.pdf, 1028048.pdf, 1028047.pdf, 5414.pdf, 5413.pdf, 2CH-202105-0013-00076612-F.pdf, 1028049 1028050.pdf, 1028038 1028040.pdf, 1028037.pdf, 1028035 1028036.pdf, 1028016 1028018.pdf, 1028007 1028008.pdf, 1028057.pdf, 1028043 1028044.pdf, 05409.pdf, 05408.pdf, 1028012 1028013.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125146 | 2021-06-29 19:15 | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551 |  | 2021-06-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00504 | Richard Doering | 2021-05-17 01:19 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type C3 Insitu Stabilisation - CH637.660 to 638.340 | 2021-06-11 |  | 2021-05-21 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00015 | [9 empty] | 637.66 | 638.34 | [15 empty] | TR0230B.pdf, TR0230A.pdf, TR0230 Panda (1).pdf, TR0231 Panda.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125120 |  |  |  | 7632-2C41552
WLD/N2NS/00503 | Kallen Doong | 2021-05-16 07:34 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH629.990 to CH630.070 - Layer 1 - 400mm | 2021-05-22 |  | 2021-05-31 10:00 | Benjamin Philip | 2021-06-28 | 2021-06-28 04:24 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00540 | [5 empty] | 629.99 | 630.07 | Benjamin Philip | 2021-06-28 04:24 |  |  |  |  | HWP/N2NS/00184 | Lot closed |  | 2021-06-28 04:24 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0283 Panda.pdf, TR0283.pdf, E3 Stabilised Layer 1 Ch 629990 to Ch 630070 Lot WLD-N2NS-00503.pdf, TR0283A.pdf, Test Request 413 Panda Results.pdf, lot map 503.pdf, IMG_0828.jpg, IMG_0811.jpg, wldn2ns00503.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125100 | 2021-06-29 19:15 |  |  |  |  | 2021-07-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00502 | Kallen Doong | 2021-05-16 07:32 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH628.398 to CH629.337 - Layer 1 - 400mm - INCLUDES SIDING CH628.440 to CH629.337 | 2021-05-16 |  | 2021-05-24 10:00 | Benjamin Philip | 2021-06-29 | 2021-06-28 22:35 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00505 | [5 empty] | 628.4 | 629.34 | Benjamin Philip | 2021-06-28 22:34 | [5 empty] | Lot closed |  | 2021-06-28 22:35 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0263A.pdf, TR0263.pdf, TR0263 Panda.pdf, TR0263 Panda Re-Test.pdf, IMG_0833.jpg, IMG_0795.jpg, TR 393 Panda Results.pdf, E3 Stabilised Layer 1 Ch 628398 to Ch 629337 Lot WLD-N2NS-00502.pdf, wldn2ns00502.pdf, lot map 502.pdf, 54BEAAB6-484D-492F-9EA3-CCEF956FA990.JPG, 2504DEB6-B9AC-4610-8C7E-1AC399B1D5B0.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125099 | 2021-06-29 19:15 |  |  |  |  | 2021-07-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00501 | Kallen Doong | 2021-05-16 07:29 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Kallen Doong | Stage 2 - CH631.600 to CH632.470 - Cut Incl. Ground Preparation | 2021-05-18 |  | 2021-05-24 10:00 | Lorne Jenks | 2021-07-14 | 2021-07-14 03:50 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 630.9 | 631.9 | Lorne Jenks | 2021-07-14 03:50 |  |  |  |  | HWP/N2NS/00102, HWP/N2NS/00109 | Lot closed |  | 2021-07-14 03:50 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_4050.JPG, IMG_4042.JPG, Foundation Excavation Conformance Report Ch 631530 to Ch 632550 Lot WLD-N2NS-00501.pdf, wldn2ns00501.pdf, Lot Map 501.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125098 | 2021-07-29 18:40 |  |  |  |  | 2021-07-17 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00500 | Frank Paraha | 2021-05-16 01:16 | Stage 2 - Penneys Road to Moree | Culverts | 635.410, 2/2400x900, remove and rebuild (RRA) | Culverts - Demolition | Other | Frank Paraha | Demolition of Existing Culverts | 2021-05-31 |  | 2021-08-27 10:00 | Benjamin Philip | 2021-06-09 | 2021-06-09 04:28 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 635.41 | 635.41 | Maddie Dahlstrom | 2021-06-09 04:19 | [5 empty] | Lot closed |  | 2021-06-09 04:28 |  |  |  | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | IMG_0458.JPG, IMG_0460.JPG, WLDN2NS00500.pdf, WLDN2NS00500 Lot Map.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125097 | 2021-06-29 19:15 |  |  |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00499 | Ryan Shenton | 2021-05-16 00:38 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Clearing & Grubbing | Earthworks | Kallen Doong | Clearing and Grubbing - Stage 2 - CH628960 to CH631150 | 2021-05-16 |  | 2021-05-01 10:00 | Benjamin Philip | 2021-07-20 | 2021-07-19 22:42 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00001 | [10 empty] | 628.96 | 631.15 | Benjamin Philip | 2021-07-19 22:42 |  |  |  |  | HWP/N2NS/00098, HWP/N2NS/00099 | Lot closed |  | 2021-07-19 22:42 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton |  | IMG_0465.jpg, IMG_0469.jpg, EXT STG2 Topography WLD-N2NS-00499.pdf, lot map 499.pdf, wldn2ns00499.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125096 | 2021-07-29 18:40 |  |  |  |  | 2021-07-22 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00498 | Ryan Shenton | 2021-05-15 05:22 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Stage 2 - CH633.810 to CH634550 - Cut Incl. Ground Preparation | 2021-05-15 |  | 2021-07-28 10:00 | Sarah Brooks | 2021-08-01 | 2021-07-31 21:30 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 633.81 | 634.55 | Sarah Brooks | 2021-07-31 21:30 |  | PNC/N2NS/00086 | Closed |  | HWP/N2NS/00095, HWP/N2NS/00101 | Lot closed |  | 2021-07-31 21:30 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_4119.JPG, IMG_4122.JPG, Excavation Foundation Ch 633840 to Ch 634500 Lot WLD-N2NS-00498.pdf, TR0415 Panda (1).pdf, TR0415.pdf, N-21-179-569.pdf, lot map 498.pdf, wldn2ns00498.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125093 | [5 empty] | 2021-08-01 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00497 | Kallen Doong | 2021-05-14 04:12 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Stage 2 - CH630600 to CH630700 - Waterloo Siding - Cut Incl. Ground Preparation | 2021-06-11 |  | 2021-05-13 10:00 |  |  |  | Open | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 630.6 | 630.7 | [6 empty] | HWP/N2NS/00093 | [6 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_0462.jpg, IMG_0461.jpg | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125080
WLD/N2NS/00496 | Kallen Doong | 2021-05-13 00:36 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH626900 to CH627140 - Layer 1 - 400mm | 2021-05-13 |  | 2021-05-19 10:00 | Lorne Jenks | 2021-06-23 | 2021-06-23 06:18 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00505 | [5 empty] | 626.9 | 627.14 | Paddy Montgomery | 2021-06-23 06:04 | [5 empty] | Lot closed |  | 2021-06-23 06:18 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | lot map 496.pdf, E3 Stabilised Fill Layer 1 Conformance Report Ch 626900 to Ch 627140 Lot WLD-N2NS-00496.pdf, TR0209 Panda (1).pdf, TR0197B (1).pdf, TR0197 Panda (1).pdf, TR0197 (1).pdf, IMG_4066.JPG, IMG_4064.JPG, wldn2ns00496.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/125016 | 2021-06-29 19:15 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00495 | Nabin Koirala | 2021-05-12 07:57 | Stage 2 - Penneys Road to Moree | Culverts | 640,080, 5/2400x900, new build | Culverts - Installation of Box Culverts | Other | Keegan Baker | Installation of Box Culverts and Wing Walls | 2021-06-22 |  | 2021-05-29 10:00 | Lorne Jenks | 2021-07-04 | 2021-07-04 05:27 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00041 | [9 empty] | 640.08 | 640.08 | Keegan Baker | 2021-07-04 05:15 | [5 empty] | Lot closed |  | 2021-07-04 05:27 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala |  | 210629 WAE Culvert 640080 Base Slab Report.pdf, Mark Up.pdf, Lot Map.pdf, IMG_0016.JPG, IMG_0009.JPG, WLD-N2NS-00495.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124993 | 2021-07-29 18:40 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00494 | Kallen Doong | 2021-05-12 04:45 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH626571 to CH626910 - Layer 2 - 400mm | 2021-05-12 |  | 2021-05-14 10:00 | Benjamin Philip | 2021-06-25 | 2021-06-25 04:46 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00505 | [5 empty] | 626.57 | 626.91 | Benjamin Philip | 2021-06-25 04:46 |  |  |  |  | HWP/N2NS/00122 | Lot closed |  | 2021-06-25 04:46 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_3980.JPG, IMG_3979.JPG, TR0226A.pdf, TR0226.pdf, TR0226 Panda.pdf, TR0235 Panda.pdf, E3 Stabilised Fill Layer 2 Conformance Report Ch 626571 to Ch 626910 Lot WLD-N2NS-00494.pdf, wldn2ns00494.pdf, lot map 494.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124990 | 2021-06-29 19:15 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00493 | Kallen Doong | 2021-05-11 06:46 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH626.288 to CH626.571- Layer 2 - 400mm | 2021-05-11 |  | 2021-05-14 10:00 | Lorne Jenks | 2021-06-23 | 2021-06-23 06:07 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00395 | [5 empty] | 626.29 | 626.57 | Paddy Montgomery | 2021-06-23 06:03 |  |  |  |  | HWP/N2NS/00122 | Lot closed |  | 2021-06-23 06:07 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_3953.JPG, IMG_4085.JPG, TR0198 PANDA.pdf, TR0194.pdf, TR0194C.pdf, TR0194D.pdf, TR0194 Panda.pdf, E3 Stabilised Fill Layer 2 Conformance Report Ch 626288 to Ch 626571 Lot WLD-N2NS-00493.pdf, lot map 493.pdf, wldn2ns00493.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124950 | 2021-06-29 19:15 |  |  |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00492 | Jeramy Smith | 2021-05-10 22:55 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 648.100, LX3067, Private (Type 1, 9.20m, rubber, unsealed), RX-2 | Ancillary Works - Other | Roadworks | Ahmad Alwan | LX3067- General Concrete Structures (Tycannah East) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 648 | 648.2 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124910
WLD/N2NS/00491 | Jeramy Smith | 2021-05-10 22:54 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 649.350, LX1829, Crown access (Type 2, 6m, rubber, unsealed), RX-2 | Ancillary Works - Other | Roadworks | Ahmad Alwan | LX1829- General Concrete Structures (Tycannah) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 649.25 | 649.45 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124909
WLD/N2NS/00490 | Jeramy Smith | 2021-05-10 22:53 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 641.060, LX556, Private (Type 2, 4.50m, rubber, sealed at crossing), RX-2 | Ancillary Works - Other | Roadworks | Ahmad Alwan | LX556- General Concrete Structures (Pad 2 Access) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 641.06 | 641.16 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124908
WLD/N2NS/00489 | Jeramy Smith | 2021-05-10 22:53 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Ancillary Works - Other | Roadworks | Ahmad Alwan | LX555- General Concrete Structures (Temp Silo, GrainCorp) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 636.2 | 636.4 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124907
WLD/N2NS/00488 | Jeramy Smith | 2021-05-10 22:52 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 635.600, LX554, Gurley Creek Road (Type 4, rubber, sealed), RX-5 | Ancillary Works - Other | Roadworks | Ahmad Alwan | LX554- General Concrete Structures (Gurley Creek RD) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 635.5 | 635.7 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124906
WLD/N2NS/00487 | Jeramy Smith | 2021-05-10 22:51 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Ancillary Works - Other | Roadworks | Ahmad Alwan | LX3066- General Concrete Structures (Turners RD) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 634.39 | 634.59 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124905
WLD/N2NS/00486 | Jeramy Smith | 2021-05-10 22:50 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Ancillary Works - Other | Roadworks | Ahmad Alwan | LX553- General Concrete Structures (Kanimbla RD) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 631.05 | 631.25 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124904
WLD/N2NS/00485 | Jeramy Smith | 2021-05-10 22:49 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Ancillary Works - Other | Roadworks | Ahmad Alwan | LX1828- General Concrete Structures (Waterloo) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 | [10 empty] | 627.75 | 627.95 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124903
WLD/N2NS/00484 | Kallen Doong | 2021-05-10 22:44 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH625990 to CH626.288 - Layer 2 - 400mm | 2021-05-11 |  | 2021-05-14 10:00 | Lorne Jenks | 2021-06-13 | 2021-06-12 23:24 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00395 | [5 empty] | 625.99 | 626.29 | Paddy Montgomery | 2021-06-11 00:58 |  |  |  |  | HWP/N2NS/00122 | Lot closed |  | 2021-06-12 23:24 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_4082.JPG, IMG_4083.JPG, E3 Stabilised Fill Layer 2 Conformance Report Ch 625990 to Ch 626288 Lot WLD-N2NS-00484.pdf, TR0195 Panda Results.pdf, TR0192 Panda.pdf, TR0192A.pdf, TR0192C.pdf, TR0192.pdf, wldn2ns00484.pdf, lot map 484.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124902 | 2021-06-29 19:15 |  |  |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00483 | Jeramy Smith | 2021-05-10 07:29 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 648.100, LX3067, Private (Type 1, 9.20m, rubber, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Ahmad Alwan | LX3067 - Pavement Marking (Tycannah East) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 648 | 648.2 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124896
WLD/N2NS/00482 | Jeramy Smith | 2021-05-10 07:28 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 649.350, LX1829, Crown access (Type 2, 6m, rubber, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Ahmad Alwan | LX1829 - Pavement Marking (Tycannah) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 649.25 | 649.45 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124895
WLD/N2NS/00481 | Jeramy Smith | 2021-05-10 07:25 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 641.060, LX556, Private (Type 2, 4.50m, rubber, sealed at crossing), RX-2 | Ancillary Works - Linemarking | Roadworks | Ahmad Alwan | LX556 - Pavement Marking (Pad 2 Access) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 641.06 | 641.16 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Sam Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124894
WLD/N2NS/00480 | Jeramy Smith | 2021-05-10 07:24 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Ancillary Works - Linemarking | Roadworks | Ahmad Alwan | LX555 - Pavement Marking (Temp Silo, GrainCorp) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 636.2 | 636.4 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124893
WLD/N2NS/00479 | Jeramy Smith | 2021-05-10 07:23 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 635.600, LX554, Gurley Creek Road (Type 4, rubber, sealed), RX-5 | Ancillary Works - Linemarking | Roadworks | Ahmad Alwan | LX554 - Pavement Marking (Gurley Creek Rd) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 635.5 | 635.7 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124892
WLD/N2NS/00478 | Jeramy Smith | 2021-05-10 07:22 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Ancillary Works - Linemarking | Roadworks | Ahmad Alwan | LX3066 - Pavement Marking (Turners Rd) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 634.39 | 634.59 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124891
WLD/N2NS/00477 | Jeramy Smith | 2021-05-10 07:21 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Ancillary Works - Linemarking | Roadworks | Ahmad Alwan | LX553 - Pavement Marking (Kanimbla Rd) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 631.05 | 631.25 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124890
WLD/N2NS/00476 | Jeramy Smith | 2021-05-10 07:20 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Ancillary Works - Linemarking | Roadworks | Ahmad Alwan | LX1828 - Pavement Marking (Waterloo) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00031 | CHK/N2NS/00019 | [9 empty] | 627.75 | 627.95 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124888
WLD/N2NS/00475 | Jeramy Smith | 2021-05-10 07:16 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 648.100, LX3067, Private (Type 1, 9.20m, rubber, unsealed), RX-2 | Ancillary Works - Barriers, Handrail & Guardrail | Track | Ahmad Alwan | LX3067- Guardrail Installation (Tycannah East) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00044 | [10 empty] | 648 | 648.2 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124887
WLD/N2NS/00474 | Jeramy Smith | 2021-05-10 07:15 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 649.350, LX1829, Crown access (Type 2, 6m, rubber, unsealed), RX-2 | Ancillary Works - Barriers, Handrail & Guardrail | Track | Ahmad Alwan | Lx1829- Guardrail Installation (Tycannah) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00044 | [10 empty] | 649.25 | 649.45 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124886
WLD/N2NS/00473 | Jeramy Smith | 2021-05-10 07:14 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 641.060, LX556, Private (Type 2, 4.50m, rubber, sealed at crossing), RX-2 | Ancillary Works - Barriers, Handrail & Guardrail | Track | Ahmad Alwan | LX556- Guardrail Installation (Pad 2 Access) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00044 | [10 empty] | 641.06 | 641.16 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124885
WLD/N2NS/00472 | Jeramy Smith | 2021-05-10 07:13 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Ancillary Works - Barriers, Handrail & Guardrail | Track | Ahmad Alwan | LX555- Guardrail Installation (Temp Silo, GrainCorp) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00044 | [10 empty] | 636.2 | 636.4 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124884
WLD/N2NS/00471 | Jeramy Smith | 2021-05-10 07:12 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 635.600, LX554, Gurley Creek Road (Type 4, rubber, sealed), RX-5 | Ancillary Works - Barriers, Handrail & Guardrail | Track | Ahmad Alwan | LX554- Guardrail Installation (Gurley Creek Rd) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00044 | [10 empty] | 635.5 | 635.7 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124883
WLD/N2NS/00470 | Jeramy Smith | 2021-05-10 07:12 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Ancillary Works - Barriers, Handrail & Guardrail | Track | Ahmad Alwan | LX553- Guardrail Installation (Kanimbla Rd) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00044 | [10 empty] | 631.05 | 631.25 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124882
WLD/N2NS/00469 | Jeramy Smith | 2021-05-10 07:11 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Ancillary Works - Barriers, Handrail & Guardrail | Track | Ahmad Alwan | LX1828- Guardrail Installation (Waterloo) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00044 | [10 empty] | 627.75 | 627.95 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124881
WLD/N2NS/00468 | Jeramy Smith | 2021-05-10 07:09 | Stage 2 - Penneys Road to Moree | Trackwork | Level Crossing - 648.100, LX3067, Private (Type 1, 9.20m, rubber, unsealed), RX-2 | Trackwork - Track Signage | Track | Ahmad Alwan | LX3067- Signage Installation (Tycannah East) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | PER/N2NS/00023 | [8 empty] | 648 | 648.2 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124880
WLD/N2NS/00467 | Jeramy Smith | 2021-05-10 07:08 | Stage 2 - Penneys Road to Moree | Trackwork | Level Crossing - 649.350, LX1829, Crown access (Type 2, 6m, rubber, unsealed), RX-2 | Trackwork - Track Signage | Track | Ahmad Alwan | LX1829 - Signage Installation (Tycannah) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | PER/N2NS/00023 | [8 empty] | 649.25 | 649.45 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124879
WLD/N2NS/00466 | Jeramy Smith | 2021-05-10 07:07 | Stage 2 - Penneys Road to Moree | Trackwork | Level Crossing - 641.060, LX556, Private (Type 2, 4.50m, rubber, sealed at crossing), RX-2 | Trackwork - Track Signage | Track | Ahmad Alwan | LX556 - Signage Installation (Pad 2 Access) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | PER/N2NS/00023 | [8 empty] | 641.06 | 641.16 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124878
WLD/N2NS/00465 | Jeramy Smith | 2021-05-10 07:06 | Stage 2 - Penneys Road to Moree | Trackwork | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Trackwork - Track Signage | Track | Ahmad Alwan | LX555 - Signage Installation (Temp Silo, GrainCorp) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | PER/N2NS/00023 | [8 empty] | 636.2 | 636.4 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124876
WLD/N2NS/00464 | Jeramy Smith | 2021-05-10 07:05 | Stage 2 - Penneys Road to Moree | Trackwork | Level Crossing - 635.600, LX554, Gurley Creek Road (Type 4, rubber, sealed), RX-5 | Trackwork - Track Signage | Track | Ahmad Alwan | LX554 - Signage Installation (Gurley Creek Rd) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | PER/N2NS/00023 | [8 empty] | 635.5 | 635.7 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124874
WLD/N2NS/00463 | Jeramy Smith | 2021-05-10 07:03 | Stage 2 - Penneys Road to Moree | Trackwork | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Trackwork - Track Signage | Track | Ahmad Alwan | LX553 - Signage Installation (Kanimbla Rd) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | PER/N2NS/00023 | [8 empty] | 631.05 | 631.25 | [13 empty] | Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124872
WLD/N2NS/00462 | Jeramy Smith | 2021-05-10 07:02 | Stage 2 - Penneys Road to Moree | Trackwork | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Trackwork - Track Signage | Track | Ahmad Alwan | LX1828 - Signage Installation (Waterloo) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | PER/N2NS/00023 | [8 empty] | 627.75 | 627.95 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124871
WLD/N2NS/00461 | Arjan Sidhu | 2021-05-10 07:00 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Drainage - Other | Other | Arjan Sidhu | Bedding Sand Classification Tests - Source JCQ | 2021-05-10 |  | 2021-05-12 10:00 | Sarah Brooks | 2021-05-11 | 2021-05-11 01:34 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 625.55 | 761 | Arjan Sidhu | 2021-05-10 07:04 | [5 empty] | Lot closed |  | 2021-05-11 01:34 |  |  |  | Jake Mossman, Miaya Tighe | Trans4m Rail Joint Venture | N-21-183-61.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124870 | 2021-05-31 05:34 |  |  |  |  | 2021-05-11 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00460 | Jeramy Smith | 2021-05-10 07:00 | Stage 2 - Penneys Road to Moree | Fencing | Level Crossing - 648.100, LX3067, Private (Type 1, 9.20m, rubber, unsealed), RX-2 | Fencing - Fencing and Gates | Earthworks | Ahmad Alwan | LX3067 - Fencing Installation (Tycannah East) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 |  | PER/N2NS/00023 | [8 empty] | 648 | 648.2 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124869
WLD/N2NS/00459 | Jeramy Smith | 2021-05-10 06:59 | Stage 2 - Penneys Road to Moree | Fencing | Level Crossing - 649.350, LX1829, Crown access (Type 2, 6m, rubber, unsealed), RX-2 | Fencing - Fencing and Gates | Earthworks | Ahmad Alwan | LX1829 - Fencing Installation (Tycannah) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 |  | PER/N2NS/00023 | [8 empty] | 649.25 | 649.45 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124868
WLD/N2NS/00458 | Kallen Doong | 2021-05-10 06:58 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH627.587 to CH627.876 - General Fill Layer 2 - 300mm @ 2% Lime | 2021-05-19 |  | 2021-05-14 10:00 | Benjamin Philip | 2021-07-22 | 2021-07-22 05:12 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 |  |  |  |  | WLD/N2NS/00505 | [5 empty] | 627.59 | 628.88 | Benjamin Philip | 2021-07-22 05:12 | [5 empty] | Lot closed |  | 2021-07-22 05:12 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0191B.pdf, TR0191A.pdf, TR0191.pdf, IMG_0363.jpg, IMG_0364.jpg, General Fill Layer 2 WLD-N2NS-00458.pdf, wldn2ns00458.pdf, lot map 458.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124867 | 2021-07-29 18:40 |  |  |  |  | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00457 | Jeramy Smith | 2021-05-10 06:58 | Stage 2 - Penneys Road to Moree | Fencing | Level Crossing - 641.060, LX556, Private (Type 2, 4.50m, rubber, sealed at crossing), RX-2 | Fencing - Fencing and Gates | Earthworks | Ahmad Alwan | LX556 - Fencing Installation (Pad 2 Access) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 |  | PER/N2NS/00023 | [8 empty] | 641.06 | 641.16 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124866
WLD/N2NS/00456 | Jeramy Smith | 2021-05-10 06:57 | Stage 2 - Penneys Road to Moree | Fencing | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Fencing - Fencing and Gates | Earthworks | Ahmad Alwan | LX555 - Fencing Installation (Temp Silo, GrainCorp) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 |  | PER/N2NS/00023 | [8 empty] | 636.2 | 636.4 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124865
WLD/N2NS/00455 | Jeramy Smith | 2021-05-10 06:56 | Stage 2 - Penneys Road to Moree | Fencing | Level Crossing - 635.600, LX554, Gurley Creek Road (Type 4, rubber, sealed), RX-5 | Fencing - Fencing and Gates | Earthworks | Ahmad Alwan | LX554 - Fencing Installation (Gurley Creek RD) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 |  | PER/N2NS/00023 | [8 empty] | 635.5 | 635.7 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124864
WLD/N2NS/00454 | Kallen Doong | 2021-05-10 06:55 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH627.587 to CH628.876 - General Fill Layer 1 - 300mm @ 2% Lime | 2021-05-19 |  | 2021-05-14 10:00 | Sarah Brooks | 2021-08-02 | 2021-08-02 00:09 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 |  |  |  |  | WLD/N2NS/00395 | [5 empty] | 627.59 | 628.88 | Sarah Brooks | 2021-08-02 00:08 | [5 empty] | Lot closed |  | 2021-08-02 00:09 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0190B.pdf, TR0190.pdf, TR0190 Panda.pdf, IMG_0363.jpg, IMG_0364.jpg, WLD-N2NS-00454.pdf, wldn2ns00454.pdf, lot map 454.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124863 | [5 empty] | 2021-08-02 | Sarah Brooks | Submitted to ARTC for Review
WLD/N2NS/00453 | Jeramy Smith | 2021-05-10 06:55 | Stage 2 - Penneys Road to Moree | Fencing | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Fencing - Fencing and Gates | Earthworks | Ahmad Alwan | LX553 - Fencing Installation (Kanimbla RD) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 |  | PER/N2NS/00023 | [8 empty] | 631.05 | 631.25 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124862
WLD/N2NS/00452 | Jeramy Smith | 2021-05-10 06:54 | Stage 2 - Penneys Road to Moree | Fencing | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Fencing - Fencing and Gates | Earthworks | Ahmad Alwan | LX1828 - Fencing Installation (Waterloo) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 |  | PER/N2NS/00023 | [8 empty] | 627.75 | 627.95 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124861
WLD/N2NS/00451 | Jeramy Smith | 2021-05-10 06:52 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 635.600, LX554, Gurley Creek Road (Type 4, rubber, sealed), RX-5 | Pavements - Asphalt | Roadworks | Ahmad Alwan | LX554 - Asphalt (Gurley Creek RD) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00011 | CHK/N2NS/00046, CHK/N2NS/00047 | PER/N2NS/00023 | [8 empty] | 635.5 | 635.7 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124859
WLD/N2NS/00450 | Jeramy Smith | 2021-05-10 06:49 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 648.100, LX3067, Private (Type 1, 9.20m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Ahmad Alwan | LX3067 - Prime, Primerseal & Seal (Tycannah East) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020, CHK/N2NS/00021 | PER/N2NS/00023 | [8 empty] | 648 | 648.2 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124858
WLD/N2NS/00449 | Jeramy Smith | 2021-05-10 06:48 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 649.350, LX1829, Crown access (Type 2, 6m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Ahmad Alwan | LX1829 - Prime, Primerseal & Seal (Tycannah) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020, CHK/N2NS/00021 | PER/N2NS/00023 | [8 empty] | 649.25 | 649.45 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124857
WLD/N2NS/00448 | Jeramy Smith | 2021-05-10 06:47 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 641.060, LX556, Private (Type 2, 4.50m, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Ahmad Alwan | LX556 - Prime, Primerseal & Seal (Pad 2 Access) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020, CHK/N2NS/00021 | PER/N2NS/00023 | [8 empty] | 641.06 | 641.16 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124856
WLD/N2NS/00447 | Jeramy Smith | 2021-05-10 06:46 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Ahmad Alwan | LX555 - Prime, Primerseal & Seal (Temp SIlo, GrainCorp) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020, CHK/N2NS/00021 | PER/N2NS/00023 | [8 empty] | 636.2 | 636.4 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124853
WLD/N2NS/00446 | Jeramy Smith | 2021-05-10 06:45 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 635.600, LX554, Gurley Creek Road (Type 4, rubber, sealed), RX-5 | Pavements - Prime/Primer Seal | Roadworks | Ahmad Alwan | LX554 - Prime, Primerseal & Seal (Gurley Creek RD) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020, CHK/N2NS/00021 | PER/N2NS/00023 | [8 empty] | 635.5 | 635.7 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124852
WLD/N2NS/00445 | Jeramy Smith | 2021-05-10 06:44 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Ahmad Alwan | LX553 - Prime, Primerseal & Seal (Kanimbla RD) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020, CHK/N2NS/00021 | PER/N2NS/00023 | [8 empty] | 631.05 | 631.25 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124851
WLD/N2NS/00444 | Jeramy Smith | 2021-05-10 06:42 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Ahmad Alwan | LX1828 - Prime, Primerseal & Seal |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020, CHK/N2NS/00021 | PER/N2NS/00023 | [8 empty] | 627.75 | 627.95 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124850
WLD/N2NS/00443 | Jeramy Smith | 2021-05-10 06:40 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 648.100, LX3067, Private (Type 1, 9.20m, rubber, unsealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Earthworks | Ahmad Alwan | LX3067- Capping Incl. Rail Maintenance Access Track (Tycannah East) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00012 | CHK/N2NS/00023, CHK/N2NS/00024 | PER/N2NS/00023 | [8 empty] | 648 | 648.2 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124849
WLD/N2NS/00442 | Jeramy Smith | 2021-05-10 06:39 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 649.350, LX1829, Crown access (Type 2, 6m, rubber, unsealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Earthworks | Ahmad Alwan | LX1829- Capping Incl. Rail Maintenance Access Track (Tycannah) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00012 | CHK/N2NS/00023, CHK/N2NS/00024 | PER/N2NS/00023 | [8 empty] | 649.25 | 649.45 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124848
WLD/N2NS/00441 | Jeramy Smith | 2021-05-10 06:38 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 641.060, LX556, Private (Type 2, 4.50m, rubber, sealed at crossing), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Earthworks | Ahmad Alwan | LX556- Capping Incl. Rail Maintenance Access Track (Pad 2 Access) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00012 | CHK/N2NS/00023, CHK/N2NS/00024 | PER/N2NS/00023 | [8 empty] | 641.06 | 641.16 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124847
WLD/N2NS/00440 | Jeramy Smith | 2021-05-10 06:35 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Earthworks | Ahmad Alwan | LX555- Capping Incl. Rail Maintenance Access Track (Temp Silo, GrainCorp) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00012 | CHK/N2NS/00023, CHK/N2NS/00024 | PER/N2NS/00023 | [8 empty] | 636.2 | 636.4 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124846
WLD/N2NS/00439 | Jeramy Smith | 2021-05-10 06:31 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 635.600, LX554, Gurley Creek Road (Type 4, rubber, sealed), RX-5 | Earthworks - Capping, inc Rail Maintenance Access Road | Earthworks | Ahmad Alwan | LX554- Capping Incl. Rail Maintenance Access Track (Gurley Creek RD) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00012 | CHK/N2NS/00023, CHK/N2NS/00024 | PER/N2NS/00023 | [8 empty] | 635.5 | 635.7 | [6 empty] | HWP/N2NS/00405 | [6 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124845
WLD/N2NS/00438 | Jeramy Smith | 2021-05-10 06:30 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Earthworks | Ahmad Alwan | LX553- Capping Incl. Rail Maintenance Access Track (Kanimbla RD) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00012 | CHK/N2NS/00023, CHK/N2NS/00024 | PER/N2NS/00023 | [8 empty] | 631.05 | 631.25 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124844
WLD/N2NS/00437 | Jeramy Smith | 2021-05-10 06:29 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Earthworks | Ahmad Alwan | LX1828- Capping Incl. Rail Maintenance Access Track (Waterloo) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00012 | CHK/N2NS/00023, CHK/N2NS/00024 | PER/N2NS/00023 | [8 empty] | 627.75 | 627.95 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124842
WLD/N2NS/00436 | Ahmed Soliman | 2021-05-10 06:17 | Stage 2 - Penneys Road to Moree | Trackwork | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Roadworks | Hayden Murphy | LX555 - Capping Incl. Rail Maintenance Access Track |  |  | 2021-05-19 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00012 | CHK/N2NS/00023, CHK/N2NS/00024 | PER/N2NS/00012 | [8 empty] | 636.2 | 636.4 | [13 empty] | Grant Mills, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124837
WLD/N2NS/00435 | Jeramy Smith | 2021-05-10 06:10 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 649.350, LX1829, Crown access (Type 2, 6m, rubber, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Earthworks | Ahmad Alwan | LX1829 - Clearing and grubbing (Tycannah) | 2021-06-27 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-07-27 | 2021-07-27 00:20 | Closed | AMS/N2NS/00004 | ITP/N2NS/00001 | [10 empty] | 649.25 | 649.45 | Jeramy Smith | 2021-07-26 23:25 |  |  |  |  | HWP/N2NS/00218, HWP/N2NS/00220 | Lot closed |  | 2021-07-27 00:20 |  |  |  | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  | Lot Map.pdf, Survey Report.pdf, 1829-01.jpg, 1829-02.jpg, WLDN2NS00435- Checklist.pdf, WLDN2NS00435-LC.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124835 | 2021-07-29 18:40 |  |  |  |  | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00434 | Ahmed Soliman | 2021-05-10 06:08 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Pavements - Concrete Pavement | Concrete | Hayden Murphy | LX555 - General Concrete Structures |  |  | 2021-05-19 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00019 |  | PER/N2NS/00012 | [8 empty] | 636.2 | 636.4 | [13 empty] | Grant Mills, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124834
WLD/N2NS/00433 | Jeramy Smith | 2021-05-10 06:01 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 649.350, LX1829, Crown access (Type 2, 6m, rubber, unsealed), RX-2 | Pavements - Concrete Pavement | Roadworks | Ahmad Alwan | LX1829 - Unbound Pavements- (Tycannah) |  |  | 2021-06-07 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 649.25 | 649.45 | [13 empty] | Ahmad Alwan, Grant Mills, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124831
WLD/N2NS/00432 | Jeramy Smith | 2021-05-10 06:00 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 635.600, LX554, Gurley Creek Road (Type 4, rubber, sealed), RX-5 | Pavements - Concrete Pavement | Roadworks | Ahmad Alwan | LX554 - Unbound Pavements- (Gurley Creek RD) | 2021-08-16 |  | 2021-06-07 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 635.5 | 635.7 | [13 empty] | Ahmad Alwan, Grant Mills, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124830
WLD/N2NS/00431 | Jeramy Smith | 2021-05-10 05:56 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Drainage - Stormwater Pits | Earthworks | Ahmad Alwan | LX555 - Conduit and Pit Installation (Temp Silo, Graincorp) | 2021-08-05 |  | 2021-06-07 10:00 | Benjamin Philip | 2021-08-17 | 2021-08-17 01:15 | Closed | AMS/N2NS/00004 | ITP/N2NS/00021 | CHK/N2NS/00045 | PER/N2NS/00023 | [8 empty] | 636.2 | 636.4 | Benjamin Philip | 2021-08-17 01:15 | [5 empty] | Lot closed |  | 2021-08-17 01:15 |  |  |  | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  | WLDN2NS00431- LC.pdf, WLDN2NS00431- Checklist.pdf, Test Report (2).pdf, Test Report.pdf, Lot Map.pdf, Subsoil Drains.pdf, Certificate of Compliance.pdf, CSR Conduits.pdf, 2.jpg, 1.jpg | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124828 | [5 empty] | 2021-08-17 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00430 | Jeramy Smith | 2021-05-10 05:54 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 635.600, LX554, Gurley Creek Road (Type 4, rubber, sealed), RX-5 | Drainage - Stormwater Pits | Earthworks | Ahmad Alwan | LX554 - Conduit and Pit Installation (Gurley Creek RD) |  |  | 2021-06-07 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00021 | CHK/N2NS/00045 | PER/N2NS/00023 | [8 empty] | 635.5 | 635.7 | [13 empty] | Ahmad Alwan, Grant Mills, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124825
WLD/N2NS/00429 | Jeramy Smith | 2021-05-10 05:50 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Ahmad Alwan | LX555 DDR1 - Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill (DN600 Single Barrel) | 2021-05-20 |  | 2021-06-14 10:00 | Benjamin Philip | 2021-08-17 | 2021-08-17 01:50 | Closed | AMS/N2NS/00004 | ITP/N2NS/00010, ITP/N2NS/00016, ITP/N2NS/00030 | [10 empty] | 636.2 | 636.4 | Benjamin Philip | 2021-08-17 01:41 |  |  |  |  | HWP/N2NS/00108, HWP/N2NS/00133, HWP/N2NS/00159, HWP/N2NS/00169 | Lot closed |  | 2021-08-17 01:50 |  |  |  | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  | IMG_8085.JPG, IMG_8086.JPG, WLDN2NS00429-Lot Confromance.pdf, WLDN2NS00429- Checklist.pdf, N-21-179-284.pdf, N-21-179-283.pdf, Survey Report.pdf, Lot Map.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124824 | [5 empty] | 2021-08-17 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00428 | Jeramy Smith | 2021-05-10 05:46 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 648.100, LX3067, Private (Type 1, 9.20m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Ahmad Alwan | LX3067- Foundation for Embankment, Embankments, Upper Zone Formation & Select Material Zone (Tycannah East) |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025, CHK/N2NS/00026, CHK/N2NS/00029, CHK/N2NS/00030 | [9 empty] | 648 | 648.2 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124823
WLD/N2NS/00427 | Jeramy Smith | 2021-05-10 05:44 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 649.350, LX1829, Crown access (Type 2, 6m, rubber, unsealed), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Ahmad Alwan | LX1829- RMS Embankments |  |  | 2021-06-14 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00026 | [9 empty] | 649.25 | 649.45 | [6 empty] | HWP/N2NS/00389 | [6 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124821
WLD/N2NS/00426 | Jeramy Smith | 2021-05-10 05:43 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Ahmad Alwan | LX555- Upper Zone Formation (UZF) (Eastern Side) to Subgrade - along control line LX0555 LX V1 only (Eastern Side) | 2021-05-18 |  | 2021-06-14 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00030 | [9 empty] | 636.2 | 636.4 | [6 empty] | HWP/N2NS/00105, HWP/N2NS/00155 | [6 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  | LX555 CBR Testing.pdf, LX555 Compaction Test.pdf, LX555 Subgrade Conformance.pdf, Survey Report.pdf, Lot Map.pdf, 2d8eb0b8-863b-41dd-91b5-4b43a7555475.JPG, IMG_0537.jpg | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124820
WLD/N2NS/00425 | Jeramy Smith | 2021-05-10 05:41 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 635.600, LX554, Gurley Creek Road (Type 4, rubber, sealed), RX-5 | Earthworks - Subgrade Preparation | Earthworks | Loui Tannous | LX554- Foundation for Embankment, Embankments, Upper Zone Formation & Select Material Zone (Gurley Creek RD) | 2021-05-27 |  | 2021-06-14 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025, CHK/N2NS/00026, CHK/N2NS/00029, CHK/N2NS/00030 | [9 empty] | 634.39 | 634.59 | [6 empty] | HWP/N2NS/00140 | [6 empty] | Ahmad Alwan, Hayden Murphy, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124819
WLD/N2NS/00424 | Jeramy Smith | 2021-05-10 05:35 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 648.100, LX3067, Private (Type 1, 9.20m, rubber, unsealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Ahmad Alwan | LX3067- Subsoil Drains (Tycannah East) |  |  | 2021-06-10 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | [10 empty] | 648 | 648.2 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124818
WLD/N2NS/00423 | Jeramy Smith | 2021-05-10 05:33 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 649.350, LX1829, Crown access (Type 2, 6m, rubber, unsealed), RX-2 | Drainage - Subsoil Drains | Roadworks | Ahmad Alwan | LX1829- Subsoil Drains (Tycannah) |  |  | 2021-06-10 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | [10 empty] | 649.25 | 649.45 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124817
WLD/N2NS/00422 | Jeramy Smith | 2021-05-10 05:27 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Drainage - Subsoil Drains | Roadworks | Ahmad Alwan | LX555- Subsoil Drains (Temp Silo, GrainCorp) |  |  | 2021-06-10 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | [10 empty] | 636.2 | 636.4 | [6 empty] | HWP/N2NS/00320 | [6 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124816
WLD/N2NS/00421 | Ahmed Soliman | 2021-05-10 05:26 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Drainage - Level Crossing Table Drain | Earthworks | Hayden Murphy | LX555 -Conduit and Pit Installation |  |  | 2021-05-19 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00021 | CHK/N2NS/00045 | PER/N2NS/00012 | [8 empty] | 636.2 | 636.4 | [13 empty] | Grant Mills, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124815
WLD/N2NS/00420 | Jeramy Smith | 2021-05-10 05:25 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 641.060, LX556, Private (Type 2, 4.50m, rubber, sealed at crossing), RX-2 | Drainage - Subsoil Drains | Roadworks | Ahmad Alwan | LX556- Subsoil Drains (Pad 2 Access) |  |  | 2021-06-10 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00010 | [10 empty] | 641.06 | 641.16 | [13 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124814
WLD/N2NS/00419 | Ahmed Soliman | 2021-05-10 05:23 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Culverts - Other | Utilities | Hayden Murphy | LX554 - Installation of Subsoils | 2021-08-10 |  | 2021-05-19 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | [9 empty] | 635.6 | 635.6 | [6 empty] | HWP/N2NS/00406 | [6 empty] | Grant Mills, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124813
WLD/N2NS/00418 | Jeramy Smith | 2021-05-10 04:02 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Drainage - Subsoil Drains | Roadworks | Ahmad Alwan | LX553- Subsoil Drains (Kanimbla RD) | 2021-08-11 |  | 2021-06-10 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00010 | [10 empty] | 631.05 | 631.25 |  |  |  | PNC/N2NS/00144 | Pending Disposition Approval |  | HWP/N2NS/00333 | [6 empty] | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  | 1.jpg, 2.jpg, Subsoil Drains.pdf, Lot Map.pdf, Certifcate of Compliance.pdf, WLDN2NS00418- Checklist.pdf, WLDN2NS00418-LC.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124810
WLD/N2NS/00417 | Jeramy Smith | 2021-05-10 02:32 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Drainage - Subsoil Drains | Roadworks | Ahmad Alwan | LX1828- Subsoil Drains (Waterloo) | 2021-07-30 |  | 2021-06-10 10:00 | Benjamin Philip | 2021-08-18 | 2021-08-17 21:47 | Closed | AMS/N2NS/00004 | ITP/N2NS/00010 | [10 empty] | 627.75 | 627.95 | Benjamin Philip | 2021-08-17 21:47 |  |  |  |  | HWP/N2NS/00315 | Lot closed |  | 2021-08-17 21:47 |  |  |  | Ahmad Alwan, Jeramy Smith, Loui Tannous, Samithy Heng |  | WLDN2NS00417- Checklist.pdf, WLDN2NS00417.pdf, Lot Map.pdf, Subsoil Drains.pdf, 2.jpg, 1.jpg, Certificate of Comliance.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124799 | [5 empty] | 2021-08-18 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00416 | Jeramy Smith | 2021-05-10 02:22 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Ahmad Alwan | LX553 - Installation of Concrete Road Culverts- Pipes and RCBC's (Kanimbla Rd) | 2021-07-06 |  | 2021-06-14 10:00 | Benjamin Philip | 2021-08-18 | 2021-08-18 01:22 | Closed | AMS/N2NS/00004 | ITP/N2NS/00010, ITP/N2NS/00016, ITP/N2NS/00030 | [10 empty] | 631.05 | 631.25 | Benjamin Philip | 2021-08-18 01:22 |  |  |  |  | HWP/N2NS/00234, HWP/N2NS/00446 | Lot closed |  | 2021-08-18 01:22 |  |  |  | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  | 1224F79B-9B7E-47E4-B183-FC45712DFF43.jpeg, IMG_8082.JPG, WLDN2NS00416- Checklist.pdf, WLDN2NS00416-LC.pdf, WLDN2NS00416- Scour Protection.pdf, N-21-179-532.pdf, N-21-179-530.pdf, N-21-179-534.pdf, Survey Report.pdf, Lot Map.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124798 | [5 empty] | 2021-08-18 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00415 | Jeramy Smith | 2021-05-10 02:16 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Drainage - Installation of Culverts | Roadworks | Ahmad Alwan | LX1828 -DDR2 - Pre-Cast Reinforced Concrete Pipes, RCBC's and End Structures Installation and Backfill (single DN600) | 2021-05-27 |  | 2021-06-07 10:00 | Sarah Brooks | 2021-07-31 | 2021-07-31 05:34 | Closed | AMS/N2NS/00004 | ITP/N2NS/00016, ITP/N2NS/00030 | [10 empty] | 627.75 | 627.95 | Sarah Brooks | 2021-07-31 05:34 |  | PNC/N2NS/00084 | Closed |  | HWP/N2NS/00168 | Lot closed |  | 2021-07-31 05:34 |  |  |  | Ahmad Alwan, Jeramy Smith, Loui Tannous, Samithy Heng |  | WLDN2NS00415- Lot Confromance.pdf, WLDN2NS00415- SW Checklist.pdf, WLDN2NS00415- Checklist.pdf, N-21-179-280- Test Report.pdf, Survey Report.pdf, Lot Map.pdf, SW Lot Map.pdf, N-21-179-275.pdf, IMG_8078.JPG, IMG_8077.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124797 | [5 empty] | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00414 | Loui Tannous | 2021-05-09 21:46 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Loui Tannous | LX553 - Foundation for Embankment, Embankments, Upper Zone Formation & Select Material Zone (Kenimbler Road) |  |  | 2021-06-29 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025, CHK/N2NS/00026, CHK/N2NS/00029, CHK/N2NS/00030 | [9 empty] | 631.05 | 631.25 | [6 empty] | HWP/N2NS/00143 | [6 empty] | Ahmad Alwan, Grant Mills, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  | 7.jpg, 6.jpg | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124762
WLD/N2NS/00413 | Loui Tannous | 2021-05-09 21:40 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Earthworks - Subgrade Preparation | Earthworks | Loui Tannous | LX1828 - Foundation for Embankment, Embankments, Upper Zone Formation & Select Material Zone (Waterloo) | 2021-05-18 |  | 2021-06-22 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025, CHK/N2NS/00026, CHK/N2NS/00029, CHK/N2NS/00030 | [9 empty] | 627.75 | 627.95 | [6 empty] | HWP/N2NS/00110, HWP/N2NS/00262 | [6 empty] | Grant Mills, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124761
WLD/N2NS/00412 | Kallen Doong | 2021-05-09 05:13 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Topsoil Removal | Earthworks | Kallen Doong | Topsoil Removal - Stage 2 - CH631100 to CH633530 | 2021-05-09 |  | 2021-05-16 10:00 | Benjamin Philip | 2021-05-19 | 2021-05-19 01:23 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 631.1 | 633.53 | Paddy Montgomery | 2021-05-14 03:49 | [5 empty] | Lot closed |  | 2021-05-19 01:23 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton |  | lot map.pdf, IMG_0043.jpg, Topsoil Stripped Quantity Report Ch 631160 to Ch 633550 Lot WLD-N2NS-00412.pdf, Lot Conformance Report WLD-N2NS-00412.pdf, 14B3497F-486C-455B-B8B0-AC382A655105.JPG, 14F5F9E9-4FBB-4DBD-BBA8-55C196F8D638.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124758 | 2021-05-31 05:34 |  |  |  |  | 2021-05-23 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00411 | Keegan Baker | 2021-05-09 01:10 | Stage 2 - Penneys Road to Moree | Culverts | 635.145, 6/1800x600, remove and rebuild (RRA) | Culverts - Other | Concrete | Keegan Baker | Culvert 635.145 - Cast in Situ Base Slab | 2021-05-31 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-06-28 | 2021-06-28 01:08 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 |  |  |  | WLD/N2NS/00622 |  |  |  |  | MIX/N2NS/00007 | 635.15 | 635.15 | Benjamin Philip | 2021-06-28 01:08 |  |  |  |  | HWP/N2NS/00121 | Lot closed |  | 2021-06-28 01:08 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | WLDN2NS00411LM.pdf, IMG_0370.JPG, IMG_0371.JPG, N-21-179-236.pdf, EXP0039_N2NS_00411_0.pdf_635145.pdf, 635.145 (IMG_0752).JPG, WLDN2NS00411.1.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124757 | 2021-06-29 19:15 |  |  |  |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00410 | Keegan Baker | 2021-05-09 01:08 | Stage 2 - Penneys Road to Moree | Culverts | 631.580, 1/600x600, remove and rebuild | Culverts - Other | Concrete | Keegan Baker | Culvert 631.580 - Cast in Situ Base Slab | 2021-05-31 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-06-28 | 2021-06-28 01:13 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 |  |  |  | WLD/N2NS/00621 |  |  |  |  | MIX/N2NS/00007 | 631.58 | 631.58 | Nabin Koirala | 2021-06-27 05:27 |  |  |  |  | HWP/N2NS/00120 | Lot closed |  | 2021-06-28 01:13 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | WLDN2NS00410.pdf, WLDN2NS00410LM.pdf, EXP0035_N2NS_00410_0.pdf_631.580.pdf, N-21-179-385.pdf, EXP0035_N2NS_00410_0.pdf_631.580.pdf, IMG_0692.JPG, IMG_0691.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124756 | 2021-06-29 19:15 |  |  |  |  | 2021-07-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00409 | Keegan Baker | 2021-05-09 01:06 | Stage 2 - Penneys Road to Moree | Culverts | 630.925, 2/600x600, remove and rebuild (RRA) | Culverts - Other | Other | Keegan Baker | Culvert 630.925 - Cast in Situ Base Slab | 2021-05-16 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-06-28 | 2021-06-28 01:03 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [9 empty] | 630.93 | 630.93 | Nabin Koirala | 2021-06-27 06:10 |  |  |  |  | HWP/N2NS/00119 | Lot closed |  | 2021-06-28 01:03 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | WLDN2NS00409LM.pdf, N-21-179-239.pdf, Survey As_Built_EXP0036_N2NS_00409_0.pdf_630.925.pdf, 630.925 (IMG_0747).JPG, 630.925 (IMG_0746).JPG, WLDN2NS00409.1.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124755 | 2021-06-29 19:15 |  |  |  |  | 2021-07-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00408 | Nabin Koirala | 2021-05-08 23:43 | Stage 2 - Penneys Road to Moree | Culverts | 635.145, 6/1800x600, remove and rebuild (RRA) | Drainage - Other | Other | Keegan Baker | Excavation and Foundation Preparation of Drainage Structure | 2021-05-31 |  | 2021-05-22 10:00 | Benjamin Philip | 2021-06-25 | 2021-06-25 06:42 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 635.15 | 635.15 | Maddie Dahlstrom | 2021-06-25 06:02 |  |  |  |  | HWP/N2NS/00084, HWP/N2NS/00087 | Lot closed |  | 2021-06-25 06:42 | [5 empty] | N-21-179-349 KPa (635.145 Foundation DCP).pdf, N-21-179-349 (635.145 Foundation DCP).pdf, N-21-179-340 (635.145 Unsuitable Replacement Nukes).pdf, EXP0034_N2NS_00408_0.pdf_635.145.pdf, IMG_0159.JPG, 635.145.png, WLDN2NS00408LM.pdf, WLDN2NS00408.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124754 | 2021-06-29 19:15 |  |  |  |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00407 | Nabin Koirala | 2021-05-08 23:42 | Stage 2 - Penneys Road to Moree | Culverts | 631.580, 1/600x600, remove and rebuild | Drainage - Other | Other | Keegan Baker | Excavation and Foundation Preparation of Drainage Structure | 2021-05-31 |  | 2021-05-22 10:00 | Benjamin Philip | 2021-06-28 | 2021-06-28 01:20 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 631.58 | 631.58 | Maddie Dahlstrom | 2021-06-27 20:10 |  |  |  |  | HWP/N2NS/00090, HWP/N2NS/00091 | Lot closed |  | 2021-06-28 01:20 | [5 empty] | N-21-179-147 KPa (631.580 DCP).pdf, WLD N2NS 407_SWR190_Culvert 631580 Unsuitable Removal Volume.pdf, Lot Map.pdf, IMG_0518.JPG, 631.580.png, N-21-179-160 (631.580 Comp).pdf_revised.pdf, N-21-179-147 (631.580 DCP).pdf_rev.pdf, Signed Lot Conformance & Checklist.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124753 | 2021-06-29 19:15 |  |  |  |  | 2021-07-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00406 | Nabin Koirala | 2021-05-08 23:41 | Stage 2 - Penneys Road to Moree | Culverts | 630.925, 2/600x600, remove and rebuild (RRA) | Drainage - Other | Other | Keegan Baker | Excavation and Foundation Preparation of Drainage Structure | 2021-05-31 |  | 2021-05-22 10:00 | Benjamin Philip | 2021-06-25 | 2021-06-25 05:57 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 630.93 | 630.93 | Maddie Dahlstrom | 2021-06-25 05:27 |  |  |  |  | HWP/N2NS/00085, HWP/N2NS/00088 | Lot closed |  | 2021-06-25 05:57 | [5 empty] | TR199 Foundation DCPs.pdf, N-21-179-141 KPa (630.925 DCP).pdf, TR466 Unsuitable raplacement Nukes.pdf, EXP0033_N2NS_00406_0.pdf_630.925.pdf, WLDN2NS00406LM.pdf, IMG_0447.JPG, 630.925.png, WLDN2NS00406.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124752 | 2021-06-29 19:15 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00405 | Nabin Koirala | 2021-05-08 23:25 | Stage 2 - Penneys Road to Moree | Culverts | 635.145, 6/1800x600, remove and rebuild (RRA) | Culverts - Demolition | Other | Nabin Koirala | 635.145 - Demolition of Existing Culvert | 2021-05-16 |  | 2021-05-11 10:00 | Benjamin Philip | 2021-06-09 | 2021-06-09 03:35 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 |  |  |  | WLD/N2NS/00622 | [5 empty] | 635.15 | 635.15 | Maddie Dahlstrom | 2021-06-09 00:44 | [5 empty] | Lot closed |  | 2021-06-09 03:35 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom |  | 635.145_Demo lot markup.pdf, 786600FB-7829-47D7-ACB1-B40268F3F56C.JPG, 011999A7-DA23-4F18-B998-CE50259E5B04.JPG, 635.145.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124751 | 2021-06-29 19:15 |  |  |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00404 | Nabin Koirala | 2021-05-08 23:24 | Stage 2 - Penneys Road to Moree | Culverts | 631.580, 1/600x600, remove and rebuild | Culverts - Demolition | Other | Nabin Koirala | 631.580 - Demolition of Existing Culvert | 2021-05-16 |  | 2021-05-11 10:00 | Benjamin Philip | 2021-06-09 | 2021-06-09 03:30 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 |  |  |  | WLD/N2NS/00621 | [5 empty] | 631.58 | 631.58 | Maddie Dahlstrom | 2021-06-09 00:47 | [5 empty] | Lot closed |  | 2021-06-09 03:30 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom |  | 631.580_Demo Markup.pdf, E4D75847-D2B9-4093-9BB3-D7D09CFCF42B.JPG, C9BE685C-33F0-442A-B88C-A3E5762ED51E.JPG, 9F678DC2-6466-4DF0-B796-E33A8FADF5B1.JPG, 631.580.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124750 | 2021-06-29 19:15 |  |  |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00403 | Nabin Koirala | 2021-05-08 23:22 | Stage 2 - Penneys Road to Moree | Culverts | 630.925, 2/600x600, remove and rebuild (RRA) | Culverts - Demolition | Other | Nabin Koirala | 630.925 - Demolition of Existing Culvert | 2021-05-16 |  | 2021-05-11 10:00 | Benjamin Philip | 2021-06-09 | 2021-06-09 03:28 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 630.93 | 630.93 | Maddie Dahlstrom | 2021-06-09 02:55 | [5 empty] | Lot closed |  | 2021-06-09 03:28 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom |  | IMG_0363.JPG, IMG_0362.JPG, 630.925.pdf, 630.925 Scanned.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124749 | 2021-06-29 19:15 |  |  |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00402 | Kallen Doong | 2021-05-08 01:27 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Kallen Doong | Stage 2 - CH629.920 to CH630.920 - Cut Incl. Ground Preparation | 2021-05-16 |  | 2021-05-20 10:00 | Benjamin Philip | 2021-05-25 | 2021-05-25 06:49 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 629.92 | 630.92 | Paddy Montgomery | 2021-05-25 01:49 |  |  |  |  | HWP/N2NS/00092 | Lot closed |  | 2021-05-25 06:49 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | WLDN2NS00402.pdf, Foundation Conformance Report Ch 629920 to Ch 630900 Lot WLD-N2NS-00402.pdf, Lot Map 402.pdf, IMG_3961.JPG, IMG_3960.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124747 | 2021-05-31 05:34 |  |  |  |  | 2021-05-26 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00401 | Arjan Sidhu | 2021-05-08 01:06 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut inc Ground Prep CH638.100 to 638.500 | 2021-05-08 | 2021-05-10 | 2021-05-10 10:00 | Lorne Jenks | 2021-06-14 | 2021-06-14 00:23 | Closed | AMS/N2NS/00001 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 638.1 | 638.5 | James Martin | 2021-06-13 23:52 |  |  |  |  | HWP/N2NS/00081, HWP/N2NS/00100 | Lot closed |  | 2021-06-14 00:23 |  |  |  | Callum Todd, Kiara Davis, Paddy Montgomery, Richard Doering, Ryan Shenton |  | IMG_0020[1].JPG, wldn2ns00401.pdf, work lot 401.pdf, Foundation Conformance Report Ch 638100 to Ch 638500 Lot WLD-N2NS-00401.pdf, IMG_0024.JPG, Foundation Quantity Report Ch 638100 to Ch 638500 Lot WLD-N2NS-00401.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124746 | 2021-06-29 19:15 |  |  | 7632-2C41220 |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00400 | Arjan Sidhu | 2021-05-08 00:45 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Cut inc Ground Prep CH637.820 to 638.100 | 2021-05-07 | 2021-05-09 | 2021-05-10 10:00 | Lorne Jenks | 2021-06-14 | 2021-06-14 00:31 | Closed | AMS/N2NS/00001 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 637.82 | 638.1 | James Martin | 2021-06-13 23:51 |  |  |  |  | HWP/N2NS/00080, HWP/N2NS/00100 | Lot closed |  | 2021-06-14 00:31 |  |  |  | Callum Todd, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_0014[1].JPG, wldn2ns00400.pdf, Foundation Conformance Report Ch 637820 to Ch 638100 Lot WLD-N2NS-00400.pdf, lot map 400.pdf, IMG_0016.JPG, Foundation Quantity Report Ch 637820 to Ch 638100 Lot WLD-N2NS-00400.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124745 | 2021-06-29 19:15 |  |  | 7632-2C41220 |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00399 | Kallen Doong | 2021-05-07 07:51 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Kallen Doong | Insitu Stabilisation - 400mm - 627.587 to 627.876 @ 2% Lime | 2021-05-07 |  | 2021-05-14 10:00 | Sarah Brooks | 2021-08-02 | 2021-08-02 00:13 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 |  |  |  |  | WLD/N2NS/00395 | [5 empty] | 627.59 | 627.88 | Sarah Brooks | 2021-08-02 00:12 | [5 empty] | Lot closed |  | 2021-08-02 00:13 |  |  |  | James Martin, Richard Doering, Ryan Shenton |  | IMG_0364.jpg, IMG_0363.jpg, Foundation Floor Insitu Stabilised WLD-N2NS-00399.pdf, N-21-179-146.pdf, N-21-179-131.pdf, TR0178 Panda.pdf, wldn2ns00399.pdf, lot map 399.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124740 | [5 empty] | 2021-08-02 | Sarah Brooks | Submitted to ARTC for Review
WLD/N2NS/00398 | Ben Foster | 2021-05-07 07:30 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 25th April to 1st May 2021 TOTAL QTY - 77.05 Tonnes | 2021-05-07 | 2021-05-01 | 2021-05-01 10:00 | Sarah Brooks | 2021-05-19 | 2021-05-19 00:31 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 0 | 0 | Ben Foster | 2021-05-19 00:29 | [5 empty] | Lot closed |  | 2021-05-19 00:31 |  |  |  | Kiara Davis |  | 2CH-202104-0005-00076407-F.pdf, 2CH-202104-0011-00076427-F.PDF, 2CH-202104-0007-00076408-F.pdf, 7632-0024 Docket 1134077.pdf, 7632-0023 Docket 1133922.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124739 | 2021-05-31 05:34 | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551 |  | 2021-06-07 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00397 | Ben Foster | 2021-05-07 07:29 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 18th April to 24th April 2021 TOTAL QTY - 78.75 Tonnes | 2021-05-07 | 2021-04-24 | 2021-04-24 10:00 | Benjamin Philip | 2021-05-19 | 2021-05-19 01:45 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 0 | 0 | Ben Foster | 2021-05-17 07:14 | [5 empty] | Lot closed |  | 2021-05-19 01:45 |  |  |  | Kiara Davis |  | 2CH-202104-0009-00076426-F.PDF, 7632-0022 Docket 1133921.pdf, 7632-0007 Docket 1133838.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124738 | 2021-05-31 05:34 | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551 |  | 2021-05-23 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00396 | Ben Foster | 2021-05-07 07:28 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 11th April to 17th April 2021 TOTAL QTY - 82.88 Tonnes | 2021-05-07 | 2021-04-17 | 2021-04-17 10:00 | Benjamin Philip | 2021-05-19 | 2021-05-19 01:55 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 0 | 0 | Ben Foster | 2021-05-18 05:54 | [5 empty] | Lot closed |  | 2021-05-19 01:55 |  |  |  | Kiara Davis |  | Docket 1133795.pdf, Docket 1068030.pdf, 2AT-202104-0021-00076260-F.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124737 | 2021-05-31 05:34 | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551 |  | 2021-05-23 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00395 | Ben Foster | 2021-05-07 07:26 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 9th May to 15th May 2021 TOTAL QTY - 254.87 Tonnes | 2021-05-07 |  | 2021-05-15 10:00 | Sarah Brooks | 2021-06-01 | 2021-06-01 03:59 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 0 | 0 | Ben Foster | 2021-06-01 03:29 | [5 empty] | Lot closed |  | 2021-06-01 03:59 |  |  |  | Kiara Davis |  | 7632-0041 Docket 1028006.pdf, 7632-0041 Docket 1028005.pdf, 7632-0037 Docket 1028001.pdf, 7632-0037 Docket 1028000.pdf, 7632-0036 Docket 05404.pdf, 7632-0034 Docket 05403.pdf, 5406.pdf, 1028004.pdf, 1028003.pdf, 2CH-202105-0009-00076544-F.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124736 | 2021-06-29 19:15 | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551 |  | 2021-06-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00394 | Ben Foster | 2021-05-07 07:23 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Lime | Earthworks | Ben Foster | Lime Weekly Supply - 2nd May to 8th May 2021 TOTAL QTY - 167.70 Tonnes | 2021-05-07 | 2021-05-08 | 2021-05-08 10:00 | Benjamin Philip | 2021-05-19 | 2021-05-19 02:00 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 0 | 0 | Ben Foster | 2021-05-18 05:56 | [5 empty] | Lot closed |  | 2021-05-19 02:00 |  |  |  | Kiara Davis |  | Docket 1027985.pdf, Docket 1027982.pdf, 7632-0025 Docket 1027978.pdf, 7632-0032 Docket 1027994.pdf, 2CH-202105-0001-00076499-F.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124735 | 2021-05-31 05:34 | GRAYMONT (AUSTRALIA) PTY LTD | PKG/N2NS/00010 | 7632-GC41551 |  | 2021-05-23 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00393 | Ahmed Soliman | 2021-05-07 06:10 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Capping, inc Rail Maintenance Access Road | Earthworks | Hayden Murphy | LX3066 - Capping Incl. Rail Maintenance Access Track |  |  | 2021-05-19 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00012 | CHK/N2NS/00023, CHK/N2NS/00024 | PER/N2NS/00023 | [8 empty] | 634.4 | 634.6 | [6 empty] | HWP/N2NS/00404 | [6 empty] | Grant Mills, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124731
WLD/N2NS/00392 | Ahmed Soliman | 2021-05-07 06:03 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Culverts - Other | Other | Hayden Murphy | LX3066 - Installation of Concrete Road Culverts – Pipes and RCBC’s | 2021-07-06 |  | 2021-05-19 10:00 | Benjamin Philip | 2021-08-18 | 2021-08-18 01:18 | Closed | AMS/N2NS/00004 | ITP/N2NS/00030 | CHK/N2NS/00038, CHK/N2NS/00039, CHK/N2NS/00040, CHK/N2NS/00042 | PER/N2NS/00023 | [8 empty] | 634.4 | 634.6 | Benjamin Philip | 2021-08-18 01:18 |  |  |  |  | HWP/N2NS/00235, HWP/N2NS/00447 | Lot closed |  | 2021-08-18 01:18 |  |  |  | Grant Mills, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  | IMG_8083.JPG, IMG_8084.JPG, WLDN2NS00392-LC.pdf, WLDN2NS00390- Checklist.pdf, N-21-179-533.pdf, N-21-179-531.pdf, Survey Report.pdf, Lot Map.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124730 | [5 empty] | 2021-08-18 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00391 | Ahmed Soliman | 2021-05-07 04:05 | Stage 2 - Penneys Road to Moree | Ancillary Works | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Ancillary Works - Barriers, Handrail & Guardrail | Track | Hayden Murphy | LX3066 - Guardrail Installation |  |  | 2021-05-19 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00044 | [10 empty] | 634.4 | 634.6 | [13 empty] | Grant Mills, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124728
WLD/N2NS/00390 | Ahmed Soliman | 2021-05-07 03:51 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Pavements - Asphalt | Roadworks | Hayden Murphy | LX3066 - Asphalt |  |  | 2021-05-19 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00011 | CHK/N2NS/00046, CHK/N2NS/00047 | PER/N2NS/00023 | [8 empty] | 634.4 | 634.6 | [13 empty] | Grant Mills, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng | Aboriginal Employment Strategy Ltd |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124726
WLD/N2NS/00389 | Ahmed Soliman | 2021-05-07 03:34 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Pavements - Prime/Primer Seal | Roadworks | Hayden Murphy | LX3066 - Prime, Primerseal & Seal |  |  | 2021-05-19 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00009 | CHK/N2NS/00020, CHK/N2NS/00021 | PER/N2NS/00023 | [8 empty] | 634.4 | 634.6 | [13 empty] | Grant Mills, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124724
WLD/N2NS/00388 | Ahmed Soliman | 2021-05-07 03:30 | Stage 2 - Penneys Road to Moree | Trackwork | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Trackwork - Track Signage | Track | Hayden Murphy | LX3066 - Signage Installation |  |  | 2021-05-19 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00032 | CHK/N2NS/00018, CHK/N2NS/00043 | PER/N2NS/00023 | [8 empty] | 634.4 | 634.6 | [13 empty] | Grant Mills, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124723
WLD/N2NS/00387 | Danika Green | 2021-05-06 04:39 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Manufacture and supply of spherical bearings |  |  | 2021-12-04 11:00 |  |  |  | Planned | [12 empty] | 736 | 738 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124679
WLD/N2NS/00386 | Danika Green | 2021-05-06 04:33 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Insitu Concrete | Concrete | Laura Buckland | In-situ concrete - FRP Deck Slab (Span 3) |  |  | 2021-12-04 11:00 |  |  |  | Planned | [12 empty] | 736 | 738 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124678
WLD/N2NS/00385 | Danika Green | 2021-05-06 04:32 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Insitu Concrete | Concrete | Laura Buckland | In-situ concrete - FRP Deck Slab (Span 2) |  |  | 2021-12-04 11:00 |  |  |  | Planned | [12 empty] | 736 | 738 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124677
WLD/N2NS/00384 | Danika Green | 2021-05-06 04:32 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Insitu Concrete | Concrete | Laura Buckland | In-situ concrete - FRP Deck Slab (Span 1) |  |  | 2021-12-04 11:00 |  |  |  | Planned | [12 empty] | 736 | 738 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124676
WLD/N2NS/00383 | Danika Green | 2021-05-06 04:06 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Insitu Concrete | Concrete | Laura Buckland | In-situ concrete - FRP Abutment Headstock B |  |  | 2021-12-04 11:00 |  |  |  | Planned | [12 empty] | 736 | 738 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124675
WLD/N2NS/00382 | Danika Green | 2021-05-06 04:06 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Insitu Concrete | Concrete | Laura Buckland | In-situ concrete - FRP Abutment Headstock A |  |  | 2021-12-04 11:00 |  |  |  | Planned | [12 empty] | 736 | 738 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124674
WLD/N2NS/00381 | Paddy Montgomery | 2021-05-06 04:04 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Insitu Stabilisation + Dry Chew - 400mm - 626.860 to 627.110 @ 2% Lime | 2021-05-15 |  | 2021-05-14 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 626.87 | 627.11 | [13 empty] | Kallen Doong, Paddy Montgomery, Tahlor Swan |  | TR0177.pdf, TR0177 Panda.pdf, TR0177B.pdf, IMG_0285.jpg, IMG_0286.jpg, C3 Stabilised Floor Quantity Report Ch 626860 to Ch 627150 Lot WLD-N2NS-00381.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124672
WLD/N2NS/00380 | Danika Green | 2021-05-06 03:39 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Insitu Concrete | Concrete | Laura Buckland | In-situ concrete - FRP cross girder |  |  | 2021-12-04 11:00 |  |  |  | Planned | [12 empty] | 736 | 738 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124665
WLD/N2NS/00379 | Danika Green | 2021-05-06 03:35 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Insitu Concrete | Concrete | Laura Buckland | In-situ concrete - FRP Pier Headstock 1 |  |  | 2021-12-04 11:00 |  |  |  | Planned | [12 empty] | 736 | 738 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124664
WLD/N2NS/00378 | Danika Green | 2021-05-06 03:34 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Insitu Concrete | Concrete | Laura Buckland | In-situ concrete - FRP Pier Headstock 2 |  |  | 2021-12-04 11:00 |  |  |  | Planned | [12 empty] | 736 | 738 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124663
WLD/N2NS/00377 | Danika Green | 2021-05-06 00:48 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Insitu Concrete | Concrete | Laura Buckland | In-situ concrete - Access Stairs |  |  | 2021-12-04 11:00 |  |  |  | Planned | [12 empty] | 736 | 738 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124622
WLD/N2NS/00376 | Danika Green | 2021-05-06 00:21 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Structural Steel and Metalwork | Other | Laura Buckland | Install handrails and walkways |  |  | 2021-12-04 11:00 |  |  |  | Planned | [12 empty] | 736 | 738 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124620
WLD/N2NS/00375 | Danika Green | 2021-05-06 00:13 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Drainage, inc Rock and Scour Protection | Other | Laura Buckland | Scour Protection |  |  | 2021-12-04 11:00 |  |  |  | Planned | [12 empty] | 736 | 738 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124619
WLD/N2NS/00374 | Danika Green | 2021-05-06 00:07 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Excavation and Filling | Earthworks | Laura Buckland | Excavation, Fill and Blinding - Abutment Earthworks |  |  | 2021-12-04 11:00 |  |  |  | Planned | [12 empty] | 736 | 738 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124617
WLD/N2NS/00373 | Danika Green | 2021-05-06 00:04 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Ancillary Works - Other | Other | Laura Buckland | Landing Precast - Transition Slabs |  |  | 2021-12-04 11:00 |  |  |  | Planned | [12 empty] | 736 | 738 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124616
WLD/N2NS/00372 | Danika Green | 2021-05-05 23:48 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Landing precast - Super T Girders |  |  | 2021-11-18 11:00 |  |  |  | Planned | [12 empty] | 736 | 738 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124615
WLD/N2NS/00371 | Danika Green | 2021-05-05 23:41 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Install bridge bearings and pedestals |  |  | 2021-11-18 11:00 |  |  |  | Planned | [12 empty] | 736 | 738 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124613
WLD/N2NS/00370 | Danika Green | 2021-05-05 23:24 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Laydown and Platform Construction | 2021-05-30 |  | 2021-07-02 10:00 |  |  |  | Open | AMS/N2NS/00002 | ITP/N2NS/00002 | [10 empty] | 736 | 738 | [6 empty] | HWP/N2NS/00107, HWP/N2NS/00116, HWP/N2NS/00135 | [6 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124584
WLD/N2NS/00369 | Danika Green | 2021-05-05 23:20 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Insitu Concrete | Concrete | Laura Buckland | In-situ Concrete - FRP columns |  |  | 2021-12-04 11:00 |  |  |  | Planned | [12 empty] | 736 | 738 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124583
WLD/N2NS/00368 | Danika Green | 2021-05-05 22:40 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Insitu Concrete | Concrete | Laura Buckland | Installation of piles |  |  | 2021-08-22 10:00 |  |  |  | Planned | [12 empty] | 736 | 738 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124581
WLD/N2NS/00367 | Danika Green | 2021-05-05 22:11 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Structural Steel and Metalwork | Other | Laura Buckland | Pile Manufacturing - Supply of steel pile liners | 2021-05-30 | 2021-07-27 | 2021-07-22 10:00 | Benjamin Philip | 2021-07-27 | 2021-07-27 03:06 | Closed | AMS/N2NS/00020 | ITP/N2NS/00063 |  | PER/N2NS/00030 |  |  | WLD/N2NS/00366, WLD/N2NS/00368 | [5 empty] | 736 | 738 | Benjamin Philip | 2021-07-27 03:06 | [5 empty] | Lot closed |  | 2021-07-27 03:06 |  |  |  | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  | BR19-02.pdf, BR19-03.pdf, BR19-07.pdf, BR19-01.pdf, BR19-04.pdf, BR19-08.pdf, BR19-05.pdf, BR19-06.pdf, VE210723-02.pdf, Pile Inspection Log BR19.pdf, 21-111.1.pdf, 21-111.3.pdf, 21-111.2.pdf, ABFI Combined MDR BR19 01-08.zip | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124580 | 2021-07-29 18:40 | ABFI Steel Group Pty Ltd | PKG/N2NS/00022 |  |  | 2021-07-30 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00366 | Danika Green | 2021-05-05 21:53 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 735.115 Croppa Creek (23m ¦ 3 spans ¦ offline) | Bridgeworks - Demolition | Other | Laura Buckland | Demolition of existing bridge structure | 2021-05-30 |  | 2021-07-29 10:00 | Benjamin Philip | 2021-07-16 | 2021-07-16 05:49 | Closed | AMS/N2NS/00018 | ITP/N2NS/00026 | [10 empty] | 736 | 738 | Danika Green | 2021-07-15 01:04 | [5 empty] | Lot closed |  | 2021-07-16 05:49 |  |  |  | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  | Lot Map - Croppa Creek.pdf, Lot Conformance Report.pdf, Survey Report.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124579 | 2021-07-29 18:40 |  |  |  |  | 2021-07-17 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00365 | Ahmed Soliman | 2021-05-05 06:17 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Drainage - Level Crossing Table Drain | Earthworks | Hayden Murphy | LX3066 - Subsoil Drains | 2021-08-11 |  | 2021-05-12 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00010 | CHK/N2NS/00044 | PER/N2NS/00023 | [8 empty] | 634.4 | 634.6 | [6 empty] | HWP/N2NS/00379 | [6 empty] | Grant Mills, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124559
WLD/N2NS/00364 | Ahmed Soliman | 2021-05-05 06:04 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Pavements - Concrete Pavement | Asphalt | Hayden Murphy | LX3066 - Unbound Pavements |  |  | 2021-05-12 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | PER/N2NS/00023 | [8 empty] | 634.4 | 634.6 | [13 empty] | Grant Mills, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124556
WLD/N2NS/00363 | Ahmed Soliman | 2021-05-05 05:11 | Stage 2 - Penneys Road to Moree | Drainage | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Drainage - Stormwater Pits | Earthworks | Hayden Murphy | LX3066 - Conduit and Pit Installation |  |  | 2021-05-12 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00021 | CHK/N2NS/00045 | PER/N2NS/00023 | [8 empty] | 634.4 | 634.6 | [13 empty] | Grant Mills, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124553
WLD/N2NS/00362 | Ahmed Soliman | 2021-05-05 04:57 | Stage 2 - Penneys Road to Moree | Fencing | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Fencing - Fencing and Gates | Earthworks | Hayden Murphy | LX3066 - Fencing Installation |  |  | 2021-05-12 10:00 |  |  |  | Planned | AMS/N2NS/00004 | ITP/N2NS/00018 |  | PER/N2NS/00023 | [8 empty] | 634.4 | 634.6 | [13 empty] | Grant Mills, Hayden Murphy, Jeramy Smith, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124552
WLD/N2NS/00361 | Miaya Tighe | 2021-05-05 03:55 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Trackwork - Bottom Ballast | Track | Jake Mossman | Runnymede Quarry, Ballast Stockpile 5 5000T | 2021-05-10 |  | 2021-05-12 10:00 | Lorne Jenks | 2021-07-11 | 2021-07-10 21:08 | Closed | AMS/N2NS/00007 | ITP/N2NS/00007 | CHK/N2NS/00033 | [9 empty] | 625.55 | 666 | Jake Mossman | 2021-07-10 06:55 | [5 empty] | Lot closed |  | 2021-07-10 21:08 |  |  |  | Arjan Sidhu, Jake Mossman, Miaya Tighe |  | RU Ballast SP5 5-5-21 v2.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124551 | 2021-07-29 18:40 |  |  |  |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00360 | Keegan Baker | 2021-05-05 03:53 | Stage 2 - Penneys Road to Moree | Culverts | 627.280, 50/3000x2400, remove and rebuild | Culverts - Installation of Box Culverts | Concrete | Keegan Baker | Installation of Precast Culvert 627.280 | 2021-07-24 |  | 2021-07-07 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 | [8 empty] | MIX/N2NS/00007 | 640.08 | 640.08 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124550
WLD/N2NS/00359 | Keegan Baker | 2021-05-05 03:52 | Stage 2 - Penneys Road to Moree | Culverts | 639.740, 60/2400x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Keegan Baker | Installation of Precast Culvert 639.740 | 2021-07-24 |  | 2021-06-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 | [9 empty] | 639.74 | 639.74 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124549
WLD/N2NS/00358 | Keegan Baker | 2021-05-05 03:51 | Stage 2 - Penneys Road to Moree | Culverts | 638.920, 14/1800x600, new build | Culverts - Installation of Box Culverts | Other | Keegan Baker | Installation of Precast Culvert 638.920 | 2021-06-22 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-06-27 | 2021-06-27 04:31 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 | [9 empty] | 638.92 | 638.92 | Nabin Koirala | 2021-06-27 02:12 | [5 empty] | Lot closed |  | 2021-06-27 04:31 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | 638.920_Precast+Lot Map.pdf, EXP0032_N2NS_00346_0.pdf, Lot Map.pdf, 638.920 (IMG_0780).JPG, 638.920 (IMG_0778).JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124548 | 2021-06-29 19:15 |  |  |  |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00357 | Keegan Baker | 2021-05-05 03:50 | Stage 2 - Penneys Road to Moree | Culverts | 638.525, 13/2400x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Keegan Baker | Installation of Precast Culvert 638.525 | 2021-07-24 |  | 2021-06-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 | [9 empty] | 638.53 | 638.53 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124547
WLD/N2NS/00356 | Keegan Baker | 2021-05-05 03:49 | Stage 2 - Penneys Road to Moree | Culverts | 638.140, 5/2400x1200, remove and rebuild | Culverts - Installation of Box Culverts | Other | Keegan Baker | Installation of Precast Culvert 638.140 | 2021-06-22 |  | 2021-06-30 10:00 | Sarah Brooks | 2021-07-31 | 2021-07-31 05:28 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 | [9 empty] | 638.14 | 638.14 | Maddie Dahlstrom | 2021-07-29 20:29 | [5 empty] | Lot closed |  | 2021-07-31 05:28 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | Signed Lot Conformance & Checklist.pdf, EXP0052_N2NS_00356_0.pdf, Lot Map.pdf, Precast Unit Number Plan.pdf, IMG_0616.JPG, IMG_0615.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124546 | [5 empty] | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00355 | Jeramy Smith | 2021-05-05 03:47 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Clearing & Grubbing | Earthworks | Hayden Murphy | LX553 - Clearing & Grubbing (Incl. Topsoil Strip) | 2021-05-23 | 2021-06-25 | 2021-05-19 10:00 | Benjamin Philip | 2021-06-09 | 2021-06-08 05:41 | Closed | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010, CHK/N2NS/00011 | PER/N2NS/00009 | [8 empty] | 631.05 | 631.25 | Jeramy Smith | 2021-06-09 03:37 |  |  |  |  | HWP/N2NS/00129, HWP/N2NS/00130 | Lot closed |  | 2021-06-09 04:03 |  |  |  | Grant Mills, Jeramy Smith, Loui Tannous, Samithy Heng |  | LX0553 Topsoil Strip Survey.pdf, Clearing Permit CH625500 - CH631200 inc LX1828 LX553.pdf, LX553 CG Checklist.pdf, LX553 ST Checklist.pdf, LX553 Lot Conformance.pdf, LX553 CG Lot Map.pdf, Clearing Permit LX553.pdf, IMG_0405.JPG, IMG_0403.JPG, IMG_0389.JPG, IMG_0388.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124545 | 2021-06-29 19:15 |  |  |  |  | 2021-06-25 | Benjamin Philip | ARTC Accepted (Conforming)
WLD/N2NS/00354 | Keegan Baker | 2021-05-05 03:46 | Stage 2 - Penneys Road to Moree | Culverts | 637.290, 1/1800x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Keegan Baker | Installation of Precast Culvert 637.290 | 2021-06-22 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-07-20 | 2021-07-19 20:53 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 | [9 empty] | 637.29 | 637.29 | Benjamin Philip | 2021-07-19 20:53 | [5 empty] | Lot closed |  | 2021-07-19 20:53 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | WLDN2NS00354 Checklist.pdf, LLP0040_N2NS_00354_0.pdf, WLDN2NS00354LM.pdf, 637.290 (IMG_0770).JPG, 637.290 (IMG_0771.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124544 | 2021-07-29 18:40 |  |  |  |  | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00353 | Keegan Baker | 2021-05-05 03:45 | Stage 2 - Penneys Road to Moree | Culverts | 637.170, 1/1800x600, remove and rebuild | Culverts - Installation of Box Culverts | Other | Keegan Baker | Installation of Precast Culvert 637.170 | 2021-06-22 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-06-27 | 2021-06-27 04:35 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 | [9 empty] | 637.17 | 637.17 | Nabin Koirala | 2021-06-27 02:20 | [5 empty] | Lot closed |  | 2021-06-27 04:35 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | 637.170_Precast +Lot Map.pdf, EXP0038_N2NS_00343_0.pdf_637.170.pdf, 637.170 (IMG_0769).JPG, 637.170 (IMG_0769).JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124543 | 2021-06-29 19:15 |  |  |  |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00352 | Keegan Baker | 2021-05-05 03:44 | Stage 2 - Penneys Road to Moree | Culverts | 636.705, 4/600x600, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Keegan Baker | Installation of Precast Culvert 636.705 | 2021-05-31 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-06-27 | 2021-06-27 04:41 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 | [9 empty] | 636.71 | 636.71 | Nabin Koirala | 2021-06-27 02:25 | [5 empty] | Lot closed |  | 2021-06-27 04:41 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | 636.705_Precast+Lot Map.pdf, EXP0037_N2NS_00341_0.pdf_636.705.pdf, 636.705 (IMG_0767).JPG, 636.705 (IMG_0768).JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124542 | 2021-06-29 19:15 |  |  |  |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00351 | Danika Green | 2021-05-05 03:33 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 734.945 Croppa Creek Tributary (9m ¦ 9 spans ¦ offline) | Bridgeworks - Insitu Concrete | Concrete | Laura Buckland | In-situ concrete - Access Stairs |  |  | 2021-10-15 11:00 |  |  |  | Planned | [12 empty] | 740 | 742 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124539
WLD/N2NS/00350 | Danika Green | 2021-05-05 03:30 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 734.945 Croppa Creek Tributary (9m ¦ 9 spans ¦ offline) | Bridgeworks - Structural Steel and Metalwork | Other | Laura Buckland | Install handrails and walkways |  |  | 2021-10-15 11:00 |  |  |  | Planned | [12 empty] | 734 | 736 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124538
WLD/N2NS/00349 | Danika Green | 2021-05-05 03:27 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 734.945 Croppa Creek Tributary (9m ¦ 9 spans ¦ offline) | Bridgeworks - Drainage, inc Rock and Scour Protection | Other | Laura Buckland | Scour Protection |  |  | 2021-10-15 11:00 |  |  |  | Planned | [12 empty] | 734 | 736 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124537
WLD/N2NS/00348 | Danika Green | 2021-05-05 01:56 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 734.945 Croppa Creek Tributary (9m ¦ 9 spans ¦ offline) | Bridgeworks - Excavation and Filling | Earthworks | Laura Buckland | Excavation, Fill and Blinding - Abutment Earthworks |  |  | 2021-10-15 11:00 |  |  |  | Planned | [12 empty] | 734 | 736 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124531
WLD/N2NS/00347 | Danika Green | 2021-05-05 01:51 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 734.945 Croppa Creek Tributary (9m ¦ 9 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Landing Precast - Transition Slabs |  |  | 2021-09-15 10:00 |  |  |  | Planned | [12 empty] | 734 | 736 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124530
WLD/N2NS/00346 | Keegan Baker | 2021-05-05 01:36 | Stage 2 - Penneys Road to Moree | Culverts | 638.920, 14/1800x600, new build | Culverts - Other | Concrete | Keegan Baker | Culvert 638.920 - Cast in Situ Base Slab | 2021-05-22 |  | 2021-05-31 10:00 | Lorne Jenks | 2021-07-03 | 2021-07-02 22:05 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 638.92 | 638.92 | Keegan Baker | 2021-07-02 07:26 |  |  |  |  | HWP/N2NS/00113 | Lot closed |  | 2021-07-02 22:05 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | N-21-179-205.pdf, Signed Lot Conformance & Checklist.pdf, EXP0032_N2NS_00346_0.pdf, Lot Map.pdf, IMG_0175.JPG, IMG_0210.JPG, IMG_0174.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124527 | 2021-07-29 18:40 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00345 | Danika Green | 2021-05-05 01:35 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 734.945 Croppa Creek Tributary (9m ¦ 9 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Landing Precast - Wingwalls |  |  | 2021-09-15 10:00 |  |  |  | Planned | [12 empty] | 734 | 736 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124526
WLD/N2NS/00344 | Danika Green | 2021-05-05 01:33 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 734.945 Croppa Creek Tributary (9m ¦ 9 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Landing Precast - PSC Girders |  |  | 2021-09-15 10:00 |  |  |  | Planned | [12 empty] | 734 | 736 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124525
WLD/N2NS/00343 | Keegan Baker | 2021-05-05 01:32 | Stage 2 - Penneys Road to Moree | Culverts | 637.170, 1/1800x600, remove and rebuild | Culverts - Other | Concrete | Keegan Baker | Culvert 637.170 - Cast in Situ Base Slab | 2021-05-31 |  | 2021-05-31 10:00 | Benjamin Philip | 2021-07-01 | 2021-07-01 00:49 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 637.17 | 637.17 | Maddie Dahlstrom | 2021-07-01 00:38 |  |  |  |  | HWP/N2NS/00077 | Lot closed |  | 2021-07-01 00:49 |  |  |  | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | N-21-179-181 (003) (637.170 Concrete Results).pdf, EXP0038_N2NS_00343_0.pdf_637.170.pdf, Lot Map.pdf, IMG_0189.JPG, IMG_0336.JPG, Proposed steel arrangement - base slabs - small sized culverts.pdf, WLDN2NS00343.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124524 | 2021-07-29 18:40 |  |  |  |  | 2021-07-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00342 | Danika Green | 2021-05-05 01:28 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 734.945 Croppa Creek Tributary (9m ¦ 9 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Landing Precast - Headstock |  |  | 2021-09-15 10:00 |  |  |  | Planned | [12 empty] | 734 | 736 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124523
WLD/N2NS/00341 | Keegan Baker | 2021-05-05 01:28 | Stage 2 - Penneys Road to Moree | Culverts | 636.705, 4/600x600, remove and rebuild (RRA) | Culverts - Other | Concrete | Keegan Baker | Culvert 636.705 - Cast in Situ Base Slab | 2021-05-31 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-06-25 | 2021-06-25 04:17 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 636.71 | 636.71 | Keegan Baker | 2021-06-20 09:50 |  |  |  |  | HWP/N2NS/00076 | Lot closed |  | 2021-06-25 04:17 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | Signed Lot Conformance & Checklist.pdf, N-21-179-181 (003) (636.705 Concrete Results).pdf, EXP0037_N2NS_00341_0.pdf_636.705.pdf, Lot Map.pdf, IMG_0518.JPG, IMG_0188.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124522 | 2021-06-29 19:15 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00340 | Danika Green | 2021-05-05 01:19 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 734.945 Croppa Creek Tributary (9m ¦ 9 spans ¦ offline) | Bridgeworks - Insitu Concrete | Concrete | Laura Buckland | Installation of Piles | 2021-07-11 |  | 2021-08-16 10:00 |  |  |  | Open | AMS/N2NS/00020 | ITP/N2NS/00025, ITP/N2NS/00063 |  |  |  |  | WLD/N2NS/00339 |  |  |  |  | MIX/N2NS/00008 | 734 | 736 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  | ABFI Combined MDR BR17 1-10.zip | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124521
WLD/N2NS/00339 | Danika Green | 2021-05-05 01:09 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 734.945 Croppa Creek Tributary (9m ¦ 9 spans ¦ offline) | Bridgeworks - Structural Steel and Metalwork | Other | Laura Buckland | Pile Manufacturing - Supply of steel pile liners | 2021-05-30 |  | 2021-07-13 10:00 | Benjamin Philip | 2021-07-17 | 2021-07-17 02:22 | Closed | AMS/N2NS/00020 | ITP/N2NS/00063 |  | PER/N2NS/00030 |  |  | WLD/N2NS/00338, WLD/N2NS/00340 | [5 empty] | 734 | 736 | Benjamin Philip | 2021-07-17 02:22 | [5 empty] | Lot closed |  | 2021-07-17 02:22 |  |  |  | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  | BR18 - 20.pdf, BR18 - 18.pdf, BR18 - 02.pdf, BR18 - 14.pdf, BR18 - 17.pdf, BR18 - 04.pdf, BR18 - 16.pdf, BR18 - 03.pdf, BR18 - 11.pdf, BR18 - 19.pdf, BR18 - 13.pdf, BR18 - 15.pdf, BR18 - 12.pdf, BR18 - 10.pdf, BR18 - 06.pdf, BR18 - 08.pdf, BR18 - 01.pdf, BR18 - 09.pdf, BR18 - 07.pdf, BR18 - 05.pdf, Pile Inspection Inspection Log BR18.pdf, 21-106.2.pdf, VE210709-03.pdf, 21-106.1.pdf, 21-106.3 .pdf, ABFI Combined MDR BR18 1-20.zip | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124520 | 2021-07-29 18:40 | ABFI Steel Group Pty Ltd | PKG/N2NS/00022 |  |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00338 | Danika Green | 2021-05-05 01:01 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 734.945 Croppa Creek Tributary (9m ¦ 9 spans ¦ offline) | Bridgeworks - Demolition | Other | Laura Buckland | Demolition of existing bridge structure | 2021-05-30 |  | 2021-06-04 10:00 | Benjamin Philip | 2021-07-16 | 2021-07-16 04:37 | Closed | AMS/N2NS/00018 | ITP/N2NS/00026 | [10 empty] | 734 | 736 | Danika Green | 2021-07-15 01:06 | [5 empty] | Lot closed |  | 2021-07-16 04:37 |  |  |  | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  | Croppa Creek Trib - Lot Map.pdf, Lot Conformance Report.pdf, Survey Report.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124519 | 2021-07-29 18:40 |  |  |  |  | 2021-07-17 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00337 | Danika Green | 2021-05-05 00:53 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 734.945 Croppa Creek Tributary (9m ¦ 9 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Laydown and Platform Construction | 2021-05-30 |  | 2021-07-02 10:00 |  |  |  | Open | AMS/N2NS/00002 | ITP/N2NS/00002 | [10 empty] | 734 | 736 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124518
WLD/N2NS/00336 | Danika Green | 2021-05-05 00:36 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 734.945 Croppa Creek Tributary (9m ¦ 9 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Install bridge bearings and pedestals |  |  | 2021-09-29 10:00 |  |  |  | Planned | [12 empty] | 734 | 736 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124517
WLD/N2NS/00335 | Miaya Tighe | 2021-05-04 23:51 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Basecourse | Other | Jake Mossman | JCQ Runnymede DGB20 Stockpile 5 4000T | 2021-05-05 |  | 2021-05-12 10:00 | Benjamin Philip | 2021-05-25 | 2021-05-25 07:41 | Closed | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 625.55 | 666 | Miaya Tighe | 2021-05-24 01:50 | [5 empty] | Lot closed |  | 2021-05-25 07:41 | [5 empty] | RU DGB20 Lot5-21 26-4-21.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124514 | 2021-05-31 05:34 |  |  |  |  | 2021-05-26 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00334 | Danika Green | 2021-05-04 23:39 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 740.665 Yallaroi Creek (9m ¦ 6 spans ¦ offline) | Bridgeworks - Insitu Concrete | Concrete | Laura Buckland | In-situ concrete - Access Stairs |  |  | 2021-10-23 11:00 |  |  |  | Planned | [12 empty] | 740 | 742 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124513
WLD/N2NS/00333 | Danika Green | 2021-05-04 23:36 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 740.665 Yallaroi Creek (9m ¦ 6 spans ¦ offline) | Bridgeworks - Structural Steel and Metalwork | Other | Laura Buckland | Install handrails and walkways |  |  | 2021-10-23 11:00 |  |  |  | Planned | [12 empty] | 740 | 742 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124512
WLD/N2NS/00332 | Danika Green | 2021-05-04 23:23 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 740.665 Yallaroi Creek (9m ¦ 6 spans ¦ offline) | Bridgeworks - Drainage, inc Rock and Scour Protection | Other | Laura Buckland | Scour Protection |  |  | 2021-10-23 11:00 |  |  |  | Planned | [12 empty] | 740 | 742 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124509
WLD/N2NS/00331 | Miaya Tighe | 2021-05-04 23:22 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Earthworks - Filling | Other | Jake Mossman | Structural fill Stockpile 2 4000T | 2021-05-05 |  | 2021-05-12 10:00 | Lorne Jenks | 2021-07-11 | 2021-07-10 21:05 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 | [9 empty] | 625.55 | 666 | Jake Mossman | 2021-07-10 21:03 | [5 empty] | Lot closed |  | 2021-07-10 21:05 | [5 empty] | N-21-183-49.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124508 | 2021-07-29 18:40 |  |  |  |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00330 | Danika Green | 2021-05-04 23:19 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 740.665 Yallaroi Creek (9m ¦ 6 spans ¦ offline) | Bridgeworks - Excavation and Filling | Earthworks | Laura Buckland | Excavation, Fill and Blinding - Abutment Earthworks |  |  | 2021-10-23 11:00 |  |  |  | Planned | [12 empty] | 740 | 742 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124507
WLD/N2NS/00329 | Danika Green | 2021-05-04 23:14 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 740.665 Yallaroi Creek (9m ¦ 6 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Install bridge bearings and pedestals |  |  | 2021-09-23 10:00 |  |  |  | Planned | [12 empty] | 740 | 742 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124506
WLD/N2NS/00328 | Danika Green | 2021-05-04 23:12 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 740.665 Yallaroi Creek (9m ¦ 6 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Landing Precast - Headstock |  |  | 2021-09-23 10:00 |  |  |  | Planned | [12 empty] | 740 | 742 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124505
WLD/N2NS/00327 | Miaya Tighe | 2021-05-04 23:10 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Earthworks - Filling | Other | Jake Mossman | Structural fill, stockpile 1 4000t | 2021-05-05 |  | 2021-05-12 10:00 | Benjamin Philip | 2021-05-19 | 2021-05-19 02:14 | Closed | AMS/N2NS/00007 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 625.55 | 666 | Miaya Tighe | 2021-05-04 23:18 | [5 empty] | Lot closed |  | 2021-05-19 02:14 | [5 empty] | RU Structural Fill Lot1 17-4-21.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124504 | 2021-05-31 05:34 |  |  |  |  | 2021-05-23 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00326 | Danika Green | 2021-05-04 23:07 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 740.665 Yallaroi Creek (9m ¦ 6 spans ¦ offline) | Bridgeworks - Insitu Concrete | Concrete | Laura Buckland | Installation of Piles | 2021-07-18 |  | 2021-09-12 10:00 |  |  |  | Open | AMS/N2NS/00020 | ITP/N2NS/00025 |  |  |  |  | WLD/N2NS/00325 |  |  |  |  | MIX/N2NS/00008 | 740 | 742 | [6 empty] | HWP/N2NS/00240 | [6 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124503
WLD/N2NS/00325 | Danika Green | 2021-05-04 22:52 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 740.665 Yallaroi Creek (9m ¦ 6 spans ¦ offline) | Bridgeworks - Structural Steel and Metalwork | Other | Laura Buckland | Pile Manufacturing - Supply of steel pile liners | 2021-07-02 | 2021-07-02 | 2021-08-09 10:00 | Benjamin Philip | 2021-07-06 | 2021-07-05 23:06 | Closed | AMS/N2NS/00020 | ITP/N2NS/00063 |  | PER/N2NS/00030 |  |  | WLD/N2NS/00261, WLD/N2NS/00326 | [5 empty] | 740.67 | 740.72 | Benjamin Philip | 2021-07-05 23:05 | [5 empty] | Lot closed |  | 2021-07-05 23:06 |  |  |  | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  | BR20-01.pdf, BR20-03.pdf, BR20-13.pdf, BR20-10.pdf, BR20-08.pdf, BR20-11.pdf, BR20-09.pdf, BR20-14.pdf, BR20-02.pdf, BR20-07.pdf, BR20-06.pdf, BR20-12.pdf, BR20-05.pdf, BR20-04.pdf, 21-101.1.pdf, 21-101.2.pdf, 21-101.3 .pdf, VE210703-02.pdf, Pile Inspection Inspection Log BR20.pdf, ABFI Combined MDR BR20 1-14.zip | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124502 | 2021-07-29 18:40 | ABFI Steel Group Pty Ltd | PKG/N2NS/00022 |  |  | 2021-07-06 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00324 | Danika Green | 2021-05-04 06:32 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 740.665 Yallaroi Creek (9m ¦ 6 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Landing Precast - Transition Slabs |  |  | 2021-09-23 10:00 |  |  |  | Planned | [12 empty] | 740 | 742 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124495
WLD/N2NS/00323 | Danika Green | 2021-05-04 06:27 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 740.665 Yallaroi Creek (9m ¦ 6 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Landing Precast - Wingwalls |  |  | 2021-09-23 10:00 |  |  |  | Planned | [12 empty] | 740 | 742 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124494
WLD/N2NS/00322 | Danika Green | 2021-05-04 06:23 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 740.665 Yallaroi Creek (9m ¦ 6 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Landing Precast - PSC Girders |  |  | 2021-09-23 10:00 |  |  |  | Planned | [12 empty] | 740 | 742 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124493
WLD/N2NS/00321 | Danika Green | 2021-05-04 06:13 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 716.850 Gil Gil Creek (9m ¦ 4 spans ¦ offline) | Bridgeworks - Insitu Concrete | Concrete | Laura Buckland | In-situ concrete - Access Stairs |  |  | 2021-09-19 10:00 |  |  |  | Planned | [12 empty] | 716 | 718 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124490
WLD/N2NS/00320 | Danika Green | 2021-05-04 06:11 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 716.850 Gil Gil Creek (9m ¦ 4 spans ¦ offline) | Bridgeworks - Structural Steel and Metalwork | Other | Laura Buckland | Install handrails and Walkways |  |  | 2021-09-19 10:00 |  |  |  | Planned | [12 empty] | 716 | 718 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124488
WLD/N2NS/00319 | Danika Green | 2021-05-04 06:06 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 716.850 Gil Gil Creek (9m ¦ 4 spans ¦ offline) | Bridgeworks - Drainage, inc Rock and Scour Protection | Other | Laura Buckland | Scour Protection |  |  | 2021-09-19 10:00 |  |  |  | Planned | [12 empty] | 716 | 718 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124487
WLD/N2NS/00318 | Danika Green | 2021-05-04 06:03 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 716.850 Gil Gil Creek (9m ¦ 4 spans ¦ offline) | Bridgeworks - Excavation and Filling | Earthworks | Laura Buckland | Excavation, Fill and Blinding - Abutment Earthworks |  |  | 2021-09-19 10:00 |  |  |  | Planned | [12 empty] | 716 | 718 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124486
WLD/N2NS/00317 | Danika Green | 2021-05-04 06:00 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 716.850 Gil Gil Creek (9m ¦ 4 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Landing Precast - Transition Slabs |  |  | 2021-08-19 10:00 |  |  |  | Planned | [12 empty] | 716 | 718 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124485
WLD/N2NS/00316 | Danika Green | 2021-05-04 05:56 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 716.850 Gil Gil Creek (9m ¦ 4 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Landing Precast - Wingwalls |  |  | 2021-08-19 10:00 |  |  |  | Planned | [12 empty] | 716 | 718 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124484
WLD/N2NS/00315 | Danika Green | 2021-05-04 05:53 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 716.850 Gil Gil Creek (9m ¦ 4 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Landing Precast - PSC Girders |  |  | 2021-08-19 10:00 |  |  |  | Planned | [12 empty] | 716 | 718 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124483
WLD/N2NS/00314 | Danika Green | 2021-05-04 05:49 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 716.850 Gil Gil Creek (9m ¦ 4 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Install bridge bearings and pedestals |  |  | 2021-08-19 10:00 |  |  |  | Planned | [12 empty] | 716 | 718 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124482
WLD/N2NS/00313 | Danika Green | 2021-05-04 05:46 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 716.850 Gil Gil Creek (9m ¦ 4 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Landing Precast - Headstock |  |  | 2021-08-19 10:00 |  |  |  | Planned | [12 empty] | 716 | 718 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124481
WLD/N2NS/00312 | Danika Green | 2021-05-04 05:27 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 716.850 Gil Gil Creek (9m ¦ 4 spans ¦ offline) | Bridgeworks - Insitu Concrete | Other | Laura Buckland | Installation of Piles | 2021-06-29 |  | 2021-07-28 10:00 |  |  |  | Open | AMS/N2NS/00020 | ITP/N2NS/00025 |  |  |  |  | WLD/N2NS/00311 | [5 empty] | 716 | 718 | [6 empty] | HWP/N2NS/00212, HWP/N2NS/00291 | [6 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  | N2NS-SUR-055-1-A.pdf, N2NS-SUR-059-1-A.pdf, N2NS-SUR-062-1-A.pdf, N2NS-SUR-058-1-A.pdf, N2NS-SUR-060-1-A.pdf, N2NS-SUR-056-1-A.pdf, N2NS-SUR-054-1-A.pdf, N2NS-SUR-063-1-A.pdf, N2NS-SUR-053-1-A.pdf, N2NS-SUR-057-1-A.pdf, N2NS-SUR-061-1-A.pdf, 210721 - Concrete Pour Record - BR17.pdf, Inland Rail_Gil Gil Creek-AB-1-EOD.report.pdf, Inland Rail_Gil Gil Creek-AA-2-EOD.report.pdf, 3842 - REP011.0-Gil Gil Ck-P1-1 EOD-280621.pdf, Inland Rail_Gil Gil Creek-P3-2-EOD.report.pdf, Inland Rail_Gil Gil Creek-P1-1-RST.report.pdf, Inland Rail_Gil Gil Creek-AA-1-EOD.report.pdf, 3842 - REP012.0-Gil Gil Ck-P1-1 RST-280621.pdf, Inland Rail_Gil Gil Creek-P2-1-RST.report.pdf, 3842 - REP009.0-Gil Gil Ck-AB-1 EOD-280621.pdf, 3842 - REP010.0-Gil Gil Ck-AB-1 RST-280621.pdf, Inland Rail_Gil Gil Creek-P2-2-EOD.report.pdf, Inland Rail_Gil Gil Creek-P3-1-EOD.report.pdf, Inland Rail_Gil Gil Creek-P2-1-EOD.report.pdf, Inland Rail_Gil Gil Creek-P1-1-EOD.report.pdf, Inland Rail_Gil Gil Creek-AB-1-RST.report.pdf, Inland Rail_Gil Gil Creek-P1-2-EOD.report.pdf, Inland Rail_Gil Gil Creek-AB-2-EOD.report.pdf, 5-0018-260-PVP-00-TP-0025, Item 7.2 - Gil Gil Creek - Representative Piles.pdf, 5-0018-260-PVP-00-TP-0025, Item 5.5 - Trimming of Pile Casings - Gil Gil Creek.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124479
WLD/N2NS/00311 | Danika Green | 2021-05-04 05:15 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 716.850 Gil Gil Creek (9m ¦ 4 spans ¦ offline) | Bridgeworks - Structural Steel and Metalwork | Other | Laura Buckland | Pile Manufacturing - Supply of steel pile liners | 2021-05-30 |  | 2021-07-02 10:00 | Benjamin Philip | 2021-07-02 | 2021-07-01 23:39 | Closed | AMS/N2NS/00020 | ITP/N2NS/00063 |  | PER/N2NS/00030 |  |  | WLD/N2NS/00312 | [5 empty] | 716 | 718 | Benjamin Philip | 2021-07-01 23:38 | [5 empty] | Lot closed |  | 2021-07-01 23:39 |  |  |  | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  | BR17-02.pdf, BR17-10.pdf, BR17-03.pdf, BR17-05.pdf, BR17-08.pdf, BR17-01.pdf, BR17-09.pdf, BR17-06.pdf, BR17-04.pdf, BR17-07.pdf, VE210618-01.pdf, 21-94.2 .pdf, 21-94.3.pdf, 21-94.1.pdf, Pile Inspection Inspection Log BR17.pdf, ABFI Combined MDR BR17 1-10.zip | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124477 | 2021-07-29 18:40 | ABFI Steel Group Pty Ltd | PKG/N2NS/00022 |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00310 | Danika Green | 2021-05-04 04:42 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 716.850 Gil Gil Creek (9m ¦ 4 spans ¦ offline) | Bridgeworks - Other | Other | Laura Buckland | Laydown and Platform Construction | 2021-05-12 |  | 2021-06-16 10:00 |  |  |  | Open | AMS/N2NS/00018 | ITP/N2NS/00002 | [10 empty] | 716 | 718 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124474
WLD/N2NS/00309 | Richard Doering | 2021-05-04 04:42 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Richard Doering | Cut inc Ground Prep CH637.285 to 637.820 | 2021-06-10 |  | 2021-05-04 10:00 | Lorne Jenks | 2021-06-13 | 2021-06-12 23:41 | Closed | AMS/N2NS/00001 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 637.29 | 637.82 | Ryan Shenton | 2021-06-12 06:32 |  |  |  |  | HWP/N2NS/00078, HWP/N2NS/00100 | Lot closed |  | 2021-06-12 23:41 | [5 empty] | wldn2ns00309.pdf, Lot Mao 309.pdf, Foundation Quantity Report Ch 637285 to Ch 637820 Lot WLD-N2NS-00309.pdf, Foundation Conformance Report Ch 637285 to Ch 637820 Lot WLD-N2NS-00309 rv 2.pdf, IMG_1029.JPG, IMG_1028.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124473 | 2021-06-29 19:15 |  |  | 7632-2C41220 |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00308 | Jasmine Daly-Hayes | 2021-05-04 04:19 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Filling | Earthworks | Hayden Murphy | Earthworks - Unsuitable Materials |  |  | 2021-07-30 10:00 |  |  |  | Planned | AMS/N2NS/00004, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 634.49 | 634.49 | [13 empty] | Hayden Murphy, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124469
WLD/N2NS/00307 | Keegan Baker | 2021-05-04 01:50 | Stage 2 - Penneys Road to Moree | Culverts | 639.160, 14/1800x600, new build | Culverts - Installation of Box Culverts | Other | Keegan Baker | Installation of Precast Culvert 639.160 | 2021-06-22 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-06-27 | 2021-06-27 04:44 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00008 | [9 empty] | 630.93 | 630.93 | Nabin Koirala | 2021-06-27 02:41 | [5 empty] | Lot closed |  | 2021-06-27 04:44 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | WLDN2NS00307.pdf, 639.160_Precast+Lot Map.pdf, EXP0031_N2NS_00248_0 (1).pdf, 639.160 (IMG_0783).JPG, 639.160 (IMG_0782).JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124465 | 2021-06-29 19:15 |  |  |  |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00306 | Danika Green | 2021-05-04 01:26 | Stage 2 - Penneys Road to Moree | Bridgeworks | Bridge - 641.540, Gurley Creek (9m ¦ 13 spans) | Bridgeworks - Insitu Concrete | Concrete | Laura Buckland | In-situ concrete - Access Stairs |  |  | 2021-09-19 10:00 |  |  |  | Planned | [12 empty] | 640 | 642 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124463
WLD/N2NS/00305 | Danika Green | 2021-05-04 01:24 | Stage 2 - Penneys Road to Moree | Bridgeworks | Bridge - 641.540, Gurley Creek (9m ¦ 13 spans) | Bridgeworks - Structural Steel and Metalwork | Other | Laura Buckland | Install handrails and Walkways | 2021-08-17 |  | 2021-09-19 10:00 |  |  |  | Open | AMS/N2NS/00014 | ITP/N2NS/00026 | [10 empty] | 640 | 642 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124462
WLD/N2NS/00304 | Danika Green | 2021-05-04 01:20 | Stage 2 - Penneys Road to Moree | Bridgeworks | Bridge - 641.540, Gurley Creek (9m ¦ 13 spans) | Bridgeworks - Drainage, inc Rock and Scour Protection | Other | Laura Buckland | Scour Protection | 2021-07-18 |  | 2021-09-19 10:00 |  |  |  | Open | AMS/N2NS/00014 | ITP/N2NS/00026 | [10 empty] | 640 | 642 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  | Geofirma Conformance Certificate 2020.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124460
WLD/N2NS/00303 | Miaya Tighe | 2021-05-04 01:12 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Basecourse | Other | Jake Mossman | JCQ Runnymede DGB20 Stockpile 1 4000t | 2021-05-04 |  | 2021-05-27 10:00 | Benjamin Philip | 2021-07-04 | 2021-07-04 01:02 | Closed | AMS/N2NS/00004 | ITP/N2NS/00006 | CHK/N2NS/00022 | [9 empty] | 625.55 | 667 | Arjan Sidhu | 2021-07-03 19:59 | [5 empty] | Lot closed |  | 2021-07-04 01:02 |  |  |  | Arjan Sidhu, Jake Mossman, Miaya Tighe |  | RU DGB20 Lot1-21 24-2-21.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124459 | 2021-07-29 18:40 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00302 | Danika Green | 2021-05-04 01:11 | Stage 2 - Penneys Road to Moree | Bridgeworks | Bridge - 641.540, Gurley Creek (9m ¦ 13 spans) | Bridgeworks - Excavation and Filling | Earthworks | Laura Buckland | Excavation, Fill and Blinding - Abutment Earthworks |  |  | 2021-09-19 10:00 |  |  |  | Planned | AMS/N2NS/00014 | ITP/N2NS/00026 | [10 empty] | 640 | 642 | [6 empty] | HWP/N2NS/00231, HWP/N2NS/00299, HWP/N2NS/00329 | [6 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124458 |  |  |  | 7632-2C41223
WLD/N2NS/00301 | Danika Green | 2021-05-04 01:00 | Stage 2 - Penneys Road to Moree | Bridgeworks | Bridge - 641.540, Gurley Creek (9m ¦ 13 spans) | Bridgeworks - Other | Other | Laura Buckland | Landing Precast - Transition Slabs | 2021-07-18 |  | 2021-08-19 10:00 |  |  |  | Open | AMS/N2NS/00014 | ITP/N2NS/00026 | [10 empty] | 640 | 642 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124457
WLD/N2NS/00300 | Miaya Tighe | 2021-05-04 00:58 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Capping | Other | Jake Mossman | JCQ Runnymede Capping Supply 400t Stockpile 10 | 2021-05-04 |  | 2021-05-27 10:00 | Sarah Brooks | 2021-06-03 | 2021-06-03 06:16 | Closed | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023, CHK/N2NS/00024 | [9 empty] | 625.55 | 667 | Miaya Tighe | 2021-06-03 06:11 | [5 empty] | Lot closed |  | 2021-06-03 06:16 |  |  |  | Arjan Sidhu, Jake Mossman, Miaya Tighe |  | RU Capping Lot 10-21 29-4-21.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124456 | 2021-06-29 19:15 |  |  |  |  | 2021-06-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00299 | Danika Green | 2021-05-04 00:57 | Stage 2 - Penneys Road to Moree | Bridgeworks | Bridge - 641.540, Gurley Creek (9m ¦ 13 spans) | Bridgeworks - Other | Other | Laura Buckland | Landing Precast - Wingwalls |  |  | 2021-08-19 10:00 |  |  |  | Planned | [12 empty] | 640 | 642 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124455
WLD/N2NS/00298 | Danika Green | 2021-05-04 00:54 | Stage 2 - Penneys Road to Moree | Bridgeworks | Bridge - 641.540, Gurley Creek (9m ¦ 13 spans) | Bridgeworks - Other | Other | Laura Buckland | Landing Precast - PSC Girders | 2021-08-17 |  | 2021-08-19 10:00 |  |  |  | Open | AMS/N2NS/00014 | ITP/N2NS/00026 | [10 empty] | 640 | 642 | [13 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124454
WLD/N2NS/00297 | Miaya Tighe | 2021-05-04 00:47 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Capping | Other | Miaya Tighe | JCQ Runnymede Capping Supply - 4000t Stockpile 9 | 2021-05-04 |  | 2021-05-26 10:00 | Benjamin Philip | 2021-05-04 | 2021-05-04 02:53 | Closed | AMS/N2NS/00007 | ITP/N2NS/00012 | CHK/N2NS/00023, CHK/N2NS/00024 | [9 empty] | 625.55 | 667 | Miaya Tighe | 2021-05-04 00:51 | [5 empty] | Lot closed |  | 2021-05-04 02:53 | [5 empty] | RU Capping Lot 9-21 22-4-21.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124453 | 2021-05-31 05:34 |  |  |  |  | 2021-05-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00296 | Danika Green | 2021-05-04 00:47 | Stage 2 - Penneys Road to Moree | Bridgeworks | Bridge - 641.540, Gurley Creek (9m ¦ 13 spans) | Bridgeworks - Other | Other | Laura Buckland | Install bridge bearings and pedestals | 2021-07-18 |  | 2021-08-19 10:00 |  |  |  | Open | AMS/N2NS/00014 | ITP/N2NS/00026 | [10 empty] | 640 | 642 | [6 empty] | HWP/N2NS/00451 | [6 empty] | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124452
WLD/N2NS/00295 | Danika Green | 2021-05-04 00:27 | Stage 2 - Penneys Road to Moree | Bridgeworks | Bridge - 641.540, Gurley Creek (9m ¦ 13 spans) | Bridgeworks - Precast Concrete | Other | Laura Buckland | Landing Precast - Headstocks | 2021-07-11 | 2021-07-29 | 2021-07-29 10:00 |  |  |  | Open | AMS/N2NS/00014 | ITP/N2NS/00026 | [10 empty] | 640 | 642 | [6 empty] | HWP/N2NS/00450 | [6 empty] | Chris Chant, Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  | N-21-179-689.pdf, N-21-179-673.pdf, N-21-179-707.pdf, N-21-179-643.pdf, N-21-179-617.pdf, N-21-179-618.pdf, N-21-179-665.pdf, N2NS-SUR-121-1-A.pdf, N2NS-SUR-120-1-A.pdf, N2NS-SUR-123-1-A.pdf, N2NS-SUR-116-1-A.pdf, N2NS-SUR-119-1-A.pdf, N2NS-SUR-115-1-A.pdf, N2NS-SUR-128-1-A.pdf, N2NS-SUR-118-1-A.pdf, N2NS-SUR-117-1-A.pdf, N2NS-SUR-124-1-A.pdf, N2NS-SUR-122-1-A.pdf, N2NS-SUR-125-1-A.pdf, N2NS-SUR-127-1-A.pdf, N2NS-SUR-126-1-A.pdf, Gurley Creek Precast CoC.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124451
WLD/N2NS/00294 | Danika Green | 2021-05-04 00:21 | Stage 2 - Penneys Road to Moree | Bridgeworks | Bridge - 641.540, Gurley Creek (9m ¦ 13 spans) | Bridgeworks - Insitu Concrete | Other | Laura Buckland | Installation of Piles for Bridges - Gurley Creek | 2021-06-05 |  | 2021-07-28 10:00 | Benjamin Philip | 2021-08-14 | 2021-08-14 06:17 | Closed | AMS/N2NS/00020 | ITP/N2NS/00025 |  | PER/N2NS/00029, PER/N2NS/00032 |  |  | WLD/N2NS/00222, WLD/N2NS/00293 |  |  |  |  | MIX/N2NS/00008 | 640 | 642 | Benjamin Philip | 2021-08-14 06:17 |  | PNC/N2NS/00080 | Closed |  | HWP/N2NS/00180 | Lot closed |  | 2021-08-14 06:17 |  |  |  | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  | 210605 Gurley Bridge Pile Setout Points.pdf, Ron Adams-Grey Card_issued 12.08.16.jpg, John Gauci-SOA-Grey Card-NSW, ACT-22.01.15.pdf, Jones, Byron - Grey Card.jpg, Michael Barrett-Grey Card_issued 12.08.16.jpg, Adam Benson-SOA-Grey Card-(NSW,ACT)-22.01.15.pdf, Grant Reeves-Card-Grey-(NSW,ACT)-22.01.15.pdf, Jason McKenna-RMS Grey Card Certificate-22.03.17.pdf, Mal Rochester-RMS Grey Card.docx, IMG_0155.JPG, IMG_0173.JPG, Item 4.3 HP Release - Concrete Mix.pdf, RFI - Pile Cage Spacer.pdf, Piling Overflow.pdf, B80-Admixture on Site.pdf, Item 4.1 HP Release.pdf, IMG_0177.JPG, IMG_0176.JPG, IMG_0173.JPG, N2NS-SUR-038-1-A - P8-1.pdf, N2NS-SUR-033-1-A - P12-1.pdf, N2NS-SUR-049-1-A - AA-1.pdf, N2NS-SUR-030-1-A - P11-1.pdf, N2NS-SUR-041-1-A - P6-2.pdf, N2NS-SUR-025-1-A - P4-2.pdf, N2NS-SUR-024-1-A - AA-2.pdf, N2NS-SUR-035-1-A - P10-2.pdf, N2NS-SUR-037-1-A - P9-2.pdf, N2NS-SUR-031-1-A P11-2.pdf, N2NS-SUR-026-1-A - P10-1.pdf, N2NS-SUR-029-1-A - P7-2.pdf, N2NS-SUR-027-1-A - AB-2.pdf, N2NS-SUR-028-1-A - P12-2.pdf, N2NS-SUR-052-1-A - P3-1.pdf, N2NS-SUR-051-1-A - P2-1.pdf, N2NS-SUR-050-1-A - P1-1.pdf, N2NS-SUR-048-1-A - P1-2.pdf, N2NS-SUR-047-1-A - P2-2.pdf, N2NS-SUR-046-1-A - P3-2.pdf, N2NS-SUR-042-1-A - P5-2.pdf, N2NS-SUR-044-1-A - P6-1.pdf, N2NS-SUR-045-1-A - P4-1.pdf, N2NS-SUR-043-1-A - P5-1.pdf, N2NS-SUR-040-1-A - P7-1.pdf, N2NS-SUR-039-1-A - P8-2.pdf, N2NS-SUR-036-1-A - P9-1.pdf, N2NS-SUR-032-1-A - PAB-1.pdf, Inland Rail_Gurley Creek-P9-1-EOD.report.pdf, Inland Rail_Gurley Creek-P3-1-EOD.report.pdf, Inland Rail_Gurley Creek-P11-2-EOD.report.pdf, Inland Rail_Gurley Creek-AB-1-EOD.report.pdf, 3842 - REP008.0-Gurly Ck-P10-1 RST-160621.pdf, Inland Rail_Gurley Creek-P11-1-EOD.report.pdf, Inland Rail_Gurley Creek-P2-1-EOD.report.pdf, Inland Rail_Gurley Creek-P2-2-EOD.report.pdf, Inland Rail_Gurley Creek-P1-2-EOD.report.pdf, Inland Rail_Gurley Creek-AB-2-.report.pdf, Inland Rail_Gurley Creek-P1-1-EOD.report.pdf, N2NS_Gurley Creek-P7-2-PDM.report.pdf, Inland Rail_Gurley Creek-AA-1-EOD.report.pdf, Inland Rail_Gurley Creek-P12-2-EOD.report.pdf, 3842 - REP007.0-Gurly Ck-P7-2 RST-160621.pdf, N2NS_Gurley Creek-AA-2-PDM.report.pdf, Inland Rail_Gurley Creek-P12-1-RDV.report.pdf, Inland Rail_Gurley Creek-P11-2-RDV.report.pdf, Inland Rail_Gurley Creek-P5-2-EOD.report.pdf, Inland Rail_Gurley Creek-P8-2-EOD.report.pdf, Inland Rail_Gurley Creek-P10-1-PDM.report.pdf, Inland Rail_Gurley Creek-P10-2-EOD.report.pdf, Inland Rail_Gurley Creek-P9-2-EOD.report.pdf, Inland Rail_Gurley Creek-P5-1-EOD.report.pdf, Inland Rail_Gurley Creek-P4-1-EOD.report.pdf, Inland Rail_Gurley Creek-P8-1-EOD.report.pdf, Inland Rail_Gurley Creek-P7-1-EOD.report.pdf, Inland Rail_Gurley Creek-P6-1-EOD.report.pdf, Inland Rail_Gurley Creek-P6-2-EOD.report.pdf, Inland Rail_Gurley Creek-P4-2-PDM.report.pdf, Inland Rail_Gurley Creek-P3-2-EOD.report.pdf, 3842RBK01A - N2NS - Gurley Creek - P2-1.pdf, N-21-179-570.pdf, N-21-179-583.pdf, N-21-179-497.pdf, N-21-179-582.pdf, N-21-179-494.pdf, N-21-179-584.pdf, N-21-179-621.pdf, 5-0018-260-PVP-00-TP-0025, Item 4.3.pdf, 5-0018-260-PVP-00-TP-0025, Item 4.1.pdf, 5-0018-260-PVP-00-TP-0025, Item 4.4.pdf, 5-0018-260-PVP-00-TP-0025, Item 7.2 - Gurley Creek - Representative Piles.pdf, 5-0018-260-PVP-00-TP-0025, Item 5.5 - Trimming of Pile Casings(02).pdf, 5-0018-260-PVP-00-TP-0025, Item 5.5 - Trimming of Pile Casings(01).pdf, 5-0018-260-PVP-00-TP-0025, Item 5.5 - Trimming of Pile Casings(04).pdf, 5-0018-260-PVP-00-TP-0025, Item 5.5 - Trimming of Pile Casings.pdf, 5-0018-260-PVP-00-TP-0025, Item No 7.3 - Pile Integrity Testing.pdf, 7632-T4MR-CL-PVP-041 Checklist - Piling Administrative (Completed).pdf, 7632-T4MR-CL-PVP-042 Checklist - Piling Verification (Completed).pdf, 210706 - Concrete Dockets - BR07.pdf, 210714 - Concrete Dockets - BR07.pdf, 210708 - Concrete Dockets - BR07.pdf, 210626 - Concrete Dockets - BR07.pdf, 210623 - Concrete Dockets - BR07.pdf, 210629 - Concrete Dockets - BR07.pdf, 210624 - Concrete Dockets - BR07.pdf, 210713 - Concrete Dockets - BR07.pdf, 210624 - Concrete Pour Record - BR07.pdf, 210713 - Concrete Pour Record - BR07.pdf, 210623 - Concrete Pour Record - BR07.pdf, 210706 - Concrete Pour Record - BR07.pdf, 210714 - Concrete Pour Record - BR07.pdf, 210708 - Concrete Pour Record - BR07.pdf, 210629 - Concrete Pour Record - BR07.pdf, 210626 - Concrete Pour Record - BR07.pdf, 00294 - RFI - Concrete Plug.pdf, 00294 - RFI - 3-0001-260-SBD-00-DR-0015 - Pile Cage Spacer.pdf, 00294 - RFI - Admixture for Concrete.pdf, 00294 - RFI - End Plate.pdf, 00294 - RFI - Overflow Methodology.pdf, 5-0018-260-PVP-00-TP-0025, Item 4.4.pdf, N-21-179-625.pdf, AA-2 - TOP Conformity Letter.pdf, P11-1 - BOT Conformity Letter.pdf, AA-2 - BOT Conformity Letter.pdf, P12-2 - TOP Inspection Sheet.pdf, AA-1 - TOP Inspection Sheet.pdf, P11-1 - TOP Conformity Letter.pdf, P04-1 - BOT Inspection Sheet.pdf, AA-2 - BOT Inspection Sheet.pdf, AA-1 - TOP Conformity Letter.pdf, AA-1 - BOT Inspection Sheet.pdf, P12-2 - TOP Conformity Letter.pdf, P12-1 - BOT Inspection Sheet.pdf, AA-1 - BOT Conformity Letter.pdf, P07-1 - BOT Inspection Sheet.pdf, P12-1 - TOP Conformity Letter.pdf, P12-1 - TOP Inspection Sheet.pdf, P08-2 - TOP Conformity Letter.pdf, P12-2 - BOT Conformity Letter.pdf, P12-1 - BOT Conformity Letter.pdf, P11-2 - TOP Conformity Letter.pdf, P09-2 - TOP Inspection Sheet.pdf, P12-2 - BOT Inspection Sheet.pdf, P10-2 - TOP Inspection Sheet.pdf, P7-1 - TOP Conformity Letter.pdf, P11-2 - TOP Inspection Sheet.pdf, P11-2 - BOT Conformity Letter.pdf, P11-2 - BOT Inspection Sheet.pdf, P11-1 - TOP Inspection Sheet.pdf, P08-2 - BOT Conformity Letter.pdf, P08-2 - BOT Inspection Sheet.pdf, P10-1 - TOP Conformity Letter.pdf, P10-2 - TOP Conformity Letter.pdf, P11-1 - BOT Inspection Sheet.pdf, P10-2 - BOT Conformity Letter.pdf, P08-1 - BOT Conformity Letter.pdf, P10-1 - TOP Inspection Sheet.pdf, P09-2 - TOP Conformity Letter.pdf, P10-2 - BOT Inspection Sheet.pdf, P10-1 - BOT Conformity Letter.pdf, P10-1 - BOT Inspection Sheet.pdf, P09-2 - BOT Inspection Sheet.pdf, P09-1 - TOP Conformity Letter.pdf, P09-1 - TOP Inspection Sheet.pdf, P09-1 - BOT Inspection Sheet.pdf, P09-2 - BOT Conformity Letter.pdf, P09-1 - BOT Conformity Letter.pdf, P07-1 - BOT Conformity Letter.pdf, P05-1 - TOP Conformity Letter.pdf, P08-1 - TOP Conformity Letter.pdf, P6-2 - TOP Conformity Letter.pdf, Inner Cage - Inspection Sheet - P7, P8, P9, P10, P11, P12.pdf, P08-2 - TOP Inspection Sheet.pdf, P7-1 - TOP Inspection Sheet.pdf, P08-1 - TOP Inspection Sheet.pdf, P08-1 - BOT Inspection Sheet.pdf, P04-2 - TOP Conformity Letter.pdf, P06-2 - BOT Conformity Letter.pdf, P01-1 - TOP Inspection Sheet.pdf, P07-2 - TOP Conformity Letter.pdf, P07-2 - TOP Inspection Sheet.pdf, P07-2 - BOT Inspection Sheet.pdf, P07-2 - BOT Conformity Letter.pdf, P06-1 - BOT Conformity Letter.pdf, P6-1 - TOP Conformity Letter.pdf, P05-2 - BOT Conformity Letter.pdf, Inner Cage - Inspection Sheet - AA , AB, P1, P2.pdf, P6-1 - TOP Inspection Sheet.pdf, P6-2 - BOT Inspection Sheet.pdf, P05-1 - BOT Conformity Letter.pdf, P03-1 - TOP Inspection Sheet.pdf, P06-1 - BOT Inspection Sheet.pdf, P06-2 - BOT Inspection Sheet.pdf, AB-1 - BOT Inspection Sheet.pdf, P05-2 - TOP Conformity Letter.pdf, P05-2 - TOP Inspection Sheet.pdf, P05-2 - BOT Inspection Sheet.pdf, P03-2 - BOT Conformity Letter.pdf, AB-1 - TOP Inspection Sheet.pdf, P05-1 - TOP Inspection Sheet.pdf, P05-1 - BOT Inspection Sheet.pdf, P04-1 - TOP Conformity Letter.pdf, P04-2 - BOT Inspection Sheet.pdf, P04-2 - BOT Conformity Letter.pdf, P04-2 - TOP Inspection Sheet.pdf, P04-1 - BOT Conformity Letter.pdf, P04-1 - TOP Inspection Sheet.pdf, P01-1 - BOT Inspection Sheet.pdf, P03-2 - TOP Conformity Letter.pdf, Inner Cage - Inspection Sheet - P3, P4, P5, P6.pdf, P01-1 - TOP Conformity Letter.pdf, P03-2 - TOP Inspection Sheet.pdf, P03-2 - BOT Inspection Sheet.pdf, P02-2 - BOT Inspection Sheet.pdf, AB-2 - BOT Conformity Letter.pdf, P02-1 - BOT Conformity Letter.pdf, P03-1 - TOP Conformity Letter.pdf, P02-2 - TOP Conformity Letter.pdf, P03-1 - BOT Inspection Sheet.pdf, P02-1 - BOT Inspection Sheet.pdf, P01-1 - BOT Conformity Letter.pdf, P03-1 - BOT Conformity Letter.pdf, P02-1 - TOP Conformity Letter.pdf, P02-2 - TOP Inspection Sheet.pdf, P01-2 - TOP Conformity Letter.pdf, Inner Cage - Conformity Letter - P3, P4, P5, P6.pdf, P02-1 - TOP Inspection Sheet.pdf, P02-2 - BOT Conformity Letter.pdf, P01-2 - TOP Inspection Sheet.pdf, AB-2 - BOT Inspection Sheet.pdf, P01-2 - BOT Conformity Letter.pdf, P01-2 - BOT Inspection Sheet.pdf, AA-2 - TOP Inspection Sheet.pdf, Inner Cage - Conformity Letter - AA , AB, P1, P2.pdf, AB-2 - TOP -Inspection Sheet.pdf, AB-2 - TOP Conformity Letter.pdf, Inner Cage - Conformity Letter - P7, P8, P9, P10, P11, P12.pdf, AB-1 - BOT Conformity Letter.pdf, AB-1 - TOP Conformity Letter.pdf, 5-0018-260-PVP-00-TP-0025 - Lot Conformance Report.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124450 |  | Caporn Piling | PKG/N2NS/00025 | 7632-GS43150 |  | 2021-08-14 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00293 | Danika Green | 2021-05-04 00:15 | Stage 2 - Penneys Road to Moree | Bridgeworks | Bridge - 641.540, Gurley Creek (9m ¦ 13 spans) | Bridgeworks - Structural Steel and Metalwork | Other | Laura Buckland | Pile Manufacturing- Supply of steel pile liners | 2021-05-28 |  | 2021-06-17 10:00 | Benjamin Philip | 2021-06-14 | 2021-06-12 02:25 | Closed | AMS/N2NS/00020 | ITP/N2NS/00063 |  | PER/N2NS/00030 |  |  | WLD/N2NS/00294 | [5 empty] | 640 | 642 | Benjamin Philip | 2021-06-13 22:40 | [5 empty] | Lot closed | NDT Reports Updated. | 2021-06-13 22:41 |  |  |  | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  | 21-85.1.pdf, 21-85.2.pdf, N2NS - BR07-09.pdf, N2NS - BR07-11.pdf, N2NS - BR07-12.pdf, N2NS - BR07-15.pdf, N2NS - BR07-06.pdf, N2NS - BR07-13.pdf, N2NS - BR07-07.pdf, N2NS - BR07-05.pdf, N2NS - BR07-03.pdf, N2NS - BR07-02.pdf, N2NS - BR07-04.pdf, N2NS - BR07-01.pdf, N2NS - BR07-20.pdf, N2NS - BR07-19.pdf, N2NS - BR07-18.pdf, N2NS - BR07-16.pdf, N2NS - BR07-14.pdf, N2NS - BR07-17.pdf, N2NS - BR07-10.pdf, N2NS - BR07-08.pdf, Pile Liners HP Release.pdf, Pile Liner Schedule HP Release.pdf, SAW 25 Rev2.pdf, GMAW 02 (Multirun fillet).pdf, Weld Bead Rev 1.pdf, 21-85.2.pdf, 21-85.1.pdf, 21-91.1.pdf, 21-91.2.pdf, N2NS BR07-24.pdf, N2NS BR07-25.pdf, N2NS BR07-26.pdf, N2NS BR07-21.pdf, N2NS BR07-22.pdf, N2NS BR07-23.pdf, N2NS BR07-28.pdf, N2NS BR07-27.pdf, Pile Inspection Log BR07.pdf, VE210609-03.pdf, ABFI Combined MDR BR07 1-28.zip | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124448 | 2021-06-29 19:15 | ABFI Steel Group Pty Ltd | PKG/N2NS/00022 |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00292 | Tahlor Swan | 2021-05-03 22:49 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - CH654.700 to CH655.000 - Insitu/Layer 1 | 2021-06-14 |  | 2021-08-01 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 654.7 | 655 | [13 empty] | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0478 Panda.pdf, TR0477 C.pdf, TR0477B.pdf, TR0477.pdf, TR0477 Panda A.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124445 |  |  |  | 7632-2C41552
WLD/N2NS/00291 | Tahlor Swan | 2021-05-03 22:48 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - CH635.700 to 635.810 - Layer 2 | 2021-05-31 | 2021-05-21 | 2021-05-21 10:00 | Benjamin Philip | 2021-06-09 | 2021-06-09 05:52 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00505 | [5 empty] | 635.7 | 635.81 | Paddy Montgomery | 2021-06-09 05:43 |  |  |  |  | HWP/N2NS/00115, HWP/N2NS/00185 | Lot closed |  | 2021-06-09 05:52 |  |  |  | James Martin, Richard Doering |  | E3 Stabilised Layer 2 Conformance Report Ch 635700 to Ch 635810 Lot WLD-N2NS-00291.pdf, IMG_4147.JPG, IMG_4171.JPG, TR0268.pdf, TR0267A.pdf, TR0267.pdf, TR0267 Panda .pdf, wldn2ns00291.pdf, lot map 291.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124444 | 2021-06-29 19:15 |  |  | 7632-2C41552 |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00290 | Tahlor Swan | 2021-05-03 22:47 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - CH638.500 to CH638.900 - Layer 1 | 2021-05-21 | 2021-05-21 | 2021-05-21 10:00 | Benjamin Philip | 2021-08-10 | 2021-08-10 05:00 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00505 | [5 empty] | 638.5 | 638.9 | Benjamin Philip | 2021-08-10 05:00 | [5 empty] | Lot closed |  | 2021-08-10 05:00 |  |  |  | James Martin, Richard Doering |  | Day 0 Compaction.pdf, Day 0 Pandas.pdf, Day 7 UCS.pdf, E3 Stabilised Fill Layer 1 Ch 638500 to Ch 638900 Lot WLD-N2NS-00290.pdf, 7624E89F-7BE6-4793-A7BF-4A17C3356407.JPG, B5CA1A69-01A3-4237-9CE0-48676CAE53B2.JPG, Test Request 0273 Panda Results.pdf, wldn2ns00290.pdf, wldn2ns00525.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124443 |  |  |  | 7632-2C41552 |  | 2021-08-10 | Benjamin Philip | Submitted to ARTC for Review
WLD/N2NS/00289 | Tahlor Swan | 2021-05-03 22:46 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - CH635.810 to 635970 - Layer 2 | 2021-05-31 | 2021-05-20 | 2021-05-20 10:00 | Lorne Jenks | 2021-06-13 | 2021-06-13 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 635.81 | 635.97 | Ryan Shenton | 2021-06-12 03:29 |  |  |  |  | HWP/N2NS/00115, HWP/N2NS/00185 | Lot closed |  | 2021-06-13 |  |  |  | James Martin, Richard Doering |  | E3 Stabilised Layer 2 Conformance Report Ch 635810 to Ch 635970 Lot WLD-N2NS-00289.pdf, IMG_4264.JPG, IMG_4263.JPG, TR0257A (2).pdf, TR0257 (1).pdf, TR0269 Panda (1).pdf, TR0270 Panda.pdf, TR0271 PANDA.pdf, TR0272 PANDA.pdf, wldn2ns00289.pdf, lot map 289.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124442 | 2021-06-29 19:15 |  |  | 7632-2C41552 |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00288 | Tahlor Swan | 2021-05-03 22:44 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - CH635.970 to 636.125 - Layer 2 | 2021-05-31 | 2021-05-20 | 2021-05-20 10:00 | Lorne Jenks | 2021-06-13 | 2021-06-13 00:21 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 635.97 | 636.13 | Ryan Shenton | 2021-06-12 03:50 |  |  |  |  | HWP/N2NS/00115, HWP/N2NS/00185 | Lot closed |  | 2021-06-13 00:21 |  |  |  | James Martin, Paddy Montgomery, Richard Doering |  | E3 Stabilised Fill Layer 2 Conformance Report Ch 635970 to Ch 636125 Lot WLD-N2NS-00288.pdf, IMG_4266.JPG, IMG_4265.JPG, TR0255A (1).pdf, TR0255 (1).pdf, TR0255 Panda (1).pdf, TR0275 Panda (1).pdf, wldn2ns00288.pdf, lot map 288.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124441 | 2021-06-29 19:15 |  |  | 7632-2C41552 |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00287 | Tahlor Swan | 2021-05-03 22:40 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - CH636125 to 636560 - Layer 2 | 2021-05-31 | 2021-05-19 | 2021-05-19 10:00 | Benjamin Philip | 2021-06-09 | 2021-06-09 05:49 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 636.13 | 636.56 | Paddy Montgomery | 2021-06-09 04:22 |  |  |  |  | HWP/N2NS/00115, HWP/N2NS/00185 | Lot closed |  | 2021-06-09 05:49 |  |  |  | James Martin, Paddy Montgomery, Richard Doering |  | TR0274 Panda.pdf, TR0240A.pdf, TR0240.pdf, TR0240 Panda.pdf, E3 Stabilised Fill Layer 2 Conformance Report Ch 636125 to Ch 636560 Lot WLD-N2NS-00287.pdf, IMG_4163.JPG, IMG_4167.JPG, wldn2ns00287.pdf, lot map 287.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124440 | 2021-06-29 19:15 |  |  | 7632-2C41552 |  | 2021-07-08 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00286 | Tahlor Swan | 2021-05-03 22:39 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - CH637120 to 637660 - Layer 1 400mm | 2021-05-28 | 2021-05-17 | 2021-05-17 10:00 | Lorne Jenks | 2021-07-09 | 2021-07-09 00:30 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00505 | [5 empty] | 637.12 | 637.66 | Lorne Jenks | 2021-07-09 00:29 | [5 empty] | Lot closed |  | 2021-07-09 00:30 |  |  |  | James Martin, Richard Doering |  | IMG_1040.JPG, IMG_1042.JPG, Day 3 Pandas.pdf, E3 Stabilised Fill Layer1 Ch 637120 to Ch 637660 Lot WLD-N2NS-00286.pdf, lot map 286.pdf, wldn2ns00286.pdf, Test Request 0223 Panda Results.pdf, Day 0 Compaction .pdf, Day 7 UCS .pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124439 | 2021-07-29 18:40 |  |  | 7632-2C41552 |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00285 | Tahlor Swan | 2021-05-03 22:38 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Ch636590 to 637120 - Layer 1 400mm | 2021-05-28 | 2021-05-16 | 2021-05-16 10:00 | Lorne Jenks | 2021-06-15 | 2021-06-15 05:33 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00505 | [5 empty] | 636.59 | 637.12 | Richard Doering | 2021-06-12 03:14 | [5 empty] | Lot closed | Closed with no photos due to limited WI-FI | 2021-06-15 05:33 |  |  |  | James Martin, Richard Doering |  | E3 Stabilised Fill Layer 1 Conformance Report Ch 636590 to Ch 637120 Lot WLD-N2NS-00285.pdf, TR0224 Panda.pdf, TR0223A.pdf, TR0223.pdf, TR0223 Panda (1).pdf, WLDN2NS00285.pdf, S66 Balo St21061115060.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124438 | 2021-06-29 19:15 |  |  | 7632-2C41552 |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00284 | Brendan Meagher | 2021-05-03 07:55 | Stage 3 - Camurra North to North Star | Culverts | 711.770, 11/3000x1200, remove and rebuild | Culverts - Demolition | Other | Nabin Koirala | Stage 3 - Demolition of Existing Structure - Ch 711.770 | 2021-05-16 |  | 2021-05-28 10:00 | Benjamin Philip | 2021-06-09 | 2021-06-09 05:28 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 639.27 | 730.32 | Maddie Dahlstrom | 2021-06-09 05:16 | [5 empty] | Lot closed |  | 2021-06-09 05:28 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS00284.pdf, WLDN2NS00284.pdf, Photo.jpg, Capture.PNG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124433 | 2021-06-29 19:15 |  |  |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00283 | Brendan Meagher | 2021-05-03 07:54 | Stage 3 - Camurra North to North Star | Culverts | 711.640, 15/3000x1500, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - Demolition of Existing Structure - Ch 711.640 | 2021-05-16 |  | 2021-04-30 10:00 | Benjamin Philip | 2021-06-09 | 2021-06-09 05:25 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 711.67 | 711.67 | Maddie Dahlstrom | 2021-06-09 05:11 | [5 empty] | Lot closed |  | 2021-06-09 05:25 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS00283.pdf, WLDN2NS00283.pdf, Capture.PNG, Photo.jpg | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124432 | 2021-06-29 19:15 |  |  |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00282 | Brendan Meagher | 2021-05-03 07:52 | Stage 3 - Camurra North to North Star | Culverts | 711.510, 6/3000x1200, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - Demolition of Existing Structure - Ch 711.510 | 2021-05-16 |  | 2021-04-30 10:00 | Benjamin Philip | 2021-06-09 | 2021-06-09 05:23 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00006 | [9 empty] | 711.53 | 711.53 | Maddie Dahlstrom | 2021-06-09 05:02 | [5 empty] | Lot closed |  | 2021-06-09 05:23 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS00282.pdf, WLDN2NS00282.pdf, IMG_0717.JPG, Capture.PNG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124431 | 2021-06-29 19:15 |  |  |  |  | 2021-07-06 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00281 | Brendan Meagher | 2021-05-03 07:40 | Stage 3 - Camurra North to North Star | Culverts | 711.410, 10/2400x900, new build | Culverts - Other | Concrete | Frank Paraha | 711.410 - Base Slab FRP | 2021-12-31 |  | 2021-04-30 10:00 | Benjamin Philip | 2021-06-25 | 2021-06-25 06:35 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 711.27 | 711.55 | Nabin Koirala | 2021-06-20 08:21 | [5 empty] | Lot closed |  | 2021-06-25 06:35 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | 7632-T4MR-FM-PVP-007 Concrete Pour Record - Culvert 711.410 Base Slab.pdf, 18ccff66-e7ff-4b44-bbd9-0db4b4811ba3.jpg, 53ed2c4a-dc0d-47d0-a166-c125dcce6266.jpg, fba54109-9bc9-4e38-bfc8-0a19cce948f6.jpg, 711.410 Base Slab 28-Day Concrete Compressive Strength Results (N-21-186-69).pdf, Completed Checklist_Base Slab.pdf, 711.410 Base Slab - Survey As-Built (EXP0042_N2NS_00281_0).pdf, 7632-T4MR-FM-PVP-007 Concrete Pour Record - Culvert 711.410 Base Slab.pdf, Lot Map_711.410.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124430 | 2021-06-29 19:15 |  |  | 7632-3S72150 |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00280 | Tahlor Swan | 2021-05-03 07:30 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - CH635700 to 636075 - Layer 1 400mm | 2021-05-15 | 2021-05-16 | 2021-05-16 10:00 |  |  |  | Open | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00395 | [5 empty] | 635.7 | 636.08 | [13 empty] | James Martin, Richard Doering |  | TR0221 Panda.pdf, TR0213 Panda.pdf, TR0213.pdf, TR0213A.pdf, TR0211.pdf, E3 Stabilised Fill Layer 1 Conformance Report Ch 635700 to Ch 636075 Lot WLD-N2NS-00280.pdf, TR0222 Panda.pdf, lot map 280.pdf, wldn2ns00280.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124429 |  |  |  | 7632-2C41552
WLD/N2NS/00279 | Tahlor Swan | 2021-05-03 07:29 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Richard Doering | Type E3 - Stage 2 - CH636075 to 636375 - Layer 1 - 400mm | 2021-05-28 |  | 2021-08-01 10:00 | Benjamin Philip | 2021-07-01 | 2021-06-29 03:11 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00395 | [5 empty] | 636.59 | 637.12 | Benjamin Philip | 2021-07-01 00:27 | [5 empty] | Lot closed |  | 2021-07-01 00:27 |  |  |  | James Martin, Richard Doering |  | E3 Stabilised Fill Layer 1 Conformance Report Ch 636075 to Ch 636375 Lot WLD-N2NS-00279.pdf, TR0196 Panda (1).pdf, TR0218 Panda.pdf, TR0196 (1).pdf, TR0196E (1).pdf, TR0196C (1).pdf, S66 Balo St21061115501.pdf, Worklot and Maps 279.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124428 | 2021-07-29 18:40 |  |  | 7632-2C41552 |  | 2021-07-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00278 | Tahlor Swan | 2021-05-03 07:28 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Richard Doering | Place holder lot - Stage 2aii |  |  | 2021-08-01 10:00 |  |  |  | Planned | [12 empty] | 647 | 658 | [6 empty] | HWP/N2NS/00075 | [6 empty] | James Martin, Richard Doering |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124426
WLD/N2NS/00277 | Tahlor Swan | 2021-05-03 07:27 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Richard Doering | Place holder lot - Stage 2aii |  |  | 2021-08-01 10:00 |  |  |  | Planned | [12 empty] | 647 | 658 | [6 empty] | HWP/N2NS/00074 | [6 empty] | James Martin, Richard Doering |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124425
WLD/N2NS/00276 | Tahlor Swan | 2021-05-03 07:27 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Richard Doering | Cut Inc Ground Prep, CH 652.030 - 652.530 | 2021-06-28 |  | 2021-08-01 10:00 | Benjamin Philip | 2021-06-29 | 2021-06-29 03:40 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 652.03 | 652.53 | Benjamin Philip | 2021-06-29 03:40 |  |  |  |  | HWP/N2NS/00073 | Lot closed |  | 2021-06-29 03:40 |  |  |  | James Martin, Richard Doering |  | Excavation Foundation Ch 652030 to Ch 652514 Lot WLD-N2NS-00276.pdf, 20210615_222145860_iOS.jpg, 20210615_222121708_iOS.jpg, S66 Balo St21062909140.pdf, S66 Balo St21062909141.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124424 | 2021-06-29 19:15 |  |  |  |  | 2021-07-01 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00275 | Tahlor Swan | 2021-05-03 07:26 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Richard Doering | Cut Inc Ground Prep, 652.530 - 653.120 |  |  | 2021-08-01 10:00 | Benjamin Philip | 2021-06-29 | 2021-06-29 03:22 | Closed | AMS/N2NS/00001 | ITP/N2NS/00001 | CHK/N2NS/00010 | [9 empty] | 652.53 | 653.12 | Benjamin Philip | 2021-06-29 03:22 |  |  |  |  | HWP/N2NS/00072 | Lot closed |  | 2021-06-29 03:22 |  |  |  | James Martin, Richard Doering |  | S66 Balo St21062909120.pdf, Foundation Excavation Ch 652550 to Ch 653110 Lot WLD-N2NS-00275.pdf, S66 Balo St21062909121.pdf, north end - post dewatering.jpg | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124423 | 2021-06-29 19:15 |  |  |  |  | 2021-07-06 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00274 | Tahlor Swan | 2021-05-03 07:25 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Richard Doering | Cut Inc Ground Preparation, CH 653.185 - 653.550 | 2021-06-29 |  | 2021-08-01 10:00 | Benjamin Philip | 2021-06-29 | 2021-06-29 03:34 | Closed | AMS/N2NS/00001 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 653.19 | 653.55 | Benjamin Philip | 2021-06-29 03:33 |  |  |  |  | HWP/N2NS/00071, HWP/N2NS/00183 | Lot closed |  | 2021-06-29 03:34 |  |  |  | James Martin, Richard Doering |  | S66 Balo St21062909130.pdf, overexcavation compaction results.pdf, Excavation Foundation Ch 653185 to Ch 653550 Lot WLD-N2NS-00274 (1).pdf, S66 Balo St21062909131.pdf, South end - foundation level - pre backfill.jpg, North end - foundation level - gravel to be overexcavated.jpg, North end - post excavation - ash&oversize pit.jpg | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124421 | 2021-06-29 19:15 |  |  |  |  | 2021-07-01 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00273 | Tahlor Swan | 2021-05-03 07:24 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Richard Doering | Cut inc Ground Prep | 2021-06-05 | 2021-06-12 | 2021-06-12 10:00 | Benjamin Philip | 2021-06-29 | 2021-06-29 03:02 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 654.28 | 655.2 | Benjamin Philip | 2021-06-29 03:02 |  |  |  |  | HWP/N2NS/00070, HWP/N2NS/00183, HWP/N2NS/00196 | Lot closed |  | 2021-06-29 03:02 |  |  |  | James Martin, Richard Doering |  | 20210613_013326922_iOS.jpg, 20210613_013454859_iOS.jpg, S66 Balo St21062909132.pdf, Excavation Foundation Ch 653800 to Ch 654280 Lot WLD-N2NS-00273 (1).pdf, S66 Balo St21062909133.pdf, TR0486.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124420 | 2021-06-29 19:15 |  |  | 7632-2C41220 |  | 2021-07-01 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00272 | Tahlor Swan | 2021-05-03 07:23 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Richard Doering | Cut inc Ground Prep | 2021-06-05 | 2021-06-12 | 2021-06-12 10:00 | Benjamin Philip | 2021-06-27 | 2021-06-27 04:52 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 653.8 | 654.8 | Richard Doering | 2021-06-27 02:51 |  |  |  |  | HWP/N2NS/00069, HWP/N2NS/00183 | Lot closed |  | 2021-06-27 04:52 |  |  |  | James Martin, Richard Doering |  | 20210613_013908589_iOS.jpg, 20210613_013635489_iOS.jpg, Excavation Foundation Ch 653800 to Ch 654280 Lot WLD-N2NS-00272.pdf, 272 checklist.pdf, 272 lot map.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124419 | 2021-06-29 19:15 |  |  | 7632-2C41220 |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00271 | Tahlor Swan | 2021-05-03 07:22 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Richard Doering | Stage 2 - CH635.190 to CH635.700 - Cut Incl. Ground Preparation | 2021-05-26 |  | 2021-05-28 10:00 | Lorne Jenks | 2021-06-23 | 2021-06-23 05:03 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 635.19 | 635.7 | Paddy Montgomery | 2021-06-23 05:01 |  |  |  |  | HWP/N2NS/00068, HWP/N2NS/00142 | Lot closed |  | 2021-06-23 05:03 |  |  |  | James Martin, Richard Doering |  | IMG_1126.JPG, IMG_1125.JPG, lot map 271.pdf, Excavation Foundation Ch 635190 to Ch 635700 Lot WLD-N2NS-00271.pdf, wldn2ns00271.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124418 | 2021-06-29 19:15 |  |  | 7632-2C41220 |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00270 | Tahlor Swan | 2021-05-03 07:20 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Richard Doering | Cut inc Ground Prep - CH638.500 to 638.900 | 2021-05-31 | 2021-05-18 | 2021-05-18 10:00 | Lorne Jenks | 2021-07-12 | 2021-07-11 23:46 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 638.5 | 638.9 | Lorne Jenks | 2021-07-11 23:46 |  |  |  |  | HWP/N2NS/00067 | Lot closed |  | 2021-07-11 23:46 |  |  |  | James Martin, Richard Doering |  | Excavation Foundation Ch 638500 to Ch 638900 Lot WLD-N2NS-00270.pdf, lot map 270.pdf, E666A139-FEFE-4472-AE35-D13D5645FDE6.JPG, wldn2ns00270.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124417 | 2021-07-29 18:40 |  |  | 7632-2C41220 |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00269 | Tahlor Swan | 2021-05-03 07:19 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Richard Doering | Cut, Inc Ground Prep - Stage 2 - CH635700 to CH636300 | 2021-05-13 |  | 2021-05-21 10:00 | Benjamin Philip | 2021-06-10 | 2021-06-10 00:34 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 635.7 | 636.31 | Paddy Montgomery | 2021-06-09 23:35 |  |  |  |  | HWP/N2NS/00066, HWP/N2NS/00086 | Lot closed |  | 2021-06-10 00:34 |  |  |  | James Martin, Richard Doering |  | IMG_1088.JPG, IMG_1083.JPG, Foundation Excavation Conformance Report Ch 635700 to Ch 636300 Lot WLD-N2NS-00269.pdf, wldn2ns00269.pdf, Lot Map 269.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124416 | 2021-06-29 19:15 |  |  | 7632-2C41220 |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00268 | Tahlor Swan | 2021-05-03 07:16 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Topsoil Removal | Earthworks | Richard Doering | Strip Topsoil - Stage 2aii | 2021-06-03 | 2021-06-06 | 2021-06-06 10:00 | Benjamin Philip | 2021-06-26 | 2021-06-25 23:12 | Closed | AMS/N2NS/00001 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 646.4 | 650 | Richard Doering | 2021-06-25 22:49 | [5 empty] | Lot closed |  | 2021-06-25 23:12 |  |  |  | James Martin, Richard Doering |  | Stripped Surface Area Ch 646400 to Ch 650000 Lot WLD-N2NS-00268.pdf, 20210615_224405138_iOS.jpg, 20210615_224446608_iOS.jpg, WLDN2NS00268.pdf, LOT MAPS 268.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124415 | 2021-06-29 19:15 |  |  | 7632-2C41190 |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00267 | Tahlor Swan | 2021-05-03 07:14 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Topsoil Removal | Earthworks | Richard Doering | Topsoil Strip - Stage 2aii | 2021-06-01 | 2021-06-03 | 2021-06-03 10:00 | Benjamin Philip | 2021-06-26 | 2021-06-25 23:16 | Closed | AMS/N2NS/00001 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 650 | 655.31 | Richard Doering | 2021-06-25 22:49 | [5 empty] | Lot closed |  | 2021-06-25 23:16 |  |  |  | James Martin, Richard Doering |  | Stripped Surface Area Ch 650000 to Ch 655310 Lot WLD-N2NS-00267.pdf, 20210615_224724235_iOS.jpg, 20210615_224658601_iOS.jpg, WLDN2NS00267.pdf, LOT MAPS 267.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124414 | 2021-06-29 19:15 |  |  | 7632-2C41190 |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00266 | Tahlor Swan | 2021-05-03 07:10 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Topsoil Removal | Earthworks | Richard Doering | Strip Topsoil | 2021-05-10 | 2021-05-15 | 2021-05-15 10:00 | Benjamin Philip | 2021-06-27 | 2021-06-27 04:55 | Closed | AMS/N2NS/00001 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 655.31 | 658.2 | Richard Doering | 2021-06-27 02:09 | [5 empty] | Lot closed |  | 2021-06-27 04:55 |  |  |  | James Martin, Richard Doering |  | Stripped Surface Area Ch 655310 to Ch 658200 Lot WLD-N2NS-00266.pdf, 20210615_230528369_iOS.jpg, WLDN2NS00266.pdf, LOT MAPS 266.pdf, 20210626_043724962_iOS.jpg, 20210626_043715999_iOS.jpg | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124413 | 2021-06-29 19:15 |  |  | 7632-2C41190 |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00265 | Tahlor Swan | 2021-05-03 07:07 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Clearing & Grubbing | Earthworks | Richard Doering | Place holder lot - Stage 2aii |  |  | 2021-08-01 10:00 |  |  |  | Abandoned | [12 empty] | 647 | 658 | [6 empty] | HWP/N2NS/00064, HWP/N2NS/00065 | [6 empty] | James Martin, Richard Doering |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124412
WLD/N2NS/00264 | Tahlor Swan | 2021-05-03 07:04 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Clearing & Grubbing | Earthworks | Richard Doering | Place holder lot - Stage 2aii |  |  | 2021-08-01 10:00 |  |  |  | Abandoned | [12 empty] | 647 | 658 | [6 empty] | HWP/N2NS/00061, HWP/N2NS/00063, HWP/N2NS/00187 | [6 empty] | James Martin, Richard Doering |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124411
WLD/N2NS/00263 | Hayden Murphy | 2021-05-03 07:03 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 641.060, LX556, Private (Type 2, 4.50m, rubber, sealed at crossing), RX-2 | Earthworks - Filling | Earthworks | Hayden Murphy | LX556 - RMS Embankments | 2021-05-03 |  | 2021-05-27 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00016 | CHK/N2NS/00025, CHK/N2NS/00026, CHK/N2NS/00030 | PER/N2NS/00024 | [8 empty] | 641 | 641.2 | [6 empty] | HWP/N2NS/00094, HWP/N2NS/00117 | [6 empty] | Grant Mills, Loui Tannous, Samithy Heng |  | 3.jpg, 5.jpg, 1.jpg, 2.jpg, 4.jpg | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124410 |  |  |  | 7632-2W47900
WLD/N2NS/00262 | Arjan Sidhu | 2021-05-03 06:57 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Culverts - Rock Protection | Other | Arjan Sidhu | Scour Rock Protection - 5000T | 2021-05-03 |  | 2021-05-21 10:00 | Lorne Jenks | 2021-07-10 | 2021-07-09 21:49 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00042 | [9 empty] | 640.08 | 640.8 | Arjan Sidhu | 2021-07-08 03:56 | [5 empty] | Lot closed |  | 2021-07-09 21:49 | [5 empty] | RU 400mm Rock 29-4-21.pdf, 21040794-PL.pdf, Sq210501smc.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124409 | 2021-07-29 18:40 |  |  |  |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00261 | Laura Buckland | 2021-05-03 03:37 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 740.665 Yallaroi Creek (9m ¦ 6 spans ¦ offline) | Bridgeworks - Demolition | Other | Laura Buckland | Demolition of existing bridge structure | 2021-05-30 |  | 2021-08-17 10:00 | Benjamin Philip | 2021-06-08 | 2021-06-08 06:49 | Closed | AMS/N2NS/00018 | ITP/N2NS/00026 | [10 empty] | 740.7 | 740.8 | Danika Green | 2021-06-08 06:14 | [5 empty] | Lot closed |  | 2021-06-08 06:49 |  |  |  | Dan Kandamby, Danika Green, Ryan Lloyd |  | Survey Report - EXP0040_N2NS_00261_0.pdf, WLDN2NS00261 (2).pdf, Lot Map-Yallaroi.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124404 | 2021-06-29 19:15 | IRONBARK DEMOLITION PTY LTD |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00260 | Ryan Shenton | 2021-05-02 03:25 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH625.980 to CH626.340 - Layer 1 - 400mm | 2021-06-01 |  | 2021-05-13 10:00 | Benjamin Philip | 2021-06-09 | 2021-06-09 04:38 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00395 | [5 empty] | 625.98 | 626.34 | Benjamin Philip | 2021-06-09 04:49 | [5 empty] | Lot closed | Photos Added | 2021-06-09 04:49 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | TR0147D.pdf, TR0147C.pdf, TR0147B.pdf, TR0147.pdf, TR0147 Panda.pdf, TR0168 Panda.pdf, E3 Stabilised Fill Layer 1 Conformance Report Ch 625980 to Ch 626340 Lot WLD-N2NS-00260.pdf, WLDN2NS00260.pdf, Lot Map 260.pdf, 87E0E5B7-1234-4157-982D-CFB6A70E1084.JPG, IMG_3913.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124327 | 2021-06-29 19:15 |  |  |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00259 | Keegan Baker | 2021-05-02 01:40 | Stage 2 - Penneys Road to Moree | Culverts | 638.525, 13/2400x900, remove and rebuild | Culverts - Other | Earthworks | Keegan Baker | Excavation and foundation preparation of drainage structure 638.525 | 2021-05-31 |  | 2021-05-31 10:00 | Lorne Jenks | 2021-07-02 | 2021-07-02 05:03 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 |  |  |  | WLD/N2NS/00709 | [5 empty] | 638.53 | 638.53 | Lorne Jenks | 2021-07-02 05:03 |  |  |  |  | HWP/N2NS/00137 | Lot closed |  | 2021-07-02 05:03 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | Signed Lot Conformance & Checklist.pdf, N-21-179-245 Re-Issue (638.525 DCP).pdf, N-21-179-245 (004) (638.525 DCP).pdf, N-21-179-288 (638.525 Compaction).pdf, Lot Map.pdf, IMG_0071.JPG, 638.525.png | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124326 | 2021-07-29 18:40 |  |  |  |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00258 | Keegan Baker | 2021-05-02 01:35 | Stage 2 - Penneys Road to Moree | Culverts | 637.290, 1/1800x900, remove and rebuild | Culverts - Other | Earthworks | Keegan Baker | Excavation and foundation preparation of drainage structure 637.290 | 2021-05-31 |  | 2021-05-31 10:00 | Benjamin Philip | 2021-06-25 | 2021-06-25 03:34 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 637.29 | 637.29 | Maddie Dahlstrom | 2021-06-25 02:05 |  |  |  |  | HWP/N2NS/00052, HWP/N2NS/00059, HWP/N2NS/00123, HWP/N2NS/00127 | Lot closed |  | 2021-06-25 03:34 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | N-21-179-118 (DCP).pdf, N-21-179-196 (637.290 Comp).pdf, N-21-179-118 (637.290 DCP).pdf, WLD N2NS 258_SWR315_Culvert 637290 Unsuitable Removal (Volume Wingwalls).pdf, EXP0029_N2NS_00258_0.pdf_637.290.pdf, 637.290.JPG, 637.290.png, WLDN2NS00258LM.pdf, WLDN2NS00258CL.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124325 | 2021-06-29 19:15 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00257 | James Martin | 2021-05-01 07:23 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Excavation (Cut) | Earthworks | James Martin | Cut Inc Ground Preparation - CH640800 - CH641100 | 2021-06-09 |  | 2021-05-14 10:00 | Benjamin Philip | 2021-07-20 | 2021-07-09 04:36 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 640.8 | 641.1 | Benjamin Philip | 2021-07-20 00:59 |  |  |  |  | HWP/N2NS/00307, HWP/N2NS/00308 | Lot closed |  | 2021-07-20 01:00 |  |  |  | Richard Doering |  | IMG_4174.JPG, IMG_4173.JPG, IMG_4395.JPG, Excavation Foundation Ch 640800 to Ch 641110 Lot WLD-N2NS-00257.pdf, TR0577.pdf, TR0581.pdf, lot map 257.pdf, wldn2ns00257.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124324 | 2021-07-29 18:40 |  |  | 7632-2C41220 |  | 2021-07-22 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00256 | Hayden Murphy | 2021-05-01 07:13 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Filling | Earthworks | Hayden Murphy | LX3066 - Earthworks | 2021-05-01 |  | 2021-05-12 10:00 |  |  |  | Open | AMS/N2NS/00004 | ITP/N2NS/00003 | CHK/N2NS/00016 | PER/N2NS/00023 | [8 empty] | 634.4 | 634.6 | [6 empty] | HWP/N2NS/00057 | [6 empty] | Grant Mills, Loui Tannous, Samithy Heng |  | 1.jpg, 2.jpg | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124323 |  |  |  | 7632-2W47900
WLD/N2NS/00255 | Hayden Murphy | 2021-05-01 06:35 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Topsoil Removal | Earthworks | Hayden Murphy | LX555 - Western Side Topsoil Strip | 2021-05-01 |  | 2021-05-04 10:00 | Benjamin Philip | 2021-07-27 | 2021-07-27 00:25 | Closed | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | PER/N2NS/00060 | [8 empty] | 636.2 | 636.4 | Jeramy Smith | 2021-07-26 23:28 | [5 empty] | Lot closed |  | 2021-07-27 00:25 |  |  |  | Grant Mills, Loui Tannous, Samithy Heng |  | Survey Report.pdf, Lot Map.pdf, 0FF3F050-3F5F-4C92-BCA8-D2AD20B5C7C6.jpeg, IMG_8071.jpg, IMG_8069.jpg, WLDN2NS00255- Checklist.pdf, WLDN2NS00255- LC.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124322 | 2021-07-29 18:40 |  |  |  |  | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00254 | Arjan Sidhu | 2021-05-01 06:27 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Offsite Manufacture/Supply - Other | Other | Arjan Sidhu | Structural Fill Material - 2000t Stockpile | 2021-05-01 |  | 2021-05-03 10:00 | Benjamin Philip | 2021-05-03 | 2021-05-03 06:18 | Closed | AMS/N2NS/00005, AMS/N2NS/00006 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 640.08 | 640.08 | Arjan Sidhu | 2021-05-03 05:19 | [5 empty] | Lot closed |  | 2021-05-03 06:18 | [5 empty] | N-21-179-88.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124321 | 2021-05-31 05:34 |  |  |  |  | 2021-05-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00253 | Keegan Baker | 2021-05-01 04:15 | Stage 2 - Penneys Road to Moree | Culverts | 656,240 New | Culverts - Other | Earthworks | Keegan Baker | (DELETE OR REPURPOSE) Excavation and foundation preparation of drainage structure 656.240 |  |  | 2021-09-05 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 656.24 | 656.24 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124320
WLD/N2NS/00252 | Keegan Baker | 2021-05-01 03:09 | Stage 2 - Penneys Road to Moree | Culverts | 638.140, 5/2400x1200, remove and rebuild | Culverts - Other | Earthworks | Keegan Baker | Excavation and foundation preparation of drainage structure 638.140 | 2021-05-01 |  | 2021-05-31 10:00 | Benjamin Philip | 2021-06-28 | 2021-06-28 01:22 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 638.14 | 638.14 | Maddie Dahlstrom | 2021-06-27 20:13 |  |  |  |  | HWP/N2NS/00051, HWP/N2NS/00055, HWP/N2NS/00124 | Lot closed |  | 2021-06-28 01:22 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | N-21-179-102 (638.140 DCP).pdf, N-21-179-24 (002) (638.140 Wing wall DCPs).pdf, N-21-179-195 (638.140 Comp).pdf, EXP0027_N2NS_00252_0.pdf_638.140.pdf, IMG_0074.JPG, Culvert 638.140.png, WLDN2NS00252.pdf, WLDN2NS00252.pdf, N-21-179-246 (002) (638.140 Wing wall DCPs).pdf, N-21-179-102 (002) (638.140 DCP).pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124319 | 2021-06-29 19:15 |  |  |  |  | 2021-07-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00251 | Tom Borchardt | 2021-05-01 01:04 | Stage 2 - Penneys Road to Moree | Bridgeworks | Bridge - 641.540, Gurley Creek (9m ¦ 13 spans) | Bridgeworks - Demolition | Other | Tom Borchardt | Demolition of Existing Bridge Structure | 2021-05-11 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-06-09 | 2021-06-08 20:42 | Closed | AMS/N2NS/00018 | ITP/N2NS/00026 | [10 empty] | 641.6 | 641.7 | Benjamin Philip | 2021-06-08 07:01 | [5 empty] | Lot closed |  | 2021-06-08 20:42 |  |  |  | Dan Kandamby, Danika Green, Laura Buckland, Ryan Lloyd |  | Checklist - Demolition of Existing Structures.pdf, Lot Conformance Report - Bridge Structures.pdf, Survey Report-EXP0041_N2NS_00251_0.pdf, Lot Map - Gurley Creek Bridge.pdf, Engineering Sign off-53957ltr-c Gurley.pdf, Aconex-TRANS4M-RFIC-000194.pdf, Mark up - Demolition Levels.pdf, Gurley Creek Bridge Deconstruction - Main Girders Lift Plan.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124318 | 2021-06-29 19:15 |  |  |  |  | 2021-07-06 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00250 | Ryan Shenton | 2021-04-30 08:16 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH636.375 to CH636.590 - Layer 1 - 400mm | 2021-04-30 |  | 2021-05-13 10:00 | Lorne Jenks | 2021-06-24 | 2021-06-24 02:43 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00016 |  |  |  | WLD/N2NS/00395 | [5 empty] | 636.38 | 636.59 | Paddy Montgomery | 2021-06-24 02:20 | [5 empty] | Lot closed |  | 2021-06-24 02:43 |  |  |  | James Martin, Richard Doering, Ryan Shenton |  | TR0169 Panda (2).pdf, E3 Stabilised Fill Layer 1 Conformance Report Ch 636375 to Ch 636590 Lot WLD-N2NS-00250.pdf, TR0169A (1).pdf, TR0169 (1).pdf, TR0217 Panda (1).pdf, TR0170 Panda (1).pdf, TR0169 UCS.pdf, wldn2ns00250.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124314 | 2021-06-29 19:15 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00249 | Ryan Shenton | 2021-04-30 08:13 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Kallen Doong | Stage 2 - CH626.300 to CH626.550 - Cut Incl. Ground Preparation | 2021-04-30 |  | 2021-05-15 10:00 | Sarah Brooks | 2021-05-31 | 2021-05-30 23:40 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 626.3 | 626.55 | Sarah Brooks | 2021-05-31 00:46 | [5 empty] | Lot closed |  | 2021-05-31 00:47 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_3784.JPG, N-21-179-109.pdf, General Fill Conformance Report Ch 626350 to Ch 626550 Lot WLD-N2NS-00249.pdf, Foundation Conformance Report Ch 626350 to Ch 626550 Lot WLD-N2NS-00249.pdf, wldn2ns00249.pdf, lot map 249.pdf, Photo 249.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124313 | 2021-05-31 05:34 |  |  |  |  | 2021-06-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00248 | Keegan Baker | 2021-04-30 08:09 | Stage 2 - Penneys Road to Moree | Culverts | 639.160, 14/1800x600, new build | Culverts - Other | Concrete | Keegan Baker | Culvert 639.160 - Cast in Situ Base Slab | 2021-05-31 |  | 2021-05-31 10:00 | Benjamin Philip | 2021-06-25 | 2021-06-25 03:28 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00005 | [8 empty] | MIX/N2NS/00007 | 639.16 | 639.16 | Benjamin Philip | 2021-06-25 03:28 |  |  |  |  | HWP/N2NS/00060, HWP/N2NS/00097 | Lot closed |  | 2021-06-25 03:28 |  |  |  | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom, Matthew Hume, Nabin Koirala, Patrick Coria |  | N-21-179-175 (002) (639.160 Concrete Test Results).pdf, EXP0031_N2NS_00248_0.pdf, IMG_0292.JPG, IMG_0293.JPG, IMG_0295.JPG, Base Slab 1.JPG, WLDN2NS00248LM.pdf, WLD-N2NS-00248 - Lot Conformance-Checklist.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124312 | 2021-06-29 19:15 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00247 | Ryan Shenton | 2021-04-30 07:51 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Insitu Dry Chew - Stage 2 - CH626.550 to CH627.110 - 400mm | 2021-05-26 |  | 2021-05-13 10:00 | Benjamin Philip | 2021-05-26 | 2021-05-26 06:44 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 625.97 | 626 | Paddy Montgomery | 2021-05-26 05:25 | [5 empty] | Lot closed |  | 2021-05-26 06:44 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton |  | wldn2ns00247.pdf, work lot 247.pdf, IMG_3791.JPG, IMG_3789.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124311 | 2021-05-31 05:34 |  |  |  |  | 2021-06-07 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00246 | Ryan Shenton | 2021-04-30 03:24 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Cut, Inc Ground Prep - Stage 2 - CH636.685 to CH637.285 | 2021-05-02 |  | 2021-05-10 10:00 |  |  |  | Open | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 636.31 | 637.69 | [6 empty] | HWP/N2NS/00044, HWP/N2NS/00049, HWP/N2NS/00050 | [6 empty] | James Martin, Kallen Doong, Richard Doering |  | IMG_1001 (1).JPG, TR0146A.pdf, wldn2ns00246.pdf, Lot Map 246.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124282
WLD/N2NS/00245 | Ryan Shenton | 2021-04-29 07:43 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | Ryan Shenton | Insitu Stabilisation - Stage 2 - CH627.600 to CH627.900 - 300mm | 2021-04-30 |  | 2021-05-13 10:00 | Benjamin Philip | 2021-05-19 | 2021-05-19 07:13 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 625.97 | 626 | Paddy Montgomery | 2021-05-19 06:13 | [5 empty] | Lot closed |  | 2021-05-19 07:13 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | WLDN2NS00245.pdf, Test Reports.pdf, Assumed Insitu Stabilised Floor 300m Deep Ch 626350 to Ch 626550 Lot WLD-N2NS-00245.pdf, Lot Map.pdf, IMG_3856.JPG, IMG_3843.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124148 | 2021-05-31 05:34 |  |  |  |  | 2021-05-23 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00244 | Ryan Shenton | 2021-04-29 07:37 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Stage 2 - CH626.340 to CH626.900 - Layer 1 - 400mm | 2021-05-16 |  | 2021-05-13 10:00 | Lorne Jenks | 2021-06-13 | 2021-06-13 00:52 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 |  |  |  |  | WLD/N2NS/00397 | [5 empty] | 626.34 | 626.9 | Paddy Montgomery | 2021-06-11 01:45 | [5 empty] | Lot closed |  | 2021-06-13 00:52 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton |  | TR0157 PANDA.pdf, TR0157D.pdf, TR172 Panda.pdf, TR0157.pdf, TR0157C.pdf, E3 Stabilised Fill Layer 1 Conformance Report Ch 626340 to Ch 626900 Lot WLD-N2NS-00244.pdf, lot map 244.pdf, IMG_3912.JPG, IMG_3889.JPG, wldn2ns00244.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124147 | 2021-06-29 19:15 |  |  |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00243 | Hayden Murphy | 2021-04-29 07:19 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 641.060, LX556, Private (Type 2, 4.50m, rubber, sealed at crossing), RX-2 | Earthworks - Topsoil Removal | Earthworks | Hayden Murphy | LX556 - Topsoil Strip | 2021-05-01 |  | 2021-05-04 10:00 |  |  |  | Abandoned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | PER/N2NS/00024 | [8 empty] | 641 | 641.2 | [13 empty] | Grant Mills, Loui Tannous, Samithy Heng |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124146
WLD/N2NS/00242 | Hayden Murphy | 2021-04-29 07:16 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Topsoil Removal | Earthworks | Hayden Murphy | LX3066 - Topsoil Strip | 2021-05-01 |  | 2021-05-01 10:00 |  |  |  | Abandoned | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00011 | PER/N2NS/00023 | [8 empty] | 634.4 | 636.6 | [13 empty] | Grant Mills, Loui Tannous, Samithy Heng |  | LX3066 Topsoil Strip West.pdf, LX3066 Topsoil Strip East.pdf, IMG_0149.JPG, IMG_0153.JPG, IMG_0132.JPG, IMG_0145.JPG, IMG_0133.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124145
WLD/N2NS/00241 | Ryan Shenton | 2021-04-28 08:01 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Stage 2 - CH629600 to CH630600 - Waterloo Siding - Cut Incl. Ground Preparation | 2021-04-28 |  | 2021-05-13 10:00 | Sarah Brooks | 2021-05-31 | 2021-05-31 01:23 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 629.6 | 630.6 | Paddy Montgomery | 2021-05-31 01:07 |  |  |  |  | HWP/N2NS/00062 | Lot closed |  | 2021-05-31 01:23 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton |  | wldn2ns00241.pdf, lot map 241.pdf, IMG_3893.JPG, IMG_3894.JPG, WLDN2NS00241 Survey Volume Report.pdf, Foundation Conformance Report Ch 629600 to Ch 630600 Lot WLD-N2NS-00241.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124093 | 2021-05-31 05:34 |  |  |  |  | 2021-07-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00240 | Ryan Shenton | 2021-04-28 07:51 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Stage 2 - CH628600 to CH629600 - Waterloo Siding - Cut Incl. Ground Preparation | 2021-04-28 |  | 2021-05-13 10:00 | Sarah Brooks | 2021-05-31 | 2021-05-31 01:17 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 628.6 | 628.6 | Paddy Montgomery | 2021-05-31 01:05 |  |  |  |  | HWP/N2NS/00062 | Lot closed |  | 2021-05-31 01:17 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton |  | wldn2ns00240.pdf, lot map 240.pdf, IMG_3855.JPG, IMG_3854.JPG, Survey Volume Report.pdf, Formation Conformance Report Ch 628740 to Ch 629600 Lot WLD-N2NS-00240.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124091 | 2021-05-31 05:34 |  |  |  |  | 2021-06-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00239 | Ryan Shenton | 2021-04-28 07:44 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Stage 2 - CH628250 to CH628750 - Waterloo Maintenance Siding - Cut Incl. Ground Preparation | 2021-05-26 |  | 2021-05-13 10:00 | Sarah Brooks | 2021-05-31 | 2021-05-31 01:08 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 628.25 | 628.75 | Paddy Montgomery | 2021-05-31 01:04 | [5 empty] | Lot closed |  | 2021-05-31 01:08 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton |  | lot map 239.pdf, IMG_3780.JPG, IMG_3783.JPG, wldn2ns00239.pdf, Survey Volume Report.pdf, Foundation Conformance Report Ch 628200 to Ch 628740 Lot WLD-N2NS-00239.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124090 | 2021-05-31 05:34 |  |  |  |  | 2021-06-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00238 | Loui Tannous | 2021-04-28 01:55 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Earthworks - Clearing & Grubbing | Earthworks | Loui Tannous | LX1828 - Clearing and Grubbing (CH 627.850) - Waterloo | 2021-04-28 | 2021-05-17 | 2021-05-07 10:00 | Benjamin Philip | 2021-06-08 | 2021-06-07 22:22 | Closed | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010, CHK/N2NS/00011 | [9 empty] | 627.75 | 627.95 | Hayden Murphy | 2021-06-06 02:48 |  |  |  |  | HWP/N2NS/00038, HWP/N2NS/00096 | Lot closed |  | 2021-06-07 22:22 |  |  |  | Grant Mills, Hayden Murphy, Samithy Heng |  | LX1828 Topsoil Strip East.pdf, LX1828 Topsoil Strip West.pdf, LX1828 CG Lot Conformance.pdf, LX1828 ST Checklist.pdf, LX1828 CG Checklist.pdf, LX1828 CG Lot Map.pdf, Clearing Permit CH625500 - CH631200 inc LX1828 LX553.pdf, IMG_0290.JPG, IMG_0293.JPG, IMG_0292.JPG, IMG_0299.JPG, IMG_0291.JPG, IMG_0294.JPG, IMG_0210.jpg, IMG_0212.jpg, IMG_0213.jpg | https://pa.jhg.com.au/Worklot/Home/Summary/5078/124075 | 2021-06-29 19:15 |  |  |  |  | 2021-06-08 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00237 | Nabin Koirala | 2021-04-27 08:35 | Stage 2 - Penneys Road to Moree | Culverts | 637.170, 1/1800x600, remove and rebuild | Drainage - Other | Other | Keegan Baker | Excavation and foundation preparation of drainage structure | 2021-05-31 |  | 2021-08-25 10:00 | Benjamin Philip | 2021-06-25 | 2021-06-25 04:21 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 637.17 | 637.17 | Maddie Dahlstrom | 2021-06-25 04:20 |  |  |  |  | HWP/N2NS/00037, HWP/N2NS/00053, HWP/N2NS/00082 | Lot closed |  | 2021-06-25 04:21 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | Signed Lot Conformance & Checklist.pdf, N-21-179-107 (002) (637.170 DCPs).pdf, N-21-179-107 (637.170 DCPs).pdf, WLD N2NS 237_SWR193_Culvert 637170 Unsuitable Removal (Volume).pdf, IMG_0099.JPG, 637.170.png, WLDN2NS00237LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123861 | 2021-06-29 19:15 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00236 | Nabin Koirala | 2021-04-27 08:34 | Stage 2 - Penneys Road to Moree | Culverts | 636.705, 4/600x600, remove and rebuild (RRA) | Drainage - Other | Other | Keegan Baker | Excavation and foundation preparation of drainage structure | 2021-05-31 |  | 2021-08-25 10:00 | Lorne Jenks | 2021-06-21 | 2021-06-20 03:43 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 636.71 | 636.71 | Lorne Jenks | 2021-06-20 23:12 |  |  |  |  | HWP/N2NS/00036, HWP/N2NS/00047, HWP/N2NS/00056 | Lot closed |  | 2021-06-20 23:14 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | N-21-179-104 (002) (636.705 Culvert & WIngwall DCPs).pdf, N-21-179-104 (636.705 Culvert & Wingwall DCPs).pdf, WLD N2NS 236_SWR192_Culvert 636705 Unsuitable Removal Volume.pdf, IMG_0100.JPG, 636.705.png, Lot Map.pdf, WLD-N2NS-00236.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123860 | 2021-06-29 19:15 |  |  |  |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00235 | Kallen Doong | 2021-04-27 07:43 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Kallen Doong | Stage 2 - CH627100 to CH627920 - Cut Incl. Ground Preparation | 2021-05-03 |  | 2021-05-15 10:00 |  |  |  | Open | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 627.1 | 627.92 | [6 empty] | HWP/N2NS/00058 | [6 empty] | James Martin, Richard Doering, Ryan Shenton |  | lot map 235.pdf, 6F4E5365-E11A-45A2-8838-AED40872AB3B.JPG, 3093BECA-04E5-45CF-890A-54268E887E8B.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123857
WLD/N2NS/00234 | Kallen Doong | 2021-04-27 07:41 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Kallen Doong | Stage 2 - CH626550 to CH627150 - Cut Incl. Ground Preparation | 2021-04-27 |  | 2021-05-15 10:00 | Benjamin Philip | 2021-05-18 | 2021-05-18 06:22 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 626.55 | 627.11 | Paddy Montgomery | 2021-05-18 03:02 |  |  |  |  | HWP/N2NS/00039 | Lot closed |  | 2021-05-18 06:22 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Foundation Conformance Report Ch 626550 to Ch 627150 Lot WLD-N2NS-00234.pdf, IMG_3841.JPG, 25EA190F-21B1-4502-821A-00C1A3CC1BDF.JPG, WLDN2NS00234.pdf, WLDN2NS00234.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123856 | 2021-05-31 05:34 |  |  |  |  | 2021-05-23 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00233 | Hayden Murphy | 2021-04-26 23:54 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Earthworks | Hayden Murphy | LX3066 - Clearing and Grubbing- Level Crossing Turners RD | 2021-04-27 |  | 2021-05-10 10:00 | Benjamin Philip | 2021-05-19 | 2021-05-19 02:30 | Closed | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010, CHK/N2NS/00011 | [9 empty] | 634400 | 634600 | Hayden Murphy | 2021-05-19 02:08 |  |  |  |  | HWP/N2NS/00035, HWP/N2NS/00041 | Lot closed |  | 2021-05-19 02:30 |  |  |  | Grant Mills, Jeramy Smith, Loui Tannous, Samithy Heng |  | LLP0001_N2NS_00242_0.pdf, LLR0001_N2NS_00242_0.pdf, LX3066 Lot Map.pdf, 9AD89ECE-27AF-425C-BD4E-7A4343E82C77.jpeg, 8C86494B-E53F-4895-948E-98CC20BEA6BB.jpeg, 6F20D76A-90D0-427A-8FFD-A971228594B1.jpeg, 0ABEC44E-15E0-4F8B-9242-60F8444DCC23.jpeg, 48F08B51-5A46-465A-9614-6C2C70B1292B.jpeg, 26A4E3EC-7761-424D-8FD0-006E985B9858.jpeg, Lot Conformance Report & Checklist 00233.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123813 | 2021-05-31 05:34 |  |  |  |  | 2021-05-23 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00232 | Hayden Murphy | 2021-04-26 23:50 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 641.060, LX556, Private (Type 2, 4.50m, rubber, sealed at crossing), RX-2 | Earthworks - Clearing & Grubbing | Earthworks | Hayden Murphy | LX556 - Clearing and Grubbing (inc. topsoil)- Level Crossing Pad 2 | 2021-04-27 |  | 2021-05-10 10:00 | Benjamin Philip | 2021-05-19 | 2021-05-19 07:38 | Closed | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010, CHK/N2NS/00011 | [9 empty] | 641000 | 641200 | Hayden Murphy | 2021-05-19 02:47 |  |  |  |  | HWP/N2NS/00034, HWP/N2NS/00046 | Lot closed |  | 2021-05-19 07:38 |  |  |  | Grant Mills, Jeramy Smith, Loui Tannous, Samithy Heng |  | LLP0004_N2NS_00243_0.pdf, LLR0004_N2NS_00243_0.pdf, LX556 Lot Map CG.pdf, WDD-N2NS-00232 Lot Conformance & Checklist.pdf, 893046E3-26AA-43D1-9B41-676CB4539452.jpeg, 0B38004C-06C9-4D0C-BFFC-1136DA47415C.jpeg, 47C6C784-6DEB-43DD-8294-9E58F344E5C9.jpeg, B1C5A259-4FCA-4221-8446-2295D8436850.jpeg, 6B97850C-37CD-4D95-A440-0C665400318C.jpeg, 30C20260-8B3D-4F50-87DB-EF4EAA9B1535.jpeg, C70585A2-3033-476F-91A5-9816E3B96F5E.jpeg | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123812 | 2021-05-31 05:34 |  |  |  |  | 2021-05-23 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00231 | Loui Tannous | 2021-04-26 23:45 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Earthworks - Clearing & Grubbing | Earthworks | Loui Tannous | LX555 - Eastern Side Topsoil Strip | 2021-04-27 |  | 2021-04-30 10:00 | Lorne Jenks | 2021-07-03 | 2021-07-03 03:40 | Closed | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010, CHK/N2NS/00011 | [9 empty] | 636200 | 636400 | Lorne Jenks | 2021-07-03 03:39 |  |  |  |  | HWP/N2NS/00033, HWP/N2NS/00045, HWP/N2NS/00089 | Lot closed |  | 2021-07-03 03:40 |  |  |  | Grant Mills, Hayden Murphy, Jeramy Smith, Samithy Heng |  | LX0555 Topsoil Strip East.pdf, IMG_0066[1].JPG, IMG_0067[1].JPG, IMG_0068[1].JPG, IMG_0025[1].JPG, IMG_0024[1].JPG, IMG_0023[1].JPG, IMG_0022[1].JPG, LX555, LX556, LX3066 Clearing Permit - signed 27.04.2021.pdf, Lot Conformance Report- LX555.pdf, WLD-N2NS-00231- CG.pdf, WLD-N2NS-00231- ST.pdf, Topsoil Strip East- LX555.pdf, Lot Map- LX555.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123811 | 2021-07-29 18:40 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00230 | Ryan Shenton | 2021-04-25 20:16 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Cut, Inc Ground Prep - Stage 2 - CH636.310 to CH637.685 - LX 555 to Culvert 636.705 | 2021-04-30 |  | 2021-05-10 10:00 | Lorne Jenks | 2021-06-23 | 2021-06-23 03:18 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00013 | [9 empty] | 636.31 | 637.69 | Lorne Jenks | 2021-06-23 03:14 |  |  |  |  | HWP/N2NS/00040 | Lot closed |  | 2021-06-23 03:18 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | IMG_1004.JPG, IMG_0990.JPG, IMG_1003.JPG, IMG_0984.JPG, IMG_1009.JPG, IMG_0986.JPG, IMG_1014.JPG, N2NS_637000-639000 LONG SECTION 32 of 93.pdf, N2NS_635000-637000 LONG SECTION 31 of 93.pdf, Lot Map 230.pdf, WLDN2NS00230.pdf, Foundation Conformance Report Ch 636310 to Ch 636685 Lot WLD-N2NS-00230 (002).pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123761 | 2021-06-29 19:15 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00229 | Kallen Doong | 2021-04-25 01:44 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Topsoil Removal | Earthworks | Kallen Doong | Topsoil Removal - Stage 2 - CH635700 to CH641900 | 2021-04-25 |  | 2021-06-30 10:00 |  |  |  | Open | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 635.7 | 641.9 | [13 empty] | James Martin, Richard Doering, Ryan Shenton |  | D316DF26-B5B6-4F9D-B56C-D668EABCA297.JPG, 229 A.jpg, 229.jpg | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123760
WLD/N2NS/00228 | Kallen Doong | 2021-04-24 06:53 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Kallen Doong | Stage 2 - CH625970 to CH626300 - Cut Incl. Ground Preparation | 2021-04-24 |  | 2021-05-15 10:00 | Benjamin Philip | 2021-05-19 | 2021-05-19 07:33 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 625.97 | 626.3 | Paddy Montgomery | 2021-05-19 03:53 |  |  |  |  | HWP/N2NS/00029 | Lot closed |  | 2021-05-19 07:33 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | 00228 - Lot Map.pdf, 00228 - Cut - Photo.JPG, Foundation Conformance Report Ch 625970 to Ch 626350 Lot WLD-N2NS-00228.pdf, AA989953-603E-488E-8E21-E9268654ED7A.JPG, WLDN2NS00228.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123759 | 2021-05-31 05:34 |  |  |  |  | 2021-05-23 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00227 | Kallen Doong | 2021-04-24 01:19 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Clearing & Grubbing | Earthworks | Kallen Doong | Clearing and Grubbing - Stage 2 - CH625700 to CH628960 | 2021-04-24 |  | 2021-05-01 10:00 | Sarah Brooks | 2021-05-09 | 2021-05-04 05:35 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00001 | [10 empty] | 625.7 | 628.96 | Kallen Doong | 2021-05-08 06:23 |  |  |  |  | HWP/N2NS/00028, HWP/N2NS/00030 | Lot closed |  | 2021-05-08 22:38 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton |  | 00227 - Lot Map.pdf, 00227 - Clear and Grub - Photo.JPG, WLD-N2NS-00227.pdf, EXT Topography Ch 625700 to CH 628960 Lot WLD-N2NS-00227.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123758 | 2021-05-31 05:34 |  |  |  |  | 2021-05-10 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00226 | Kallen Doong | 2021-04-22 02:49 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Kallen Doong | Stage 2 - CH628.920 to CH629.920 - Cut Incl. Ground Preparation | 2021-05-03 |  | 2021-05-05 10:00 | Benjamin Philip | 2021-05-25 | 2021-05-25 06:51 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 628.92 | 629.92 | Paddy Montgomery | 2021-05-24 23:51 |  |  |  |  | HWP/N2NS/00079 | Lot closed |  | 2021-05-25 06:51 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | Foundation Excavation Conformance Report Ch 628960 to Ch 629920 Lot WLD-N2NS-00226.pdf, IMG_3832.JPG, IMG_3827.JPG, WLDN2NS00226.pdf, Lot Map 226.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123689 | 2021-05-31 05:34 |  |  |  |  | 2021-05-26 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00225 | Loui Tannous | 2021-04-21 07:27 | Temporary Works (Outside of Stages) | Camp | Specify Location in Lot | Temporary Works - Other - Camp | Concrete | Loui Tannous | Survey Set out of Pit FI20A |  |  | 2021-04-30 10:00 |  |  |  | Planned | [12 empty] | 0 | 0 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123652 |  | HN QCV PTY LIMITED & QANTAC VILLAGES PTY LIMITED |  | 7632-OH11200
WLD/N2NS/00224 | Kallen Doong | 2021-04-20 07:30 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Kallen Doong | Type E3 - Stage 2 - CH627.950 to CH628.398 - Layer 1 - 400mm | 2021-04-21 |  | 2021-04-29 10:00 | Lorne Jenks | 2021-07-09 | 2021-07-09 00:25 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 |  |  |  |  | WLD/N2NS/00505 | [5 empty] | 627.95 | 628.4 | Lorne Jenks | 2021-07-09 00:25 | [5 empty] | Lot closed |  | 2021-07-09 00:25 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | E3 Stabilised Layer 1 Ch 628050 to Ch 628400 Lot WLD-N2NS-00224.pdf, TR0253.pdf, TR0253 Panda .pdf, TR0253A.pdf, Test Request 480 Panda Results Re-Tests.pdf, wldn2ns00224.pdf, lot map 224.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123605 | 2021-07-29 18:40 |  |  |  |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00223 | Dan Kandamby | 2021-04-20 05:55 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 740.665 Yallaroi Creek (9m ¦ 6 spans ¦ offline) | Bridgeworks - Other | Earthworks | Dan Kandamby | Work platform at Yallaroi Creek Bridge | 2021-05-11 |  | 2021-05-25 10:00 |  |  |  | Open | AMS/N2NS/00018 | ITP/N2NS/00002 | [10 empty] | 740.6 | 740.7 | [13 empty] | Danika Green, Laura Buckland, Ryan Lloyd |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123602
WLD/N2NS/00222 | Dan Kandamby | 2021-04-20 05:49 | Stage 2 - Penneys Road to Moree | Bridgeworks | Bridge - 641.540, Gurley Creek (9m ¦ 13 spans) | Bridgeworks - Other | Earthworks | Dan Kandamby | Crane and Piling Platform at Gurley Creek | 2021-05-11 | 2021-06-01 | 2021-04-30 10:00 |  |  |  | Open | AMS/N2NS/00018 | ITP/N2NS/00002 | CHK/N2NS/00012 | PER/N2NS/00029 |  |  | WLD/N2NS/00294 | [5 empty] | 641.5 | 641.7 | [13 empty] | Danika Green, Laura Buckland, Ryan Lloyd |  | N-21-179-108.pdf, N-21-179-216.pdf, Test Request 0215 Vane Shears.pdf, N-21-179-191.pdf, N-21-179-119.pdf, RU DGB20 Lot2-21 26-2-21 perm.pdf, Test Request 0232 Vane Shear.pdf, TR0113.pdf, Test Request 0112.pdf, Test Request 0132 - Crane Pad Pier 3 to Abut B.pdf, TR0120 - Laydown Area South.pdf, Test Request 0112 - Laydown Area South.pdf, Test Request 0251 Vane Shear.pdf, TR0113 - Laydown Area South.pdf, RU Crusher Run 23-4-21.pdf, N-21-179-111.pdf, Test Request 0220.pdf, Test Request 0148.pdf, RU DGB20 Lot1-21 24-2-21.pdf, Test Request 0113 - Crane Pad Abut A to Pier 3.pdf, N-21-179-122.pdf, All pick ups up to 03.05.pdf, LLP0006_N2NS_0.pdf, EXP0025_N2NS_00222_1.pdf, Plot Gurley FDN SWR Combined SWR 67 and 88 and 105.pdf, LLP0003_N2NS_222_0 .pdf, LLR0006_N2NS_0.pdf, N2NS-SUR-021_A.pdf, IMG_0060.JPG, IMG_0076.JPG, IMG_0061.JPG, IMG_0068.JPG, IMG_0072.JPG, IMG_0071.JPG, IMG_0074.JPG, IMG_0073.JPG, TW Site Validation Form - Gurley - Signed rev 1.pdf, TW Site Validation Form - Gurley Piling - Signed.pdf, Test Request 0148.pdf, N-21-179-119.pdf, 3.4 HP - Submit Temp Works Design.pdf, B01102-51AG Gurley Ck Platform Rev C.pdf, 016 Temporary Works Design Check Certificate - Gurley Ck.pdf, Temp Works - flood impact assessment + geotechnical correspondance.pdf, Hazardous Materials survey - Croppa Creek 23-4-21.pdf, B01102-51AG Gurley Ck Platform Rev C (1).pdf, RU Crusher Run 23-4-21 (1).pdf, Test Request 0251 Vane Shear.pdf, Test Request 0220.pdf, Test Request 0232 Vane Shear.pdf, Test Request 0215 Vane Shears.pdf, TW Site Validation Form - Gurley Piling - Signed (1).pdf, TW Site Validation Form - Gurley - Signed rev 1 (1).pdf, RU DGB20 Lot2-21 26-2-21 perm.pdf, RE_ B01102-51AQ - Piling Pad Equipment Changes.msg, 210411 Gurley Bridge Existing Detail TB Markup.pdf, Gurley platform profile.pdf, GURLEY CREEK CRANE PAD AND LAYDOWN AREA_VERSION 3 (002).pdf, B01102-51AG Gurley Ck Platform Rev C (2).pdf, 016 Temporary Works Design Certificate - Gurley Ck.pdf, 2021-0085-Trans4m Rail-Newell Hwy-Guerly Creek Rd-Site Access- SS-11.01.2021.pdf, Moree Plains Council Permit -ROP-21-1001.pdf, Clearing Permit Croppa Creek.pdf, Gurley Demoltion Site Plan.pdf, 3-0001-260-SBD-00-DR-1902_0 Markup Croppa Demo layout part 2 rev 1.pdf, Gurley Piling Combined.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123601
WLD/N2NS/00221 | Dan Kandamby | 2021-04-18 02:57 | Stage 3 - Camurra North to North Star | Bridgeworks | Bridge - 716.850 Gil Gil Creek (9m ¦ 4 spans ¦ offline) | Bridgeworks - Demolition | Other | Dan Kandamby | Remove Rail and Demolish Existing Bridge in Gil Gil creek | 2021-05-11 |  | 2021-05-12 10:00 | Benjamin Philip | 2021-06-08 | 2021-06-08 06:58 | Closed | AMS/N2NS/00018 | ITP/N2NS/00026 | [10 empty] | 716.8 | 716.9 | Danika Green | 2021-06-08 06:16 |  |  |  |  | HWP/N2NS/00025 | Lot closed |  | 2021-06-08 06:58 | [5 empty] | WLDN2NS00221.pdf, Survey Report - LLP0026_N2NS_00221_0.pdf, Lot Map - Gil Gil.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123492 | 2021-06-29 19:15 | IRONBARK DEMOLITION PTY LTD | PKG/N2NS/00048 |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00220 | Kallen Doong | 2021-04-18 01:56 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Kallen Doong | Stage 2 - CH627960 to CH628960 - Cut Incl. Ground Preparation | 2021-04-20 |  | 2021-04-28 10:00 | Benjamin Philip | 2021-05-21 | 2021-05-21 07:01 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | [10 empty] | 627.96 | 628.96 | Paddy Montgomery | 2021-05-20 02:09 |  |  |  |  | HWP/N2NS/00027, HWP/N2NS/00048 | Lot closed |  | 2021-05-21 07:01 |  |  |  | James Martin, Kallen Doong, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | WLDN2NS00220.pdf, Formation Excavation Conformance Report Ch 627960 to Ch 628960 Lot WLD-N2NS-00220.pdf, WLDN2NS00220.pdf, IMG_3848.JPG, IMG_3855.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123491 | 2021-05-31 05:34 |  |  |  |  | 2021-05-23 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00219 | Kallen Doong | 2021-04-18 01:20 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Topsoil Removal | Earthworks | Kallen Doong | Topsoil Removal - Stage 2 - CH625700 to CH631100 - Penny's to Kanimbla | 2021-04-19 |  | 2021-05-22 10:00 | Benjamin Philip | 2021-05-18 | 2021-05-18 05:52 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 625.7 | 631.1 | Paddy Montgomery | 2021-05-18 03:29 | [5 empty] | Lot closed |  | 2021-05-18 05:52 |  |  |  | James Martin, Paddy Montgomery, Richard Doering, Ryan Shenton, Tahlor Swan |  | ABBA1E22-5991-4EA0-B80D-86F118A53F59.JPG, Topsoil Stripped Quantity Report Ch 625970 to Ch 631130 Lot WLD-N2NS-000219.pdf, 47DCBEB9-B608-447F-A518-50F4D55E0D7A.JPG, WLDN2NS00219.pdf, WLDN2NS00219.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123490 | 2021-05-31 05:34 |  |  |  |  | 2021-05-23 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00218 | James Martin | 2021-04-11 05:48 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Roydon Rd Formation Trial - Layer 1 Type E3 Treatment - CH687.500 to CH687.940 | 2021-05-23 |  | 2021-05-28 10:00 | Lorne Jenks | 2021-06-23 | 2021-06-23 03:02 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00001 |  |  |  |  | WLD/N2NS/00397 | [5 empty] | 687.5 | 687.94 | Paddy Montgomery | 2021-06-23 02:29 | [5 empty] | Lot closed |  | 2021-06-23 03:02 |  |  |  | Richard Doering |  | TR0115.pdf, TR0115B.pdf, TR0115A.pdf, TR0115C.pdf, IMG_0961.JPG, IMG_0962.JPG, E3 Stabilised Layer 1 Ch 687500 to Ch 687870 Lot WLD-N2NS-00218.pdf, Test Report P21004-65 LWD.pdf, Test Report P21004-65 Panda.pdf, Test Report P21004-64 Portable LWD.pdf, Test Report P21004-64 Panda.pdf, Test Report P21004-63 Portable LWD.pdf, Test Report P21004-63 Panda.pdf, Test Report P21004-63 Portable LWD 15kg.pdf, Test Report P21004-62 Panda.pdf, Test Report P21004-62 Portable LWD.pdf, Test Report P21004-61 Panda.pdf, Test Report P21004-61 Portable Impluse.pdf, wldn2ns00218.pdf, lot map 218.pdf, TR0118.pdf, TR0118C.pdf, TR0118D.pdf, TR0118A.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123193 | 2021-06-29 19:15 |  |  | 7632-GC48000 |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00217 | James Martin | 2021-04-11 05:45 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | James Martin | Roydon Rd Formation Trial - Cut Inc Ground Preparation - CH687.500 to CH687.940 | 2021-04-13 |  | 2021-04-16 10:00 | Lorne Jenks | 2021-06-23 | 2021-06-23 03:03 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00001 | [10 empty] | 687.5 | 687.94 | Lorne Jenks | 2021-06-23 03:03 |  |  |  |  | HWP/N2NS/00024 | Lot closed |  | 2021-06-23 03:03 |  |  |  | Richard Doering |  | TR0105.pdf, TR0105 R1.pdf, TR0105 - Test Locations.pdf, TR0102.pdf, IMG_0872.JPG, IMG_0931.JPG, Foundation Excavation Ch 687470 to Ch 687920 Lot WLD-N2NS-00217.pdf, lot map 217.pdf, wldn2ns00217.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123192 | 2021-06-29 19:15 |  |  | 7632-GC48000 |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00216 | James Martin | 2021-04-11 05:42 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Topsoil Removal | Earthworks | James Martin | Roydon Rd Formation Trial - Topsoil Removal - CH687.500 to CH688.600 | 2021-04-13 |  | 2021-04-16 10:00 | Lorne Jenks | 2021-06-14 | 2021-06-14 00:48 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 687.5 | 688.6 | James Martin | 2021-06-14 00:46 | [5 empty] | Lot closed |  | 2021-06-14 00:48 |  |  |  | Richard Doering |  | Topsoil Stripped Quantity Ch 687500 to Ch 688600 Lot WLD-N2NS-00216.pdf, IMG_0862.JPG, IMG_0861.JPG, WLDN2NS00216 - Lot Map.pdf, WLDN2NS00216 - Completed Checklist.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123191 | 2021-06-29 19:15 |  |  | 7632-GC48000 |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00215 | Richard Doering | 2021-04-09 08:38 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Richard Doering | Milguy Trial - Layer 1/2 Fill - 711.350 to 711.760 not inc culverts | 2021-04-08 |  | 2021-04-16 10:00 | Lorne Jenks | 2021-06-21 | 2021-06-21 05:23 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 | [9 empty] | 711.35 | 711.76 | James Martin | 2021-06-21 02:33 | [5 empty] | Lot closed |  | 2021-06-21 05:23 |  |  |  | James Martin, Kallen Doong, Ryan Shenton |  | TR0093.pdf, N-21-186-40.pdf, TR0096A.pdf, 300 - 10kg 16-4-21 - TR0096.pdf, N-21-186-41.pdf, TR0096B.pdf, 300 - 15kg 16-4-21 - TR0096.pdf, TR0095A.pdf, Rockfill_2021.04.12.pdf, N-21-186-37.pdf, TR0096.pdf, TR0095B.pdf, TR0095C.pdf, N-21-186-36.pdf, IMG_0852.JPG, IMG_0850.JPG, WLDN2NS00215 - Completed Checklist.pdf, General Fill Layer 1&2 Ch 711440 to Ch 711740 Lot WLD-N2NS-00214 & 00215.pdf, WLD-N2NS-0215 - Lot Map.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123167 | 2021-06-29 19:15 |  |  | 7632-2C41222 |  | 2021-07-06 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00214 | Richard Doering | 2021-04-09 08:36 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Richard Doering | Milguy Trial - Rock Fill Layer 1+2 - CH711.350 to 711.760 not inc culverts | 2021-04-08 |  | 2021-04-16 10:00 | Lorne Jenks | 2021-06-21 | 2021-06-21 05:25 | Closed | AMS/N2NS/00001, AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00017 | [9 empty] | 711.35 | 711.76 | James Martin | 2021-06-21 02:28 | [5 empty] | Lot closed |  | 2021-06-21 05:25 |  |  |  | James Martin, Kallen Doong, Ryan Shenton |  | 300 - 10kg 16-4-21 - TR0096.pdf, 300 - 15kg 16-4-21 - TR0096.pdf, N-21-186-36.pdf, TR0096.pdf, TR0095C.pdf, N-21-186-40.pdf, Rockfill_2021.04.12.pdf, TR0096A.pdf, TR0096B.pdf, N-21-186-41.pdf, TR0095B.pdf, TR0095A.pdf, N-21-186-37.pdf, TR0093.pdf, IMG_0829.JPG, IMG_0830.JPG, WLD-N2NS-0214 - Lot Map.pdf, General Fill Layer 1&2 Ch 711440 to Ch 711740 Lot WLD-N2NS-00214 & 00215.pdf, WLD-N2NS-00214.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123166 | 2021-06-29 19:15 |  |  | 7632-2C41222 |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00213 | Jake Mossman | 2021-04-07 04:45 | Stage 3 - Camurra North to North Star | Pavements | Main Alignment (Specify Chainage in Lot) | Pavements - Capping | Earthworks | Arjan Sidhu | Milguy Trial - CH 711.000 - CH 711.350 | 2021-04-07 |  | 2021-04-28 10:00 |  |  |  | Abandoned | AMS/N2NS/00007 | ITP/N2NS/00012 | [10 empty] | 711 | 711.35 | [6 empty] | HWP/N2NS/00019, HWP/N2NS/00020 | [6 empty] | Arjan Sidhu, Jake Mossman |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123005
WLD/N2NS/00212 | Nabin Koirala | 2021-04-07 04:37 | Stage 2 - Penneys Road to Moree | Culverts | 639.160, 14/1800x600, new build | Drainage - Other | Other | Nabin Koirala | Excavation and Foundation Preparation for Drainage Structures | 2021-05-31 | 2021-07-24 | 2021-08-25 10:00 | Benjamin Philip | 2021-06-25 | 2021-06-25 03:21 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 639.16 | 639.16 | Maddie Dahlstrom | 2021-06-23 05:47 |  |  |  |  | HWP/N2NS/00032, HWP/N2NS/00106 | Lot closed |  | 2021-06-25 03:21 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | Lot map_639.160.pdf, IMG_0445.JPG, IMG_0276.JPG, N-21-179-94 (004) (639.160 Base DCP).pdf, Test Request 0131 (002) (639.160 Base DCP).pdf, Test Request 0131 (002) (639.160 Base DCP).pdf, Checklist_639.160_Foundation.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123004 | 2021-06-29 19:15 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00211 | Nabin Koirala | 2021-04-07 04:35 | Stage 2 - Penneys Road to Moree | Culverts | 640,080, 5/2400x900, new build | Drainage - Other | Other | Nabin Koirala | Excavation and foundation preparation of existing structures - 640.08 - Base Slab and Wing Wall | 2021-05-05 |  | 2021-08-25 10:00 | Benjamin Philip | 2021-06-25 | 2021-06-25 03:17 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00040 | [9 empty] | 633.05 | 647.13 | Maddie Dahlstrom | 2021-06-24 23:07 |  |  |  |  | HWP/N2NS/00042, HWP/N2NS/00043, HWP/N2NS/00054, HWP/N2NS/00083 | Lot closed |  | 2021-06-25 03:17 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | 2021.05.11 - 640.080 Wing wall blinding.pdf, IMG_0423.JPG, IMG_0422.JPG, IMG_0092.JPG, IMG_0091.JPG, N-21-179-348 (640.080 Wings DCP).pdf, N-21-179-125 (640.080 Base Compaction).pdf, N-21-179-103 (640.080 Base DCP).pdf, EXP0028_N2NS_00211_0.pdf, WLD N2NS 211_SWR409_Culvert 640080 Unsuitable Removal.pdf, WLDN2NS00211.pdf, S66 Balo St21062509570.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123003 | 2021-06-29 19:15 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00210 | Nabin Koirala | 2021-04-07 04:34 | Stage 2 - Penneys Road to Moree | Culverts | 638.920, 14/1800x600, new build | Earthworks - Excavation (Cut) | Earthworks | Keegan Baker | Stage 2 - Installation and Backfill of 28 RCBCS 1800X600 - Excavation and Foundation Preparation of Drainage Structures | 2021-05-22 | 2021-07-17 | 2021-08-25 10:00 | Benjamin Philip | 2021-06-25 | 2021-06-25 05:59 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 638.92 | 638.92 | Maddie Dahlstrom | 2021-06-25 05:12 |  |  |  |  | HWP/N2NS/00031, HWP/N2NS/00125, HWP/N2NS/00128 | Lot closed |  | 2021-06-25 05:59 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | N-21-179-230 (003) (638.920 Wingwalls).pdf, N-21-179-230 (003) (638.920 Wings DCP).pdf, N-21-179-93 (638.920 DCP).pdf, N-21-179-93-2 (638.920 DCP).pdf, WLD N2NS 210_SWR289_Culvert 638920 Unsuitable Removal (Volume Report).pdf, IMG_0315.JPG, IMG_0446.JPG, 638.920.png, WLDN2NS00210LM.pdf, WLDN2NS00210.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123002 | 2021-06-29 19:15 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00209 | Sarah Brooks | 2021-04-07 03:53 | Manufacture / Material Supply Lots | Offsite Manufacture | Other (Specify in Lot) | Offsite Manufacture/Supply - Signalling Huts | M & E | Jason Cheah | Fabrication of Signalling Huts | 2021-04-07 |  | 2021-10-31 11:00 |  |  |  | Open | AMS/N2NS/00010 | ITP/N2NS/00046 | [10 empty] | 0 | 0 | [15 empty] | Seq 4-5-6 Signed ITP.pdf, Seq 1 and 2 Signed ITP.pdf, 2021-03-12 Seq 1 to 6 Chassis Fab (1).pdf, 2021-03-12 Seq 1 to 6 Chassis Fab (2).pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123001
WLD/N2NS/00208 | Sarah Brooks | 2021-04-07 03:43 | Manufacture / Material Supply Lots | Offsite Manufacture | Other (Specify in Lot) | Offsite Manufacture/Supply - Signalling Huts | M & E | Sarah Brooks | Manufacture of Signalling Huts - April 2021 |  |  | 2021-04-30 10:00 |  |  |  | Planned | AMS/N2NS/00010 | [11 empty] | 0 | 0 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/123000
WLD/N2NS/00207 | Nabin Koirala | 2021-04-05 01:11 | Stage 3 - Camurra North to North Star | Culverts | 746.600, 2/1800x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 6 1800X900 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 744.5 | 748.71 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122945
WLD/N2NS/00206 | Nabin Koirala | 2021-04-05 01:10 | Stage 3 - Camurra North to North Star | Culverts | 746.040, 1/1800x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 1800X900 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 745 | 747.09 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122944
WLD/N2NS/00205 | Nabin Koirala | 2021-04-05 01:08 | Stage 3 - Camurra North to North Star | Culverts | 745.430, 1/1800x1200, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 1800X1200 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 744.37 | 746.49 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122943
WLD/N2NS/00204 | Nabin Koirala | 2021-04-05 01:07 | Stage 3 - Camurra North to North Star | Culverts | 744.570, 10/3000x2400, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 20 3000X2400 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 727.6 | 761.58 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122942
WLD/N2NS/00203 | Nabin Koirala | 2021-04-05 01:07 | Stage 3 - Camurra North to North Star | Culverts | 742.710, 1/1800x1800, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 1800X1800 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 741.51 | 743.91 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122941
WLD/N2NS/00202 | Nabin Koirala | 2021-04-05 01:06 | Stage 3 - Camurra North to North Star | Culverts | 742.260, 1/1800x600, demo and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 1800X600 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 741.22 | 743.3 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122940
WLD/N2NS/00201 | Nabin Koirala | 2021-04-05 01:05 | Stage 3 - Camurra North to North Star | Culverts | 742.140, 3/2400x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 6 2400X900 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 738.02 | 746.28 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122939
WLD/N2NS/00200 | Nabin Koirala | 2021-04-05 01:04 | Stage 3 - Camurra North to North Star | Culverts | 741.460, 2/1800x1200, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 4 1800X1200 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 739.34 | 743.6 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122938
WLD/N2NS/00199 | Nabin Koirala | 2021-04-05 01:03 | Stage 3 - Camurra North to North Star | Culverts | 740.960, 24/3000x2400, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 48 3000X2400 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 700.21 | 781.79 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122937
WLD/N2NS/00198 | Nabin Koirala | 2021-04-05 01:03 | Stage 3 - Camurra North to North Star | Culverts | 737.570, 4/3000x2100, new build (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 24 3000X2100 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 730.79 | 744.37 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122936
WLD/N2NS/00197 | Nabin Koirala | 2021-04-05 01:02 | Stage 3 - Camurra North to North Star | Culverts | 736.310, 2/2400x900, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 4 2400X900 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 733.56 | 739.07 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122935
WLD/N2NS/00196 | Nabin Koirala | 2021-04-05 01:01 | Stage 3 - Camurra North to North Star | Culverts | 736.220, 3/2400x900, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 6 2400X900 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 732.09 | 740.36 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122934
WLD/N2NS/00195 | Nabin Koirala | 2021-04-05 01:00 | Stage 3 - Camurra North to North Star | Culverts | 732.020, 1/3000x1200, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 3000X1200 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 730.35 | 733.7 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122933
WLD/N2NS/00194 | Nabin Koirala | 2021-04-05 00:59 | Stage 3 - Camurra North to North Star | Culverts | 730.580, 1/2400x1500, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 2400X1500 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 729.21 | 731.96 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122932
WLD/N2NS/00193 | Nabin Koirala | 2021-04-05 00:57 | Stage 3 - Camurra North to North Star | Culverts | 730.400, 1/900x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 900X900 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 729.83 | 730.98 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122931
WLD/N2NS/00192 | Nabin Koirala | 2021-04-05 00:56 | Stage 3 - Camurra North to North Star | Culverts | 729.970, 4/3000x1500, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 8 3000X1500 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 723.25 | 736.71 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122930
WLD/N2NS/00191 | Nabin Koirala | 2021-04-05 00:55 | Stage 3 - Camurra North to North Star | Culverts | 729.890, 1/1800x1200, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 1800X1200 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 728.83 | 730.95 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122929
WLD/N2NS/00190 | Nabin Koirala | 2021-04-05 00:54 | Stage 3 - Camurra North to North Star | Culverts | 729.710, 1/2400x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 2400X900 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 728.34 | 731.08 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122928
WLD/N2NS/00189 | Nabin Koirala | 2021-04-05 00:53 | Stage 3 - Camurra North to North Star | Culverts | 728.920, 1/2400x1500, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 2400X1500 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 727.55 | 730.3 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122927
WLD/N2NS/00188 | Nabin Koirala | 2021-04-05 00:49 | Stage 3 - Camurra North to North Star | Culverts | 728.440, 4/3000x1500, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 8 3000X1500 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 721.72 | 738.18 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122926
WLD/N2NS/00187 | Nabin Koirala | 2021-04-05 00:48 | Stage 3 - Camurra North to North Star | Culverts | 728.360, 1/1200x600, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 1200X600 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 727.63 | 729.08 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122925
WLD/N2NS/00186 | Nabin Koirala | 2021-04-05 00:47 | Stage 3 - Camurra North to North Star | Culverts | 727.710, 1/3000x1200, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 3000X1200 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 726.04 | 729.39 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122924
WLD/N2NS/00185 | Nabin Koirala | 2021-04-05 00:46 | Stage 3 - Camurra North to North Star | Culverts | 727.130, 3/1800x600, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 6 1800X600 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 724 | 730.26 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122923
WLD/N2NS/00184 | Nabin Koirala | 2021-04-05 00:46 | Stage 3 - Camurra North to North Star | Culverts | 726.970, 2/3000x1500, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 4 3000X1500 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 723.61 | 730.33 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122922
WLD/N2NS/00183 | Nabin Koirala | 2021-04-05 00:45 | Stage 3 - Camurra North to North Star | Culverts | 726.550, 2/3000x1200, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 4 3000X1200 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 723.19 | 729.91 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122921
WLD/N2NS/00182 | Nabin Koirala | 2021-04-05 00:44 | Stage 3 - Camurra North to North Star | Culverts | 726.210, 1/1800x600, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 1800X600 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 725.17 | 727.25 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122920
WLD/N2NS/00181 | Nabin Koirala | 2021-04-05 00:43 | Stage 3 - Camurra North to North Star | Culverts | 726.120, 2/3000x1200, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 4 3000X1200 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 722.77 | 729.49 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122919
WLD/N2NS/00180 | Nabin Koirala | 2021-04-05 00:43 | Stage 3 - Camurra North to North Star | Culverts | 725.600, 1/1800x1800, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 1800X1800 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 724.4 | 726.8 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122918
WLD/N2NS/00179 | Nabin Koirala | 2021-04-05 00:39 | Stage 3 - Camurra North to North Star | Culverts | 725.560, 1/2400x1200, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 2400X1200 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 724.19 | 726.93 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122917
WLD/N2NS/00178 | Nabin Koirala | 2021-04-05 00:38 | Stage 3 - Camurra North to North Star | Culverts | 725.280, 4/3000x1800, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 8 3000X1800 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 718.56 | 732.02 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122916
WLD/N2NS/00177 | Nabin Koirala | 2021-04-05 00:37 | Stage 3 - Camurra North to North Star | Culverts | 724.630, 2/2400x1500, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 4 2400X1500 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 721.88 | 727.39 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122915
WLD/N2NS/00176 | Nabin Koirala | 2021-04-05 00:35 | Stage 3 - Camurra North to North Star | Culverts | 723.880, 2/2400x1500, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 4 2400X1500 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 721.14 | 726.64 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122914
WLD/N2NS/00175 | Nabin Koirala | 2021-04-05 00:35 | Stage 3 - Camurra North to North Star | Culverts | 723.610, 2/2400x1800, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 6 2400X1800 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 719.48 | 727.75 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122913
WLD/N2NS/00174 | Nabin Koirala | 2021-04-05 00:34 | Stage 3 - Camurra North to North Star | Culverts | 723.230, 3/2400x1500, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 6 2400X1500 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 719.1 | 727.37 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122912
WLD/N2NS/00173 | Nabin Koirala | 2021-04-05 00:32 | Stage 3 - Camurra North to North Star | Culverts | 723.010, 2/2400x1500, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 4 2400X1500 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 720.27 | 725.77 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122911
WLD/N2NS/00172 | Nabin Koirala | 2021-04-05 00:31 | Stage 3 - Camurra North to North Star | Culverts | 722.820, 1/2400x1500, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 2400X1500 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 721.46 | 724.2 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122910
WLD/N2NS/00171 | Nabin Koirala | 2021-04-05 00:30 | Stage 3 - Camurra North to North Star | Culverts | 721.650, 2/2400x1800, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 4 2400X1800 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 718.9 | 724.4 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122909
WLD/N2NS/00170 | Nabin Koirala | 2021-04-04 23:20 | Stage 3 - Camurra North to North Star | Culverts | 721.040, 6/3000x2100, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 12 3000X1200 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 710.86 | 731.24 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122908
WLD/N2NS/00169 | Nabin Koirala | 2021-04-04 23:14 | Stage 3 - Camurra North to North Star | Culverts | 720.740, 3/3000x1800, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 6 3000X1800 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 715.71 | 725.8 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122907
WLD/N2NS/00168 | Nabin Koirala | 2021-04-04 23:09 | Stage 3 - Camurra North to North Star | Culverts | 720.370, 3/3000x1800, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 6 3000X1800 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 715.33 | 725.42 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122906
WLD/N2NS/00167 | Nabin Koirala | 2021-04-04 23:08 | Stage 3 - Camurra North to North Star | Culverts | 720.180, 3/3000x1800, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 3000X1800 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 718.51 | 721.86 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122905
WLD/N2NS/00166 | Nabin Koirala | 2021-04-04 23:07 | Stage 3 - Camurra North to North Star | Culverts | 719.910, 1/1800x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 1800X900 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 718.87 | 720.96 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122904
WLD/N2NS/00165 | Nabin Koirala | 2021-04-04 23:04 | Stage 3 - Camurra North to North Star | Culverts | 719.180, 3/1800x600, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 3000X1800 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 718.51 | 721.86 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122903
WLD/N2NS/00164 | Nabin Koirala | 2021-04-04 22:46 | Stage 3 - Camurra North to North Star | Culverts | 719.130, 2/1800x600, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 4 1800X600 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 717.05 | 721.22 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122902
WLD/N2NS/00163 | Nabin Koirala | 2021-04-04 22:44 | Stage 3 - Camurra North to North Star | Culverts | 719.080, 3/1800x600, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 6 RCBCS 1800X600 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 715.96 | 722.22 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122901
WLD/N2NS/00162 | Nabin Koirala | 2021-04-04 22:44 | Stage 3 - Camurra North to North Star | Culverts | 718.910, 2/2400x900, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 6 RCBCS 2400X900 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 716.16 | 721.67 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122900
WLD/N2NS/00161 | Nabin Koirala | 2021-04-04 22:43 | Stage 3 - Camurra North to North Star | Culverts | 718.390, 1/1800x600, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 RCBCS 1800X600 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 717.36 | 719.43 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122899
WLD/N2NS/00160 | Nabin Koirala | 2021-04-04 22:41 | Stage 3 - Camurra North to North Star | Culverts | 718.390, 1/1800x600, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 RCBCS 1800X600 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 717.48 | 718.93 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122898
WLD/N2NS/00159 | Nabin Koirala | 2021-04-04 22:40 | Stage 3 - Camurra North to North Star | Culverts | 718.050, 1/1800x600, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 1800X600 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 717.02 | 719.09 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122897
WLD/N2NS/00158 | Nabin Koirala | 2021-04-04 22:39 | Stage 3 - Camurra North to North Star | Culverts | 716.730, 7/3000x2100, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 14 3000X2100 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 704.86 | 728.64 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122896
WLD/N2NS/00157 | Nabin Koirala | 2021-04-04 22:38 | Stage 3 - Camurra North to North Star | Culverts | 716.640, 32/3000x1800, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 64 3000X1800 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 662.75 | 770.57 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122895
WLD/N2NS/00156 | Nabin Koirala | 2021-04-04 22:37 | Stage 3 - Camurra North to North Star | Culverts | 716.410, 14/2400x900, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 28 2400X900 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 697.11 | 735.75 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122894
WLD/N2NS/00155 | Nabin Koirala | 2021-04-04 22:36 | Stage 3 - Camurra North to North Star | Culverts | 716.280, 17/1800x600, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 34 1800X600 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 698.51 | 734.09 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122893
WLD/N2NS/00154 | Nabin Koirala | 2021-04-04 22:35 | Stage 3 - Camurra North to North Star | Culverts | 714.830, 1/1800x600, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 1800X600 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 713.79 | 715.87 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122892
WLD/N2NS/00153 | Nabin Koirala | 2021-04-04 22:34 | Stage 3 - Camurra North to North Star | Culverts | 714.620, 13/2400x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 26 2400x900 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 696.7 | 732.58 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122891
WLD/N2NS/00152 | Nabin Koirala | 2021-04-04 22:04 | Stage 3 - Camurra North to North Star | Culverts | 713.500, 1/1800x600, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 1800X600 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 712.46 | 714.54 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122889
WLD/N2NS/00151 | Nabin Koirala | 2021-04-04 22:03 | Stage 3 - Camurra North to North Star | Culverts | 713.350, 11/1800x600, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 22 1800X600 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 701.86 | 724.88 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122888
WLD/N2NS/00150 | Nabin Koirala | 2021-04-04 22:02 | Stage 3 - Camurra North to North Star | Culverts | 712.820, 1/1800x600, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 1800X600 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 711.78 | 713.86 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122887
WLD/N2NS/00149 | Nabin Koirala | 2021-04-04 22:01 | Stage 3 - Camurra North to North Star | Culverts | 712.610, 10/1800x600, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 20 RCBCS 1800X600 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 702.16 | 723.08 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122886
WLD/N2NS/00148 | Nabin Koirala | 2021-04-04 22:00 | Stage 3 - Camurra North to North Star | Culverts | 712.540, 12/2400x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 24 RCBCS 2400X900 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 696 | 729.12 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122885
WLD/N2NS/00147 | Nabin Koirala | 2021-04-04 21:59 | Stage 3 - Camurra North to North Star | Culverts | 712.070, 7/1800x600, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 14 1800X600 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 704.77 | 719.4 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122884
WLD/N2NS/00146 | Nabin Koirala | 2021-04-04 21:58 | Stage 3 - Camurra North to North Star | Culverts | 709.740, 5/2400x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 10 3000X1200 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 702.86 | 716.65 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122883
WLD/N2NS/00145 | Nabin Koirala | 2021-04-04 21:58 | Stage 3 - Camurra North to North Star | Culverts | 708.445, 13/3000x1200, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 26 3000X1200 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 686.58 | 730.37 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122882
WLD/N2NS/00144 | Nabin Koirala | 2021-04-04 21:54 | Stage 3 - Camurra North to North Star | Culverts | 707.575, 8/1800x600, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 48 1800X600 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 699.22 | 715.96 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122881
WLD/N2NS/00143 | Nabin Koirala | 2021-04-04 21:53 | Stage 3 - Camurra North to North Star | Culverts | 707.405, 2/1800x600, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 4 1800X600 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 705.32 | 709.49 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122880
WLD/N2NS/00142 | Nabin Koirala | 2021-04-04 21:52 | Stage 3 - Camurra North to North Star | Culverts | 706.695, 3/1200x600, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 18 1200X600 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 704.51 | 708.89 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122879
WLD/N2NS/00141 | Nabin Koirala | 2021-04-04 21:51 | Stage 3 - Camurra North to North Star | Culverts | 706.505, 1/3000x1100, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 6 1200X600 RCBC |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 704.83 | 708.18 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122878
WLD/N2NS/00140 | Nabin Koirala | 2021-04-04 21:50 | Stage 3 - Camurra North to North Star | Culverts | 706.250, 3/2400x1800, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 6 1200X600 RCBC |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 702.12 | 710.39 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122877
WLD/N2NS/00139 | Nabin Koirala | 2021-04-04 21:49 | Stage 3 - Camurra North to North Star | Culverts | 706.100, 6/1200x600, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 12 1200X600 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 701.72 | 710.49 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122876
WLD/N2NS/00138 | Nabin Koirala | 2021-04-04 21:48 | Stage 3 - Camurra North to North Star | Culverts | 704.810, 14/3000x1800, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 28 3000X1800 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 681.25 | 728.41 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122875
WLD/N2NS/00137 | Nabin Koirala | 2021-04-04 21:47 | Stage 3 - Camurra North to North Star | Culverts | 703.065, 2/1800x600, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 4 1800X600 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 700.98 | 705.15 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122874
WLD/N2NS/00136 | Nabin Koirala | 2021-04-04 21:46 | Stage 3 - Camurra North to North Star | Culverts | 702.380, 1/1200x600, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 1200X600 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 701.66 | 703.11 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122873
WLD/N2NS/00135 | Nabin Koirala | 2021-04-04 21:44 | Stage 3 - Camurra North to North Star | Culverts | 702.370, 1/1200x600, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 1200X600 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 701.65 | 703.09 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122872
WLD/N2NS/00134 | Nabin Koirala | 2021-04-04 21:44 | Stage 3 - Camurra North to North Star | Culverts | 699.875, 12/3000x1800, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 24 3000X1800 RCBC |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 679.69 | 720.11 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122871
WLD/N2NS/00133 | Nabin Koirala | 2021-04-04 21:43 | Stage 3 - Camurra North to North Star | Culverts | 699.790, 8/3000x1200, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 16 3000X1200 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 646.33 | 673.27 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122870
WLD/N2NS/00132 | Nabin Koirala | 2021-04-04 21:42 | Stage 3 - Camurra North to North Star | Culverts | 696.985, 5/2400x1500, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 10 2400X1500 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 690.1 | 703.89 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122869
WLD/N2NS/00131 | Nabin Koirala | 2021-04-04 21:40 | Stage 3 - Camurra North to North Star | Culverts | 695.285, 1/2100x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 2100X900 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 692.09 | 694.49 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122868
WLD/N2NS/00130 | Nabin Koirala | 2021-04-04 21:39 | Stage 3 - Camurra North to North Star | Culverts | 695.210, 1/1200x1200, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 2 1200X1200 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 694.47 | 695.95 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122867
WLD/N2NS/00129 | Nabin Koirala | 2021-04-04 21:38 | Stage 3 - Camurra North to North Star | Culverts | 691.020, 4/1800x600, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 8 1800X600 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 686.85 | 695.95 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122866
WLD/N2NS/00128 | Nabin Koirala | 2021-04-04 21:35 | Stage 3 - Camurra North to North Star | Culverts | 690.820, 8/2400x1500, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 8 1800X600 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 686.85 | 695.2 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122865
WLD/N2NS/00127 | Nabin Koirala | 2021-04-04 21:34 | Stage 3 - Camurra North to North Star | Culverts | 686.490, 2/1800x1200, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 3 - INSTALLATION OF 4 1800X1200 RCBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 684.36 | 688.62 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122864
WLD/N2NS/00126 | Nabin Koirala | 2021-04-04 21:31 | Stage 3 - Camurra North to North Star | Culverts | 686.410, 2/1800x900, remove and rebuild | Culverts - Other | Other | Nabin Koirala | Excavation and Foundation Preparation for Drainage Structures |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 684.31 | 688.52 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122863
WLD/N2NS/00125 | Nabin Koirala | 2021-04-04 20:53 | Stage 2B - Ch641.000km to 647.000km | Culverts | 646.160, 10/3000x1200, demo and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2B - INSTALLATION OF 4 3000X1200 4SBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 642.71 | 649.61 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122862
WLD/N2NS/00124 | Nabin Koirala | 2021-04-04 20:51 | Stage 2B - Ch641.000km to 647.000km | Culverts | 646.065, 2/2400x900, demo and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2B - INSTALLATION OF 2 2400X900 4SBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 644.67 | 647.47 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122861
WLD/N2NS/00123 | Nabin Koirala | 2021-04-04 20:50 | Stage 2B - Ch641.000km to 647.000km | Culverts | 645.920, 2/2400x900, demo and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2B - INSTALLATION OF 2 1800X900 4SBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 644.82 | 647.02 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122860
WLD/N2NS/00122 | Nabin Koirala | 2021-04-04 20:49 | Stage 2B - Ch641.000km to 647.000km | Culverts | 645.490, 20/3000x1200, demo and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2B - INSTALLATION OF 4 3000X1200 4SBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 642.04 | 648.94 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122859
WLD/N2NS/00121 | Nabin Koirala | 2021-04-04 20:48 | Stage 2B - Ch641.000km to 647.000km | Culverts | 644.980, 55/3000x1200, demo and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2B - INSTALLATION OF 10 4SBCS 3000X1200 |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 636.35 | 653.63 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122858
WLD/N2NS/00120 | Nabin Koirala | 2021-04-04 20:46 | Stage 2B - Ch641.000km to 647.000km | Culverts | 643.980, 72/3000x1200, demo and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2B - INSTALLATION OF 12 3000X1200 4SBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 633.62 | 654.36 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122857
WLD/N2NS/00119 | Nabin Koirala | 2021-04-04 20:44 | Stage 2B - Ch641.000km to 647.000km | Culverts | 643.000, 45/1800x1200, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2B - INSTALLATION OF 12 1800X1200 4SBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 636.36 | 649.66 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122856
WLD/N2NS/00118 | Nabin Koirala | 2021-04-04 20:42 | Stage 2B - Ch641.000km to 647.000km | Culverts | 641.950, 35/3000x2400, new build | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2B - INSTALLATION OF 70 3000X2400 4SBCS |  |  | 2021-09-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 581.47 | 702.55 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122855
WLD/N2NS/00117 | Nabin Koirala | 2021-04-04 20:40 | Stage 2 - Penneys Road to Moree | Culverts | 631.140, 3/1800x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Backfill of 4SBCS 1800 X 900 | 2021-07-24 |  | 2021-09-25 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 617.82 | 624.46 | [6 empty] | HWP/N2NS/00392, HWP/N2NS/00393 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122854
WLD/N2NS/00116 | Nabin Koirala | 2021-04-03 04:45 | Stage 3 - Camurra North to North Star | Culverts | 711.770, 11/3000x1200, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Excavation and Foundation Preparation for Drainage Structures - Base Slab | 2021-06-25 |  | 2021-05-28 10:00 | Benjamin Philip | 2021-07-01 | 2021-07-01 00:37 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 639.27 | 730.32 | Benjamin Philip | 2021-07-01 00:45 |  |  |  |  | HWP/N2NS/00017 | Lot closed |  | 2021-07-01 00:45 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | IMG_0884.JPG, Photo.jpg, N-21-186-25.pdf, WLDN2NS00116.pdf, WLDN2NS00116LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122851 | 2021-07-29 18:40 |  |  |  |  | 2021-07-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00115 | Arjan Sidhu | 2021-03-31 03:57 | Stage 2 - Penneys Road to Moree | Ancillary Works | Other (Specify Location in Lot) | Temporary Works - Other - Camp | Concrete | Arjan Sidhu | 1x 7day and 2 x 28 day concrete strength tests for Camp Kerb N32/10 |  |  | 2021-04-09 10:00 |  |  |  | Abandoned | AMS/N2NS/00002 | ITP/N2NS/00004 | [10 empty] | 0 | 0 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122661 |  | HN QCV PTY LIMITED & QANTAC VILLAGES PTY LIMITED
WLD/N2NS/00114 | Arjan Sidhu | 2021-03-31 03:56 | Stage 2 - Penneys Road to Moree | Ancillary Works | Other (Specify Location in Lot) | Temporary Works - Other - Camp | Concrete | Arjan Sidhu | 1x 7day and 2 x 28 day concrete strength tests for Camp Kerb N32/10 |  |  | 2021-04-08 10:00 |  |  |  | Abandoned | AMS/N2NS/00002 | ITP/N2NS/00004 | [10 empty] | 0 | 0 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122660 |  | HN QCV PTY LIMITED & QANTAC VILLAGES PTY LIMITED
WLD/N2NS/00113 | Arjan Sidhu | 2021-03-31 03:56 | Stage 2 - Penneys Road to Moree | Ancillary Works | Other (Specify Location in Lot) | Temporary Works - Other - Camp | Concrete | Arjan Sidhu | 1x 7day and 2 x 28 day concrete strength tests for Camp Kerb N32/10 |  |  | 2021-04-07 10:00 |  |  |  | Abandoned | AMS/N2NS/00002 | ITP/N2NS/00004 | [10 empty] | 0 | 0 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122659 |  | HN QCV PTY LIMITED & QANTAC VILLAGES PTY LIMITED
WLD/N2NS/00112 | Arjan Sidhu | 2021-03-31 03:56 | Stage 2 - Penneys Road to Moree | Ancillary Works | Other (Specify Location in Lot) | Temporary Works - Other - Camp | Concrete | Arjan Sidhu | 1x 7day and 2 x 28 day concrete strength tests for Camp Kerb N32/10 |  |  | 2021-04-06 10:00 |  |  |  | Abandoned | AMS/N2NS/00002 | ITP/N2NS/00004 | [10 empty] | 0 | 0 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122658 |  | HN QCV PTY LIMITED & QANTAC VILLAGES PTY LIMITED
WLD/N2NS/00111 | Arjan Sidhu | 2021-03-31 03:40 | Stage 2 - Penneys Road to Moree | Ancillary Works | Other (Specify Location in Lot) | Temporary Works - Other - Camp | Concrete | Arjan Sidhu | 1x 7day and 2 x 28 day concrete strength tests for Camp Kerb N32/10 |  |  | 2021-04-01 11:00 |  |  |  | Abandoned | AMS/N2NS/00002 | ITP/N2NS/00004 | [10 empty] | 0 | 0 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122657 |  | HN QCV PTY LIMITED & QANTAC VILLAGES PTY LIMITED
WLD/N2NS/00110 | Nabin Koirala | 2021-03-27 22:51 | Stage 2 - Penneys Road to Moree | Culverts | 664.982, 1/1800x600, new build (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2 - Installation and Backfill of 6 RCBCS 1800X600 |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 663.94 | 666.02 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122472
WLD/N2NS/00109 | Nabin Koirala | 2021-03-27 22:50 | Stage 2 - Penneys Road to Moree | Culverts | 664.870, 3/1800x600, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2 - Installation and Backfill of 6 RCBCS 1800X600 |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 661.74 | 668 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122471
WLD/N2NS/00108 | Nabin Koirala | 2021-03-27 22:49 | Stage 2 - Penneys Road to Moree | Culverts | 663.460, 4/1800x600, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2 - Installation and Backfill of 8 RCBCS 1800X600 |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 659.27 | 667 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122470
WLD/N2NS/00107 | Nabin Koirala | 2021-03-27 22:48 | Stage 2 - Penneys Road to Moree | Culverts | 663.135, 1/600x600, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2 - Installation and Backfill of 2 RCBCS 600X600 |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 662.73 | 663.53 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122469
WLD/N2NS/00106 | Nabin Koirala | 2021-03-27 22:47 | Stage 2 - Penneys Road to Moree | Culverts | 660.705, 45/3000x2400, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2 - Installation and Backfill of 225 4SBCS 3000X2400 |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 582.94 | 738.62 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122468
WLD/N2NS/00105 | Nabin Koirala | 2021-03-27 22:45 | Stage 2 - Penneys Road to Moree | Culverts | 659,780 NEW | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2 - Installation and Backfill of 4 RCBCS 1800X600 |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 657.7 | 661.87 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122467
WLD/N2NS/00104 | Nabin Koirala | 2021-03-27 22:45 | Stage 2 - Penneys Road to Moree | Culverts | 659,400 NEW | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2 - Installation and Backfill of 10 RCBC 1800X600 |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 654.18 | 664.63 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122466
WLD/N2NS/00103 | Nabin Koirala | 2021-03-27 22:44 | Stage 2 - Penneys Road to Moree | Culverts | 659,095 NEW | Drainage - Reinforced Concrete Pipes | Other | Nabin Koirala | Stage 2 - Installation and Backfill of 15 RCPS 450 DIA |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 657.44 | 660.75 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122465
WLD/N2NS/00102 | Nabin Koirala | 2021-03-27 22:42 | Stage 2 - Penneys Road to Moree | Culverts | 658,820 NEW | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2 - Installation and Backfill of 15 RCBCS 1800X600 |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 655.69 | 661.95 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122464
WLD/N2NS/00101 | Nabin Koirala | 2021-03-27 22:41 | Stage 2 - Penneys Road to Moree | Culverts | 656,240 New | Culverts - Installation of Box Culverts | Other | Frank Paraha | 656.240 - Installation of Pre-Cast Units | 2021-07-20 |  | 2021-08-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 |  |  |  |  | WLD/N2NS/01342 | [5 empty] | 656.24 | 656.24 |  |  |  | PNC/N2NS/00104 | Pending Disposition Approval | [8 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS00101LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122463 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/00100 | Nabin Koirala | 2021-03-27 22:40 | Stage 2 - Penneys Road to Moree | Culverts | 655.980, 5/3000x1200, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Frank Paraha | 655.980 - Installation of Pre-Cast Units |  |  | 2021-08-25 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 655.98 | 655.98 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122462 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/00099 | Nabin Koirala | 2021-03-27 22:39 | Stage 2 - Penneys Road to Moree | Culverts | 655.270, 6/3000x1200, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Frank Paraha | 655.270 - Installation of Pre-Cast Units |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 655.27 | 655.27 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122461 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/00098 | Nabin Koirala | 2021-03-27 22:36 | Stage 2 - Penneys Road to Moree | Culverts | 654.525, 1/1800x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | 654.525 - Installation of Pre-Cast Units | 2021-07-24 |  | 2021-07-29 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 654.53 | 654.53 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122460 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/00097 | Nabin Koirala | 2021-03-27 22:34 | Stage 2 - Penneys Road to Moree | Culverts | 653.700, 1/2400x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | 653.700 - Installation of Pre-Cast Units |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 653.7 | 653.7 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122459 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/00096 | Nabin Koirala | 2021-03-27 22:33 | Stage 2 - Penneys Road to Moree | Culverts | 653.620, 6/2400x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | 653.620 - Installation of Pre-Cast Units |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 653.62 | 653.62 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122458 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/00095 | Nabin Koirala | 2021-03-27 22:31 | Stage 2 - Penneys Road to Moree | Culverts | 653.150, 1/600x600, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | (DELETE OR REPURPOSE) Stage 2 - Installation and Backfill of 48 RCBCS 1800X600 |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 628.06 | 678.29 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122457
WLD/N2NS/00094 | Nabin Koirala | 2021-03-27 22:29 | Stage 2 - Penneys Road to Moree | Culverts | 652.715, 1/1800x600, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | (DELETE OR REPURPOSE) Stage 2 - Installation and Backfill of 4 RCBCS 1800X600 |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 652.72 | 652.72 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122456 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041
WLD/N2NS/00093 | Nabin Koirala | 2021-03-27 22:28 | Stage 2 - Penneys Road to Moree | Culverts | 652.530, 2/1800x600, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | DELETE OR REPURPOSE - Installation of Pre-Cast Units | 2021-07-24 |  | 2021-07-20 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 652.53 | 652.53 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122455 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/00092 | Nabin Koirala | 2021-03-27 22:28 | Stage 2 - Penneys Road to Moree | Culverts | 650.690, 2/2400x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | 650.690 - Installation of Pre-Cast Units |  |  | 2021-08-14 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 650.69 | 650.69 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122454 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/00091 | Nabin Koirala | 2021-03-27 22:27 | Stage 2 - Penneys Road to Moree | Culverts | 650.330, 1/2400x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | 650.330 - Installation of Pre-Cast Units |  |  | 2021-08-07 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 650.33 | 650.33 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122453 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/00090 | Nabin Koirala | 2021-03-27 22:24 | Stage 2 - Penneys Road to Moree | Culverts | 650,040 NEW | Culverts - Installation of Box Culverts | Other | Frank Paraha | 650.040 - Installation of Pre-Cast Units |  |  | 2021-08-14 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 650.04 | 650.04 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122452 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/00089 | Nabin Koirala | 2021-03-27 22:23 | Stage 2 - Penneys Road to Moree | Culverts | 649.185, 2/1800x600, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | 649.185 - Installation of Pre-Cast Units | 2021-07-24 |  | 2021-07-27 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 |  |  |  |  | WLD/N2NS/00575, WLD/N2NS/01333 | [5 empty] | 649.19 | 649.19 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS00089LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122451 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/00088 | Nabin Koirala | 2021-03-27 22:22 | Stage 2 - Penneys Road to Moree | Culverts | 649,700 NEW | Culverts - Installation of Box Culverts | Other | Frank Paraha | 649.700 - Installation of Pre-Cast Units |  |  | 2021-08-14 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 649.7 | 649.7 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122450 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/00087 | Nabin Koirala | 2021-03-27 22:21 | Stage 2 - Penneys Road to Moree | Culverts | 648.635, 6/2400x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | 648.635 - Installation of Pre-Cast Units |  |  | 2021-08-11 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 648.64 | 648.64 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122449 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/00086 | Nabin Koirala | 2021-03-27 22:19 | Stage 2 - Penneys Road to Moree | Culverts | 648.395, 10/3000x2400, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | 648.395 - Installation of Pre-Cast Units |  |  | 2021-08-14 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 648.4 | 648.4 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122448 |  |  |  | 7632-2S72150
WLD/N2NS/00085 | Nabin Koirala | 2021-03-27 22:18 | Stage 2 - Penneys Road to Moree | Culverts | 648.240, 6/2400x900, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | DELETE OR REPURPOSE Installation of Pre-Cast Units | 2021-07-24 | 2021-07-22 | 2021-07-22 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 648.24 | 648.24 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122447 |  |  |  | 7632-2S72150
WLD/N2NS/00084 | Nabin Koirala | 2021-03-27 22:17 | Stage 2 - Penneys Road to Moree | Culverts | 647.925, 4/2400x1200, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | 647.925 - Installation of Pre-Cast Units |  |  | 2021-08-14 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 647.93 | 647.93 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122446 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/00083 | Nabin Koirala | 2021-03-27 22:16 | Stage 2 - Penneys Road to Moree | Culverts | 647.670, 10/3000x1500, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | 647.670 - Installation of Pre-Cast Units |  |  | 2021-08-21 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 647.67 | 647.67 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122445 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/00082 | Nabin Koirala | 2021-03-27 22:14 | Stage 2 - Penneys Road to Moree | Culverts | 647.315, 10/3000x1200, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | 647.315 - Installation of Pre-Cast Units | 2021-07-24 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 |  |  |  |  | WLD/N2NS/00569, WLD/N2NS/01322 | [5 empty] | 647.32 | 647.32 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | WLDN2NS00082LM.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122444 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/00081 | Nabin Koirala | 2021-03-27 22:10 | Stage 2 - Penneys Road to Moree | Culverts | 647.155, 40/3000x2400, remove and rebuild | Culverts - Installation of Box Culverts | Other | Frank Paraha | 647.155 - Installation of Pre-Cast Units |  |  | 2021-08-31 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 |  |  |  |  | WLD/N2NS/00578 | [5 empty] | 647.16 | 647.16 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122443 |  | MCS CIVIL (NSW) PTY LTD | PKG/N2NS/00041 | 7632-2S72150
WLD/N2NS/00080 | Nabin Koirala | 2021-03-27 22:09 | Stage 2 - Penneys Road to Moree | Culverts | 640.650, 15/1800x1200, new build | Drainage - Other | Other | Nabin Koirala | Excavation and Foundation preparation of Drainage Structure 640.650 |  |  | 2021-05-31 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 624.03 | 657.31 | [6 empty] | HWP/N2NS/00227, HWP/N2NS/00411 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122442
WLD/N2NS/00079 | Nabin Koirala | 2021-03-27 22:08 | Stage 2 - Penneys Road to Moree | Culverts | 640.380, 20/1800x900, new build | Drainage - Other | Other | Nabin Koirala | Excavation and Foundation preparation of drainage structure 640.380 |  |  | 2021-05-31 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 618.21 | 662.59 | [6 empty] | HWP/N2NS/00228, HWP/N2NS/00229, HWP/N2NS/00410 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122441
WLD/N2NS/00078 | Nabin Koirala | 2021-03-27 22:07 | Stage 2 - Penneys Road to Moree | Culverts | 639.740, 60/2400x900, remove and rebuild | Culverts - Demolition | Other | Nabin Koirala | Demolition of Existing Structures | 2021-04-28 | 2021-04-27 | 2021-04-28 10:00 | Benjamin Philip | 2021-04-29 | 2021-04-29 06:25 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 639.74 | 639.74 | Benjamin Philip | 2021-04-29 06:25 | [5 empty] | Lot closed |  | 2021-04-29 06:25 |  |  |  | Brendan Meagher, Emma Donovan, George Yousef, Keegan Baker, Maddie Dahlstrom |  | 639.740_Demo Markup.pdf, 20210425_224119671_iOS.jpg, Checklist & Lot Conformance - 00078.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122440 | 2021-05-31 05:34 |  |  |  |  | 2021-05-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00077 | Nabin Koirala | 2021-03-27 22:05 | Stage 2 - Penneys Road to Moree | Culverts | 638.525, 13/2400x900, remove and rebuild | Culverts - Demolition | Other | Nabin Koirala | Demolition of Existing Structures | 2021-04-28 | 2021-04-28 | 2021-04-28 10:00 | Benjamin Philip | 2021-04-29 | 2021-04-29 06:24 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 638.53 | 638.53 | Benjamin Philip | 2021-04-29 06:24 | [5 empty] | Lot closed |  | 2021-04-29 06:24 |  |  |  | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom |  | 638.525_Demo Markup.pdf, 20210427_065625834_iOS.jpg, Checklist & Lot Conformance - 00077.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122439 | 2021-05-31 05:34 |  |  |  |  | 2021-05-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00076 | Nabin Koirala | 2021-03-27 22:04 | Stage 2 - Penneys Road to Moree | Culverts | 638.140, 5/2400x1200, remove and rebuild | Culverts - Demolition | Other | Nabin Koirala | Demolition of Existing Structures | 2021-04-28 | 2021-04-27 | 2021-04-27 10:00 | Benjamin Philip | 2021-04-29 | 2021-04-29 06:22 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 638.14 | 638.14 | Benjamin Philip | 2021-04-29 06:22 | [5 empty] | Lot closed |  | 2021-04-29 06:22 |  |  |  | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom |  | 638.140_Demo Markup.pdf, 20210426_025550041_iOS.jpg, Checklist & Lot Conformance - 00076.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122438 | 2021-05-31 05:34 |  |  |  |  | 2021-05-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00075 | Nabin Koirala | 2021-03-27 22:00 | Stage 2 - Penneys Road to Moree | Culverts | 637.290, 1/1800x900, remove and rebuild | Culverts - Demolition | Other | Nabin Koirala | Demolition of Existing Culvert | 2021-04-28 | 2021-04-27 | 2021-04-27 10:00 | Benjamin Philip | 2021-04-29 | 2021-04-29 06:20 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 637.29 | 637.29 | Benjamin Philip | 2021-04-29 06:20 | [5 empty] | Lot closed |  | 2021-04-29 06:20 |  |  |  | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom |  | 637.290_Demo Markup.pdf, 20210427_064831756_iOS.jpg, Checklist & Lot Conformance - 00075.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122437 | 2021-05-31 05:34 |  |  |  |  | 2021-05-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00074 | Nabin Koirala | 2021-03-27 21:59 | Stage 2 - Penneys Road to Moree | Culverts | 637.170, 1/1800x600, remove and rebuild | Culverts - Demolition | Other | Nabin Koirala | Demolition of Existing Culvert | 2021-04-26 | 2021-04-27 | 2021-04-27 10:00 | Benjamin Philip | 2021-04-29 | 2021-04-29 06:18 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 637.1 | 637.1 | Benjamin Philip | 2021-04-29 06:18 | [5 empty] | Lot closed |  | 2021-04-29 06:18 |  |  |  | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom |  | 20210426_025854068_iOS.jpg, 637.170_Demo Markup.pdf, Checklist & Lot Conformance - 00074.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122436 | 2021-05-31 05:34 |  |  |  |  | 2021-05-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00073 | Nabin Koirala | 2021-03-27 21:58 | Stage 2 - Penneys Road to Moree | Culverts | 636.705, 4/600x600, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Demolition of Existing Structures | 2021-04-28 | 2021-04-26 | 2021-04-26 10:00 | Benjamin Philip | 2021-04-29 | 2021-04-29 06:17 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 636.71 | 636.71 | Benjamin Philip | 2021-04-29 06:16 | [5 empty] | Lot closed |  | 2021-04-29 06:17 |  |  |  | Brendan Meagher, Emma Conroy, George Yousef, Keegan Baker, Maddie Dahlstrom |  | 20210425_233708355_iOS.jpg, 20210425_233708355_iOS.jpg, 636.705_Demo Markup.pdf, Checklist & Lot Conformance - 00073.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122435 | 2021-05-31 05:34 |  |  |  |  | 2021-05-05 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00072 | Nabin Koirala | 2021-03-27 21:55 | Stage 2 - Penneys Road to Moree | Culverts | 635.410, 2/2400x900, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2 - Installation and Backfill of 2 4SBCs 2400x900 |  |  | 2021-04-30 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 634.01 | 636.81 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122434
WLD/N2NS/00071 | Arjan Sidhu | 2021-03-26 21:49 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Capping | Earthworks | Arjan Sidhu | Process control - Runnymead Capping Material. Stockpile 8/21 - 4000t lot. | 2021-03-27 |  | 2021-03-25 11:00 | Benjamin Philip | 2021-04-09 | 2021-04-09 06:11 | Closed | AMS/N2NS/00007 | ITP/N2NS/00006 | [10 empty] | 0 | 0 | Arjan Sidhu | 2021-04-08 21:27 | [5 empty] | Lot closed |  | 2021-04-09 06:11 | [5 empty] | RU Capping Lot 8-21 16-3-21.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122426 | 2021-05-31 05:34 |  |  |  |  | 2021-04-28 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00070 | Arjan Sidhu | 2021-03-26 21:47 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Capping | Earthworks | Arjan Sidhu | Process control - Runnymead Capping Material. Stockpile 7/21 - 4000t lot. | 2021-03-27 |  | 2021-03-25 11:00 | Benjamin Philip | 2021-04-09 | 2021-04-09 06:06 | Closed | AMS/N2NS/00007 | ITP/N2NS/00006 | [10 empty] | 0 | 0 | Arjan Sidhu | 2021-04-08 21:30 | [5 empty] | Lot closed |  | 2021-04-09 06:06 | [5 empty] | RU Capping Lot 7-21 21-3-21.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122425 | 2021-05-31 05:34 |  |  |  |  | 2021-04-28 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00069 | Arjan Sidhu | 2021-03-26 21:43 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Pavements - Capping | Track | Arjan Sidhu | Process control - Runnymead Capping Material. Stockpile 6/21 - 4000t lot. | 2021-03-27 |  | 2021-03-25 11:00 | Benjamin Philip | 2021-04-09 | 2021-04-09 06:01 | Closed | AMS/N2NS/00007 | ITP/N2NS/00006 | [10 empty] | 0 | 0 | Arjan Sidhu | 2021-04-08 21:33 | [5 empty] | Lot closed |  | 2021-04-09 06:01 | [5 empty] | RU Capping Lot 6-21 24-3-21 perm.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122424 | 2021-05-31 05:34 |  |  |  |  | 2021-04-28 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00068 | Arjan Sidhu | 2021-03-26 21:20 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Trackwork - Bottom Ballast | Track | Arjan Sidhu | Process control - Runnymead 63mm ballast. Stockpile 4 - 5000t lot. | 2021-03-27 |  | 2021-03-25 11:00 | Sarah Brooks | 2021-05-09 | 2021-05-08 22:37 | Closed | AMS/N2NS/00007 | ITP/N2NS/00007 | [10 empty] | 0 | 0 | Arjan Sidhu | 2021-05-08 06:20 |  |  |  |  | HWP/N2NS/00014 | Lot closed |  | 2021-05-08 22:37 | [5 empty] | RU Ballast SP4 25-3-21.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122423 | 2021-05-31 05:34 |  |  |  |  | 2021-05-10 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00067 | Arjan Sidhu | 2021-03-26 21:11 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Trackwork - Bottom Ballast | Track | Arjan Sidhu | Process Control - Runnymead 63mm Ballast - 5000t Lot. Stockpile 3. | 2021-03-27 |  | 2021-03-25 11:00 | Sarah Brooks | 2021-05-09 | 2021-05-08 22:36 | Closed | AMS/N2NS/00007 | ITP/N2NS/00007 | [10 empty] | 0 | 0 | Arjan Sidhu | 2021-05-08 06:22 | [5 empty] | Lot closed |  | 2021-05-08 22:36 | [5 empty] | RU Ballast SP3 25-3-21.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122422 | 2021-05-31 05:34 | Johnstone Concrete & Quarries Pty Ltd (Moree) |  |  |  | 2021-05-10 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00066 | Hayden Murphy | 2021-03-25 00:55 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 649.350, LX1829, Crown access (Type 2, 6m, rubber, unsealed), RX-2 | Pavements - Level Crossing Pavement | Roadworks | Hayden Murphy | LX3067 Works |  |  | 2021-06-30 10:00 |  |  |  | Planned | AMS/N2NS/00001, AMS/N2NS/00004, AMS/N2NS/00005, AMS/N2NS/00016 | ITP/N2NS/00001, ITP/N2NS/00003, ITP/N2NS/00006, ITP/N2NS/00009, ITP/N2NS/00010, ITP/N2NS/00031, ITP/N2NS/00032 | [10 empty] | 649.35 | 649.36 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122348
WLD/N2NS/00065 | Hayden Murphy | 2021-03-25 00:54 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 648.100, LX3067, Private (Type 1, 9.20m, rubber, unsealed), RX-2 | Earthworks - Clearing & Grubbing | Roadworks | Hayden Murphy | LX3067 - Clear and Grubbing | 2021-06-27 |  | 2021-06-30 10:00 | Benjamin Philip | 2021-07-27 | 2021-07-27 00:30 | Closed | AMS/N2NS/00004 | ITP/N2NS/00001 | [10 empty] | 648.1 | 648.11 | Jeramy Smith | 2021-07-26 23:24 |  |  |  |  | HWP/N2NS/00219, HWP/N2NS/00221 | Lot closed |  | 2021-07-27 00:30 |  |  |  | Ahmad Alwan, Aziz Kamaoui, Loui Tannous, Sam Heng |  | 00065- Lot Map.pdf, Survey Report.pdf, 3067-1.jpeg, 3067-2.jpeg, WLDN2NS00065- Checklist.pdf, WLDN2NS00065- LC.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122347 | 2021-07-29 18:40 |  |  |  |  | 2021-07-31 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00064 | Hayden Murphy | 2021-03-25 00:53 | Stage 2 - Penneys Road to Moree | Pavements |  | Pavements - Level Crossing Pavement | Roadworks | Hayden Murphy | LX557 Works |  |  | 2021-06-30 10:00 |  |  |  | Planned | AMS/N2NS/00001, AMS/N2NS/00004, AMS/N2NS/00005, AMS/N2NS/00016 | ITP/N2NS/00001, ITP/N2NS/00003, ITP/N2NS/00006, ITP/N2NS/00009, ITP/N2NS/00010, ITP/N2NS/00031, ITP/N2NS/00032 | [10 empty] | 643.57 | 643.58 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122346
WLD/N2NS/00063 | Hayden Murphy | 2021-03-25 00:53 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 641.060, LX556, Private (Type 2, 4.50m, rubber, sealed at crossing), RX-2 | Pavements - Level Crossing Pavement | Roadworks | Hayden Murphy | LX556 Works |  |  | 2021-06-30 10:00 |  |  |  | Planned | AMS/N2NS/00001, AMS/N2NS/00004, AMS/N2NS/00005, AMS/N2NS/00016 | ITP/N2NS/00001, ITP/N2NS/00003, ITP/N2NS/00006, ITP/N2NS/00009, ITP/N2NS/00010, ITP/N2NS/00031, ITP/N2NS/00032 | [10 empty] | 641.06 | 641.07 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122345
WLD/N2NS/00062 | Hayden Murphy | 2021-03-25 00:08 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 636.300, LX555, To Temp Silo (Graincorp) (Type 3, rubber, sealed at crossing), RX-2 | Pavements - Level Crossing Pavement | Roadworks | Hayden Murphy | LX555 Works |  |  | 2021-06-30 10:00 |  |  |  | Planned | AMS/N2NS/00001, AMS/N2NS/00004, AMS/N2NS/00005, AMS/N2NS/00016 | ITP/N2NS/00001, ITP/N2NS/00003, ITP/N2NS/00006, ITP/N2NS/00009, ITP/N2NS/00010, ITP/N2NS/00031, ITP/N2NS/00032 | [10 empty] | 636.3 | 636.31 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122344
WLD/N2NS/00061 | Hayden Murphy | 2021-03-24 05:33 | Stage 2 - Penneys Road to Moree | Earthworks | Level Crossing - 635.600, LX554, Gurley Creek Road (Type 4, rubber, sealed), RX-5 | Earthworks - Clearing & Grubbing | Roadworks | Hayden Murphy | LX554 Clear and Grubbing (incl. Topsoil Strip) Northern Side (Temp Road) | 2021-05-24 | 2021-05-27 | 2021-06-30 10:00 | Benjamin Philip | 2021-06-08 | 2021-06-08 05:56 | Closed | AMS/N2NS/00004 | ITP/N2NS/00001 | CHK/N2NS/00010, CHK/N2NS/00011 | PER/N2NS/00008 | [8 empty] | 635.6 | 635.61 | Benjamin Philip | 2021-06-08 05:56 |  |  |  |  | HWP/N2NS/00136, HWP/N2NS/00139, HWP/N2NS/00144 | Lot closed |  | 2021-06-08 05:56 |  |  |  | Jeramy Smith |  | LX 554 TEMP RD TOPSOIL STRIP.pdf, IMG_0509.JPG, IMG_0516.JPG, IMG_0501.JPG, IMG_0518.JPG, IMG_0504.JPG, IMG_0508.JPG, IMG_0505.JPG, IMG_0503.JPG, IMG_0517.JPG, LX554 TR312.pdf, LX554 CG Lot Conformance.pdf, LX554 CG Checklist.pdf, LX554 ST Checklist.pdf, LX554 CG North Lot Map.pdf, LX554 Clearing Permit.pdf, Clearing Permit LX554.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122312 | 2021-06-29 19:15 |  |  |  |  | 2021-06-25 | Benjamin Philip | ARTC Accepted (Conforming)
WLD/N2NS/00060 | Hayden Murphy | 2021-03-24 05:30 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 634.490, LX3066, Private (Type 1, 6m, rubber, unsealed), RX-2 | Pavements - Level Crossing Pavement | Roadworks | Hayden Murphy | LX3066 Works |  |  | 2021-06-30 10:00 |  |  |  | Planned | AMS/N2NS/00001, AMS/N2NS/00004, AMS/N2NS/00005, AMS/N2NS/00016 | ITP/N2NS/00001, ITP/N2NS/00003, ITP/N2NS/00006, ITP/N2NS/00009, ITP/N2NS/00010, ITP/N2NS/00031, ITP/N2NS/00032 | [10 empty] | 634.49 | 634.5 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122311
WLD/N2NS/00059 | Hayden Murphy | 2021-03-24 05:28 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 631.150, LX553, Merimbula Road (Type 3, rubber, sealed at crossing), RX-2 | Pavements - Level Crossing Pavement | Roadworks | Hayden Murphy | LX553 Basecourse (DGB20) Layer 190mm |  |  | 2021-06-30 10:00 |  |  |  | Planned | AMS/N2NS/00001, AMS/N2NS/00004, AMS/N2NS/00005, AMS/N2NS/00016 | ITP/N2NS/00001, ITP/N2NS/00003, ITP/N2NS/00006, ITP/N2NS/00009, ITP/N2NS/00010, ITP/N2NS/00031, ITP/N2NS/00032 | [10 empty] | 631.15 | 631.16 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122310
WLD/N2NS/00058 | Hayden Murphy | 2021-03-24 05:15 | Stage 2 - Penneys Road to Moree | Pavements | Level Crossing - 627.850, LX1828, Private (Type 2, 4.5m, rubber, sealed at crossing), RX-2 | Pavements - Level Crossing Pavement | Roadworks | Hayden Murphy | LX1828 Works | 2021-07-23 |  | 2021-06-30 10:00 |  |  |  | Open | AMS/N2NS/00001, AMS/N2NS/00004, AMS/N2NS/00005, AMS/N2NS/00016 | ITP/N2NS/00001, ITP/N2NS/00003, ITP/N2NS/00006, ITP/N2NS/00009, ITP/N2NS/00010, ITP/N2NS/00031, ITP/N2NS/00032 | [10 empty] | 627.85 | 627.86 | [6 empty] | HWP/N2NS/00134 | [9 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122308
WLD/N2NS/00057 | George Yousef | 2021-03-24 03:41 | Stage 3 - Camurra North to North Star | Culverts | 711.640, 15/3000x1500, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Excavation and Foundation Preparation for Drainage Structures - Base Slab | 2021-06-22 |  | 2021-12-31 11:00 | Benjamin Philip | 2021-06-27 | 2021-06-26 23:07 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 711.67 | 711.67 | Nabin Koirala | 2021-06-26 06:19 |  |  |  |  | HWP/N2NS/00013, HWP/N2NS/00021 | Lot closed |  | 2021-06-26 23:07 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | Test Request 0344 Panda Results.pdf, N-21-179-266 (711.640 Comp).pdf, Culvert_711.640 (Base Slab Foundation Panda Testing).pdf, 711.640_Checklist.pdf, Milguy Trial.pdf, IMG_1215 (1).JPG, IMG_1216 (1).JPG, IMG_0756.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122306 | 2021-06-29 19:15 |  |  |  |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00056 | George Yousef | 2021-03-24 03:37 | Stage 3 - Camurra North to North Star | Culverts | 711.510, 6/3000x1200, remove and rebuild | Culverts - Other | Other | Nabin Koirala | Excavation and foundation preparation for Drainage Structures - Base Slab | 2021-06-22 |  | 2021-12-31 11:00 | Benjamin Philip | 2021-06-28 | 2021-06-27 23:04 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 711.51 | 711.51 | Emma Conroy | 2021-06-27 22:52 |  |  |  |  | HWP/N2NS/00016, HWP/N2NS/00023, HWP/N2NS/00209 | Lot closed |  | 2021-06-27 23:04 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | Test Request0065.pdf, Culvert Wingwalls_2021.04.09.pdf, Milguy Trial.pdf, IMG_1215 (1).JPG, IMG_1216 (1).JPG, S66 Balo St21062809380.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122305 | 2021-06-29 19:15 |  |  |  |  | 2021-07-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00055 | James Martin | 2021-03-24 00:20 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Insitu Treatments/Stabilisation | Earthworks | James Martin | Type C3 Foundation - Milguy Formation Trial - CH711.30 to CH712.00 - Insitu Layer 250mm | 2021-05-23 |  | 2021-04-02 11:00 | Lorne Jenks | 2021-06-23 | 2021-06-23 03:36 | Closed | AMS/N2NS/00006 | ITP/N2NS/00003 | CHK/N2NS/00015 | [9 empty] | 711.3 | 711.76 | Lorne Jenks | 2021-06-23 03:35 | [5 empty] | Lot closed |  | 2021-06-23 03:36 |  |  |  | Richard Doering, Ryan Shenton |  | TR0098C - PANDA.pdf, TR0098D - PANDA.pdf, TR0098B - PANDA.pdf, TR0098A - PANDA.pdf, IMG_0766.JPG, IMG_0849.JPG, Insitu Stabilised Treatment Ch 711390 to Ch 711800 Lot WLD-N2NS-00055.pdf, WLDN2NS00055 - Completed Checklist.pdf, WLD-N2NS-0055 - Lot Map.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122299 | 2021-06-29 19:15 |  |  | 7632-2C41552 |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00054 | Johannes Mason | 2021-03-15 19:33 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Bridgeworks | Offsite Manufacture/Supply - Prestressed Concrete Deck and Kerb Units | Concrete | Johannes Mason | Manufacture of Precast Pre-stressed Deck Units - June 2021 | 2021-06-05 |  | 2021-06-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00062 | [9 empty] | MIX/N2NS/00002 | 0 | 0 |  |  |  | PNC/N2NS/00063 | Closed |  | HWP/N2NS/00167, HWP/N2NS/00170, HWP/N2NS/00171 | [9 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122029 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/00053 | Johannes Mason | 2021-03-15 19:32 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Bridgeworks | Offsite Manufacture/Supply - Prestressed Concrete Deck and Kerb Units | Concrete | Johannes Mason | Manufacture of Precast Pre-stressed Deck Units - May 2021 | 2021-05-03 |  | 2021-05-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00062 | [9 empty] | MIX/N2NS/00002 | 0 | 0 | [6 empty] | HWP/N2NS/00166, HWP/N2NS/00167, HWP/N2NS/00170 | [9 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122028 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/00052 | Johannes Mason | 2021-03-15 19:31 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Bridgeworks | Offsite Manufacture/Supply - Prestressed Concrete Deck and Kerb Units | Concrete | Johannes Mason | Manufacture of Precast Pre-stressed Deck Units - April 2021 | 2021-05-03 |  | 2021-04-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00062 | [9 empty] | MIX/N2NS/00002 | 0 | 0 | [6 empty] | HWP/N2NS/00166 | [9 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122027 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/00051 | Johannes Mason | 2021-03-15 19:31 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Bridgeworks | Offsite Manufacture/Supply - Prestressed Concrete Deck and Kerb Units | Concrete | Johannes Mason | Manufacture of Precast Pre-stressed Deck Units - March 2021 | 2021-03-16 |  | 2021-03-31 11:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00062 | [9 empty] | MIX/N2NS/00002 | 0 | 0 |  |  |  | PNC/N2NS/00004, PNC/N2NS/00005, PNC/N2NS/00020, PNC/N2NS/00027, PNC/N2NS/00046, PNC/N2NS/00047 | Closed, Closed, Closed, Closed, Disposition Approved, Disposition Approved | [11 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122026 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/00050 | Johannes Mason | 2021-03-15 19:28 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Bridgeworks | Offsite Manufacture/Supply - Prestressed Concrete Deck and Kerb Units | Concrete | Johannes Mason | Manufacture of Precast Underbridge Abutments, Headstocks & Transition Slab - June 2021 |  |  | 2021-06-30 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00061 | [9 empty] | MIX/N2NS/00003 | 0 | 0 | [6 empty] | HWP/N2NS/00175, HWP/N2NS/00176, HWP/N2NS/00177 | [9 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122025 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/00049 | Johannes Mason | 2021-03-15 19:28 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Bridgeworks | Offsite Manufacture/Supply - Prestressed Concrete Deck and Kerb Units | Concrete | Johannes Mason | Manufacture of Precast Underbridge Abutments, Headstocks & Transition Slab - May 2021 | 2021-05-03 |  | 2021-05-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00061 | [9 empty] | MIX/N2NS/00003 | 0 | 0 |  |  |  | PNC/N2NS/00062, PNC/N2NS/00081, PNC/N2NS/00087 | Closed, Closed, Disposition Rejected |  | HWP/N2NS/00177 | [9 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122024 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/00048 | Johannes Mason | 2021-03-15 19:27 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Bridgeworks | Offsite Manufacture/Supply - Prestressed Concrete Deck and Kerb Units | Concrete | Johannes Mason | Manufacture of Precast Underbridge Abutments, Headstocks & Transition Slab - April 2021 | 2021-05-03 |  | 2021-04-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00061 | [9 empty] | MIX/N2NS/00003 | 0 | 0 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122023 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/00047 | Johannes Mason | 2021-03-15 19:25 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Manufacture of Precast Rail Large & Small Concrete Box Culvert and Wing Walls - June 2021 | 2021-06-04 |  | 2021-06-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058 | [9 empty] | MIX/N2NS/00001 | 0 | 0 |  |  |  | PNC/N2NS/00058, PNC/N2NS/00059, PNC/N2NS/00060, PNC/N2NS/00061, PNC/N2NS/00065, PNC/N2NS/00066, PNC/N2NS/00070, PNC/N2NS/00071, PNC/N2NS/00072, PNC/N2NS/00073, PNC/N2NS/00074, PNC/N2NS/00075, PNC/N2NS/00076, PNC/N2NS/00077, PNC/N2NS/00078, PNC/N2NS/00079, PNC/N2NS/00087, PNC/N2NS/00089, PNC/N2NS/00090, PNC/N2NS/00091, PNC/N2NS/00092, PNC/N2NS/00093, PNC/N2NS/00094, PNC/N2NS/00095, PNC/N2NS/00096, PNC/N2NS/00098, PNC/N2NS/00101, PNC/N2NS/00102, PNC/N2NS/00105, PNC/N2NS/00106, PNC/N2NS/00107, PNC/N2NS/00110, PNC/N2NS/00117, PNC/N2NS/00119, PNC/N2NS/00121, PNC/N2NS/00124, PNC/N2NS/00125, PNC/N2NS/00126, PNC/N2NS/00127 | Closed, Closed, Closed, Closed, Closed, Closed, Closed, Closed, Closed, Closed, Closed, Closed, Closed, Closed, Closed, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Rejected, Disposition Rejected, Disposition Rejected, Disposition Rejected | [11 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122022 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/00046 | Johannes Mason | 2021-03-15 19:24 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Manufacture of Precast Rail Large & Small Concrete Box Culvert and Wing Walls - May 2021 | 2021-05-03 |  | 2021-05-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058 | [9 empty] | MIX/N2NS/00001 | 0 | 0 |  |  |  | PNC/N2NS/00034, PNC/N2NS/00035, PNC/N2NS/00037, PNC/N2NS/00040, PNC/N2NS/00041, PNC/N2NS/00042, PNC/N2NS/00043, PNC/N2NS/00044, PNC/N2NS/00045, PNC/N2NS/00048, PNC/N2NS/00049, PNC/N2NS/00050, PNC/N2NS/00051, PNC/N2NS/00052, PNC/N2NS/00053, PNC/N2NS/00054, PNC/N2NS/00055, PNC/N2NS/00056, PNC/N2NS/00057, PNC/N2NS/00058, PNC/N2NS/00059, PNC/N2NS/00067, PNC/N2NS/00068, PNC/N2NS/00069, PNC/N2NS/00070, PNC/N2NS/00071, PNC/N2NS/00078, PNC/N2NS/00082, PNC/N2NS/00083, PNC/N2NS/00088, PNC/N2NS/00096, PNC/N2NS/00097, PNC/N2NS/00098, PNC/N2NS/00117 | Closed, Closed, Closed, Closed, Closed, Closed, Closed, Closed, Closed, Closed, Closed, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Rejected, Disposition Rejected, Disposition Rejected, Disposition Rejected | [11 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122021 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/00045 | Johannes Mason | 2021-03-15 19:23 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Manufacture of Precast Rail Large & Small Concrete Box Culvert and Wing Walls - April 2021 | 2021-05-03 |  | 2021-04-30 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058 | [9 empty] | MIX/N2NS/00001 | 0 | 0 |  |  |  | PNC/N2NS/00021, PNC/N2NS/00022, PNC/N2NS/00023, PNC/N2NS/00024, PNC/N2NS/00031, PNC/N2NS/00032, PNC/N2NS/00033, PNC/N2NS/00036, PNC/N2NS/00039, PNC/N2NS/00053, PNC/N2NS/00064, PNC/N2NS/00066, PNC/N2NS/00067, PNC/N2NS/00068, PNC/N2NS/00117 | Closed, Closed, Closed, Closed, Closed, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Rejected, Disposition Rejected, Disposition Rejected | [11 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122020 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/00044 | Johannes Mason | 2021-03-15 19:22 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Manufacture of Precast Rail Large & Small Concrete Box Culvert and Wing Walls - March 2021 | 2021-03-16 |  | 2021-03-31 11:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058 | [9 empty] | MIX/N2NS/00001 | 0 | 0 |  |  |  | PNC/N2NS/00011, PNC/N2NS/00012, PNC/N2NS/00013, PNC/N2NS/00014, PNC/N2NS/00015, PNC/N2NS/00016, PNC/N2NS/00017, PNC/N2NS/00018, PNC/N2NS/00019, PNC/N2NS/00026, PNC/N2NS/00028, PNC/N2NS/00029, PNC/N2NS/00109, PNC/N2NS/00117 | Closed, Closed, Closed, Closed, Closed, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved, Disposition Approved | [11 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122019 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/00043 | Johannes Mason | 2021-03-15 19:21 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Manufacture of Precast Rail Large & Small Concrete Box Culvert and Wing Walls - February 2021 | 2021-03-16 |  | 2021-02-28 11:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058 | [9 empty] | MIX/N2NS/00001 | 0 | 0 |  |  |  | PNC/N2NS/00006, PNC/N2NS/00007, PNC/N2NS/00008, PNC/N2NS/00009, PNC/N2NS/00010, PNC/N2NS/00012, PNC/N2NS/00030 | Closed, Closed, Closed, Closed, Disposition Approved, Disposition Approved, Disposition Approved | [11 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/122018 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/00042 | Nabin Koirala | 2021-03-14 02:32 | Stage 2 - Penneys Road to Moree | Culverts | 635.145, 6/1800x600, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2 - Installation and Backfill of 6RCBC 1800x600 |  |  | 2021-04-30 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 628.88 | 641.42 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121919
WLD/N2NS/00041 | Nabin Koirala | 2021-03-14 02:29 | Stage 2 - Penneys Road to Moree | Culverts | 633.780, 35/3000x2400, remove and rebuild | Culverts - Demolition | Other | Nabin Koirala | 633.780 - Demolition of Existing Structures | 2021-06-19 |  | 2021-06-30 10:00 | Lorne Jenks | 2021-07-09 | 2021-07-09 06:08 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 554.29 | 713.43 | Lorne Jenks | 2021-07-09 06:08 | [5 empty] | Lot closed |  | 2021-07-09 06:08 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | Signed Lot Conformance & Checklist.pdf, Lot Map.pdf, IMG_0435.jpg, IMG_0139 (1).JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121918 | 2021-07-29 18:40 |  |  |  |  | 2021-07-18 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00040 | Nabin Koirala | 2021-03-14 02:25 | Stage 2 - Penneys Road to Moree | Culverts | 631.580, 1/600x600, remove and rebuild | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2 - Installation and Backfill of RCBC 600x600 |  |  | 2021-04-30 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 631.18 | 631.98 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121917
WLD/N2NS/00039 | Nabin Koirala | 2021-03-14 02:21 | Stage 2 - Penneys Road to Moree | Culverts | 630.925, 2/600x600, remove and rebuild (RRA) | Culverts - Installation of Box Culverts | Other | Nabin Koirala | Stage 2 - Installation and Backfill of RCBC 600x600 |  |  | 2021-04-30 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 630.93 | 630.93 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121916
WLD/N2NS/00038 | Nabin Koirala | 2021-03-14 02:13 | Stage 2 - Penneys Road to Moree | Culverts | 627.760, 10/2400x1200, new build | Culverts - Installation of Box Culverts | Other | Keegan Baker | Stage 2 - Backfill of 4SBC's - Ch627.760 | 2021-07-24 |  | 2021-07-31 10:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 627.77 | 627.77 | [6 empty] | HWP/N2NS/00330, HWP/N2NS/00387 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121915
WLD/N2NS/00037 | Nabin Koirala | 2021-03-14 02:10 | Stage 2 - Penneys Road to Moree | Culverts | 627.430, 30/3000x2100, remove and rebuild | Culverts - Installation of Box Culverts | Other | Keegan Baker | 627.430 - Backfill of 4SBC's |  |  | 2021-04-30 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 627.48 | 627.48 | [6 empty] | HWP/N2NS/00385 | [6 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121914
WLD/N2NS/00036 | Nabin Koirala | 2021-03-14 02:09 | Stage 2 - Penneys Road to Moree | Culverts | 627.280, 50/3000x2400, remove and rebuild | Earthworks - Topsoil Removal | Earthworks | Keegan Baker | Topsoil Strip for Stage 2 - Installation and Backfill of 4SBC's - Ch 627.280 |  |  | 2021-04-30 10:00 |  |  |  | Abandoned | AMS/N2NS/00002 | ITP/N2NS/00001 | CHK/N2NS/00011 | [9 empty] | 627.35 | 627.35 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121913
WLD/N2NS/00035 | Nabin Koirala | 2021-03-14 02:07 | Stage 2 - Penneys Road to Moree | Culverts | 625.570, 2/1200x450, remove and rebuild | Culverts - Installation of Box Culverts | Other | Keegan Baker | Stage 2 - Installation and Backfill of RCBC's - Ch 625.710 |  |  | 2021-04-30 10:00 |  |  |  | Planned | AMS/N2NS/00005 | ITP/N2NS/00017 | [10 empty] | 625.57 | 625.57 | [13 empty] | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121912
WLD/N2NS/00034 | George Yousef | 2021-03-12 05:18 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Other | Nabin Koirala | Supply of Pre-cast Culverts - April 2021 |  |  | 2021-04-30 10:00 |  |  |  | Abandoned | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058, ITP/N2NS/00059, ITP/N2NS/00060, ITP/N2NS/00062 | [10 empty] | 575 | 760 | [13 empty] | Brendan Meagher, George Yousef, Nabin Koirala |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121903 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/00033 | George Yousef | 2021-03-12 05:01 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Other | Nabin Koirala | Supply of Pre-cast Culverts - March 2021 | 2021-03-12 |  | 2021-03-31 11:00 |  |  |  | Abandoned | AMS/N2NS/00005 | ITP/N2NS/00057, ITP/N2NS/00058, ITP/N2NS/00059, ITP/N2NS/00060, ITP/N2NS/00062 | [10 empty] | 575 | 760 | [13 empty] | Brendan Meagher, George Yousef, Nabin Koirala |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121899 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/00032 | Johannes Mason | 2021-03-03 01:18 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Bridgeworks | Offsite Manufacture/Supply - Prestressed Concrete Deck and Kerb Units | Concrete | Johannes Mason | Manufacture of Precast Underbridge Abutments, Headstocks & Transition Slab - March 2021 | 2021-03-05 |  | 2021-03-31 11:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00061 | [9 empty] | MIX/N2NS/00003 | 0 | 0 |  |  |  | PNC/N2NS/00025 | Disposition Rejected |  | HWP/N2NS/00012 | [9 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121406 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/00031 | Hayden Murphy | 2021-03-03 00:15 | Stage 3 - Camurra North to North Star | Temporary Works - Compounds and Laydowns | Laydown 6 | Temporary Works - Compounds and Laydowns - Earthworks | Earthworks | Hayden Murphy | Stabilisation and Placement of Gravel for Stage 3, Laydown 6 |  |  | 2021-06-02 10:00 |  |  |  | Planned | AMS/N2NS/00002 | ITP/N2NS/00002 | [10 empty] | 734.85 | 735.1 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121402 |  |  |  | 7632-GA38050
WLD/N2NS/00030 | Brendan Meagher | 2021-03-02 07:20 | Stage 3 - Camurra North to North Star | Culverts | 711.410, 10/2400x900, new build | Culverts - Installation of Box Culverts | Other | Brendan Meagher | Stage 3 - Culvert Ch 711.410 - Excavation and Foundation Preparation | 2021-03-08 |  | 2021-04-30 10:00 | Sarah Brooks | 2021-05-09 | 2021-05-08 22:27 | Closed | AMS/N2NS/00005 | ITP/N2NS/00017 | CHK/N2NS/00007 | [9 empty] | 697.62 | 725.22 | Brendan Meagher | 2021-05-08 04:46 |  |  |  |  | HWP/N2NS/00015, HWP/N2NS/00017, HWP/N2NS/00022, HWP/N2NS/00026 | Lot closed |  | 2021-05-08 22:27 |  |  |  | Brendan Meagher, Emma Conroy, Frank Paraha, George Yousef, Keegan Baker, Maddie Dahlstrom, Nabin Koirala, Patrick Coria |  | N-21-186-22.pdf, Culvert Wingwalls_2021.04.09.pdf, 2021.04.10 - Concrete - Culvert 711.410 base slab blinding.pdf, IMG_0081.JPG, IMG_0162.jpg, IMG_0113.JPG, IMG_0129.PNG, 711.410 Lot Conformance Report (Excavation).pdf, 711.410 Excavation Checklist.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121390 | 2021-05-31 05:34 |  |  |  |  | 2021-06-07 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00029 | Ryan Shenton | 2021-03-02 06:27 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Earthworks - Filling | Earthworks | Ryan Shenton | Process Control - Attunga Quicklime - Lot 1 - Milguy Trial | 2021-03-02 |  | 2021-03-16 11:00 | Benjamin Philip | 2021-03-17 | 2021-03-16 21:04 | Closed | AMS/N2NS/00001 | ITP/N2NS/00003 | [10 empty] | 0 | 0 | Ryan Shenton | 2021-03-02 06:46 | [5 empty] | Lot closed |  | 2021-03-16 21:04 | [5 empty] | 2AT-202102-0029-00075801-F.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121385 | 2021-05-31 05:34 |  |  |  |  | 2021-04-06 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00028 | Ryan Shenton | 2021-03-02 01:23 | Stage 3 - Camurra North to North Star | Drainage | Main Alignment (Specify Chainage in Lot) | Drainage - CESS Drains | Earthworks | Ryan Shenton | Cess Drain - Milguy Trail - CH711.00 to CH711.155 |  |  | 2021-04-15 10:00 |  |  |  | Abandoned | [12 empty] | 711 | 711.16 | [6 empty] | HWP/N2NS/00011 | [9 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121352
WLD/N2NS/00027 | Kiara Davis | 2021-03-01 05:26 | Stage 3 - Camurra North to North Star | Temporary Works - Compounds and Laydowns | Other (Specify Location in Lot) | Temporary Works - Compounds and Laydowns - Earthworks | Earthworks | Kiara Davis | Stage 3 - Milguy Pad, adjacent to Laydown 2 |  |  | 2021-04-03 11:00 |  |  |  | Abandoned | [12 empty] | 706.6 | 707.3 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121315
WLD/N2NS/00026 | Ryan Shenton | 2021-02-26 20:00 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 - Milguy Formation Trial - CH711.800 to CH712.000 - Layer 2 - 400mm | 2021-06-11 |  | 2021-04-30 10:00 | Lorne Jenks | 2021-06-24 | 2021-06-23 20:56 | Closed | AMS/N2NS/00001 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 711.8 | 712 | Lorne Jenks | 2021-06-23 20:55 | [5 empty] | Lot closed |  | 2021-06-23 20:56 |  |  |  | Richard Doering |  | TR0129.pdf, TR0127.pdf, TR0126B.pdf, TR0126A.pdf, TR0126.pdf, 1.jpg, 2.jpg, E3 Stabilised Layer 2 Ch 711820 to Ch 712000 Lot WLD-N2NS-00026.pdf, WLDN2NS00026 - Completed Checklist.pdf, WLD-N2NS-0026 - Lot Map.pdf, Test Report LWD P21004-72 15kg.pdf, Test Report P21004-72 Panda.pdf, Test Report LWD P21004-72 10kg.pdf, Test Report P21004-71 Panda.pdf, Test Report LWD P21004-71 15kg.pdf, Test Report P21004-70 Panda.pdf, Test Report LWD P21004-70 10kg.pdf, Test Report LWD P21004-70 15kg.pdf, Test Report LWD P21004-69 10kg.pdf, Test Report P21004-69 Panda.pdf, Test Report LWD P21004-69 15kg.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121148 | 2021-06-29 19:15 |  |  | 7632-GC48000 |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00025 | Ryan Shenton | 2021-02-26 19:59 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | James Martin | Type E3 - Milguy Formation Trial - CH711.800 to CH712.000 - Layer 1 - 400mm | 2021-04-17 |  | 2021-04-23 10:00 | Lorne Jenks | 2021-06-24 | 2021-06-23 20:56 | Closed | AMS/N2NS/00001 | ITP/N2NS/00003 | CHK/N2NS/00016 | [9 empty] | 711.8 | 712 | Lorne Jenks | 2021-06-23 20:55 |  |  |  |  | HWP/N2NS/00018 | Lot closed |  | 2021-06-23 20:56 |  |  |  | Kallen Doong, Richard Doering, Ryan Shenton |  | P21004-57-10kg Portable Impluse.pdf, P21004-57 T9PL Panda.pdf, P21004-57 T9PL LWD.pdf, P21004-57-15kg Portable Impluse.pdf, P21004-57 Plate Load.pdf, N-21-186-52.pdf, TR0108A.pdf, TR0108.pdf, TR0103A.1.pdf, TR0103A.pdf, TR0103.pdf, TR0103B.pdf, IMG_0918.JPG, IMG_0907.JPG, WLDN2NS00025 - Completed Checklist.pdf, WLD-N2NS-0025 - Lot Map.pdf, E3 Stabilised Layer 1 Ch 711810 to Ch 712000 Lot WLD-N2NS-00025.pdf, Test Report LWD P21004-67 15kg.pdf, Test Report LWD P21004-67 10kg.pdf, Test Report P21004-4 Panda.pdf, Test Report LWD P21004-66 15kg.pdf, Test Report P21004-66 Panda.pdf, Test Report LWD P21004-66 10kg.pdf, TestResult-P21004-58 (2).pdf, Test Report P21004-58 Panda.pdf, P21004-57-15kg Portable Impluse.pdf, P21004-57 T9PL Panda.pdf, P21004-57 T9PL LWD.pdf, P21004-57-10kg Portable Impluse.pdf, P21004-57 Plate Load.pdf, Test Report P21004-68.pdf, Test Report LWD P21004-68 15kg.pdf, Test Report LWD P21004-68 10kg.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121147 | 2021-06-29 19:15 |  |  | 7632-2C41552 |  | 2021-06-28 | Sarah Brooks | ARTC Accepted (Conforming)
WLD/N2NS/00024 | Ryan Shenton | 2021-02-26 19:57 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 Foundation - Milguy Formation Trial - CH711.000 to CH711.300 - Layer 2 - 400mm | 2021-04-10 |  | 2021-03-16 11:00 |  |  |  | Open | AMS/N2NS/00001 | ITP/N2NS/00003 | [10 empty] | 711 | 711.3 | [13 empty] | James Martin |  | TR0061A - PANDA.pdf, TR0061C - LWD.pdf, TR0061 Layer 2 Day 3.pdf, TR0061B - PANDA.pdf, TR0059 - PANDA.pdf, TR00058 Layer 2 Day 1.pdf, TR0058 - PANDA.pdf, TR0057A - PANDA.pdf, TR0057 Layer 2 Day 0.pdf, TR0057.pdf, IMG_0835.JPG, IMG_0834.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121146
WLD/N2NS/00023 | Ryan Shenton | 2021-02-26 19:56 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 Foundation - Milguy Formation Trial - CH711.000 to CH711.350 - Layer 1 - 400mm | 2021-03-24 |  | 2021-03-14 11:00 | Lorne Jenks | 2021-06-23 | 2021-06-23 02:33 | Closed | AMS/N2NS/00001 | ITP/N2NS/00003 | [10 empty] | 711 | 711.35 | Lorne Jenks | 2021-06-23 02:33 | [5 empty] | Lot closed |  | 2021-06-23 02:33 |  |  |  | James Martin |  | TR00054 Layer 1 Day 3.pdf, TR0052C - LWD.pdf, TR0054B - PANDA.pdf, TR0049A.pdf, TR0052.pdf, TR0051D - LWD.pdf, TR0052A - PANDA.pdf, TR0049.pdf, TR0051C - PANDA.pdf, TR0054A - PANDA.pdf, TR0074.pdf, TR0051.pdf, TR00074A.pdf, TR0051F - LWD.pdf, TR0052B - LWD.pdf, TR0051E - LWD.pdf, TR0051A.pdf, TR00049B.pdf, TR0051B.pdf, IMG_0754.JPG, IMG_0752.JPG, lot map 23.pdf, E3 Stabilised Layer 1 Conformance Report Ch 711020 to Ch 711350 Lot WLD-N2NS-00023.pdf, WLDN2NS00023 - Completed Checklist.pdf, N-21-186-21.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121145 | 2021-06-29 19:15 |  |  |  |  | 2021-07-04 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00022 | Ryan Shenton | 2021-02-26 19:53 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Milguy Earthworks Trials - CH 711.300 to 712.000 - Cut Inc Ground Prep | 2021-03-04 | 2021-04-01 | 2021-03-09 11:00 | Benjamin Philip | 2021-05-05 | 2021-04-13 00:04 | Closed | AMS/N2NS/00001 | ITP/N2NS/00003 | [10 empty] | 711.3 | 712 | Benjamin Philip | 2021-05-04 21:06 |  |  |  |  | HWP/N2NS/00008 | Lot closed | Rescanned Lot Report added | 2021-05-04 21:06 |  |  |  | Daniel Peyre, James Martin |  | WLD-N2NS-00022 - Conformance Report Ch 711300 to Ch 712000.pdf, N2NS_711000-713000 LONG SECTION 69 of 93 (1).pdf, Lot Maps WLD-N2NS-00022.pdf, IMG_0831.JPG, IMG_0829.JPG, IMG_0833.JPG, IMG_0830.JPG, IMG_0832.JPG, Lot Conformance Report WLD-N2NS-00022.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121144 | 2021-05-31 05:34 |  |  |  |  | 2021-04-28 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00021 | Ryan Shenton | 2021-02-26 19:52 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Milguy Earthworks Trials - CH 711.000 to 711.300 - Cut Inc Ground Prep | 2021-03-04 |  | 2021-03-09 11:00 | Sarah Brooks | 2021-04-06 | 2021-03-27 19:39 | Closed | AMS/N2NS/00001 | ITP/N2NS/00003 | [10 empty] | 711 | 711.3 | Sarah Brooks | 2021-04-05 23:13 |  |  |  |  | HWP/N2NS/00007 | Lot closed |  | 2021-04-05 23:13 |  |  |  | Daniel Peyre, James Martin |  | N2NS_711000-713000 LONG SECTION 69 of 93.pdf, IMG_0687[1].JPG, IMG_0683[1].JPG, WLD-N2NS-00021 - Conformance Report Ch 711010 to Ch 711300.pdf, WLDN2NS00021 Lot Maps.pdf, WLDN2NS00021 Checklist.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121143 | 2021-05-31 05:34 |  |  |  |  | 2021-04-06 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00020 | Ryan Shenton | 2021-02-24 22:21 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Topsoil Removal | Earthworks | Ryan Shenton | Topsoil Strip - Milguy Trial - CH711.000 to CH712.000 | 2021-03-03 |  | 2021-03-08 11:00 | Benjamin Philip | 2021-03-17 | 2021-03-16 23:27 | Closed | AMS/N2NS/00001 | ITP/N2NS/00001 | [10 empty] | 711 | 712 | Benjamin Philip | 2021-03-16 23:27 | [5 empty] | Lot closed |  | 2021-03-16 23:27 |  |  |  | James Martin |  | Lot Conformance Report - WLD-N2NS-00020.pdf, Survey Conformance Report - WLD-N2NS-00020.pdf, Lot Maps - WLD-N2NS-00020.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121022 | 2021-05-31 05:34 |  |  |  |  | 2021-04-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00019 | Ryan Shenton | 2021-02-24 22:18 | Stage 3 - Camurra North to North Star | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Clearing & Grubbing | Earthworks | Ryan Shenton | Clear and Grubbing - Milguy Earthworks Trials - CH711.000 to CH712.000 | 2021-03-02 |  | 2021-03-11 11:00 | Benjamin Philip | 2021-03-17 | 2021-03-16 23:12 | Closed | AMS/N2NS/00001 | ITP/N2NS/00001 | [10 empty] | 711 | 712 | Benjamin Philip | 2021-03-16 23:11 |  |  |  |  | HWP/N2NS/00006, HWP/N2NS/00009 | Lot closed |  | 2021-03-16 23:12 |  |  |  | James Martin |  | Lot Conformance Report - WLD-N2NS-00019.pdf, Lot Maps WLD-N2NS-00019.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/121021 | 2021-05-31 05:34 |  |  |  |  | 2021-04-06 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00018 | Hayden Murphy | 2021-02-19 04:43 | Stage 3 - Camurra North to North Star | Temporary Works - Compounds and Laydowns | Laydown 5 | Temporary Works - Compounds and Laydowns - Earthworks | Earthworks |  | Stabilisation and Placement of Gravel for Stage 3, Laydown 5 |  |  | 2021-04-02 11:00 |  |  |  | Planned | AMS/N2NS/00002 | ITP/N2NS/00002 | [10 empty] | 729.7 | 729.9 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/120740 |  |  |  | 7632-GA38050
WLD/N2NS/00017 | Kiara Davis | 2021-02-11 22:11 | Temporary Works (Outside of Stages) | Camp | Specify Location in Lot | Temporary Works - Other - Camp | Earthworks | Hayden Murphy | Topsoil Strip for Moree Camp | 2021-02-16 |  | 2021-02-19 11:00 | Benjamin Philip | 2021-03-23 | 2021-03-22 23:35 | Closed | AMS/N2NS/00002 | ITP/N2NS/00001 | [10 empty] | 663.85 | 664 | Hayden Murphy | 2021-03-22 22:40 |  |  |  |  | HWP/N2NS/00010 | Lot closed |  | 2021-03-22 23:35 | [5 empty] | Topsoil Checklist CAMP.pdf, Camp Map.PNG, Lot Conformance Topsoil CAMP.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/120458 | 2021-05-31 05:34 |  |  |  |  | 2021-04-02 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00016 | Kiara Davis | 2021-02-11 21:51 | Temporary Works (Outside of Stages) | Camp | Specify Location in Lot | Temporary Works - Other - Camp | Other | Kiara Davis | Temporary Works - Moree Camp Construction | 2021-03-03 |  | 2021-04-03 11:00 | Benjamin Philip | 2021-05-23 | 2021-05-23 03:41 | Closed | AMS/N2NS/00002 | ITP/N2NS/00004 | [10 empty] | 663.85 | 664 | Hayden Murphy | 2021-05-19 05:39 | [5 empty] | Lot closed |  | 2021-05-23 03:41 |  |  |  | Ahmad Alwan, Hayden Murphy, Jeramy Smith, Samithy Heng |  | WLD-N2NS-00016.pdf, Test Request 41.pdf, NSW Notice to Commence Work (ID 221227).pdf, Camp Lot Map.pdf, N-21-179-72.pdf, N-21-179-45.pdf, N-21-179-71.pdf, N-21-179-63.pdf, N-21-179-75.pdf, N-21-179-74.pdf, 210409 Concrete Dockets.pdf, 210408 Concrete Dockets.pdf, 210416 Concrete Docket.pdf, 210407 Concrete Dockets.pdf, 210410 Concrete Dockets.pdf, QCV Moree Village - Stage 1 CC.pdf, NSW Appointment of PCA (ID 221226).pdf, NSW Notice to Commence Work (ID 221227).pdf, Part Occupation Certificate - QCV Moree Village.pdf, 19MAY2021 CERTIFICATE OF COMPLIANCE StormPro.pdf, 22042021 Certificate of Conformancy Pits.pdf, 210421 Spray Seal _ Camp.pdf, 210416 Gabion Rock pt 1.pdf, 210416 Gabion Rock pt 2.pdf, 210416 Gabion rock pt 3.pdf, DGB Stockpile.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/120455 | 2021-05-31 05:34 | HN QCV PTY LIMITED & QANTAC VILLAGES PTY LIMITED |  |  |  | 2021-05-23 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00015 | Johannes Mason | 2021-02-11 02:56 | Manufacture / Material Supply Lots | Offsite Manufacture | Pre-Cast Culverts | Culverts - Other | Concrete | Johannes Mason | Manufacture of Precast Rail Large Concrete Box Culvert and Wing Walls - January 2021 | 2021-04-08 |  | 2021-01-24 11:00 |  |  |  | Open | AMS/N2NS/00005 | ITP/N2NS/00057 | [9 empty] | MIX/N2NS/00001 | 0 | 0 |  |  |  | PNC/N2NS/00001, PNC/N2NS/00002, PNC/N2NS/00008, PNC/N2NS/00009, PNC/N2NS/00030, PNC/N2NS/00038 | Closed, Closed, Closed, Closed, Closed, Closed | [11 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/120411 |  | Holcim Australia Pty Ltd | PKG/N2NS/00006
WLD/N2NS/00014 | Ryan Shenton | 2021-02-09 00:37 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Trackwork - Bottom Ballast | Track | Ryan Shenton | Process Control - Runnymede 63mm Ballast - Stockpile 2 - 5000t | 2021-02-10 |  | 2021-01-29 11:00 | Sarah Brooks | 2021-02-26 | 2021-02-10 04:36 | Closed | AMS/N2NS/00001 | ITP/N2NS/00015 | [10 empty] | 0 | 0 | Ryan Shenton | 2021-02-24 06:45 | [5 empty] | Lot closed |  | 2021-02-25 22:26 | [5 empty] | RU Ballast SP2 15-2-21.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/120263 | 2021-05-31 05:34 |  |  |  |  | 2021-04-06 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00013 | Kiara Davis | 2021-02-02 06:59 | Stage 1 - Narrabri to Penneys Road | Temporary Works - Compounds and Laydowns | Laydown 6 | Temporary Works - Access Points - Earthworks | Earthworks | Kiara Davis | Stabilisation and Placement of Gravel for Stage 1, Laydown 6 |  |  | 2021-04-02 11:00 |  |  |  | Abandoned | AMS/N2NS/00002 | ITP/N2NS/00002 | [10 empty] | 621.6 | 621.8 | [13 empty] | Hayden Murphy |  |  | https://pa.jhg.com.au/Worklot/Home/Summary/5078/120051 |  |  |  | 7632-GA38050
WLD/N2NS/00012 | Sarah Brooks | 2021-01-29 02:06 | Stage 2 - Penneys Road to Moree | Trackwork | Loops & Siding - Gurley Siding, Ch 635.200 - 636.325 | Trackwork - Reinstatement | Track | Andy Buchanan | Gurley Trials - Formation Trials Temporary Track Reinstatement | 2021-01-29 |  | 2021-01-31 11:00 | Sarah Brooks | 2021-04-06 | 2021-03-03 06:13 | Closed | AMS/N2NS/00001 | ITP/N2NS/00015 | [10 empty] | 635.2 | 636.33 | Sarah Brooks | 2021-04-05 23:11 |  | PNC/N2NS/00003 | Closed |  | HWP/N2NS/00004 | Lot closed |  | 2021-04-05 23:11 | [5 empty] | WK30 N2NS Gurley Trials - IBA.pdf, WK30 N2NS Gurley Trials - Weld Return.pdf, WK30 N2NS Gurley Trials - Track Certification.pdf, WK30 N2NS Gurley Trials - Stress Records.pdf, WK30 N2NS Gurley Trials - Heat numbers.pdf, WK30 N2NS Gurley Trials - Final geometry measurements.pdf, Ballast profile 2.JPG, Rail into Rail seat 1.JPG, Destress.JPG, Track Lift 2.JPG, Welding 1.JPG, Track Lift 1.JPG, Set out.JPG, Clip Up 1.JPG, Spread Ballast.JPG, Sleepers 3.JPG, Stick weld 1.JPG, Sleepers 4.JPG, Sleepers 1.JPG, Ballast Profile 1.JPG, Sleepers 2.JPG, Bottom Ballast.JPG, N2NS - Gurley.zip, WLDN2NS00012 Checklist.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/119858 | 2021-05-31 05:34 |  |  |  |  | 2021-03-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00011 | Kiara Davis | 2021-01-25 06:00 | Stage 2 - Penneys Road to Moree | Temporary Works - Compounds and Laydowns | Laydown 4 | Temporary Works - Compounds and Laydowns - Earthworks | Earthworks | Kiara Davis | Stabilisation and Placement of Gravel for Stage 2, Laydown 4 | 2021-02-15 |  | 2021-02-23 11:00 | Sarah Brooks | 2021-04-06 | 2021-03-16 20:58 | Closed | AMS/N2NS/00002 | ITP/N2NS/00002 | [10 empty] | 663.6 | 663.8 | Sarah Brooks | 2021-04-05 23:09 | [5 empty] | Lot closed |  | 2021-04-05 23:09 |  |  |  | Hayden Murphy |  | Completed Checklist S2L4.pdf, Lot Conformance S2L4.pdf, S2L4 Nata Test Reports.pdf, S2L4 Survey.pdf, IMG_2406.jpg, IMG_2413.jpg, IMG_2409.jpg, IMG_2408.jpg, IMG_2407.jpg, IMG_2411.jpg, IMG_2412.jpg, IMG_2410.jpg, Lot Map S2L4.pdf, S2L4 Working Platform Certificate - Signed Off.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/119569 | 2021-05-31 05:34 |  |  | 7632-GA38050 |  | 2021-04-06 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00010 | Kiara Davis | 2021-01-25 05:58 | Stage 2 - Penneys Road to Moree | Temporary Works - Compounds and Laydowns | Laydown 4 | Earthworks - Topsoil Removal | Earthworks | Kiara Davis | Topsoil Strip for Stage 2 Laydown 4 | 2021-02-11 |  | 2021-02-19 11:00 | Benjamin Philip | 2021-03-17 | 2021-03-16 20:46 | Closed | AMS/N2NS/00002 | ITP/N2NS/00001 | [10 empty] | 663.6 | 663.8 | Kiara Davis | 2021-03-16 06:17 |  |  |  |  | HWP/N2NS/00005 | Lot closed |  | 2021-03-16 20:46 |  |  |  | Hayden Murphy |  | Lot Map S2L4.pdf, Lot Conformance Topsoil S2L4 R1.pdf, Completed Checklist Topsoil S2L4 R1.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/119568 | 2021-05-31 05:34 |  |  | 7632-GA38050 |  | 2021-04-28 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00009 | Ryan Shenton | 2021-01-22 00:53 | Manufacture / Material Supply Lots | Material Supply (inc quarry) | Quarry Materials | Trackwork - Bottom Ballast | Track | Ryan Shenton | Process Control - Runnymede 63mm Ballast - Stockpile 1 - 300t | 2021-01-22 |  | 2021-01-29 11:00 | Sarah Brooks | 2021-02-10 | 2021-02-10 05:10 | Closed | AMS/N2NS/00001 | ITP/N2NS/00015 | [10 empty] | 0 | 0 | Ryan Shenton | 2021-02-10 03:33 | [5 empty] | Lot closed |  | 2021-02-10 05:10 | [5 empty] | Runnymede 63mm Rail Ballast 30-9-20.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/119497 | 2021-05-31 05:34 |  |  |  |  | 2021-03-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00008 | Kiara Davis | 2021-01-21 06:02 | Stage 2 - Penneys Road to Moree | Temporary Works - Access Points | Ch 625.509 - 641.950, 16.441km (Start Stg 3 to Gurley) | Earthworks - Subgrade Preparation | Earthworks | Kiara Davis | Stage 2 - Subgrade Preparation - Access Gate 6411 |  |  | 2021-04-03 11:00 |  |  |  | Abandoned | AMS/N2NS/00002 | ITP/N2NS/00003 | [10 empty] | 640.53 | 641.49 | [16 empty] | https://pa.jhg.com.au/Worklot/Home/Summary/5078/119477
WLD/N2NS/00007 | Ryan Shenton | 2021-01-17 03:36 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 Foundation - Gurley Formation Trial - Ch 635.546 to 635.658 - Layer 2 - 250mm | 2021-01-20 |  | 2021-01-27 11:00 | Sarah Brooks | 2021-02-26 | 2021-02-25 19:46 | Closed | AMS/N2NS/00001 | ITP/N2NS/00003 | [10 empty] | 635.55 | 635.66 | Ryan Shenton | 2021-02-25 02:16 | [5 empty] | Lot closed |  | 2021-02-25 19:46 |  |  |  | Daniel Peyre |  | P21004-39 V1 LWD Day 4 250mm L2.pdf, P21004-38 V1 LWD Day 4 250mm L2.pdf, N-21-179-33 Day 4 250mm L2.pdf, P21004-32 V1 LWD Day 3 250mm L2.pdf, P21004-33 V1 LWD Day 3 250mm L2.pdf, P21004-21 V1 LWD Day 1 250mm L2.pdf, P21004-26 V1 LWD Day 2 250mm L2.pdf, Trans4m N2NS TR0026.pdf, N-21-179-29 Day 3 250mm L2 .pdf, P21004-27 V1 LWD Day 2 250mm L2.pdf, N-21-179-27 Day 2 250mm L2.pdf, P21004-20 V1 LWD Day 1 250mm L2.pdf, Trans4m N2NS TR0023.pdf, N-21-179-26 Day 1 250mm L2.pdf, P21004-15 V1 LWD Day 0 250mm L2.pdf, P21004-14 V1 LWD Day 0 250mm L2.pdf, N-21-179-20 Day 0 250mm L1.pdf, N-21-179-38.pdf, Trans4m N2NS TR0018.pdf, Inland Rail_250mm Layer_2021.01.23.pdf, Inland Rail_250mm Layer_2021.01.27.pdf, Inland Rail_250mm Layer_2021.01.26.pdf, Inland Rail_250mm Layer_2021.01.24.pdf, Inland Rail_250mm Layer_2021.01.25.pdf, Layer 2 Embankment Thickness Ch 635600 to Ch 635660 - Gurley Trial Area.pdf, Layer 2 250mm Conformance Ch 635600 to Ch 635660 - Gurley Trial Area.pdf, WLDN2NS00007.pdf, WLDN2NS00007.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/119199 | 2021-05-31 05:34 |  |  |  |  | 2021-03-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00006 | Ryan Shenton | 2021-01-17 03:35 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 Foundation - Gurley Formation Trial - Ch 635.546 to 635.600 - Layer 1 - 400mm | 2021-01-20 |  | 2021-01-27 11:00 | Sarah Brooks | 2021-02-26 | 2021-02-25 20:01 | Closed | AMS/N2NS/00001 | ITP/N2NS/00003 | [10 empty] | 635.55 | 635.6 | Ryan Shenton | 2021-02-25 02:17 | [5 empty] | Lot closed |  | 2021-02-25 20:01 |  |  |  | Daniel Peyre |  | P21004-36 V1 LWD Day 8 400mm L1.pdf, N-21-179-31 Day 8 400mm L1.pdf, P21004-30 V1 LWD Day 7 400mm L1.pdf, P21004-29 V1 LWD Day 7 400mm L1.pdf, N-21-179-32 Day 7 400mm L1.pdf, P21004-23 V1 LWD Day 6 400mm L1.pdf, P21004-24 V1 LWD Day 6 400mm L1.pdf, N-21-179-28 Day 6 400mm L1.pdf, P21004-18 V1 LWD Day 5 400mm L1.pdf, P21004-17 V1 LWD Day 5 400mm L1.pdf, Trans4m N2NS TR0024.pdf, N-21-179-25 Day 5 400mm L1.pdf, Trans4m N2NS TR0017 Day 5 400mm L1.pdf, P21004-11 V1 LWD Day 4 400mm L1.pdf, P21004-12 V1 LWD Day 4 400mm L1.pdf, N-21-179-24 Day 4 400mm L1.pdf, P21004-9 V1 LWD Day 3 400mm L1.pdf, P21004-6 Part 3 of 3 V1 LWD Day 2 400mm L1.pdf, N-21-179-14 Day 3 400mm L1.pdf, P21004-5 V1 LWD Day 2 40mm L1.pdf, P21004-6 Part 2 of 3 V1 LWD Day 2 400mm L1.pdf, N-21-179-12 Day 2 400mm L1.pdf, N-21-179-12.pdf, P21004-3 V1 LWD Day 1 400mm L1.pdf, Trans4m N2NS TR0012.pdf, N-21-179-10 Day 1 400mm L1.pdf, Trans4m N2NS TR0010.pdf, P21004-1 V1 LWD - Day 0 400mm L1.pdf, N-21-179-18 Day 0 400mm L1 .pdf, N-21-179-8 Day 0 400mm L1 1.pdf, N-21-179-18 Day 0 400mm L1.pdf, Inland Rail_400mm Layer_2021.01.19.pdf, Inland Rail_400mm Layer_2021.01.20.pdf, Layer 1 Embankment Thickness Ch 635550 to Ch 635600 - Gurley Trial Area.pdf, Layer 1 400mm Conformance Ch 635600 to Ch 635660 - Gurley Trial Area.pdf, WLDN2NS00006.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/119198 | 2021-05-31 05:34 |  |  |  |  | 2021-03-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00005 | Ryan Shenton | 2021-01-17 03:34 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Filling | Earthworks | Ryan Shenton | Type E3 Foundation - Gurley Formation Trial - Ch 635.610 to 635.658 - Layer 1 - 250mm | 2021-01-20 |  | 2021-01-27 11:00 | Sarah Brooks | 2021-02-26 | 2021-02-25 19:58 | Closed | AMS/N2NS/00001 | ITP/N2NS/00003 | [10 empty] | 635.61 | 635.66 | Ryan Shenton | 2021-02-25 02:18 | [5 empty] | Lot closed |  | 2021-02-25 19:58 |  |  |  | Daniel Peyre |  | P21004-9 V1 LWD Day 3 250mm L1.pdf, Trans4m N2NS TR0016.pdf, N-21-179-13 Day 3 250mm L1.pdf, P21004-6 Part 1 of 3 V1 LWD Day 2 250mm L1.pdf, P21004-5 V1 LWD Day 2 250mm L1.pdf, N-21-179-11 Day 2 250mm L1 -1 .pdf, Trans4m N2NS TR0011.pdf, P21004-3 V1 LWD Day 1 250mm L1.pdf, N-21-179-11 Day 2 250mm L1.pdf, N-21-179-9 Day 1 250mm L1.pdf, Trans4m N2NS TR0009.pdf, P21004-1 V1 LWD - Day 0 250mm L1.pdf, N-21-179-19 Day 0 250mm L1.pdf, N-21-179-8 Day 0 250mm L1 1.pdf, N-21-179-19 Day 0 250mm L1 - 1.pdf, Inland Rail_250mm Layer_2021.01.21.pdf, Inland Rail_250mm Layer_2021.01.22.pdf, Inland Rail_250mm Layer_2021.01.19.pdf, Inland Rail_250mm Layer_2021.01.20.pdf, Layer 1 250mm Conformance Ch 635600 to Ch 635660 - Gurley Trial Area.pdf, WLDN2NS00005.pdf, WLDN2NS00005.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/119197 | 2021-05-31 05:34 |  |  |  |  | 2021-03-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00004 | Ryan Shenton | 2021-01-13 22:59 | Stage 2 - Penneys Road to Moree | Earthworks | Main Alignment (Specify Chainage in Lot) | Earthworks - Topsoil Removal | Earthworks | Ryan Shenton | Gurley Formation Trial - Ch 635.490 to 635.620 - Topsoil Strip | 2021-01-15 |  | 2021-01-20 11:00 | Sarah Brooks | 2021-03-12 | 2021-02-25 20:00 | Closed | AMS/N2NS/00001 | ITP/N2NS/00001 | [10 empty] | 635.49 | 635.62 | Ryan Shenton | 2021-03-12 00:35 | [5 empty] | Lot closed | Missing survey report has been added. | 2021-03-12 00:42 |  |  |  | Daniel Peyre |  | WLDN2NS00004.pdf, Gurley Trial Topsoil Strip.txt | https://pa.jhg.com.au/Worklot/Home/Summary/5078/119033 | 2021-05-31 05:34 |  |  |  |  | 2021-03-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00003 | Ryan Shenton | 2021-01-13 03:18 | Stage 2 - Penneys Road to Moree | Earthworks | Loops & Siding - Gurley Siding, Ch 635.200 - 636.325 | Earthworks - Cut, Inc Ground Preparation | Earthworks | Ryan Shenton | Gurley Formation Trial - Ch 635.490 to 635.620 - Cut Inc Ground Prep | 2021-01-15 |  | 2021-01-20 11:00 | Sarah Brooks | 2021-02-26 | 2021-02-25 19:56 | Closed | AMS/N2NS/00001 | ITP/N2NS/00003 | [10 empty] | 635.49 | 635.62 | Ryan Shenton | 2021-02-25 02:18 |  |  |  |  | HWP/N2NS/00001, HWP/N2NS/00002, HWP/N2NS/00003 | Lot closed |  | 2021-02-25 19:56 |  |  |  | Daniel Peyre |  | N-21-179-6.pdf, N-21-179-5.pdf, TR0006.pdf, TR0002.pdf, N-21-179-4.pdf, N-21-179-3.pdf, N-21-179-17.pdf, N-21-179-2.pdf, Foundation Conformance Ch 635550 to Ch 635660 - Gurley Trial Area.pdf, WLDN2NS00003.pdf, WLDN2NS00003.JPG | https://pa.jhg.com.au/Worklot/Home/Summary/5078/119001 | 2021-05-31 05:34 |  |  |  |  | 2021-03-03 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00002 | Kiara Davis | 2021-01-05 23:13 | Stage 2 - Penneys Road to Moree | Temporary Works - Compounds and Laydowns | Laydown 2 | Temporary Works - Compounds and Laydowns - Earthworks | Earthworks | Kiara Davis | Stage 2 - Stabilisation and Placement of Gravel - Laydown 2 Ch641.2 | 2021-01-13 |  | 2021-02-12 11:00 | Sarah Brooks | 2021-04-06 | 2021-03-16 20:26 | Closed | AMS/N2NS/00002 | ITP/N2NS/00002 | [10 empty] | 640.65 | 641 | Shane Aberdeen | 2021-04-05 22:51 | [5 empty] | Lot closed |  | 2021-04-05 23:05 | [5 empty] | NATA Test Reports S2L2.pdf, Survey Report S2L2.pdf, IMG_3243.JPG, IMG_3246.JPG, IMG_3251.JPG, IMG_3249.JPG, LD2.jpg, IMG_1164.JPG, LD2-1.jpg, IMG_1163.JPG, Topsoil Bund3.jpg, Topsoil Bund1.jpg, Topsoil Bund5.jpg, Topsoil Bund4.jpg, Topsoil Bund2.jpg, Lot Conformance S2L2.pdf, Completed Checklist S2L2.pdf, S2L2 0 Working Platform Certificate Signed.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/118665 | 2021-05-31 05:34 |  |  | 7632-GA38050 |  | 2021-04-06 | Mike Harris | ARTC Accepted (Conforming)
WLD/N2NS/00001 | Kiara Davis | 2021-01-05 23:07 | Stage 2 - Penneys Road to Moree | Temporary Works - Compounds and Laydowns | Laydown 2 | Temporary Works - Compounds and Laydowns - Earthworks | Earthworks | Kiara Davis | Stage 2 - Topsoil Strip - Laydown 2 Ch641.2 | 2021-01-11 |  | 2021-01-14 11:00 | Benjamin Philip | 2021-03-17 | 2021-03-16 20:24 | Closed | AMS/N2NS/00002 | ITP/N2NS/00001 | [10 empty] | 640.65 | 641 | Kiara Davis | 2021-03-16 06:20 | [5 empty] | Lot closed |  | 2021-03-16 20:24 | [5 empty] | Site Layout - Stage 2 Site Area 2.pdf, Lot Conformance Topsoil S2L2 R1.pdf, Completed Checklist Topsoil S2L2 R1.pdf | https://pa.jhg.com.au/Worklot/Home/Summary/5078/118664 | 2021-05-31 05:34 |  |  | 7632-GA38050 |  | 2021-04-02 | Mike Harris | ARTC Accepted (Conforming)